## Slide 1
SAPO: Report to Parliament Portfolio Committee
20 March 2018
SAPO Status Update on
SASSA readiness

## Slide 2: SAPO Responsibilities
SAPO will provide the following services to SASSA on a Build, Operate and Transfer (BOT) model commencing on 1 April 2018 for a period of 5 years where after the solution will be transferred to SASSA:
Electronic banking services, including:
A Corporate (Holding) Account; and
Special Disbursement Accounts for beneficiaries
On-boarding of new beneficiaries through instant account opening and card issuance at SASSA local offices
Card body production and distribution
Biometric authentication of beneficiaries
On-boarding of the existing 5,7 million beneficiaries in the National Payment System through a phase-in/phase-out process to migrate beneficiaries from CPS to SAPO on or before 30 September 2018.
Development of software, in conjunction with other state entities

## Slide 3: Current beneficiary payment category profile
Payment Category | Infrastructure Utilised | Numbers
Cash Recipients | Mobile pay points (specialised ATM’s) | 1,833,230
 | Designated merchants (till points) | 212,799
 | Designated Net1 (Grindrod Bank) premises (specialised static ATM’s) | 846,332
Sub Total |  | 2,892,361
SASSA/Grindrod Bank cardholders | ATM (commercial banks & specialised Net1 (Grindrod Bank) | 5,761,448
Electronic Recipients (Commercial Banks, including Grindrod Bank EPE cardholders) | Commercial Banks’ own and NPS facilities | 2,083,144
Sub Total |  | 7,844,592
Total |  | 10,736,953
Included in the SASSA/SAPO Service Agreement
Source: SASSA’s fourth report to the Concourt dated 16 March 2018: Statistics as at January 2018

## Slide 4: SAPO Readiness
Electronic banking service inclusive of a Corporate Control (Holding) Account and Special Disbursement Accounts (SDAs)
Corporate Control (Holding Account)
National Treasury declined the opening of a Corporate Account at Postbank on account of Postbank not yet being a registered bank
SASSA will utilise its Paymaster General account at the SA Reserve Bank to facilitate direct transfers into the SDAs via Bankserv
This arrangement has no impact on SAPO/Postbank’s ability to execute its obligations and render the Corporate Control Account at Postbank superfluous
Special Disbursement Accounts
The SDA product has been created in Postbank’s core banking system and is ready
Individual accounts will be opened during on-boarding of new beneficiaries commencing 3 April 2018 at all SASSA offices; and
Card-swop of existing beneficiaries will commence at all SAPO branches on 16 March 2018 and at all identified community halls and other venues wef 30 April to be completed by 30 September 2018

## Slide 5: Card Body Production & Distribution
Receive VISA certification of cards on 19 March 2018
Receive 100 sample cards for launch ceremony (on 22 March) on 20 March 2018
Deliver 500 cards for testing and dry run at four identified sites on 28 March 2018
First 250K production cards delivered to Bloemfontein on 29 March 2018
PASA and domestic banking industry testing on expedited (out of cycle) testing programme from 20 March to 1 April 2018
Supplier commence delivery of 250K cards per day from 9 April 2018 for 43 days until full delivery of the 10.6 million cards
        5,7million cards required for card swop of electronic payments in the National Payment System will be delivered by 9 May 2018
Postbank will continue to use its current card distribution process and capacity to distribute the SASSA cards to all SAPO branches and SASSA offices
Should the new SASSA cards not be ready by 3 April 2018, Postbank will issue beneficiaries with a Mzansi card which will be replaced with a SASSA card during the card swop programme

## Slide 6: Integrated Grant Payment Solution (BOT)
Contract signed 16 April 2017
Commence implementation, testing and configuration by 18 May 2018
Sign-off for Implementation in Production 25 May 2108
Migrate all data captured on Postbank’s Flexcube system (FCUBS) to the new solution by 15 June 2018
Contingency:
Hosting the Special Disbursement accounts in Postbank’s core banking solution (FCUBS) until the IGPS is available.
No impact on either SASSA or the beneficiaries

## Slide 7: Biometric Engine (BE)
Contract signed 16 March 2018
Solution will be delivered by 26 March 2018
Commissioning of the solution on 28 March 2018
Contingency: Using SASSA’s IAM software in the interim until the permanent BE solution is available – this has already been tested successfully

## Slide 8: On-boarding of beneficiaries
Proof of concept to test technology and human resources will take place on 22 March at four offices selected to launch the new SASSA/SAPO card:
Manguze – KwaZulu-Natal
Mount Fletcher – Eastern Cape
Tonga – Mpumalanga
Worcester – Western Cape
SAPO will proceed with on-boarding of new beneficiaries on 3 April 2018 at all SASSA offices
Commence card swop initially at ALL SAPO branches only on 16 April 2018; and
Commence with full card swop programme at SAPO branches and dedicated card swop venues (community halls, depots, etc) on 30 April 2018
Card swop programme to migrate all 5,7 million existing beneficiaries to be completed by 30 September 2018

## Slide 9: Migration of Cash to Non-Cash
SAPO branches currently has 5,000 counters that are classified as ‘ATMs’ and provide banking experience to its customers. In relation to SASSA pay-points, SAPO’s footprint detail is as follows;
53.5% of the branches are within the 5 km radius
17.6% are between 5 & 10 km
20.9% between 10 & 20 km
8% are outside the 20 km radius
SAPO has identified 860 branches within a 5km radius of a SASSA pay-point which potentially could be used as an alternative to strictly cash
SAPO & Postbank is working on a business case to upgrade the Network, IT infrastructure and capacity at these offices to handle the increased demand to pay SASSA grants at SAPO branches

## Slide 10: Migration of Cash to Non-Cash
Migration targets | 2018/19 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | Profile after 5 years
Maintained cash pay points (migration from current to new SASSA card) | 2,531,680 | 2,119,680 | 1,499,680 | 849,680 | 549680 | 549,680
Migrated to SAPO outlets and merchants | 250,000 | 300,000 | 500,000 | 500,000 | 100,000 | 1,650,000
Possible migration to banks | 100,000 | 100,000 | 100,000 | 100,000 | 100,000 | 500,000
Cooperatives and village banks | 10,000 | 15,000 | 20,000 | 50,000 | 100,000 | 195,000
Total |  |  |  |  |  | 2,894,680
Target number of beneficiaries to be migrated from Cash to SAPO branches
Source: SASSA’s fourth report to the Concourt dated 16 March 2018

## Slide 11: Thank you