****

**Status of the Small-Scale Fisheries Implementation Process as of 22 May 2018**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Milestone Activities** | | **Provinces** | | | | |
| **Northern Cape** | | **Western Cape** | **Eastern Cape** | **KwaZulu-Natal** |
| **Legal Framework (Amended Act promulgated and SSF Regs approved)** | | **Completed –**  **8 Mar 2016** | | **Completed –**  **8 Mar 2016** | **Completed –**  **8 Mar 2016** | **Completed –**  **8 Mar 2016** |
| **Closing of Expression of Interest Process for communities** | | **Completed – Apr 2016** | | **Completed –**  **Apr 2016** | **Completed – Apr 2016** | **Completed –**  **Apr 2016** |
| **Registration and Verification of fishers per community** | | **Completed – Mar – Aug 2016** | | **Completed –**  **Mar – Aug 2016** | **Completed – Mar – Aug 2016** | **Completed –**  **Mar – Aug 2016** |
| **Announcement of provisional lists of successful fishers** | | **Completed – Aug 2016** | | **Completed –**  **Oct 2016** | **Completed – Nov 2016** | **Completed –**  **Jul 2017** |
| **Appeals closed** | | **Completed –**  **Sep 2016** | | **Completed –**  **Dec 2016** | **Completed – Apr 2017** | **Completed –**  **Aug 2017** |
| **Tip-off info followed-up** | | **None received** | | **Completed –**  **Nov 2017** | **None received** | **None received** |
| **Appeals assessment** | | **Completed – Jun 2017** | | **Completed April 2018** | **Completed – Nov 2017** | **Completed –**  **Nov 2017** |
| **SSF Fee Structure Determination** | | **Jun 2017 – Jul 2018** | | **Jun 2017 – Jul 2018** | **Jun 2017 – Jul 2018** | **Jun 2017 – Jul 2018** |
| **Approval of final list of fishers** | | **Completed - Nov 2017** | | **May/Jun 2018** | **Completed – Jan 2018** | **Completed – Jan 2018** |
| **Announcement of final list of successful fishers** | | **Completed – Nov 2017** | | **Jun-Jul 2018 (subject to approval of submission)** | **Completed- Feb 2018** | **Completed- Feb 2018** |
| **Co-op Training** | | **Completed- Feb 2018** | | **Jul 2018** | **May/June 2018** | **Completed Mar 2018** |
| **Co-op Registration** | | **Feb-May 2018** | | **Aug 2018** | **May 2018** | **Mar-May 2018** |
| **SSF Rights Allocation** | | **May/Jun 2018 (subject to co-ops registered and by-laws adopted)** | | **Sep/Oct 2018**  **(subject to co-ops registered and by-laws adopted)** | **Jul 2018**  **(subject to co-ops registered and by-laws adopted)** | **Jun/Jul 2018**  **(subject to co-ops registered and by-laws adopted)** |
| **Conclude rights appeals** | | **Jul 2018** | | **Dec 2018** | **Oct 2018** | **Sep 2018** |
| **Support Programmes** | | **2018 – 2021 (subject to needs of co-op)** | | **2018 – 2021 (subject to needs of co-op)** | **2018 – 2021 (subject to needs of co-op)** | **2018 – 2021 (subject to needs of co-op)** |
| **Green - Activity completed** | |
| **Amber – In progress** | |
| **Red – Still to be done** | |

**NB - Dates for activities still to be done are tentative and are subject to change**