## Deviation register 2016-2017
DEVIATION REGISTER 2016/ 2017
Item No. | Bid Number | Description | Bidder | Date recommended/Noted by DBAC | Date approved by DG | DATE REPORTED TO TREASURY [Above threshold values] | DATE REPORTED TO AG[Above threshold values] | Contract Value | Supported/ Not Supported by Treasury | WTE Proceeded/ Not proceeded
1 | DWS62-1016 | The extension of the appointment of Diners Club International to pay all water trading entity air travelling transaction reserved through Hamba Nathi Travel for the period of twelve (12) months | Diners Club International | 31/03/2016 | 03/04/2016 | 18/04/2016 | 18/04/2016 | Travel Lodge card for R501.75 P.A AND Additional cards for R111.40 P.A [ Vat Exclusive] | Supported
2 | N/A | To appoint talent emporium academy PTY (Ltd) which is registered on the Department database urgently as the preferred services provider to facilitate the planned National Water Resources Infrastructure Branch (NWRI) Strategic Planning Session scheduled to take place on 14 and 15 April 2016 | Talent Emporium Academy Pty (Ltd) | 27/05/2016 | 12/04/2016 | N/A below R1 million threshold for reporting to National Treasury as per National Treasury Oractice Note No.6 of 2007/2007 | N/A | 410000 | N/A | The DG already approved the deviation, this was prior to the communication of National Treasury Instruction Note No. 3 of 2016/2017 as it was issued and communicated on 19/04/2016
3 | ITC A16996 | To appoint Solicad as preferred service service provider for the procurement of ansys mechanical CDF with maintenance until end of May 2017. | SoliCad | 24/05/2016 | 29/05/2016 | N/A | N/A | 739974 | This was procured from a sole service provider of which the Accounting Officer can approved and it is below R1million, National Treasury only requires reports of deviations which are above R1 million as per the NATIONAL TREASURY PRACTICE NOTE 6 OF 2007/2008
4 | WQ6214 WTE | Procurement of ammunitions for the national key point for Central Operations. | J.J Wapens & Geweersmede | 22/05/2016 | 02/06/2016 | N/A | N/A | 153650 | This was procured from a sole service provider of which the Accounting Officer can approved and it is below R1million, National Treasury only requires reports of deviations which are above R1 million as per the NATIONAL TREASURY PRACTICE NOTE 6 OF 2007/2008
5 | W1098 WTE | Maintenance and repair of all Tienfonten Pump Station Pump sets as and when required for a period of twelve (12) months. | Sulzer Pumps South Africa (PTY) LTD | 23/06/2016 | 30/06/2016 | 21/07/2016 | 21/07/2016 | 6449101.98 | This was procured from a sole service provider of which the Accounting Officer can approved and its reported to National Treasury.
6 | DWS62-1016 | The extension of the appointment of Diners Club International to pay all water trading entity accommodation transactions reserved through Hamba Nathi Travel for the period of twelve (12) months | Diners Club International | 04/08/2016 | N/A | 15/08/2016 |  | Travel Lodge card for R501.75 P.A AND Additional cards for R111.40 P.A [ Vat Exclusive] | Supported
7 | 11/06/2016 | For the sourcing of the services to assist in preparing consolidated annual financial statements for year ended 31 March 2016 to comply to generally recognised accounting practice(GRAP) for the Water Trading Entity (WTE) | Ernest and Young | 13/06/2016 | 14/06/2016 | 14/06/2016 | 14/06/2016 | 308940 | Not supported | Not proceeded with the procurement
8 | WQ6424 WTE: | Appointment of as a sole service provider for the service,repair,supply batteries and charges and calibrate the trimble GPS systems and trimple survey instruments of survey services Bloemfontein. | Optron (PTY)Ltd | 25/08/2016 | 31/08/2016 | N/A | N/A | 35753.61 | This was procured from a sole service provider of which the Accounting Officer can approved and it is below R1million, National Treasury only requires reports of deviations which are above R1 million as per the NATIONAL TREASURY PRACTICE NOTE 6 OF 2007/2008
9 | DM-00010 | Appointment of SAMSA as a sole supplier of Local General Safety Certificates (LGSC)of DWS Vessels as per National Small Vessels Safety Regulations of 2007. | SAMSA South Africa | 10/11/2016 | 24/11/2016 | N/A | N/A | 3837.67 | This was procured from a sole service provider of which the Accounting Officer can approved and it is below R1million, National Treasury only requires reports of deviations which are above R1 million as per the NATIONAL TREASURY PRACTICE NOTE 6 OF 2007/2008
10 | DEV V0002 WTE | Request to appoint a sole supplier for renewal of Omnistar Annual Satellite-Based VBS signal (differential GPS)subscription used by survey services in the Free State Province for 2016/17 financial year. | Omnistar/Trimble Navigation Technology South Africa | 20/10/2016 | 19/12/2016 | N/A | N/A | 21067.2 | This was procured from a sole service provider of which the Accounting Officer can approved and it is below R1million, National Treasury only requires reports of deviations which are above R1 million as per the NATIONAL TREASURY PRACTICE NOTE 6 OF 2007/2008
11 | WP0485 WTE | Request to approach and re-appoint Royal Haskoning DHV to carry out construction supervision at Rietspruit Dam. | Royal Haskoning DHV | 17/11/2016 | 24/11/2016 | 05/12/2016 | 07/02/2017 | 1116900 | Supported Conditionally
12 | WP0485 WTE | Request for the emergency upgrade of the Thukela Goedertrouw scheme for a contract period of eighteen(18) months on engineering,procurement and construction programme. | Aecom SA (PTY) LTD | 09/03/2017 | 07/03/2017 | 13/03/2017 | 17/03/2017 | 646502802.8 | Approved by the Acting DG as it was an emergency.Only reported to National Treasury
13 | Dev-0004 | Request for the appointmentment of Sulzer Pumps South Africa (PTY) Ltd as a sole supplier for the refurbishment of pump number 2 at Camden Pump Station. | Sulzer Pumps South Africa (PTY) LTD | 14/10/2016 | 19/10/2016 | 17/03/2017 | 17/03/2017 | 6354087.99 | Supported
14 | Dev-0005 | Request for the appointmentment of Messrs Rockwell (South Africa) software designer and manufacture of electrical control systems hardware installed at Vresap High and Lowlift Pump Stations for the repair of Vresap low lift electrical control systems. | Messrs Rockwell South Africa | 15/09/2016 | 07/10/2016 | 17/03/2017 | 17/03/2017 | 8740139 | This was procured from a sole service provider of which the Accounting Officer can approved and its reported to National Treasury.
15 | W1088WTE | Le Meetse Public Participation Programme held at Izwilesizwe Primary School on the 22nd April 2016 | Tae Marketing |  | 15/04/2016 |  |  | 2702324 | N/A | The DG already approved the deviation, this was prior to the communication of National Treasury Instruction Note No. 3 of 2016/2017 as it was issued and communicated on 19/04/2016
16 | W1088WTE | Mzimvubu dam site pubklic participation | DA Brains Event and Hiring |  | 15/04/2016 |  |  | 3640161.36 | N/A | The DG already approved the deviation, this was prior to the communication of National Treasury Instruction Note No. 3 of 2016/2017 as it was issued and communicated on 19/04/2016
17 | W1088WTE | Water Exhibition | Anzomonde Jobe Creative |  | 15/04/2016 |  |  | 5129373 | N/A | The DG already approved the deviation, this was prior to the communication of National Treasury Instruction Note No. 3 of 2016/2017 as it was issued and communicated on 19/04/2016
18 | W1088WTE | PresidentIAL Visit to Melmoth | Gou - Gou Trading |  | 31/03/2016 |  |  | 5835945 | Not supported | The DG already approved the deviation, this was prior to the communication of National Treasury Instruction Note No. 3 of 2016/2017 as it was issued and communicated on 19/04/2019

## Variation Order 2016-2017
EXPANSIONS/ VARIATION ORDER REGISTER 2016-2017
| Bid Number | Description | Contractor | Contract amount | Variation amount | Time only | Cost only | Both | Date recommended by DBAC | Date approved by DG | Percentage | SAP contract number | Comments
1 | WP0485 WTE | To extend the scope in order to carry out clear day dam break flood lines for dams in the Central, Eastern, Northern Clusters and an extension of time for the drafting of operation and maintenance manuals (OMM) as well as emergency preparedness plans (EPP) for all category 2 and category 3 dams in the central, Eastern, Northern and Southern Clusters with no associated cost.[VO1] | Babereki Consulting Engineers cc | 40501255.5 | 0 | x |  |  | 31/03/2016 | 03/04/2016 | 0% | 4600501234
2 | WP0485 WTE | Approval for variation order on term contract project: PSP to render professional services in design, contract documentation, project management and construction monitoring of the access road rehabilitation at Gubu Dam in the Eastern Cape.[VO1] | Engineering Advice and Services | 461683 | 0 | x |  |  | 31/03/2016 | 03/04/2016 | 0% | 4600501065
3 | WP0485 WTE | Approval for variation order on term contract project: PSP to render professional services in design, contract documentation, project management and construction monitoring of the road network rehabilitation of the Uitkeer staff complex in the Eastern Cape.[VO1] | Shuma Africa Projects (Pty) Ltd | 3318514 | 0 | x |  |  | 31/03/2016 | 03/04/2016 | 0% | 4600501067
4 | WP0485 WTE | Request for extension of time on existing contract: Condition assessment of irrigation canals contract.[VO1] | LTE Consulting | 75553963.4 | 0 | x |  |  | 31/03/2016 | 03/04/2016 | 0% | 4600004148
5 | WP0485 WTE | Approval for variation order on term contract project: PSP to render professional services in design, contract documentation, project management and construction monitoring of the Moordkuil Pump Station in the Western Cape.[VO1] | Niel Lyners and Associates cc | 3067300 | 0 | x |  |  | 31/03/2016 | 03/04/2016 | 0% | 4600501071
6 | WP0485 WTE | Approval for variation order on term contract project: PSP to render professional services in design, contract documentation, project management and construction monitoring of the Gauda Siphon Rehabilitation in the Western Cape.[VO1] | Jeffares and Green (Pty) Ltd | 1050520.17 | 0 | x |  |  | 31/03/2016 | 03/04/2016 | 0% | 4600501070
7 | WP0485 WTE | Approval for variation order on term contract project: PSP to render professional services in condition assessment and design of the raw water canals of the NCORA Irrigation Scheme in the Eastern Cape.[VO1] | AC Aphane Consulting cc | 16764712 | 0 | x |  |  | 31/03/2016 | 03/04/2016 | 0% | 4600501068
8 | WP0485 WTE | Approval for variation order on term contract project: PSP to render professional services in design, contract documentation, project management and construction monitoring of the Elandskloof pipeline in the Western Cape.[VO1] | Dihlase Consulting Engineers | 1777225 | 0 | x |  |  | 31/03/2016 | 03/04/2016 | 0% | 4600501066
9 | WP0485 WTE | Approval for variation order on term contract project: PSP to render professional services in design, contract documentation, project management and construction monitoring of the Hoekklip Siphon Rehabilitation in the Western Cape.[VO1] | Bigen Africa Services (Pty) Ltd | 2937643.86 | 0 | x |  |  | 31/03/2016 | 03/04/2016 | 0% | 4600501180
10 | WP0485 WTE | Extension of contract period without increase in contract: Conduct feasibility studies, design, preparation of contract documentation and drawings for the rehabilitation of Skoenmakers River.[VO1] | BVI Engineering Procurement Management (Pty) Ltd | 12692947.18 | 0 | x |  |  | 10/03/2016 | 09/04/2016 | 0% | 4600501062
11 | WQ5913 WTE | Extension of contract on month to month: For rendering of cleaning services at Praetor Forum Building until the finalization of bidding process and appointment of new service provider(VO1) | Sikuphatha Kahle Enterprise | 246096 | 123048 |  |  | x | 03/03/2016 | 15/04/2016 | 50% | 4600500100 | The original contract was for 6 months and the extension was from 16 April 2016 for 3 months to 15 July 2016. This was approved before National Treasury Instruction 3 was issued and was reported to National Treasury.
12 | W0857 WTE | Approval for variation order for existing cleaning service contract for the period of three(3) months within Gauteng Provincial Office. | Zwito Cleaning Service | 1378944 | 193655.46 |  |  | x | 22/04/2016 | 22/04/2016 | 14.04% | 4600003612
13 | WP0485 WTE | Approval for variation order on term contract project: PSP to render professional services in design, contract documentation, project management and construction monitoring and the CATA Pipeline replacement in the Eastern Cape.[VO1] | Calliper Consulting Engineers | 5075200 | 0 | x |  |  | 31/03/2016 | 03/04/2016 | 0% | 4600501073
14 | W0658 WTE | Extension of the SAP Support and maintenance contract with T-System. VO2 | T-System | 77004774.51 | 4783613.42 |  |  | x | 27/05/2016 | 30/05/2016 | 6% | 4600002761
15 | WP1003 WTE | Luvuvhu River Government Scheme: Completion of construction of the new steel pipelines that replace the problematic GRP pipes. Construction of part A of the 800MM diameter steel pipeline.[VO1] | QI-TIS Quality Services (Pty)Ltd | 2599155.2 | 0 | x |  |  | 22/05/2016 | 30/06/2016 | 0% | 4600501058
16 | WP0497 WTE | Luvuvhu River Government Scheme: Completion of construction of the new steel pipelines that replace the problematic GRP pipes. Construction of part B of the 800MM diameter steel pipeline.[VO3] | Ascul Construction cc | 50048759.05 | 0 | x |  |  | 22/05/2016 | 30/06/2016 | 0% | 4600501056
17 | WP0497 WTE | Luvuvhu River Government Scheme: Completion of construction of the new steel pipelines that replace the problematic GRP pipes. Construction of part C of the 800MM diameter steel pipeline.[VO3] | Murray and Dickson Construction (Pty) Ltd | 72170623.05 | 0 | x |  |  | 22/05/2016 | 30/06/2016 | 0% | 4600501056
18 | WP0497 WTE | Luvuvhu River Government Scheme: Completion of construction of the new steel pipelines that replace the problematic GRP pipes. Construction of part A of the 800MM diameter steel pipeline.[VO3] | WK Construction SA (Pty) Ltd | 48116477.54 | 0 | x |  |  | 22/05/2016 | 30/06/2016 | 0% | 4600501056
19 | W10922 | Rendering of a cleaning service at the Department of Water and Sanitation Gauteng Provincial Office: Bothongo Plaza East.[VO2] | Gombameni Risk and Events | 31831260.84 | 2113629.2 |  |  | x | 28/07/2016 | 25/07/2016 | 6.64% | 4600501124
20 | WP0485 WTE | To increase the approved contract amount : Mzimvubu Water Project : Urgent Geotechnical Investigations and surveys for various structures within the project area. [VO1] | Pro-Plan Consulting Engineers (Pty) Ltd) | 680370615.4 | 20833500 |  | x |  | 18/08/2016 | 15/08/2016 | 3.06% | 4600501072 | The rand value deviation is above the R20 million threshold , This was supported by National Treasury.
21 | WP0565 WTE | Construction supervision of Vlakfontein Canal.[VO1] | SMEC | 16148045 | 0 | x |  |  | 15/09/2016 | N/A | 0% | 4600003053
22 | 1/2/4/257/2015/16 | Design and construction supervision of the rehabilitation of Kalfontein Dam-Dam Safety Rehabilitation Pragramme.[VO2] | Mr Hans Durieux | 641700 | 96255 |  | x |  | 01/09/2016 | 03/10/2016 | 15%
23 | W0647 WTE | Motivation to complete outstanding maintenance and refurbishment work after the expiry date on the maintenance and electrical term contract to be completed.[VO1] | Belta Services | 586427137 | 0 | x |  |  | 22/09/2016 | 07/10/2016 | 0% | 4600500578
|  |  | Pro-Electro System | 586427137 | 0 | x |  |  | 22/09/2016 | 07/10/2016 | 0% | 4600500578
|  |  | Bicacon | 586427137 | 0 | x |  |  | 22/09/2016 | 07/10/2016 | 0% | 4600500578
24 | W0500 WTE | Three year term contract for the service, maintenance and repair of lifts installed at various dams and pump stations in accordance with the Occupational Health and Safety Act.[VO1] | Otis (Pty) Ltd | 34255 | 0 | x |  |  | 13/10/2016 | 13/10/2016 | 0% | 4600501057
|  |  | Schindler Lifts | 16861.65 | 0 | x |  |  | 13/10/2016 | 13/10/2016 | 0% | 4600501057
25 | WP0485WTE | For the appointment of the approved service Provider Professional person for the duration of the construction period of the alternative implementation model. Option 2C:olfanrs Doorns river water resources development project- raising of (No Suggestions) dam: [VO1] | Bigen Africa (Pty) Ltd | 154206613 | 14874891 |  | x |  | 13/10/2016 | 24/11/2016 | 9.65% | 4600501060
26 | WP0538 WTE | Request for extension of time on the EOH Mthombo contract to roll out SAP to the Catchment Agencies at no additional cost to the Department until 31 July 2017.[VO1] | EOH Mthombo | 118555440 | 0 | x |  |  | 29/09/2016 | 04/11/2016 | 0% | 4600501116
27 | WP0485 WTE | Request for extension of time for the development of resource management plans for prioritised government waterworks. [VO1] | Engineerex (PTY)Ltd | 29448936.16 | 0 | x |  |  | 08/12/2016 | 20/12/2016 | 0% | 4600004024
28 | W0647 WTE | Request approval for additional cost for the manufacture, supply and installation of an additional hydraulic cylinder on the three radial gates at Pongolapoort Dam as detailed under RFQ 025C.[VO1] | Bicacon | 586427137 | 985302.12 |  |  | x | 22/09/2016 | 22/09/2016 | 0,16% | 4600501113
29 | WP1050 WTE | Augment capacity for CMA,s to complete the project to roll out SAP to the catchment Agencies (CMAS). [VO1] | Rangewave | 16190280 | 2428542 |  |  | x | 31/10/2016 | 31/10/2016 | 15% | 4600501110
30 | WP0815WTE | Supply, installation and maintenance of smart flow meters for a term contract for a period of three years. [VO1] | Lesira Technologies | 120000000 | 0 | x |  |  | 12/12/2016 | 19/12/2016 | 0.16% | 4600501115
31 | WP0485 WTE | Request for scope extension and additional funds on the existing contract: Condition assessment of irrigation canals contract.[VO2] | LTE Consulting | 75553963.4 | 9172760.49 |  |  | x | 28/09/2016 | 28/09/2016 | 12.01% | 4600501133
32 | WP0564WTE | Rehabilitation of Hammarsdale dam: Request for variation order to extend the contract period.[VO3] | Naidu Consulting | 2568374.4 | 0 | x |  |  | 16/02/2017 | 09/03/2017 | 0.16% | 4600501207
33 | WP1059 WTE | Request for the approval of variation of the project timeline for the implementation of validation and verification of the existing water use in the Mzimvubu to Tsitsikamma and Berg to Olifants Water Management Areas.[VO1] | MHP Geospace (Pty)Ltd | 17809353.6 | 0 | x |  |  | 14/03/2017 | 27/03/2017 | 0.16% | 4600500597
|  |  | Aurecon South Africa(Pty) Ltd | 25202035.27 | 0 | x |  |  | 14/03/2017 | 27/03/2017 | 0.16% | 4600500597
34 | WP0708 WTE | Request for the extension of time of the laboratory services for the water quality testing: Mzimvubu-Tsitsikamma Proto CMA. [VO1] | Talbot &Talbot (Pty) Ltd | 7824960 | 0 | x |  |  | 30/03/2017 | 29/03/2017 | 0.16% | 4600003465
35 | W1020 WTE | Provision of bulk printing and mailing services for the Chief Directorate : Revenue Management -Water Trading Entity: [VO1] | Mailtronic Direct Marketing cc | 32059134.72 | 2600000 |  |  | x | 24/03/2017 | 28/03/2017 | 8.01% | 4600501254
|  |  | Total |  | 58205196.69

## Deviations Register 2017-2018
DEVIATION REGISTER 2017/2018
ITEM NO | BID NUMBER | DESCRIPTION | BIDDER | DATE RECOMMENDED/NOTED BY DBAC | DATE APPROVED BY DG | DATE SUBMISSION FORWARDED TO NT | CONTRACT VALUE | SUPPORTED / NOT SUPPORTED BY TREASURY | WTE PROCEEDED/ WTE NOT PROCEEDED
1 | DEV0019WTE | Request to deviate from the normal procurement process by appointing FCL farming CC as per the court order for the removal of the razor wire fence and erection of a six strand bard wire fence: Tugela Vaal Government Waterwork in the Kwa-Zulu Natal Province. | FCL Farming CC | N/A Court Order | 2017-05-11 | 2017-05-17 | 6814582.56 | Conditional Support
2 | DEV0020WTE | Deviation form the normal SCM procurement process by appointing SABS as a sole supplier for the renewal of the annual subscription service to the SANS complete electronic collection of standards for a period of one year. | SABS | 2017-07-05 | 2017-07-12 | N/A below R1 million threshold for reporting to National Treasury as per National Treasury Oractice Note No.6 of 2007/2007 | 94819.31 | Not supported
3 | DEV0021 WTE | Request for approval to deviate from normal procurement process to approint Oracle Corporation as the original equipment manufacturer of Sun Microsystems servers and storage devices, for the support and maintenance of the sun servers and storage device | Oracle Corporation | 2017-07-06 | 2017-07-12 | N/A | 434179.97
4 | DEV0022 WTE | Response to the issues raised by DBAC on 16 March 2017 on the submission for deviation from the normal procurement procedure to approach and appoint South African Weather Service (SAWS) as sole service provider and approval of term of reference (ToR) for appointing SAWS to replicate and rollout the Inkomati-Usutu Catchment Management Agency Hydronet Water Control Room System to all 7 Water Management Areas. | SAWS | 2017-07-28 | 28/07/2017 | 2017-09-13 | 8400000 | Sole supplier , Accounting Officer can approve
5 | DEV0023 WTE | Request to deviate from normal procecures to appoint MSC Software as sole service provider for the renewal of annual maintenance and support of MSC Masterkey Software 2017-2018. | MSC | 2017-01-20 | 2017-08-25 | 2017-09-13 | 502855.27
6 | DEV0024 WTE | Request for approval to deviate fron normal procurement procedure to appoint Model Maker Systems as sole supplier of Model Maker in South Africa for annual software licence and support subscription used by survey services in the Free State Provice for the 2017/18 financial year. | Model Maker Systems | 2017-09-28 | 2017-10-02 | 2017-10-13 | 7854.1 | Sole supplier , Accounting Officer can approve
7 | 2 | Request for approval to deviate from normal procurement procedure to appoint C & C Technonologies South Africa (Pty) Ltd as sole supplier of Hypack in South Africa for renewal of annual Hypack Hydrographic Software licence and maintenance plan used by survey services in the Free State Povince for the 2017/18 financial year | C & C Technologies South Africa (Pty) Ltd | 2017-09-28 | 2017-10-02 | 2017-10-13 | 17330 | Sole supplier , Accounting Officer can approve
8 | W0432 WTE | Request to deviate from normal procurement processes by reinstating the term contract W0432 WTE in order to comply with the court judgement dated 23 May 2017 as the court order was used for the withdrawal of contempt against the minister and avoid possible litigation. | Messrs Surface Preparation Equipment and Coating (SPEC) | 2017-10-05 | 2017-10-02 | 2017-10-10 | 129623840.35 | Supported
9 | DEV 0026 WTE | Motivation for Deviation to procure goods/services from C & C Technologies South Africa, a sole supplier for the renewal of HYPACK Hydrographic Annual Aoftware Maintenance plan | C & C Technologies South Africa (Pty) Ltd | 19/10/2017 | 27/10/2017 | N/A | 8379 | Sole supplier , Accounting Officer can approve
10 | DEV 0027 WTE | Request to Deviate from normal Supply Chain Rules by using a single prefered service provider (Mr H Durieux) as approved professional person (APP) for dam safety rehabilitation of Nkadimeng Dam (category II) | Mr H Durieux (APP) | 14/11/2017 | 13/12/2017 | 18/12/2017 | R849 000.00 | Not supported
11 | DEV 0028 WTE | Request to Deviate from normal Supply Chain Rules by using a single prefered service provider (Mr H Durieux) as approved professional person (APP) for dam safety rehabilitation of Casteel Dam (category II) | Mr H Durieux (APP) | 14/11/2017 | 13/12/2017 | 18/12/2017 | R1 795 000.00 | Not supported
12 | DEV 0029 WTE | Request for approval to deviate from normal procurement processes to appoint Solidcad as the sole service provider of software maintenance and support (Tecs) for ANSYS Mechanical and support CFD Software products for 2017/18 | Solidcad | 09/11/2017 | 13/12/2017 | N/A | 247608 | Sole supplier , Accounting Officer can approve
13 | DEV 0030 WTE | Request for approval to deviate from normal procurement processes to appoint Optron (Pty) Ltd as a sole service provider to repair Trimble Survey Equipment for Southern Operations | Optron (Pty) Ltd | 23/11/2017 | 13/12/2017 | N/A | 22941 | Sole supplier , Accounting Officer can approve
14 | DEV 0031 WTE | Request for approval to deviate from normal supply chain management process for the appointment of Black Dot Property Consultants (Pty) Ltd as preferred service provider for a period of 10 month to complete the work previously appointed under bid WP0915WTE in which the contract was erroneously signed for 8 months instead of 18 months as per report to the portfolio comittee on Water and Sanitation on the status of the implementation of the Public Protector's remedial action | Black Dot Property Consultants (Pty) Ltd | 08/01/2018 | 19/01/2018 | 23/01/2018 | R701 926..89 | Not supported
16 | DEV 0033 WTE | Request for approval to deviate from normal procurement process to appoint Oracle Corporation South Africa as the original equipment manufacturer of Sun Microsystems and sole provider of technical support on all Oracle products, for the support and maintenance of the Sun servers and storage devices for a period of 1 year | Oracle Corporation South Africa | 06/02/2018 | 21/02/2018 | N/A | R638 021.75 | Sole supplier , Accounting Officer can approve
17 | DEV 0034 WTE | Request for approval to deviate from normal procurement procedure and appoint Drehmo Africa (Pty) Ltd, as the sole representative in South Africa, for servicing of Drehmo Actuators at Wagendrift Dam and Lavumisa Pump Station | Drehmo Africa (Pty) Ltd | 01/02/2018 | 21/02/2018 | N/A | 80000 | Sole supplier , Accounting Officer can approve

## Variation Order 2017- 2018
VARIATION ORDER REGISTER 2017-2018
| BID NUMBER | DESCRIPTION | CONTRACTOR | CONTRACT AMOUNT | VARIATION AMOUNT | TIME ONLY | COST ONLY | BOTH | DATE RECOMMENDED/APPROVED /NOTED BY DBAC | DATE APPROVED BY DG | PERCENTAGE | DATE REPORTED TO NATIONAL TREASURY AND AG (ABOVE THRESHOLD VALUES) | SAP CONTRACT NUMBER | COMMENTS
1 | W1020 WTE | Provision of bulk printing,packaging and mailing services for Chief Directorate: Revenue Management-Water Trading Entity: Approval of variation order for the extension of time for a period of one (1) month at no additional cost.[VO2] | Mailtronic Direct Marketing cc | 32059134.72 | 0 | x |  |  | 30/05/2017 | 30/05/2017 | 0% | N/A | 4600501218
2 | WP0485 WTE | Development of annual operating rules for the integrated Vaal River System (IVRS):[VO1] | Aurecon | 14802326 | 1400000 |  |  | x | 11/05/2017 | 11/05/2017 | 9.05% | N/A | 4600501364
3 | W0772 WTE | Request for extension of time of appraisal corporation's contract for the evaluation of properties affected by the raising of Clanwilliam Dam Wall.[VO1] | Appraisal Corporation (PTY)Ltd | 6127500 | 0 | x |  |  | 30/05/2017 | 30/05/2017 | 0% | N/A | 4600500985
4 | W0871 WTE | Mdloti River Development Project: Raising of Hazelmere Dam: Request to extend contract period.[VO2] | Group Five Construction | 498157000 | 0 | x |  |  | 13/07/2017 | 31/07/2017 | 0% | N/A | 4600004635
5 | WP0538 WTE | Request for extension of time for the roll out of SAP to the catchment management agencies for the department.[VO2] | EOH Mthombo | 118555444 | 0 | x |  |  | 28/07/2017 | 31/07/2017 | 0% | N/A | 4600501116
6 | WP0485 WTE | Request for extension of time for the the asset management plans (AMP's) as well as other asset management support for the four operational areas and one national AMP done by Bicacon.[VO2] | Bicacon (PTY) Ltd | 112889991.24 | 0 | x |  |  | 14/09/2017 | 19/09/2017 | 0% | N/A | 4600501512
7 | WP1059 WTE | Request for the approval of variation of the project timeline for the implementation of validation and verification of the existing water use in the Mzimvubu to Tsitsikamma and Berg to Olifants Water Management Areas.[VO2] | MHP Geospace (Pty)Ltd | 17809353.6 | 0 | x |  |  | 14/09/2017 | 19/09/2017 | 0.16% | N/A | 4600500597
|  |  | Aurecon South Africa(Pty) Ltd | 25202035.27 | 0 | x |  |  | 14/09/2017 | 19/09/2017 | 0.16% | N/A | 4600500597
8 | W1098 WTE | Request for extension of time for completing the outstanding maitenance and repair of all Tienfontein Pump Station Pump sets as and when required.[VO1] | Sulzer Pumps South Africa (PTY) Ltd | 15000000 | 0 | x |  |  | 28/09/2017 | 20/09/2017 | 0.16% | N/A | 4600500770
9 | WP0485 WTE | Request for extension of time for the engineering services/Manahano: For the completion of construction monitoring works of the new steel pipelines that replace the problematic GRP pipes on the Luvuvhu River Government Scheme.[VO1] | Bigen Africa Services (Pty)Ltd | 7887943.17 | 0 | x |  |  | 14/09/2017 | 19/09/2017 | 0.16% | N/A | 4600501217
10 | WP1003 WTE | Extension of contract periods for the Luvuvhu River Government Water Scheme: Completion of construction of new steel pipelines that replaces the problematic GRP pipes.[VO2] | QPI TIS Quality Service (Pty)Ltd | 1294781.43 | 0 | x |  |  | 14/09/2017 | 19/09/2017 | 0% | N/A | 4600501058
11 | WP0479 WTE | Extension of contract periods for the Luvuvhu River Government Water Scheme: Completion of construction of new steel pipelines that replaces the problematic GRP pipes. [VO4] | Murray and Dickson Construction (PTY)Ltd | 72170623.05 | 0 | x |  |  | 14/09/2017 | 19/09/2017 | 0% | N/A | 4600501056
|  |  | Ascul Construction cc | 50048759.05 | 0 | x |  |  | 14/09/2017 | 19/09/2017 | 0% | N/A | 4600501056
|  |  | WK Construction SA (Pty) Ltd | 48116477.54 | 0 | x |  |  | 14/09/2017 | 19/09/2017 | 0% | N/A | 4600501056
12 | W0399 WTE | Request for extension of time: Luvuvhu River Government Water Scheme Vuwani Pump Station mechanical contract.[VO3] | KSB Pumps and Valves(Pty)Ltd | 22832211.25 | 0 | x |  |  | 05/10/2017 | 12/10/2012 | 0% | N/A | 4600001413
13 | W0647 WTE | Request to extend term contract for maintenance,repair and refurbishment projects for the central operational area: Mechanical and electrical asset management support of major plant and machinery for the Northern,Central,Eastern and Western Operations ( Limpopo,Mpumalanga,North-West,Gauteng,Free State,Northern Cape, Kwa-Zulu Natal,Eastern-Cape and Western Cape)[VO2] | Bicacon (PTY) Ltd | 7480985.83 | 0 | x |  |  | 08/11/2017 | 10/11/2017 | 0% | N/A | 4600500578
14 | W0871 WTE | Request to extend contract period for Mdloti River Development Project: Raising of Hazelmere Dam. [VO3] | Group Five Construction | 498157000 | 0 | x |  |  | 28/11/2017 | 28/11/2017 | 0% | N/A | 4600004635
15 | DWS 13-0216 WTE | Request for extension of contract period for the implementation of validation and verification of existing lawful water use in Vaal,Orange and Limpopo Water Management Areas.[VO1] | DMT Kai Batla (Pty)Ltd | 52546191 | 0 | x |  |  | 12/12/2017 | 13/12/2017 | 0% | N/A | 4600501149
16 | WP0268 WTE | Request for extension of the contract completion date without costs for environmental control officer: Mdloti River Development : Hazelmere Dam Raising.[VO3] | Iliso Consulting | 1154546.4 | 0 | x |  |  | 07/12/2017 | 13/12/2017 | 0% | N/A | 4600004344
17 | WP0824 WTE | Request for extension of the contract period without costs for project management and construction supervision professionalservices for the raising of Hazelmere Dam.[VO2] | Ingerop South Africa | 23286016 | 0 | x |  |  | 07/12/2017 | 13/12/2017 | 0% | N/A | 4600003566
18 | W0401 WTE | Request for extension of time-Luvuvhu River Government Water Scheme-Vuwani Pump Station: Electrical contract.[VO3] | E.D.S.E.Projects (Pty) Ltd | 16668292.88 | 0 | x |  |  | 14/12/2017 | 28/12/2017 | 0% | N/A | 4600001414
19 | W0028 WTE | Request for extension of contract period for hydrological and specialised consulting engineering services in the Limpopo Province to complete final oversight work of contracts W0399 WTE and W0401 WTE until the handing over of the completion certificate of the project.[VO1] | EVN Africa Consulting Services (Pty) Ltd | 771198.82 | 0 | x |  |  | 14/12/2017 | 28/12/2017 | 0% | N/A | 4600501647
20 | DWS03-1115 WTE | Request for approval to extend time and cost for support,maintenance and enhancements for the electronic water use licence application and authorisation system (E-wulaas) over a perid of three(3) months. VO1 | IEMSYS cc | 10493928 | 1311728.49 |  |  | x | 25/01/2018 | 25/01/2018 | 12.49% | N/A | 4600500280
21 | W0647 WTE | Request to extend term contract for maintenance,repair and refurbishment projects for the central operational area: Mechanical and electrical asset management support of major plant and machinery for the Northern,Central,Eastern and Western Operations ( Limpopo,Mpumalanga,North-West,Gauteng,Free State,Northern Cape, Kwa-Zulu Natal,Eastern-Cape and Western Cape)[VO3] | Bicacon (PTY) Ltd | 7480985.83 | 0 | x |  |  | 15/03/2018 | 23/03/2018 | 0% |  | 4600500578
|  |  | Total |  | 2711728.49