## Slide 1: ROBBEN ISLAND MUSEUM INFRASTRUCTURE PLAN FACILITIES MANAGEMENT AND CAPEX PROGRAMME
Director General: Arts and Culture
Date: 21 August 2018

## Slide 2: OUTLINE OF THE PRESENTATION
ABREVIATIONS
BACKGROUND
OVERVIEW
OBJECTIVE
FACILITIES MANAGEMENT
CAPEX PROJECTS AND FUNDING
PROGRESS
CHALLENGES
FINANCIAL IMPLICATIONS
FUTURE CAPITAL INFRASTRUCTURE PROJECTS
RIM STATE OF READINESS
OVER ARCHING AGREEMENT AMOUNGST THE TRIPARTITE MEMBERS
CONCLUSION

## Slide 3: ABBREVIATIONS
DPW: Department of Public Works
DAC: Department of Arts & Culture
DPSA: Department of Public Service Administration
RIM: Robben Island Museum
CDC: Coega Development Cooperation
FM: Facilities Management
Capex: Capital Infrastructure
SDA: Service Delivery Agreement
STEERCO: Steering committee
UNESCO: United Nations Educational, Scientific and Cultural Organisation.

## Slide 4: ABBREVIATIONS, cont…
SAHRA: South African Heritage Resources Agency
OUV: Outstanding universal value
TOR: Terms of Reference
IA: Implementing Agent
OHSA: Occupational Health and Safety Act
PSP: Professional Service Providers
DG: Director General
PM: Project Manager
SLA: Service Level Agreement

## Slide 5: PURPOSE
To provide feedback and progress on the RIM FM and Capex programs to date.
To report on Milestones achieved.
To report on challenges encountered and,
To indicate interventions and to present solutions under consideration

## Slide 6: INTRODUCTION
DPW is the custodian of immovable assets on behalf of the State, and therefore is responsible for infrastructure operations & maintenance.
RIM is an entity of DAC, therefore DAC is responsible for funding of Capex projects.
RIM is a World Heritage Site and a National Heritage Site.
Given RIM’s significance and World Heritage status, DAC and DPW Ministers and DGs established an infrastructure governance structure headed by a steering committee (Steercom), that was mandated to speedily address the Tripartite Agreement (DAC/DPW/RIM SDA 12/06/2015) mandates, noting the following:
  The definition of roles and responsibilities for tripartite parties (DPW, DAC & RIM)
  Ensuring that all qualified and appropriate resources required to carry out the necessary work are provided.
  Develop a programme and implementation plan for infrastructure and asset management.
  Develop a facilities management strategy specific to the island.
  Establish a task prioritisation model and develop a Priority List for minor works and projects.
  Ensure logistic support for smooth running of the programme, such as accommodation, cargo and personnel transportation.
  Ensure compliance with all relevant regulations.

## Slide 7: BACKGROUND
Maintenance on the Island was carried out by DPW personnel, stationed at the Island between 1996 until 2011.
During 1996 and 2002, many qualified artisans, horticulturists and gardeners left the DPW and they could not be replaced, this resulted in deterioration in the Island’s infrastructure.
RIM took over the maintenance from DPW in 2012 after continued deterioration and lack of maintenance.
In 2015 DPW, DAC and RIM signed the Tripartite Agreement (SDA) to collaborate on FM and Capex programs for the operations and maintenance of the Island’s infrastructure and facilities.
In May 2015, DPW concluded a 4-year SLA with CDC as the implementing agent for FM and Capex services required at Robben Island.
Priority projects were identified and approved, following a condition assessment of active facilities.
In 2016 a decision was passed by the Steercom that DAC transfers Capex funds to RIM.
In June 2016, RIM entered into an SLA with CDC for Capex projects on the basis of the Tripartite Agreement and FM SLA.

## Slide 8: PROBLEM STATEMENT
Robben Island (RIM) infrastructure and facilities are dilapidated and in a state of disrepair due to the lack of maintenance and slow progress of the Capital Works programme
The process that has been put in place through the tripartite agreement has not been able to adequately address and support RIM’s visitor management plan and as a result visitor experience has been negatively impacted
The Portfolio Committee visited RIM and raised concerns about the deteriorating conditions
A follow up visit by a team led by the DG of DAC comprised of DPW, DEA, and RIM was done
Failure to maintain and repair infrastructure on the Island threatens the Outstanding Universal Value status of this iconic site if not urgently arrested.

## Slide 9: OVERVIEW
Components of the Programme and Funding streams
Components | Description | Responsible institution for Funding
Facilities Management | Maintenance and breakdowns | DPW
Capex Projects | Upgrading, replacements, restorations and extensions | DAC
Municipal Services | Diesel to provide electricity | RIM (Cost of doing business)

## Slide 10: FACILITIES MANAGEMENT CONTRACT
Objectives of the CDC SLA:
CDC to serve as the Implementing Agent to DPW, to do maintenance, capital projects and to put together an FM strategy for Robben Island
To serve as a catalyst to implement resources and systems in order to ensure that all assets (covered in the scope) on Robben Island are properly maintained.
To address immediate threats by reducing the potential risk to assets and losing its Outstanding Universal Value (OUV) to the World Heritage Committee
To cover a wide range of assets including buildings, infrastructure, cemeteries, gardens, quarries, recreational facilities, maritime safety as well as the natural environment
To conserve and maintain according to International Best Practice as well as SAHRA (South African Heritage Resources Agency) principles and UNESCO

## Slide 11: FACILITIES MANAGEMENT CONTRACT
CDC SLA Scope:
The FM contract addresses:
  Assessments
  Repairs
  Maintenance (planned, statutory, preventative, adhoc and emergency maintenance)
  Project management
  Expert advice
  Compliance to statutory and legislated regulations e.g. OHS, heritage etc.

## Slide 12: FACILITIES MANAGEMENT CONTRACT
CDC SLA Scope:
It includes all maintenance work related to the active buildings as well as natural fabric and covers:
  Soft services (e.g. waste and environmental management, pest control)
  Technical services (e.g. roads and sidewalks, storm water reticulation)
  General services (e.g. external buildings cleaning, helipad, event support)
  Plant operations (e.g. desalination plant, power plant, diesel storage)
  Asset Management (Health and Safety environment)
The FM programme is geared towards RIM retaining its Outstanding Universal Value, in the execution of conservation and maintenance of the facilities

## Slide 13: FACILITIES MANAGEMENT CONTRACT
FM Progress:
Technical and Bulk Services repairs, upgrades and operations:
Power supply stabilisation - Operations contract is in place, All original generators upgraded, Power supply network repaired
Water supply stabilisation - Desalination plant operations contract in place, Pumps and the filtration system repaired and upgraded
Sewer system maintenance - Pumps upgraded
Diesel reticulation and storage – Filtration system upgraded, Tanks cleaned, Reticulation upgraded
General maintenance:
Attention given to projects on the original priority projects list at the beginning of the programme
Planned maintenance schedule in place for the above projects
Call centre established
Soft services:
Waste collection in place

## Slide 14: FACILITIES MANAGEMENT CONTRACT
FM Progress: continued
Repairs and maintenance:
Implementation is done based on the plan that was approved by Steercom however, progress is not satisfactory hence the proposal for RIM to takeover the implementation of the infrastructure programme
Horticultural services:
This services falls under ‘Soft Services’, however Steercom approved the proposal for RIM to provide the services and invoice DPW.
The approval was over 3 years through a team of 13 employees contracted to RIM and their contract ended 31 March 2018.
Following the expiry of the team of 13 contracted employees, RIM appointed a team of 5 contract workers as an interim solution.
The current team of 5 has not been able to push back the horticulture backlog resulting in long grass, trees etc.
Agreement has been reached that DPW will allocate funding for RIM to increase the team for the duration of CDC/FM contract ending March 2018.
The agreement includes the use of the DPW tractor to urgently reduce overgrown grass.

## Slide 15: CAPEX PROJECTS
Objectives and Scope of the RIM CDC SLA:
CDC to provide design to construction and contract administration of the following identified and funded capital projects:
  Bluestone quarry wall
  Waster water treatment plant
  Desalination plant
  Power generation
  Diesel plant and reticulation
  Electrical reticulation MV
  Harbour precinct
CDC to address the work in line with the objectives stated under the FM contract noting; the protection of RIM’s OUV, compliance to all applicable regulations

## Slide 16: CAPEX PROJECTS
Progress on projects
Stage/Status | Proposed approach/ Way forward | Timeframes
BLUE STONE QUARY WALL |  | 
Stage 4 (Documentation and Procurement) – Complete | RIM will take over the project: The Technical Proposal for implementation has been drawn. The appointment of a conservation/ restoration specialist has started (to design and implement the restoration in consultation with Ex-political prisoners). The specialist will manage the wall restoration with the advise of Ex-political prisoners to ensure authenticity | Construction to start end of September 2018 for 12 Months
DESALINATION PLANT |  | 
Stage 4 (Documentation and Procurement) – Not completed | DPW to proceed with implementation of the project. The proposed new project sequence approach to be the investigation of the existing reticulation and the sea water intake before the plant upgrade. | Investigations, designs, budget revisions and tender process over Q2/4 2018 Construction for reticulation to start from Q2 of 2018/19 (on available budget) New budgets addressed in AUMP by June 2019
NEW FLOATING JETTY |  | 
Stage 5 (construction) – Complete | N/A – Project complete. | N/A
WASTE WATER TREATMENT PLANT |  | 
Stage 4 (Documentation and Procurement) – Complete | DPW to proceed with implementation of the project. Proposed new procurement process to allow for alternative designs and technical solutions. | Procurement to start September 2018 Construction to start Q1 of 2019/20
HARBOR SAFETY |  | 
Stage 5 – Service provider has been appointed and currently manufacturing. | DPW to proceed with implementation of project. | 3 Months

## Slide 17: CAPEX PROJECTS
ROBBEN ISLAND CAPEX | Allocation 2015/16 | Allocation 2016/17 | Allocation 2017/18 | Total Allocation
Power Generators 1000 kVa & 450 kVa | 6,000,000 | 6,000,000 | 00 | 6,000,000
Diesel Reticulation | 250,000 | 1,500,000 | 00 | 1,500,000
Blue Stone Quarry Wall | 16,354,829 | 9,328,723 | 10,000,000 | 19,328,723
Waste Water Treatment Plant | 1,800,000 | 5,300,000 | 00 | 5,300,000
Desalination Plant | 6,844,000 | 7,000,000 | 00 | 7,000,000
Floating Jetty | 7,064,894 | 8,690,000 | 00 | 8,690,000
Safety Handrail | 1,000,000 | 1,500,000 | 00 | 1,500,000
Total | 39,313,723 | 39,318,723 | 10,000,000 | 49,318,723
Budget allocation on projects

## Slide 18: CAPEX PROJECTS
Project | Approved Budget 16/17 & 17/18 | Tranche 1 Receipt: 14 July 2016 (Qtr1&2) | Tranche 2 Partly paid in April/May 2018 | Actual Expenditure 16/17 | Actual Expenditure 17/18 | Actual Expenditure 18/19 | Paid CDC Fees 17/18 | Total Project Cost | Tranche Balance Available
New Power Plant Generator Engine (1000kva) no 5 & 2x450kva | 6 000 000 | 1 700 000 | 4 634 771 | 5 480 683 | 331 366 | - | 494 024 | 6 306 073 | 28 698
Effluent Plant - New | 5 300 000 | 850 000 | -361 788 | 43 502 | 406 462 | - | 38 247 | 488 212 | -
Bluestone Quarry | 9 328 723 | 3 749 401 | -2 967 212 | 608 137 | 935 421 | - | 47 739 | 1 591 297 | -809 109
Desalination Plant (new reverse osmosis plant) | 7 000 000 | 1 050 000 | -520 775 | 54 264 | 442 661 | - | 32 300 | 529 225 | -
Harbour Precinct - New Jetty | 8 690 000 | 3 090 000 | 5 967 309 | 227 034 | 2 310 973 | 4 610 140 | 24 005 | 7 172 151 | 1 885 158
Harbour Precinct - Safety | 1 500 000 | 400 000 | 2 466 942 | - | 246 029 | - | 20 912 | 266 942 | 2 600 000
Diesel Plant & Reticulation - new fuel storage plant complete | 1 500 000 | 290 000 | 1 542 049 | 60 192 | 1 628 332 | - | 132 400 | 1 820 925 | 11 124
TOTAL (VAT INCL) | 39 318 723 | 11 129 401 | 10 761 296 | 6 473 812 | 6 301 244 | 4 610 140 | 789 628 | 18 174 824 | 3 715 872
Budget expenditure on projects

## Slide 19: CAPEX PROJECTS
Allocation 2015/16 | Allocation 2016/17 | Allocation 2017/18 | Total Allocation | Pre-tender Estimate | Market | Variance | Consultant Fees | IA Fee (CDC)
Power Generators 1000 kVa & 450 kVa |  |  |  |  |  |  |  | 
6,000,000.00 | 6,000,000.00 | - | 6,000,000.00 | 6,000,000.00 | 5,586,559.00 | 7% | 251,740.00 | 496,255.42
Diesel Reticulation |  |  |  |  |  |  |  | 
250,000.00 | 1,500,000.00 | - | 1,500,000.00 | 1,500,000.00 | 1,600,000.00 | 6% | 60,192.00 | 132,616.32
Blue Stone Quarry Wall |  |  |  |  |  |  |  | 
16,354,829.00 | 9,328,723.00 | 10,000,000.00 | 19,328,723.00 | 20,638,070.66 | 28,920,881.60 | 29% | 1,774,874.08 | 1,456,841.41
Waste Water Treatment Plant |  |  |  |  |  |  |  | 
1,800,000.00 | 5,300,000.00 | - | 5,300,000.00 | 8,298,411.54 | 17,529,429.18 | 53% | 122,257.00 | 547,343.46
Desalination Plant |  |  |  |  |  |  |  | 
6,844,000.00 | 7,000,000.00 | - | 7,000,000.00 | 13,045,567.20 | - | 0% | 211,191.00 | 861,689.28
Floating Jetty |  |  |  |  |  |  |  | 
7,064,894.00 | 8,690,000.00 | - | 8,690,000.00 | 8,690,000.00 | 8,690,000.00 | 0% | 369,304.00 | 588,854.76
Safety Handrail |  |  |  |  |  |  |  | 
1,000,000.00 | 1,500,000.00 | - | 1,500,000.00 | 1,500,000.00 | 1,500,000.00 | 0% | 246,029.00 | 148,412.47
39,313,723.00 | 39,318,723.00 | 10,000,000.00 | 49,318,723.00 | 59,672,049.40 |  |  | 3,035,587.08 | 4,232,013.11
Variance between estimates and market price on completed and tendered projects

## Slide 20: CHALLENGES EXPERIENCED WITH THE FM AND CAPEX PROGRAM
Challenge | Solution | Responsible | Date
Steercom not functioning | Executives commit to attend Steercom meetings. | DAC, RIM and DPW executives. | Immediately
Delays on signing SLA and transfer of funds between RIM and CDC. This resulted on 6 months delay to start capex projects. | Fast track processes related to finalisation of SLA between RIM and CDC especially approval by RIM Council. | RIM | Resolved
Establishment of structures outside tripartite arrangement e.g RIM and CDC meetings without DPW and DAC. | Capex progress and decisions to be discussed at Steercom. | RIM | Immediately
Delays on implementation of Capex and decision making. | Steercom to revert to monthly seating. | All | Immediately
Price variance between estimates and market. | Consultants to use market related prices for logistics & not RIM prices. | DPW | Immediately
Establishment of structures outside tripartite arrangement e.g.

## Slide 21: CHALLENGES EXPERIENCED WITH THE FM AND CAPEX PROGRAM
Challenge | Solution | Responsible | Date
Non-availability of the boat for (service providers/cargo) to & from the Island (currently service providers are only allowed on the staff ferry departing 07h00 returning 17h00). It should be noted that Service providers pay for their tickets to the Island and they charge for the hours waiting for the boat. | Service providers to be accommodated on the commercial boat in order to contain costs. | RIM | Immediately
Project Manager refused to take the needs of the client over the Architect’s inputs especially on Blue Stone Quary project. Project Manager was replaced in February 2017. | Project Manager to be replaced. | CDC | Resolved. Project Manager was replaced.
RIM and CDC updates established outside Steetrcom | Steercom to align all external meeting requirements | RIM | At next Steercom
Establishment of structures outside tripartite arrangement e.g.

## Slide 22: FINANCIAL IMPLICATIONS
Facilities Management
The facilities management project is funded by DPW.
The 1st allocation before the appointment of CDC and condition assessment was R52m
Estimated value at end of 4 year contract after the condition assessment is at R112m.
Capex
Capex project are funded by DAC.
Allocations before the tripartite agreement was R16m
Allocations during tripartite agreement was R49m
Total allocations as at end of 2017/18 financial year is R65m
All the above mentioned capex allocations were transferred to RIM.

## Slide 23: FINANCIAL IMPLICATIONS
Future capex projects
Description of the project | Budget for 2018/19 | Budget for 2019/20 | Budget for 2020/21
Effluent Plant: New WWTW | 16 300 000,00 | 0 | 0
Restoration and conservation of the build environment (high, low priority, village precinct): including Asbestos management, removal and disposal of unsafe structures, replacement of deteriorated rainwater installations on buildings along the value chain | 5 000 000,00 | 9 625 000,00 | 1 200 000,00
Harbour Precinct: New floating jetty | 2 000 000,00 | 0 | 0
Harbour Precinct: Safety hand rail | 1 800 000,00 | 0 | 0
Restoration and repairs to helicopter landings and transport depot | 5 000 000,00 | 0 | 0
Upgrade of facilities to enhance interpretation and visitor management: maximum security prison, sobukwe house, visitors centre, alpha 1 ablutions and MPLC kitchen | 1 900 000,00 | 3 000 000,00 | 500 000,00
Nelson Mandela Gateway: Reconfiguration of space to accommodate exhibition and executive office space, Fire and OHS compliance | 1 400 000,00 | 2 000 000,00 | 1 000 000,00
Mayibuye Archives alternative accommodation | 1 500 000,00 | 15 000 000,00 | 3 522 000.00
Refurbishment of the single quarters (Block A & B): R6 200 000,00 Allocation reprioritised to the refurbishment | 0 | 6 200 000,00 | 0
Refurbishment of the Ou Tronk as part of the Interpretation | 0 | 2 000 000,00 | 1 000 000,00
Conditional assessment of existing buildings and structures. | 0 | 0 | 1 500 000,00
TOTALS | 34 900 000 | 37 825 000 | 8 722 000

## Slide 24: RIM STATE OF READINESS
RIM has proposed to DAC/ DPW to be the Implementing Agent for DPW for FM services and Capex projects. (DAC has already indicated the willingness to allow RIM to implement the capex projects as the funds were already transferred to RIM and RIM has demonstrated capacity to manage the projects).
This is based on the overall experience that RIM has had with infrastructure and the decision taken by RIM’s Council to established a fully-fledged Infrastructure and Facilities Management Department to address the islands complex infrastructure requirements.
RIM’s organisational structure in relation to Infrastructure and Facilities Management, is in place as outlined below.
The structure derives direct support from the Heritage (GIS and conservation management) and Finance (procurement).
A guideline of this proposed arrangement in draft format is in discussion with DPW and DAC, it outlines RIM’s State of Readiness for the implementation of Infrastructure projects
RIM has already tested the structure in facilitating 3rd party funded projects such as the PV and battery power plant design installation and the Lotto funded memorialisation projects that resulted in the restoration of the harbour wall and buildings amongst others.

## Slide 25: RIM STATE OF READINESS

## Slide 26: OVER ARCHING AGREEMENT AMONGST THE TRIPARTITE MEMBERS
The following interim measures and interventions are results of meetings of the Tripartite parties to resolve their challenges and address RIM’s infrastructure needs:
FM measures and interventions:
On RIM’s proposal assume the role of Implementing Agent for FM services: DPW has received and is processing the proposal with a view to give its outcome by the end of September 2018.
The CDC agreement will run its full course until 31st March 2019.
Horticulture services: Increase the horticulture contract workers from 5 to 13 with immediate effect. Funds for the 13 contract workers will be catered for under the FM budget until the end of the CDC contract
Capex measures and interventions:
Condition assessment will be conducted for all the active and non active buildings on the island.
A comprehensive rehabilitation plan will be developed and implemented for all the buildings, guided by the condition assessment results.
Rehabilitation implementation will be guided by RIM, noting compliance, health and safety and the interpretation plan, and may necessitate temporary route closures for implementation plan.
DPW remains the custodian of RIM infrastructure programme

## Slide 27: CONCLUSION
The Tripartite parties are in agreement that Robben Island’s infrastructure must undergo comprehensive rehabilitation.
A detailed implementation plan will be finalised after the completion of the conditions assessment.
Steercom will be resuscitated starting in September 2018 and will meet on a monthly basis.
DG to DG meetings to be held one per quarter to strengthen oversight and monitoring.

## Slide 28: ENKOSI