## Slide 1: First QUARTER PERFORMANCE REPORT first quarter for the 2018/19 financial year
Director-General : Arts and Culture
Date:28 August 2018

## Slide 2: PRESENTATION OUTLINE
Performance Overview
First quarter performance overview
Comparative Analysis of the first Quarter 2017/18 and the first Quarter of 2018/19
Programme- Specific performance
Highlights of the first quarter
Performance targets which were achieved in the first quarter
Performance targets which were not achieved in the first quarter
Expenditure Report

## Slide 3: PERFORMANCE OVERVIEW
The Department planned to implement and achieve 27 performance targets between 01 April 2018 to 30 June 2018 , however 24 (89%) of those were achieved and 3 (11%) were not achieved. Below were contributing factors to non achievement:
Approved feasibility and due diligence reports on amalgamation of DAC public entities- The market quoted above the threshold of the budgeted amount.
No. of flags installed in schools- The process of getting inputs that inform the scope of the project from provinces took longer than envisaged which impacted on the drafting scope of the project.
Feasibility study report on Resistance and Liberation Movements Museum completed - the indepth technicality of the TORs for the appointment of the service provider to undertake the Feasibility Study for the establishment of the RLMM required external expertise, as a result dependency on external stakeholders caused delays

## Slide 4: PERFORMANCE OVERVIEW…Cont.
It is noteworthy that this is a preliminary report of the first quarter, as per Treasury guidelines. The preliminary reports are generated 30 days after the end of the quarter and should be presented to internal audit for further scrutiny and validation before presenting it to the Audit Committee for final assurance.
The final performance report should d be submitted to National Treasury 120 days after the end of each quarter. The Portfolio Committee (PC) is therefore requested to note this, and that the final score or performance may be different from the scores or performance presented in this preliminary report.

## Slide 5: 1st QUARTER PERFORMANCE OVERVIEW
Chart: 
| Achieved | Not Achieved
 | 0.89 | 0.11

## Slide 6
Comparative Analysis of the FIRST Quarters
first quarter 2017-18 vs first quarter 2018-19

## Slide 7: Comparative Analysis of the FIRST Quarters (2017-18 vs 2018-19)
NB: The 1st quarter performance of 2018/19 has improved compared to 2017/18 by 10%
Chart: 
| 2017-18 First Quarter | 2018-19 First Quarter
Achieved | 0.79 | 0.89
Not Achieved | 0.21 | 0.11

## Slide 8
Programme-Specific Performance

## Slide 9: Programme-specific performance
Chart: 
| Administration | Institutional Governance | Arts and Culture Promotion and Development | Heritage Preservation and Promotion
Achieved | 1 | 0.86 | 1 | 0.67
Not Achieved | 0 | 0.14 | 0 | 0.33

## Slide 10: Highlights of the first quarter
As part of Africa Month celebrations, the DAC in collaboration with the African Cultural Music and Dance Association (ACUMDA) hosted the Gcwala-Ngamasiko Cultural Festival on Sunday, 27 May 2018 at the Freedom Square in Kliptown, Soweto. Gcwala-Ngamasiko Cultural Festival is one of the initiatives that is aimed at promoting and preserving our rich cultural heritage.
Youth Day was commemorated on Saturday 16 June 2018 at Orlando Stadium in Soweto. Youth Day commemorates the Youth of 1976 who stood up against the apartheid government and laid down their lives fighting for freedom and the right to equal education. This year’s Youth Month took place during the centenary year of Nelson Mandela and Albertina Sisulu, was commemorated under the theme “Live the legacy: Towards a socio-economically empowered youth”.

## Slide 11: Highlights of the first quarter
On Friday, 15 June 2018, Minister Nathi Mthethwa led Youth Month Dialogue on racism, social cohesion and nation building at the Imbizo Hall, University of Johannesburg, Soweto Campus in partnership with Unilever and the University of Johannesburg. The dialogue which was broadcast live on SA FM, formed part of the 2018 Youth Month under the theme, Live the legacy: Towards a socio-economically empowered youth”.
Minister Nathi Mthethwa opened the newly constructed Tshing Community Library as part of Government’s ongoing efforts to create a reading nation. The event took place on Thursday, 14 June 2018 at Tshing, JB Marks Local Municipality, Ventersdorp in North West. Thousands of children from rural schools around Tshing and other neighboring communities are set to benefit from this structure built to bring access to library service and learning tools closer to people of all ages. The newly constructed community library will be fully equipped with all the necessary resources and books that will allow easy access to information. The community will also have access to the use of computers with internet that will assist mostly job seekers, especially unemployed graduates and youth on their career development and access to information.

## Slide 12: Highlights of the first quarter
The Deputy Minister of Arts and Culture, Ms Makhotso Maggie Sotyu has in partnership with the Free State Provincial Archives, and the Department Sport, Arts, Culture and Recreation MEC, launched the 2018 Annual Archives Awareness Week, under the theme “Archives: Our Lives, Our Legacy: Workers Rights”
Minister Nathi Mthethwa hosted the USIBA Awards on Friday, 01 June 2018 at the Emperor’s Palace. The awards celebrate the immense richness of the arts heritage across the creative arts landscape. According to the Minister, it’s a moment to pay tribute to those who make the creative arts of South Africa known in the continent and globally. We are deliberate in ensuring that we do this while they are still alive and not upon their deaths when they can no longer hear us praise them and thank them. The awards showcase and boasts not only the pride and excellence of the nation’s artistic, creative and cultural industries, but that of the African continent and further represents what we as Africans have to offer to the world as a whole

## Slide 13
PERFORMANCE TARGETS WHICH WERE ACHIEVED in the first QUARTER

## Slide 14: ADMINISTRATION
PERFORMANCE INDICATOR | 2018/19 ANNUAL TARGET | 1st QUARTER TARGET | ACTUAL ACHEIVEMENT AS AT 30 JUNE 2018 | % ACHIEVEMENT
No. of communication and marketing campaigns implemented to profile the Department | 8 | 3 | 3 communication and marketing campaigns were implemented to profile the Department (Freedom Day, Africa Month and Youth Day) | 100%
% of total value of procurement awarded to BBBEE-compliant service providers | >70% | >70% | 86% of the total value of procurement was awarded to BBBEE compliant service providers | Overachieved by 22%
No. of Izimbizo held | 20 | 5 | 9 Izimbizo were held. EC 2, FS 1, KZN 1, WC 1, LP 1, NW 1, and GP 2 | Overachieved by 80%
Approved workplace skills plan | WSP approved by DG by 30 April 2018 | WSP approved by DG by 30 April 2018 | The WSP was approved by DG before 30 April 2018 and submitted to PSETA | 100%
Number of quarterly monitoring reports approved | 4 | 1 | 1 quarterly monitoring report was approved | 100%

## Slide 15: INSTITUTIONAL GOVERNANCE
PERFORMANCE INDICATOR | 2018/19 ANNUAL TARGET | 1ST QUARTER TARGET | ACTUAL ACHEIVEMENT AS AT 30 JUNE 2018 | % ACHIEVEMENT
Number of departmental and entities’ performance information reports or documents approved | 15 | 3 | Fourth quarter report of public entities analysed and approved 4th quarter report was completed and is preliminary pending audit. 3rd quarter report was finalised and audited The outcome 14 report was approved and submitted to Cabinet | 100%
Approved governance tools for DAC public entities | Approved governance framework for DAC public entities | First draft governance framework developed | The first draft of the governance framework was developed as planned | 100%

## Slide 16: INSTITUTIONAL GOVERNANCE
PERFORMANCE INDICATOR | 2018/19 ANNUAL TARGET | 1ST QUARTER TARGET | ACTUAL ACHEIVEMENT AS AT 31 JUNE 2018 | % ACHIEVEMENT
No. of cultural diplomacy engagements coordinated | 20 | 5 | DAC participated in the Working Visit to Angola on the 10 - 12 April 2018. DAC attended and participated in the 36th Session of the World Intellectual Property Organisation Standing Committee on Copyright and Related Rights in Geneva, Switzerland on the 28 May – 01 June 2018. DAC hosted the Africa Month programme in May 2018 and this involved participation of other African countries DAC hosted and participated in the Algerian Week/Seasons in South Africa on the 01 - 10 May 2018. DAC participated in the AU Workshop on the Charter for African Cultural Renaissance in Mozambique on 5 - 7 June 2018 | 100%

## Slide 17: INSTITUTIONAL GOVERNANCE
PERFORMANCE INDICATOR | 2018/19 ANNUAL TARGET | 1ST QUARTER TARGET | ACTUAL ACHEIVEMENT AS AT 31 JUNE 2018 | % ACHIEVEMENT
No. of national days commemorated | 6 | 2 | Two National Days were hosted. The Freedom Day was held on 27 April 2018 in Bloemfontein, Free State Province. The Youth Day was held at Orlando Stadium, Soweto in Johannesburg on 16 June 2018. | 100%
No. of social cohesion projects implemented | 12 | 3 | 6 community dialogues convened | Overachieved by 100%
No. of target-group programmes supported | 3 | 1 | 1 Target Group Programme supported (Youth Month Programme) with the following projects: 1. My History Educational Tour 2. Youth Activation Event 3. Basha Uhuru Youth Festival | 100%

## Slide 18: ARTS AND CULTURE PROMOTION AND DEVELOPMENT
PERFORMANCE INDICATOR | 2018/19 ANNUAL TARGET | 1ST QUARTER TARGET | ACTUAL ACHEIVEMENT AS AT 31 JUNE 2018 | % ACHIEVEMENT
No. of flagship projects supported | 20 | 3 | 3 flagship projects were supported | 100%
No. of professional artists projects supported | 6 | 3 | 3 professional artists’ projects were supported | 100%
No. of multi-year Human Language Technologies (HLT) projects supported | 6 | 6 HLT projects supported | 6 multi-year HLT projects were supported | 100%

## Slide 19: ARTS AND CULTURE PROMOTION AND DEVELOPMENT
PERFORMANCE INDICATOR | 2018/19 ANNUAL TARGET | 1st QUARTER TARGET | ACTUAL ACHEIVEMENT AS AT 31 JUNE 2018 | % ACHIEVEMENT
No. of domains in which terminologies are developed | 4 | 100 Road Safety terminologies developed | 100 Road Safety terminologies were developed | 100%
 |  | 100 Pharmaceutical Terminologies developed | 100 Pharmaceutical terminologies were developed | 
 |  | 100 Engineering and Construction terminologies developed | 100 Engineering & Construction terminologies were developed | 
 |  | 100 Indigenous Plants and Animals terminologies developed | 100 Indigenous Plants & Animals terminologies were developed | 100%
% of documents received and accepted that are translated and/or edited | 100% | 100% | 158 documents completed as per clients' specifications, representing 100% of documents accepted for completion by 22 June 2018. | 100%
No. of sector organisations supported | 10 | 10 sector organisations selected | 10 Sector organisations were selected | 100%

## Slide 20: HERITAGE PRESERVATION AND PROMOTION
PERFORMANCE INDICATOR | 2018/19 ANNUAL TARGET | 1ST QUARTER TARGET | ACTUAL ACHIEVEMENT AS AT 31 JUNE 2018 | % ACHIEVEMENT
No. of heritage infrastructure projects financially supported | 4 | Progress report developed | One quarterly progress report developed on heritage infrastructure projects financially supported (report on JL Dube, Khananda, OR Tambo & Winnie Madikizela Mandela projects) | 100%
No. of newly built and/or modular libraries supported financially | 29 | 29 newly built and/or modular libraries supported financially | 29 newly built and/or modular libraries supported financially | 100%
Legislative framework SA Libraries & Information Services Bill (SALIS Bill) Developed | SALIS Bill submitted to Cabinet for approval | Ministerial approval for presentation to the SPCHD cluster | The Minister approved presentation of the SALIS to government clusters. | 100%
No. of policies developed | 1 policy on Underwater cultural heritage developed | Underwater Cultural Heritage Policy presented to SPCHD cluster | The policy was presented and approved by the SPCHD Cluster. The policy was submitted to the Minister's Office for submission to Cabinet | 100%

## Slide 21
Performance TARGETS which WERE not ACHIEVED in the first QUARTER

## Slide 22
INSTITUTIONAL GOVERNANCE
PERFORMANCE INDICATOR | 2018/19 ANNUAL TARGET | 1ST QUARTER TARGET | ACTUAL ACHEIVEMENT AS AT 30 JUNE 2018 | REASON FOR DEVIATION | CORRECTIVE ACTIONS
Approved feasibility and due diligence reports on amalgamation of DAC public entities | Approved feasibility and due diligence report on amalgamation DAC public entities | Service provider appointed to conduct feasibility and due diligence studies | The service provider has not been appointed yet. Request for proposals have gone out and the closing date for quotations was 27 June 2018. Quotations have been received. | A call to the public to send quotations was done and it was found that all the received quotes were above the threshold of R500 000.00. | To restart the process and appoint a service provider by 30 September 2018.

## Slide 23: HERITAGE PRESERVATION AND PROMOTION
PERFORMANCE INDICATOR | 2018/19 ANNUAL TARGET | 1st QUARTER TARGET | ACTUAL ACHIEVEMENT AS AT 30 JUNE 2018 | REASON FOR DEVIATION | CORRECTIVE ACTIONS
Feasibility study report on Resistance and Liberation Movements Museum completed | Draft feasibility study report on Resistance and Liberation Movements Museum | Terms of reference developed, approved and advertised | The draft Terms of Reference (ToR) have been developed and submitted to Supply Chain Management (SCM). SCM has been requested to convene a Bid Specifications Committee to discuss and approve the ToR’s. | Upon HPP having completed, the nomination process of the BSC members, SCM indicated that each nominee needs personalised appointment letters for external experts. This delayed the process. The letters were signed on 06 June 2018. The BSC meeting was held on 19 June 2018. | Session 2 for BSC is 24 July 2018. BAC for approval by 27 July 2018. Submission to DG for approval of ToRs and to advertise on 30 July 2018. The advert went out on 13 August 2018. Tender will close on 10 Sept Appointment by 25 September 2018.

## Slide 24: HERITAGE PRESERVATION AND PROMOTION
PERFORMANCE INDICATOR | 2018/19 ANNUAL TARGET | 1st QUARTER TARGET | ACTUAL ACHIEVEMENT AS AT 30 JUNE 2018 | REASON FOR DEVIATION | CORRECTIVE ACTIONS
No. of flags installed in schools | 1 000 | Service provider appointed | The call for bids has been made and it is closing on the 13th of July 2018. | The process of getting inputs that inform the scope of the project from provinces took longer than envisaged which impacted on the drafting scope of the project | The call for bids is closing on the 13th of July 2018 and a service provider will be appointed within 40 working days after the closing date.

## Slide 25
EXPENDITURE REPORT

## Slide 26
SUMMARY OF MAIN APPROPRIATION (ANNUAL) VS EXPENDITURE
AND
QUARTERLY PROJECTED BUDGET
VS EXPENDITURE

## Slide 27
Summary of Annual Appropriation (Annual) and Quarterly Projected Budget versus Expenditure
Per Programme
Programmes | Main Appropriation 2018/19 | Expenditure (April-June) 2018 | Total Available | % Spent | Projected Budget Quarter 1 (April-June) 2018 | Expenditure Quarter 1 (April-June) 2018 | (Over)/Under | % Spent
 | R’000 | R’000 | R’000 |  | R’000 | R’000 | R’000 | 
Administration | 300 844 | 61 914 | 238 930 | 21% | 75 383 | 61 914 | 13 469 | 82%
Institutional Governance | 416 027 | 26 602 | 389 425 | 6% | 102 509 | 26 602 | 75 907 | 26%
Arts & Culture Promotion & Development | 1 184 413 | 298 071 | 886 342 | 25% | 314 416 | 298 071 | 16 345 | 95%
Heritage Promotion & Preservation | 2 470 980 | 532 535 | 1 938 445 | 22% | 555 187 | 532 535 | 22 652 | 96%
Total | 4 372 264 | 919 122 | 3 453 142 | 21% | 1 047 495 | 919 122 | 128 373 | 88%

## Slide 28
QUARTERLY PROJECTED BUDGET VERSUS EXPENDITURE PER PROGRAMME DEPICTED ON A GRAPH
Chart: 
| Administration | Institutional Governance | Arts & Culture Promotion & Development | Heritage Promotion & Preservation
Projected budget | 75 | 103 | 314 | 555
Expenditure | 62 | 27 | 298 | 532

## Slide 29
SUMMARY OF MAIN APPROPRIATION (ANNUAL) & QUARTERLY PROJECTED BUDGET VERSUS EXPENDITURE PER ECONOMIC CLASSIFICATION
Economic Classification | Main Appropriation 2018/19 | Expenditure April - June 2018 | Total Available | % Spent | Projected Budget April - June 2018 | Expenditure April - June 2018 | (Over)/Under | % Spent
 | R’000 | R’000 | R’000 |  | R’000 | R’000 | R’000 | 
Compensation of Employees | 253 530 | 55 038 | 198 492 | 22% | 62 229 | 55 038 | 7 191 | 88%
Goods & Services | 387 112 | 78 906 | 308 206 | 20% | 98 648 | 78 906 | 19 742 | 80%
Provinces & Municipalities | 1 423 684 | 251 998 | 1 171 686 | 18% | 251 998 | 251 998 | - | 100%
Dept Agencies & Accounts (Cur) | 1 502 525 | 365 800 | 1 136 725 | 24% | 430 050 | 407 502 | 22 548 | 95%
Dept Agencies & Accounts (Cap) | 204 564 | 44 702 | 159 862 | 22% | 14 625 | 3 000 | 11 625 | 21%
Non Profit Org (Cur) | 167 875 | 54 959 | 112 916 | 33% | 73 855 | 54 959 | 18 896 | 74%
Non Profit Org (Cap) | 11 050 | 2 509 | 8 541 | 23% | 3 100 | 2 509 | 591 | 81%
Households | 20 708 | 8 475 | 12 233 | 41% | 14 593 | 8 475 | 6 118 | 58%
Public Corporations (Cur) | 93 816 | 32 554 | 61 262 | 35% | 45 823 | 32 554 | 13 269 | 71%
Public Corporations (Cap) | 62 541 | 8 461 | 54 080 | 14% | 4 750 | 8 461 | (3 711) | 178%
Foreign Gov & International Org | 4 809 | - | 4 809 | 0% | 1 000 | - | 1 000 | 0%
Heritage Assets | 218 478 | - | 218 478 | 0% | 44 380 | - | 44 380 | 0%
Machinery and equipment | 8 177 | 5 855 | 2 322 | 72% | 544 | 5 855 | (5 311) | 1076%
Software and other intangible | 6 267 | 947 | 5 320 | 15% | - | 947 | (947) | 
Payments for financial assets | - | 31 | (31) |  | - | 31 | (31) | 
Higher Education Institutions | 7 128 | - | 7 128 | 0% | 1 900 | - | 1 900 | 0%
Interest and rent on land | - | - | - |  | - | 8 887 | (8 887) | 
Total | 4 372 264 | 919 122 | 3 453 142 | 21% | 1 047 495 | 919 122 | 128 373 | 88%

## Slide 30
QUARTERLY PROJECTED BUDGET VERSUS EXPENDITURE PER ECONOMIC CLASSIFICATION DEPICTED ON A GRAPH
Chart: 
| Compensation of Employees | Goods & Services | Provinces & Municipalities | Dept Agencies & Accounts (Cur) | Dept Agencies & Accounts (Cap) | Non Profit Org (Cur) | Non Profit Org (Cap) | Households | Public Corporations (Cur) | Public Corporations (Cap) | Foreign Gov & International Org | Heritage Assets | Machinery and equipment | Software and other intangible | Payments for financial assets | Higher Education Institutions | Interest and rent on land
Projected budget | 62 | 99 | 252 | 430 | 15 | 74 | 3 | 14 | 46 | 5 | 1 | 44 | 0 | 0 | 0 | 2 | 0
Expenditure | 55 | 79 | 252 | 407 | 3 | 55 | 3 | 8 | 33 | 8 | 0 | 0 | 6 | 1 | 0 | 0 | 9

## Slide 31
EXPLANATION OF EXPENDITURE VARIANCE
ON QUARTERLY PROJECTED BUDGET
PER ECONOMIC CLASSIFICATION

## Slide 32
Economic classification | Description of the line item | Remarks
Compensation of Employees | The line item includes remuneration in cash, social contributions by the employer, basic wages and salaries, overtime, remuneration of nightshift, cost of living allowances, house allowances, bonuses, pension, medical aid etc. | An actual expenditure of R55.0 million (88%) versus a quarterly projected budget of R62.2 million, was incurred in the 1st quarter. The variance is caused by vacant posts in the process of being filled.
Explanation of Expenditure Variance Per Economic Classification

## Slide 33
Economic classification | Description of the line item | Remarks
Goods and Services | The item includes payments for all goods and services to be used by a government unit i.e. goods or services of a current nature, excluding purchases of capital assets. | An actual expenditure of R78.9 million (80%) versus a quarterly projected budget of R98.6 million, was incurred in the 1st quarter. The under expenditure is due to the following: DPW invoices for municipal charges for the 1st quarter were not paid as the invoices included Entities billings. Meetings were held between the Office of the CFO and DPW officials and it was resolved that DAC should only settle Sechaba Building and Archives & Film billings. The said invoices will be processes in August. The Youth Day invoice was only processed in July due to unresolved queries with the invoiced amount by the supplier.
Explanation of Expenditure Variance Per Economic Classification

## Slide 34
Economic Classification | Description of the line item | Remarks
Provinces and Municipalities (Conditional Grant on Community Libraries) | The expenditure relates to the transfers for the Conditional grant on Community Libraries and funds are transferred to various Provinces on a quarterly basis, including MGE projects. | An actual expenditure of R252.0 (100%) versus a quarterly projected budget of R252.0 million was incurred in the 1st quarter. This is in line with the projections.
Explanation of Expenditure Variance Per Economic Classification

## Slide 35
Summary of Main Appropriation (Annual) & Quarterly Projected Budget versus Expenditure Per Province
Per Province | Total allocation 2018/19 | Payment Schedule April-June 2018 | Actual Expenditure by Province April-June 2018 | % Transferred of National allocation | % Actual Expenditure by Province of total allocation | Projected Actual transfer by National April-June 2018 | Actual Expenditure by Province April-June 2018 | (Over) / Under | % Spent
 | R’000 | R’000 | R’000 |  |  | R’000 | R’000 | R’000 | 
Eastern Cape | 160 584 | 26 900 | 21 899 | 16.8% | 13.6% | 26 900 | 21 899 | 5 001 | 81.4%
Free State | 159 504 | 32 861 | 23 143 | 20.6% | 14.5% | 32 861 | 23 143 | 9 718 | 70.4%
Gauteng | 168 530 | 10 151 | 4 512 | 6.0% | 2.7% | 10 151 | 4 512 | 5 639 | 44.4%
KwaZulu-Natal | 174 397 | 33 721 | 18 117 | 19.3% | 10.4% | 33 721 | 18 117 | 15 604 | 53.7%
Limpopo | 125 643 | 28 155 | 23 098 | 22.4% | 18.4% | 28 155 | 23 098 | 5 057 | 82.0%
Mpumalanga | 162 479 | 38 668 | 31 605 | 23.8% | 19.5% | 38 668 | 31 605 | 7 063 | 81.7%
Northern Cape | 159 554 | 49 463 | 31 106 | 31.0% | 19.5% | 49 463 | 31 106 | 18 357 | 62.9%
North West | 136 369 | 28 661 | 22 771 | 21.0% | 16.7% | 28 661 | 22 771 | 5 890 | 79.4%
Western Cape | 176 624 | 3 418 | 3 776 | 1.9% | 2.1% | 3 418 | 3 776 | -358 | 110.5%
Total | 1 423 684 | 251 998 | 180 027 | 17.7% | 12.6% | 251 998 | 180 027 | 71 971 | 71.4%

## Slide 36
Economic Classification | Description of the line item | Remarks
Departmental Agencies & Accounts (Current) | This expenditure item relates to subsidies to the Departments’ Public Entities. The Performing Arts Institutions transfers are processed quarterly, Libraries and Heritage Institutions on a monthly basis. | An actual expenditure of R407.5 million (95%) versus a quarterly projected budget of R430.1 million for subsidies, was transferred to the various entities in the 1st quarter. The variance is as a result of a transfer to National Library SA for the community library conditional grant project which was based on the signed MOA. The remaining balance will be transferred in October in line with the MOA.
Explanation of Expenditure Variance Per Economic Classification

## Slide 37
Economic Classification | Description of the line item | Remarks
Departmental Agencies & Accounts (Capital) | This expenditure item relates to maintenance, upgrade and refurbishment of the Departments’ Playhouses, Museums and Libraries as well as the construction of Legacy Projects. | An actual expenditure of R3 million (21%) versus a quarterly projected budget of R14.6 million was incurred in the 1st quarter. Transfers for capital works projects to entities were only processed beginning of July due to internal routing processes for authorization of payments by delegated authorities.
Explanation of Expenditure Variance Per Economic Classification

## Slide 38
Economic Classification | Description of the line item | Remarks
Non Profit Institutions (Current) | This expenditure relates to subsidies to BASA, Blind SA, Engelenburg Arts Collection and Non-Profit Organisations beneficiaries of MGE, Cultural Development, Heritage as well as Arts & Youth Development projects. | A current transfer of R55.0 million (74%) versus a quarterly projected budget of R73.9 million, was incurred in the 1st quarter. Less than projected spending is as a result of the process with regards to acquiring approval for the introduction and creation of MGE beneficiaries on SCOA. Spending will therefore be high in the 2nd quarter. Delays were experienced with the processing of submission for the Artist in Schools projects pending Treasury advise on the Auditor General’s finding relating to the 2017/18 Financial Year.
Explanation of Expenditure Variance Per Economic Classification

## Slide 39
Economic Classification | Description of the line item | Remarks
Non Profit Institutions (Capital) Households | This expenditure relates to Capital works transfers made to Non Profit Organizations. This expenditure item relates to financial assistance projects that the Department fund during the financial year, MGE funding to individuals/persons and employer social benefits. | An actual transfer of R2.5 million (81%) was incurred versus a quarterly projected budget of R3.1 million in the 1st quarter. The department was not in receipt of the progress report relating to the previous contracted allocation from the Steve Biko Foundation. This had an impact in facilitation of the second tranche payment. An expenditure of R8.5 million (58%) versus a quarterly projected budget of R14.6 million was incurred in the 1st quarter. The underspending is as a result of delays with the vetting of MOAs between DAC and institutions of higher learning for the Heritage Professionals Bursaries.
Explanation of Expenditure Variance Per Economic Classification

## Slide 40
Economic Classification | Description of the line item | Remarks
Public Corporations (Current) | This expenditure relates to transfer payments to MGE, Cultural Development, Human Language Technologies and Institutional Governance projects. | A current transfer of R32.5 million (71%) was incurred versus a quarterly projected budget of R45.8 million, in the 1st quarter. The underspending is owing to the process with regards to acquiring approval for the introduction and creation of MGE beneficiaries on SCOA.
Explanation of Expenditure Variance Per Economic Classification

## Slide 41
Economic Classification | Description of the line item | Remarks
Public Corporations (Capital) Foreign Government & International Organisations | This expenditure relates to transfer payments to public and private enterprises beneficiaries implementing Performing Arts and Heritage Legacy infrastructure projects. This budget relates to transfers made to Foreign Government and International Organisations. | An actual transfer of R8.5 million (178%) versus a quarterly projected budget of R4.8 million was incurred in the 1st quarter. The over-expenditure is as a result of payment made to Mpumalanga Economic Growth Agency for the upgrading of community arts centres projects which could not be made in the prior financial year due to late submission of the entity form by the beneficiary for verification of its banking details. No expenditure was incurred versus a quarterly projected budget of R1 million in the 1st quarter. The African World Heritage Fund experienced challenges with acquiring its tax certificate from SARS. This resulted in DAC not being able to make a transfer to the beneficiary.
Explanation of Expenditure Variance Per Economic Classification
41.

## Slide 42
Economic Classification | Description of the line item | Remarks
Heritage Assets | This expenditure item relates to assets of significant value for conservation of a historical, agricultural or heritage purposes. | No expenditure was incurred versus a quarterly projected budget of R44.4 million in the 1st quarter. Varied challenges are experienced with regards to implementation of capital works of legacy projects. The reprioritisation exercise of capital works projects was done during the 2019 Adjusted Estimates of National Expenditure (AENE) process for Treasury approval.
Explanation of Expenditure Variance Per Economic Classification
42.

## Slide 43
Economic Classification | Description of the line item | Remarks
Machinery and equipment Interest and rent on land | This budget relates to the procurement of machinery and equipment including IT equipment. This item includes the total value of interest payments. These are payments associated with debt and overdue accounts. | An expenditure of R5.9 million (1076%) was incurred versus a quarterly projected budget of R544 000 in the 1st quarter. The over-expenditure relates to payment of invoice for the procured Departmental Office furniture (chairs) ordered in the prior financial year; Desktop computers for the intake of the interns and Laptops. An actual expenditure of R8.9 million was incurred versus a nil quarterly projected budget in the 1st quarter. This relates to interest overdue on withheld payment on receipt of the qualified report from Opiconsivia Investments 314 (Pty) Ltd a department’s MGE beneficiary.
Explanation of Expenditure Variance Per Economic Classification
43.

## Slide 44
Economic Classification | Description of the line item | Remarks
Software and other intangible assets Payment for financial assets Higher Education Institutions | This budget relates to the procurement of computer software. This item consists mainly of transactions that were written off as a result of theft, loss and irrecoverable debts. This expenditure item relates to Transfers made to Higher Education Institutions. | An actual expenditure of R947 300 was incurred versus a nil quarterly projected budget in the 1st quarter. The expenditure relates to the procurement of security information and event management solution and Mimecast licenses. An actual expenditure of R30 545 was incurred versus a nil quarterly projected budget in the 1st quarter. The expenditure relates to hired car damages incurred by officials whilst on duty. No expenditure was incurred versus a quarterly projected budget of R1.9 million in the 1st quarter. The underspending is as a result of delays in signing of MOA between DAC and institution of higher learning towards the financially supported Human Language Technology project.
Explanation of Expenditure Variance Per Economic Classification
44.

## Slide 45: Remarks
The department incurred an actual expenditure of R919 million (88%) versus a quarterly projected budget of R1.0 billion in the 1st quarter.
An annual budget of R4.4 billion, versus an actual expenditure of R919 million (21%) was incurred in the 1st quarter.

## Slide 46: ANNEXURE: Acronyms and Abbreviations
ITEM | Description | ITEM | Description
ACH | ARTS, CULTURE AND HERITAGE | DPW | DEPARTMENT OF PUBLIC WORKS
ACUMDA | AFRICAN CULTURAL MUSIC AND DANCE ASSOCIATION | EC | EASTERN CAPE
AU | AFRICAN UNION | FBF | FIELD BAND FOUNDATION
AENE | ADJUSTED ESTIMATES OF NATIONAL EXPENDITURE | FS | FREE STATE
AWHF | AFRICAN WORLD HERITAGE FUND | GP | GAUTENG PROVINCE
BAC | BID ADJUDCATION COMMITTEE | HLT | HUMAN LANGUAGE TECHNOLOGY
BASA | BUSINESS AND ARTS SOUTH AFRICA | HPP | HERITAGE PROMOTIION AND PRESERVATION
BBBEE | BROAD-BASED BLACK ECONOMIC EMPOWERMENT | ICT | INFORMATION COMMUNICATION TECHNOLOGY
BSC | Bid Specification Committee | IT | INFORMATION TECHNOLOGY
CACs | NUMBER OF COMMUNITY ARTS CENTRES | LP | LIMPOPO PROVINCE
CIFSA | CREATIVE INDUSTRY FEDERATION SOUTH AFRICA | LIASA | LIBRARY AND INFORMATION ASSOCIATION OF SOUTH AFRICA
CSD | CENTRAL SUPPLIER DATABASE | LLLP | LIVING LEGENDS LEGACY PROGRAMMES
DAC | DEPARTMENT OF ARTS AND CULTURE | MGE | MZANSI GOLDEN ECONOMY
DG | DIRECTOR-GENERAL | MIL | MILLION
DPME | DEPARTMENT OF PLANNING MONITORING AND EVALUATION |  | 

## Slide 47: Acronyms and Abbreviations…cont.
ITEM | Description | ITEM | Description
MOA | MEMORANDUM OF AGREEMENT | RWP | REVISED WHITE PAPER
NFVF | NATIONAL FILM AND VIDEO FOUNDATION | SA | SOUTH AFRICA
NLSA | NATIONAL LIBRARY OF SOUTH AFRICA | SALIS | SOUTH AFRICAN LIBRARY AND INFORMATION SERVICES
NO. | NUMBER | SCM | SUPPLY CHAIN MANAGEMENT
NT | NATIONAL TREASURY | SPCHD | SOCIAL PROTECTION,COMMUNITY AND HUMAN DEVELOPMENT CLUSTER
NW | NORTH WEST | SCOA | STANDARD CHART OF ACCOUNTS
QPR | QUARTERLY PERFORMANCE REPORT | UAMP | USER IMMOVABLE ASSET MANAGEMENT PLAN
PACOFS | PERFORMING ARTS CENTRE OF THE FREE STATE | UNESCO | UNITED NATIONS EDUCATIONAL, SCIENTIFIC AND CULTURAL ORGANIZATION
PSETA | PUBLIC SERVICE SECTOR EDUCATION AND TRAINING AUTHORITY | WC | WESTERN CAPE
 |  | WSP | WORKPLACE SKILLS PLAN

## Slide 48
THANK YOU