## Slide 1
DEPARTMENT OF LABOUR
29 Aug 2018
QUARTER 4 2017/18: PERFORMANCE REPORT
PORTFOLIO COMMITTEE : SUPPORTED EMPLOYMENT ENTERPRICES

## Slide 2
Implication: ACHIEVED
Performance Indicator is on track or reflects complete implementation. Target achieved
100% + Complete
Implication: NOT ACHIEVED
Performance Indicator behind schedule. Target not achieved
0% - 99% Complete
LEGEND

## Slide 3: QUARTER 4 OVERALL PERFORMANCE
OVERALL ACHIEVEMENTS PER STRATEGIC OBJECTIVE DURING QUARTER 4
JAN TO MARCH 2017-18

## Slide 4: QUARTER 4 PERFORMANCE PER STRATEGIC OBJECTIVE 2017/18
Strategic Objective | Annual Planned Indictors | Indicators with targets reporting in Q4 | Achieved | Not Achieved | Overall Achievement %
Provide work opportunities for People with Disabilities | 5 | 5 | 3 | 2 | 60%
Total number of Indicators | 5 | 5 | 3 | 2 | 60%
Overall Performance |  |  | 60% | 40% | 

## Slide 5: QUARTER 4 PERFORMANCE PER PROGRAMME 2017/18
Entity | Annual Planned Indicators | Indicators with targets reporting in Quarter 1 | Achieved | Not Achieved | Overall % Achievement
Supported Employment Enterprises | 5 | 5 | 3 | 2 | 60%
Total number of Indicators | 5 | 5 | 3 | 2 | 60%
Overall Performance |  |  | 60% | 40% | 

## Slide 6: COMPARATIVE ANALYSIS PER PROGRAMME FOR Q1 TO Q4 2017/18
Entity | QUARTER 1 2017/18 |  |  | QUARTER 2 2017/18 |  |  | QUARTER 3 2017/18 |  |  | QUARTER 4 2017/18 |  | 
 | Quarter1 Planned targets | Overall Achieved | % | Quarter2 Planned targets | Overall Achieved | % | Quarter 3 Planned targets | Overall Achieved | % | Quarter 4 Planned targets | Overall Achieved | %
Supported Employment Enterprises | 5 | 2 | 40% | 5 | 3 | 60% | 5 | 4 | 80% | 5 | 3 | 60%
Total | 5 | 2 | 40% | 5 | 3 | 60% | 5 | 4 | 80% | 5 | 3 | 60%

## Slide 7: PERFORMANCE TREND
Chart: 
| Q1 17-18 | Q2 17-18 | Q3 17-18 | Q4 17-18
Performance Trend | 0.4 | 0.6 | 0.8 | 0.6

## Slide 8: ANNUAL PERFORMANCE PLAN (APP) 2017/18
QUARTER 4
JAN – MARCH 2017/18
PROGRESS AND MAJOR PERFORMANCE CHALLENGES ENCOUNTERED DURING REPORTING PERIOD
With a special focus on NOT ACHIEVED Targets

## Slide 9: PRAGRAMME 1: ADMINISTRATION
PROGRAMME PERFORMANCE INDICATOR | QUARTER 4 TARGET | ACTUAL PERFORMANCE | REASON FOR VARIANCE | REMEDIAL ACTION
Provide work opportunities for People with Disabilities (MTSF Outcome 4: Decent Employment through inclusive economic growth) |  |  |  | 
1. Number of persons with disabilities provided with employment opportunities | 150 persons with disabilities provided with employment opportunities in the SEE by the end of March 2018 | Not achieved 85 new PWDs appointed between 1 April 2017 –31 March 2018 | Insufficient work in the form of order book to enable the SEE to reach its employment creation target and capacity constraints within the Business Development unit The SEE needs to balance the creation of employment whilst ensuring enough work to be performed by new incumbents and this requires more sales orders | A sales plan is currently being developed to increase the sales in the new financial year. The recruitment process for the Business Development Executive has been concluded
2. Number of radio campaigns conducted per annum | 2 radio campaigns conducted by the end of March 2018 to create awareness of the existence of the SEE | Not achieved 1 radio campaigns conducted to create awareness about the SEE’s new name by the end of March 2018 | Request for the campaign was sent to the service provider in time, however the actual campaign was only conducted in April 2018 due to delays from GCIS | Campaign were done in April 2018

## Slide 10: AUDITOR GENERAL MANAGEMENT REPORT
Name of entity | Audit outcome |  | 
 | Financial statement opinion | Findings on the performance report | Findings on compliance
Sheltered Employment Enterprises (SEE) | Unqualified | Yes | Yes

## Slide 11: STRATEGY TO OVERCOME UNDER- PERFORMANCE
Monitor the implementation of the mitigation strategies
Develop an M&E plan

## Slide 12
Thank You…