## Slide 1: Progress Report on Implementation of Constitutional Court Order - Presentation to Portfolio Committee
7 November 2018
Out with the Old
In with the New

## Slide 2: Purpose
  To present to the Portfolio Committee on Social Development with a progress report on the implementation of the Constitutional Court Order

## Slide 3: Priorities during the 1st Phase of the Payment Transition
Phase out CPS services by 30 September 2018
Decommissioning of old SASSA cards by December 2018
Phase-in the services of SAPO
  Systems development
  Card swap
  Resourcing (staff and financing)
  Actual payments
Migrate beneficiaries who choose to be paid using own bank accounts – collection and processing of Annexure “C” mandates
Rationalization and re-alignment of pay points
Insourcing certain critical components of the payment process

## Slide 4: Phasing out CPS services
The contract between SASSA and CPS came to an end on 30 September 2018
All beneficiaries (3 160 832) that were serviced by CPS have been migrated to SAPO and to banks of their choice
The migration was done progressively over a period of five months mainly through the card swap process and capturing of banking requests mandates
Process to collect outstanding information has commenced
Objective achieved !

## Slide 5: Transition from old SASSA Card to New SASSA/SAPO Card
Baseline as at April 2018 indicated that there were approximately 8.5 million beneficiaries that were paid through the old SASSA card (to be card swapped or migrated to ACB).
Approximately 7 223 307 have been card swapped (as at 30 October 2018
  Old SASSA Card Biometric CVM - 3 160 832 (fully migrated)
  Old SASSA Card NPS – 5.3 million (4.8 million swapped)
Approximately 523 420 still remain to be swapped before the end of December 2018 (Old SASSA cards in the NPS)
Other beneficiaries have since migrated to other banks
Objective achieved !

## Slide 6: Decommissioning the Old SASSA Card
SASSA intends to fully decommission the old SASSA card by end of December 2018.
This will be done through the migration of beneficiaries that are still using the old SASSA in the NPS to the new SASSA card or any Bank of their choice.
In September there were still 1 616 937 beneficiaries that were still using the old SASSA card in the NPS.
The reduced has been reduced to 523 420 (as at 23 October 2018) beneficiaries that still remain to be swapped before the end of December 2018.

## Slide 7: Card swap
Number of Beneficiaries with Old SASSA cards who are with Grindrod Bank as at 23 October 2018 |  |  |  | 
Region | Old SASSA cards with Grindrod 201810 extraction (baseline) | Remaining (still to be swapped) | Total card Swaps to date | % swapped to date
Eastern Cape | 143 246 | 92 450 | 50 796 | 35%
Free State | 51 432 | 26 588 | 24 844 | 48%
Gauteng | 195 985 | 115 007 | 80 978 | 41%
KwaZulu Natal | 125 324 | 73 078 | 52 246 | 42%
Limpopo | 82 732 | 45 833 | 36 899 | 45%
Mpumalanga | 54 994 | 31 689 | 23 305 | 42%
North West | 74 602 | 51 595 | 23 007 | 31%
Northern Cape | 27 153 | 19 101 | 8 052 | 30%
Western Cape | 113 121 | 68 079 | 45 042 | 40%
Grand Total | 868 589 | 523 420 | 345 169 | 40%

## Slide 8
OCTOBER AND NOVEMBER PAYMENT REPORT

## Slide 9: Background
GRANT TYPE | End Sept
CDG | 148 562
CSG | 12 337 152
FCG | 446 475
DG | 1 049 479
GIA | 206 096
OAG | 3 478 358
WVG | 113
TOTAL | 17 666 235
REGION | END SEPT 2018
EC | 2 800 884
FS | 1 011 946
GP | 2 615 990
KZN | 3 933 259
LP | 2 510 732
MP | 1 489 520
NW | 1 240 617
NC | 479 895
WC | 1 583 392
TOTAL | 17 666 235
SASSA pays 17.6 million social grants to approximately 10.9 million beneficiaries across the country

## Slide 10: Number of Beneficiaries paid from April to November 2018
Month | CPS | PostBank | Grindrod |  | Other Banks | Total Beneficiaries
 |  |  | ACB Direct (SASSA) | SASSA/ Grindrod (Bilateral agreement ) |  | 
April 2018 | 3 160 832 | 31 448 | 1,877,392 | 5 342 376 | 439,267 | 10 851 315
May 2018 | 3 110 333 | 83 448 | 2,802,095 | 4 221 999 | 646,191 | 10 864 066
June 2018 | 1 950 249 | 233,215 | 7,714,443 |  | 980,449 | 10 878 356
July 2018 | 1 637 975 | 936,680 | 6,970,925 |  | 1,340,148 | 10 874 920
August 2018 | 1 098 669 | 2,548,045 | 5,589,506 |  | 1,663,083 | 10 893 801
September 2018 | 221 599 | 5,439,905 | 3,267,733 |  | 1,990,052 | 10 919 289
October 2018 | 0 | 6,708,791 | 2,131,576 |  | 2,101,312 | 10 941 787
November 2018 | 0 | 7,205,997 | 1,642,753 |  | 2,122,151 | 10,970,901

## Slide 11: October/November 2018 Payments
In terms of the October payment extraction file, approximately 10 941 787 beneficiaries were paid throughout the country.
The number increased to 10 970 901 in November 2018.
All beneficiaries are paid through ACB transfers facilitated directly by SASSA
Availability of funds – ALL beneficiary accounts were debited on the last working day of the month
  October payments - 29 September 2018.
  November payments - 31 October 2018
Objective achieved !

## Slide 12: October/November 2018 Payments
Breakdown of the 10.9 million beneficiaries in October 2018,
  SAPO
    approximately 61% (6 708 791) are paid through Post Bank; The number will increase to 7 205 997 in November 2018.
    Total value of grants paid by SAPO in October is R 8 433 888 314
  Grindrod
    19% (2 131 576) are be paid through Grindrod Bank. The Grindrod Bank transfers included 868,589 beneficiaries who were still using the old SASSA card in the NPS system in October;
    The Grindrod account holders decreased to 1 642 753 in November payment file. This number still include the 523,420 old SASSA card holders still to be migrated
  Other Banks
    The remaining 20% (2 101 420) were paid through the beneficiaries personal bank accounts in October
    Marginal increase of 20,731 in November to 2,122,151

## Slide 13: ACB Payments up to Nov. 2018
Sum of Number Of Beneficiaries |  |  |  |  |  |  |  | 
Row Labels | 201804 | 201805 | 201806 | 201807 | 201808 | 201809 | 201810 | 201811
ABSA BANK | 88,180 | 119,007 | 165,646 | 211,358 | 249,934 | 283,844 | 294,956 | 296,425
UBank BANK | 1,047 | 2,583 | 5,800 | 9,225 | 12,023 | 15,405 | 16,285 | 16,382
ALBARAKA BANK | 43 | 58 | 70 | 89 | 118 | 127 | 136 | 142
BANK OF ATHENS | 1,419 | 2,637 | 3,534 | 5,069 | 6,447 | 7,149 | 8,208 | 9,509
BANK WINDHOEK | 152 | 154 | 153 | 154 | 153 | 152 | 142 | 140
BIDVEST BANK | 1,755 | 3,403 | 5,138 | 7,196 | 9,932 | 13,364 | 14,621 | 14,776
CAPITEC BANK | 124,280 | 189,616 | 301,158 | 421,107 | 532,078 | 655,150 | 704,747 | 717,022
FINBOND MUTUAL | 10,067 | 14,776 | 20,600 | 24,947 | 31,710 | 36,893 | 40,445 | 42,924
FIRSTRAND BANK | 93,149 | 137,309 | 200,812 | 271,464 | 332,285 | 392,767 | 410,427 | 410,906
GRINDROD BANK | 1,877,392 | 2,802,095 | 7,714,443 | 6,970,925 | 5,589,506 | 3,267,733 | 2,131,576 | 1,642,753
HABIB OVERSEAS |  |  | 1 | 1 | 3 | 3 | 3 | 3
HBZ BANK |  | 1 | 4 | 6 | 8 | 9 | 9 | 10
HSBC BANK | 4 | 4 | 2 | 2 | 3 | 1 | 1 | 
INVESTEC BANK LTD | 5 | 5 | 5 | 8 | 13 | 13 | 14 | 13
ITHALA | 1,447 | 3,522 | 7,552 | 10,850 | 13,710 | 15,462 | 15,568 | 15,226

## Slide 14: ACB Payments up to Nov. 2018
Sum of Number Of Beneficiaries |  |  |  |  |  |  |  | 
Row Labels | 201804 | 201805 | 201806 | 201807 | 201808 | 201809 | 201810 | 201811
MERCANTILE BANK | 73 | 94 | 119 | 151 | 184 | 208 | 223 | 234
NBS | 57 | 56 | 56 | 55 | 55 | 56 | 55 | 54
NEDBANK |  | 2 | 4 | 6 | 3 | 2 | 1 | 
NEDBANK EX PERM | 1 | 1 | 1 |  |  |  |  | 
NEDBANK INC. BOE | 12 | 12 | 12 | 12 | 12 | 13 | 15 | 15
NEDBANK LIMITED | 54,310 | 83,164 | 136,306 | 203,661 | 263,363 | 327,530 | 344,219 | 346,329
NEDBANK NAMIBIA | 39 | 39 | 38 | 38 | 38 | 38 | 37 | 35
POSTBANK | 31,448 | 83,448 | 233,215 | 936,680 | 2,548,045 | 5,439,905 | 6,708,791 | 7,205,997
SASFIN |  |  |  |  |  |  |  | 1
STANDARD CHARTERED |  | 2 |  |  |  |  |  | 
STANDARD NAMIBIA |  | 1 | 1 | 1 | 3 | 3 | 3 | 3
STANDARD SA | 63,018 | 89,519 | 133,186 | 174,557 | 210,926 | 241,842 | 251,182 | 251,987
STATE BANK OF INDIA | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
UNIBANK |  |  |  | 1 | 1 | 2 | 2 | 2
VBS MUTUAL | 208 | 225 | 250 | 189 | 80 | 18 | 12 | 12
Grand Total | 2,348,107 | 3,531,734 | 8,928,107 | 9,247,753 | 9,800,634 | 10,697,690 | 10,941,679 | 10,970,901

## Slide 15: Cash Pay-points
Region | No. of Active Pay point as at April 2018 | No. of closed pay points | No. of Remaining Pay Points
Eastern Cape | 2590 | 1990 | 600
Free State | 212 | 140 | 72
Gauteng | 144 | 133 | 11
Kwa-Zulu Natal | 1700 | 1343 | 357
Limpopo | 1839 | 1399 | 440
Mpumalanga | 386 | 348 | 38
North West | 609 | 435 | 174
Northern Cape | 344 | 307 | 37
Western Cape | 262 | 251 | 11
Total | 8086 | 6346* | 1740
SAPO will service no more than 1740 pay points in November and December per the Master Services Agreement. The number is subject to review based on beneficiary behaviour

## Slide 16: Payments at Cash Pay Points
To accommodate human resource constraints of SAPO, payments at cash pay points were scheduled to start on 8 October 2018.
Pay points serviced by SAPO in October 2018 were 1 269
REGION | TARGETED | NUMBER OF PAYPOINTS SERVICED
Eastern Cape | 600 | 414
Free State | 72 | 76
Gauteng | 11 | 7
Kwazulu-Natal | 357 | 191
Limpopo | 440 | 329
Mpumalanga | 38 | 28
Northern Cape | 174 | 53
North-west | 37 | 162
Western Cape | 11 | 9
Total | 1740 | 1,269

## Slide 18: October Payment Observations
The payment cycle was in general successful and beneficiaries were able to access their grants through a variety of payment channels without major challenges.
Almost 90% of beneficiaries accessed their grants through the NPS primarily ATMS and retailer POS
The number of beneficiaries accessing their grants at cash pay points was significantly lower than originally projected.
Long queues and over crowding: Shopping malls, SAPO outlets, ATMs on the first three days of the months
Security challenges remain a concern – Post Office burglaries, CIT heists, fraud across the payments value chain both within SASSA/ SAPO and outside

## Slide 19: Payment Dates – November, December
Payments have been scheduled as follows:
November
  ACB payments - 31 October 2018
  Cash pay point payments on the 6th except for Free State and N Cape that will start on the 5th
December
  ACB payments – 28 November 2018
  Cash payments to start on the 3rd
The 2019 schedule will be confirmed by end of November 2018

## Slide 20: SASSA – SAPO Risk Management
Status Update
Risks and Mitigations effectiveness (low and medium residual risk)
Key Strategic Risk | Key Operational Risk
Unable to pay at all cash pay point site Safety of beneficiaries and staff Appointment of skilled staff Overnight cash at SAPO outlets Unable to complete financial reconciliations IGPS fully functional at all branches Network connectivity and capacity Cyber crime, fraud, robberies | Offline functionalities and data upload Pay Point rationalization Training/reskilling of staff Cash projections for SAPO branches Delayed payment of service providers Termination of service/systems Overdrawn accounts “Double dipping” Appointment of cash payment contractor Dignity issue

## Slide 21: Recommendations
It is recommended that the Portfolio Committee on Social Development note progress report on the implementation of the Constitutional Court Order