FOURTH QUARTER PROGRAMME PERFORMANCE REPORT

THE DEPARTMENT OF SOCIAL DEVELOPMENT

01 JANUARY 2019 – 31 MARCH 2019

FINANCIAL YEAR 2018/19

TABLE OF CONTENTS

| Item No | Item | Page No |
| --- | --- | --- |
| PART A |
| I | Introduction | 1 |
| II | Background and significance of the report | 1 |
| III | Discussion | 1 |
| IV | Summary of performance | 1 |
| V | Performance trends | 4 |
| Part B | PROGRAMME PERFORMANCE |  |
| 1 | Programme 1: Administration | 5 |
| 2 | Programme 2: Social Assistance | 9 |
| 3 | Programme 3: Social Security Policy and Administration | 10 |
| 4 | Programme 4: Welfare Services Policy Development and Implementation Support | 12 |
| 5 | Programme 5: Social Policy and Integrated Service Delivery | 22 |
| PART C | ABBREVIATIONS |  |
|  | Abbreviations | 29 |

- Introduction

The purpose of this report is to provide progress to the Minister, the Deputy Minister and other relevant stakeholders on the implementation of targets as set out in the Annual Performance Plan (APP) of the Department for 2018/2019. The report presents the status of the Department’s programme performance at the end of the fourth quarter of the 2018/19 financial year.

- Background and significance of the Report

According to Section 5.3 of Treasury Regulations, read together with Section 36(5) of the Public Finance Management Act (PFMA), the Accounting Officer of an institution must establish procedures for reporting to the Executive Authority in order to facilitate effective performance monitoring, evaluation and recommend corrective action. This report will enable the Minister and the Deputy Minister to have a sense of how the Department has performed during the fourth quarter of the financial year. It is also hoped that the report generate debate on how to address areas where performance is below par and help with the allocation of resources, both human and material going into the new financial year.

- Discussion

The report provides progress on programme performance for the fourth quarter of the 2018/19 financial year (01 January 2019 – 31 March 2019) against performance targets set out in the 2018/19 APP of the Department.

- Summary of Performance:

Social Assistance: The provision of a comprehensive social security, including income support and a safety net for those in needs remains the cornerstone of the fight against poverty. The Social Grants have shown a substantial growth since the first quarter. As such, the Department, through SASSA, extended the social assistance programme to more than 17.8 million individuals at the end of the fourth quarter. This includes more than 12.4 million (12 452 072) recipients of the child support grant and more than 3.5 million (3 553 317) recipients of the old age grant.  Among all the social grants, the War Veterans Grant is the only grant which is declining. This is mainly because the grant is not actively pursued and projects are dependent on the veteran’s life span. The grant may be discontinued in the nearer future. The Social Assistance programme contribute immensely to the alleviation of poverty and improving the quality of lives of many South Africans and makes the Department a key player in the realisation of Outcome 7, vibrant equitable and sustainable rural communities with food security for all and Outcome 13 An inclusive and responsive social protection system.

Early Childhood Development and Children Services, Orphans and Vulnerable Children: As part of its efforts towards improving access and the quality of ECD services, the Department continued to monitor the implementation of the National Integrated Implementation Plan on ECD Policy. Quarterly reports on the implementation of the National Integrated Implementation Plan on ECD policy were produced in the period under review. The implementation of the ECD Policy and Plans are part of the Department’s response to the NDPs call for universal access to ECD services by all children in the country.

The Department also monitored the implementation of the Children`s Act, 2005 (Act No. 38 of 2005) as part of strengthening child protection services. A consolidated progress report on the implementation of the Act was compiled inclusive of progress from six provinces namely Limpopo, Mpumalanga, North West, Free State, Northern Cape and the Western Cape. Similarly, the Department developed the National Plan of Action for Children in South Africa. The Plan of Action was presented to the Justice, Crime Prevention and Security (JCPS) Cluster and approval was granted for it to be presented to Cabinet. This Plan will be presented to Cabinet during 2019/20

Social Crime Prevention and Victim Empowerment: The Department continued to develop and implement policies to reduce incidences of social crime and substance abuse as well as to facilitate the provision of services to target groups. In this regard, capacity building on the reviewed Policy Framework on Accreditation of Diversion Services was conducted in KZN as part of the Department’s implementation of the Child Justice Act, 2008 (Act No. 75 of 2008). Similarly, the Department conducted awareness campaigns on the Multidisciplinary Integrated Social Crime Strategy in NC and KZN.

Expanded Public Works Programme: The Department continued to lead the coordination of the Expanded Public Works Programme (EPWP) for the Social Sector, which comprises of the departments of Health, Education, Social Development, Community Safety and Sports and Recreation South Africa.  During the reporting period, the Department commenced with the planning of the Social Sector EPWP Phase 4 through development of the Business Plan to be implemented from 2019/20 to 2023/24. The Plan was consulted with various stakeholder, including provincial departments and municipalities. A notable achievement in this regard was the approval of the Phase 4 Business Plan by the Cabinet Committee on ESEID. The agreed target for the Social Sector for the next five years is creation of 875 754 work opportunities. This will form the key coordination focus for the Special Projects Unit for the five years.

NPOs Compliance Monitoring and Funding Coordination: Effective Non-Profit Organisations are key partners in the realisation of Outcome 7, vibrant, equitable and sustainable communities. In its efforts to achieve this outcome, the Department facilitated the implementation of both the DSD Sector Funding Policy and the DSD-NPO Partnership model. The facilitation was achieved through various engagements with stakeholders. The implementation of the Policy and the Model will enhance the relationship between government and the NPO sector in outlining the funding requirements and the service delivery model.

Community Development: As part of its contribution towards poverty eradication and elimination of hunger, the Department continued with the provision of food and nutrition security services. In this regard, a total of 413 069 vulnerable individuals accessed food through CNDCs. The Department further developed and consulted on a Developmental Model for CNDCs in its efforts to formalise and empower the CNDCs operations. The Model will be presented to the Community Development Forum for approval. The Department also assessed the implementation of the Integrated Food and Nutrition Security Plan. A consolidated assessment report with province specific assessments was consolidated. All these efforts makes the Department a key contributor to the realisation of Outcome 7 Vibrant, equitable, sustainable rural communities contributing towards food security for all and Outcome 13 An inclusive and responsive social protection system

- Performance Trends: January 2019- March 2019

Chart 1 below indicates overall performance trends for the period April 2018 to March 2019 (first to fourth quarters of 2018/19). During the fourth quarter, performance increased as compared to the third quarter. A total of 69% of the set targets were achieved in the fourth quarter as compared to 63% in the third quarter, an increase of 6% in achievement of targets. As a result, targets which are in progress (partially met) decreased from 18% in the third quarter to 13% in the fourth quarter. Targets which are not achieved at all decreased by 1% from 19% in the third quarter to 18% in fourth quarter.

The targets which were not  achieved includes among others; the analysing of the integrated quarterly report for entities and associated  institutions, the draft governance and capacity building guidelines developed in programme 1. The following targets were also not achieved under programme 4: the submission of White Paper to Cabinet for approval, dissemination of the Child Care and Protection Policy, Submission of the draft Policy on Social Development Services to SPCHD cluster and FOSAD clusters and the submission of the National Strategic Framework on Disability Rights awareness campaigns to Cabinet for approval to mentioned the few.

Reasons for non-achievement of targets included amongst others the following: Lack of capacity, Parliament being unable to process the Bills, Policies and the Plans due to time constraints, and the lengthy consultation process on the Policies, Bills and Plans before submission to Parliament.

Chart 1: Overall DSD Performance Trends – Quarter 1, 2, 3 and 4 Performance 2018/19

Programme 1: Administration

Human Capital Management

| Strategic objectives | High-level Outputs | Performance indicator | Estimated Performance 2017/18 | Annual Target 2018/19 | 4th Quarter target 2018/19 | 4th Quarter actual output 2018/19 | Reason for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ensure adequate capacity, capability and sound employee relations for the department to deliver on its mandate | Sector Human Resource Plan (SHRP) (2017-2022) | Sector Human Resource Plan | Submit SHRP to the Minister and Members of the Executive Council (MINMEC) for approval | Implementation of the key elements of the SHRP | Capacity building of social service practitioners on occupation-specific training intervention of the skills audit findings | Based on the findings of the skills audit, (38) occupational specific training programmes as well as (19) generic training programmes were successfully implemented for SSP's. | No deviation | Not applicable |  |

Intergovernmental Relations

| Strategic Objectives | High-level Outputs | Performance indicator | Estimated Performance 2017/18 | Annual Target 2018/19 | 4th Quarter target 2018/19 | 4th Quarter actual output 2018/19 | Reason for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ensure adequate capacity , capability and sound employee relations for the department to deliver on its mandate | International obligations facilitated | Number of international engagements facilitated | Facilitate DSD participation in 8 international events | Facilitate DSD participation in 8 international engagements | Facilitate DSD participation in 2 international engagements | The Unit facilitated DSD participation in 4 international engagements. | Exceeded the quarterly target due to participation in additional Ministerial engagements that are relevant to the mandate of the Department. | It is difficult to anticipate ad-hock engagements. In the near future DSD can only assess the relevance of individual invitation |  |

Information Management Systems and Technology

| Strategic objectives | High-level Outputs | Performance indicator | Estimated Performance 2017/18 | Annual Target 2018/19 | 4th Quarter 2018/19 target | 4th Quarter 2018/19 actual output | Reason for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Integrated planning and performance management by 2019 | Integrated information systems | Integrated social Sector-wide information, Communications, and Technology (ICT) service delivery platform | Integrate existing welfare services into the Single Information Case Management System | Establish NISIS development governance framework and enhance existing data sources | Integrate community development services into a single information case management system | NISIS has been successfully redeveloped into single information case management system and accepted by business to be a true reflection of community development services which is household profiling and community profiling. | No deviation | Not applicable |  |

Entity Oversight

| Strategic objectives | High-level Outputs | Performance indicator | Estimated Performance 2017/18 | Annual Target 2018/19 | 4th Quarter target 2018/19 | 4th Quarter actual output 2018/19 | Reason for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Integrated planning and performance management by 2019 | Entity governance and oversight framework implemented | Entity governance and oversight framework implemented | New indicator | Annual assessment of compliance of entities to the department’s governance and oversight framework | Analysed, integrated quarterly report for entities and associated institutions submitted | Target not achieved | The entity oversight function could not be fully capacitated and operationalised as the Department has not finalised the review of its organisational structure | The Entity Oversight function is prioritized for 2019/20 financial year |  |
|  |  |  |  |  | Entity management forum coordinated | Target not achieved | The entity oversight function could not be fully capacitated and operationalised as the Department has not finalised the review of its organisational structure | The Entity Oversight function is prioritized for 2019/20 financial year |  |
|  |  |  |  | Development and approval of governance and capacity building standards | Draft governance and capacity building guidelines developed | The draft governance and capacity building concept paper developed | The entity oversight function could not be fully capacitated and operationalised as the Department has not finalised the review of its organisational structure | The Entity Oversight function is prioritized for 2019/20 financial year |  |

Monitoring and Evaluation

| Strategic objectives | High-level Outputs | Performance indicator | Estimated Performance 2017/18 | Annual Target 2018/19 | 4th Quarter target 2018/19 | 4th Quarter actual output 2018/19 | Reason for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Integrated planning and performance management by 2019 | Effective M&E systems for the Social Development Sector (SDS) | Evaluation reports | Conduct an evaluation of the integrated Social Crime Prevention Strategy | Conduct an evaluation on Project Mikondzo | Draft report compiled on the evaluation of Project Mikondzo | Project Mikondzo draft evaluation report produced | No deviation | Not applicable |  |

Finance

| Strategic objectives | High-level Outputs | Performance indicator | Estimated Performance 2017/18 | Annual Target 2018/19 | 4th Quarter target 2018/19 | 4th Quarter actual output 2018/19 | Reason for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Good governance and effective financial management by 2019 | Sound internal controls in place | Unqualified audit report on Annual Financial Statements (AFS) | Unqualified audit report on AFS | Unqualified audit report on AFS | 3rd interim financial statements for the 2018/19 financial year submitted for audit | The 3rd quarter interim financial statements was submitted to NT on 31 January 2019 for audit. | No deviation | Not applicable |  |

Programme 2: Social Assistance

| Strategic Objectives | High-level outputs | Performance indicator | Estimated performance 2017/18 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reason for deviation | Corrective Action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Extend the provision of social Assistance to eligible individuals by 2019 | Social grants for eligible individuals | Number of social grant beneficiaries | Older persons grant | 3 400 343 | 3 513 372 | 3 513 372 | 3 553 317 | No deviation | Not applicable |  |
|  |  |  | Child support gran | 12 245 784 | 12 402 241 | 12 402 241 | 12 452 072 | No deviation | Not applicable |  |
|  |  |  | War veterans grant | 133 | 107 | 107 | 92 | This grant is not actively pursued and projections dependent on the person’s life span. | Not applicable |  |
|  |  |  | Disability grant | 1 060 313 | 1 049 811 | 1 049 811 | 1 048 255 | No deviation | Not applicable |  |
|  |  |  | Care dependency grant | 150 272 | 154 353 | 154 353 | 150 001 | No deviation | Not applicable |  |
|  |  |  | Foster child grant | 406 503 | 397 888 | 397 888 | 386 019 | No deviation | Not applicable |  |
|  |  |  | Grant-in-aid | 188 923 | 215 880 | 215 880 | 221 989 | No deviation | Not applicable |  |
|  |  | Number of Social Relief of Distress (SRD) applications awarded | 500 000 | 252 833 | 52 521 | 96 052 | Social Relief is need driven and is dependent on meeting the qualifying criteria | Not applicable |  |

Programme 3: Social Security Policy and Administration

Social Security Policy Development

| Strategic Objectives | High-level outputs | Performance indicator | Estimated performance 2017/2018 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reason for deviation | Corrective Action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| An effective and efficient social security system that protects poor and vulnerable people against income poverty by 2019 | Expansion of the CSG to orphans and vulnerable children (OVC) | Legislation to increase the value of the CSG to Orphans and Child Headed Households | Introduce the Bill to Parliament | Draft Regulations on Social Assistance Amendment Act developed | Draft Regulations on Social Assistance Amendment Act developed. | Draft Regulations were developed and consulted with stakeholders | No deviation | Not applicable |  |
|  | Universalisation of the OPG and CSG | Policy on the Universalisation of the CSG | Consultations on the Discussion Paper on the Universalisation of the CSG | Draft Policy on the Universalisation of the CSG | Internal consultation on the universalisation of the CSG | The Unit consulted internally and Draft Policy on the Universalisation of the CSG was developed. | No deviation | Not applicable |  |
|  | Review of SASSA Act | Legislative Review of SASSA Act | New Indicator | Discussion Paper on the review of SASSA Act | Discussion Paper on the review of SASSA Act | Discussion Paper on the review of the SASSA Act was completed. Presented to CSS branch forum and MANCO | No deviation | Not applicable |  |

PROGRAMME 4: WELFARE SERVICES POLICY DEVELOPMENT AND IMPLEMENTATION

Professional Social Services and Older Persons

| Strategic Objectives | High-level outputs | Performance indicator | Estimated performance 2018/19 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reasons for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strengthen social welfare service delivery through legislative and policy reforms by 2019 | Reviewed social welfare White Paper | White Paper on Social Welfare | Consult with stakeholders within the sector on the White Paper on social welfare | Submit the White Paper on Social Welfare to Cabinet for approval | Submit the White Paper on Social Welfare to Cabinet for approval | The White Paper could not be submitted to Cabinet for approval. However, the draft White Paper was consulted with internal stakeholders to further enrich the draft document | The White Paper could not be submitted for approval to Cabinet as it has to be further consulted with key stakeholders | The White Paper will be finalised and submitted to the Cabinet for approval in the next financial year |  |
|  | Demand and Supply Model for social services practitioners developed (SSPs) | Demand and supply Model for SSPs | Submit Demand and Supply Model for SSPs for approval | Develop an implementation Plan for the Demand and Supply model for SSPs | Submit the implementation plan for the Demand and Supply Model for SSPs for approval | The implementation plan for the Demand and Supply Model for SSP’s was presented to the HR Forum for approval | No deviation | Not applicable |  |
|  | Recruitment and Retention Strategy for SSPs developed | Recruitment and Retention Strategy for SSPs | Monitor implementation of Recruitment and Retention Strategy for SSPs | Monitor implementation of Recruitment and Retention Strategy for SSPs | Progress report on implementation of the Recruitment and Retention Strategy for SSPs | Drafted progress report on implementation of the Recruitment and Retention Strategy for SSPs | No deviation | Not applicable |  |
|  | Legislation on the professionalisation of SSPs | Social Service Practitioners Bill | Submit the Bill to Cabinet for approval and gazette for public comments | Submit the Bill to Forum of South African Directors- General (FOSAD) | Submit the Bill to FOSAD | Presented the SSP Bill to the SPCHD FOSAD cluster in February 2019 and approval was granted to proceed to Cabinet. | No deviation | Not applicable |  |
|  | Older Persons services strengthened | Active Ageing Programme implemented | Conduct older persons Parliament and Active Ageing Programme | Conduct Older Person Parliament and Active Ageing Programme | Evaluate Older Persons Parliament and Active Ageing Programme | The 2018 Older Persons Parliament and Active Ageing Programme were evaluated | No deviation | Not applicable |  |

Early Childhood Development

| Strategic Objectives | High-level outputs | Performance indicator | Estimated performance 2018/19 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reasons for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strengthen child protection services and improve the quality of ECD services by 2019 | ECD services improved | National Integrated Implementation plan on ECD Policy | Approval of the National Integrated Implementation Plan on ECD Policy | Monitor the implementation of the National Integrated Implementation Plan on ECD Policy | Consolidate quarterly reports on the implementation of the National Integrated Implementation Plan on ECD Policy. | The quarterly reports on the implementation of the National Integrated implementation Plan on ECD Policy were consolidated | No deviation | Not applicable |  |

Children Services, Orphan and vulnerable Children (OVC)

| Strategic Objectives | High-level outputs | Performance indicator | Estimated performance 2018/19 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2017/18 | Reasons for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strengthen child protection services and improve the quality of ECD services by 2019 | Child rights governance and compliance systems strengthened | National Plan of Action for Children in South Africa | Approval of the National Plan of Action for Children in South Africa by 2018-2022 | Approval of the National Plan of Action for Children in South Africa by 2018-2022 | Present the National Plan of Action for Children to Cabinet | The draft National Plan of Action for Children was presented to the JCPS Cluster and was approved for presentation to Cabinet | The National Plan of Action for Children has to be approved by the Social Cluster before Cabinet. The Social Cluster consultation has been scheduled for April 2019 | The National Plan of Action for Children will be presented to Cabinet in the first Quarter of 2019-2020 |  |
|  |  | Implementation of Children’s Act monitored | Build the provinces’ capacity to implement the Children’s Amendment Act and Children’s Second Amendment Act | Monitor the implementation of the Children’s Act | Monitor the implementation of the Children’s Act | The implementation of children’s Act was monitored in six provinces (FS, LP, MP, NC, NW and WC). A consolidated national report has been compiled. | No deviation | Not applicable |  |
|  | Child Care and Protection Policy | Child Care and Protection Policy | Consultation with key stakeholders on the Child Care and Protection Policy | Submit the Child Care and Protection Policy to Cabinet for approval | Dissemination of the Child Care and Protection Policy | Dissemination of the Child Care and Protection Policy could not be done as it had to be further consulted with the Office of the Chief State Law Adviser (OCSLA) as directed by Cabinet | Waiting for the response from OCSLA and Cabinet final consideration before dissemination | The unit will make follow- ups with the Office of the Chief State Law Adviser. |  |
|  |  | Implementation of guidelines on community based prevention and early intervention services to vulnerable children | New indicator | Develop uniform implementation guidelines for provinces | Finalise the guidelines | Final uniform implementation guidelines were developed | No deviation | Not applicable |  |
|  | Child Care and Protection Policy | Programmes for statutory services for children in need of care and protection | New indicator | Capacitate 9 provinces to implement guidelines and strategies for adoption, foster care and Child and Youth Care Centres (CYCCs) | Produce a consolidated report for statutory services for children in need of care and protection | A consolidated report on statutory services for children in need of care and protection was produced. | No deviation | Not applicable |  |
|  |  | Inter-sectoral protocol to respond to violence against children, child abuse, neglect and exploitation | New indicator | Develop the Intersectoral protocol | Finalised inter-sectoral protocol to respond to violence, child abuse, neglect and exploitation of children | An draft intersectoral protocol document is finalised | No deviation | Not applicable |  |
|  | Care and support services to families strengthened | Number of provinces trained on Active Teenage Parenting Programme | Train 9 provinces on Active Teenage Parenting Programme | Build capacity in 9 provinces on Active Teenage Parenting Programme | Capacity building of three provinces to implement the Teenage Parenting Programme | Capacity building workshops were conducted in two provinces: Eastern and Western Cape | Four capacity building workshops were conducted during the 3rd quarter. The WC and EC were the only two provinces remaining to conclude the capacity building sessions. | Not applicable |  |

Social Crime Prevention and Victim Empowerment

| Strategic Objectives | High-level outputs | Performance indicator | Estimated performance 2018/19 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reasons for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Reduce the incidences of social crime and substance abuse and facilitate the provision of support services to target groups by 2019 | Child Justice Act implemented | Policy framework on Accreditation of Diversion Services | Submit Policy Framework on Accreditation of Diversion Services to Cabinet for approval | Capacity Building in 9 provinces to implement the reviewed policy framework on Accreditation of Diversion Services | Capacity building on the reviewed Policy framework on Accreditation of Diversion Services in 3 Provinces. | Capacity building on the reviewed Policy framework on Accreditation of Diversion Services took place in KZN. | This was the only remaining province to be trained as per plan | Not applicable |  |
|  | Integrated Social Crime Prevention Strategy implemented | Integrated Social Crime Prevention Strategy | 5 provincial multidisciplinary committees were established in GP, LP, MP, NC and EC | Conduct awareness campaigns in 9 provinces on multidisciplinary Integrated Social Crime Prevention Strategy | Conduct awareness campaigns in 1 province on multidisciplinary Integrated Social Crime Prevention Strategy | Awareness campaigns took place in NC and KZN | The other province was capacitated to catch-up on the underachievement of the previous quarters. | Not applicable |  |
|  | Legislation on Victim Empowerment Support Services | Bill on Victim Empowerment Support Services | Submit the Bill to Cabinet for approval and gazette for public comments | Draft final report on costing. | Draft final report on costing. | Draft final report on costing not done | Technical experts only started costing process during the third quarter hence the final report on costing could not be compiled. | The unit will revise the project plan, to fast-track the costing process. |  |
|  |  | South African Integrated Programme of Action addressing Gender Based Violence (GBV) (2013- 2018) | Implementation plan for the POA | Submit the reviewed South African Integrated Programme of Action that addresses Gender Based Violence to Cabinet for approval | Submit the reviewed South African Integrated Programme of Action (POA) addressing Gender Based Violence to Cabinet for approval | Draft POA has not been submitted to Cabinet for approval. | The process of reviewing the POA was delayed in order to link the POA with the presidential GBV and Femicide National Summit outcomes. | The Departments’ representative will serve on the GBV Interim Committee that is responsible for redrafting the POA and the National Plan of Action. |  |
|  | Anti- Substance Abuse Plan of Action implemented | Anti-substance abuse policy implemented | New Indicator | Submit draft Anti-Substance Abuse Policy to Cabinet for approval | Submit draft Anti-substance abuse Policy to FOSAD SPCHD Cluster for approval. | Draft Anti-substance abuse Policy was submitted to SPCHD Cluster for approval. | No deviation | Not applicable |  |
|  |  | National Drug Master Plan implemented | Submit Draft NDMP to Cabinet for approval | Submit draft National Drug Master Plan to Cabinet | Capacitate 2 provinces to implement NDMP | Capacitated the North West and Free State Provinces on the development of Provincial Plans. | No deviation | Not applicable |  |

HIV and AIDS

| Strategic Objectives | High-level outputs | Performance indicator | Estimated performance 2018/19 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reasons for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contribute to the reduction in HIV risky behaviour and promote psychological wellbeing amongst targeted key populations by 2019 | Improved co-ordination, joint planning and Integrated service delivery in high- burden districts by 2019 | Integrated action plan to respond to the social and structural drivers of HIV, tuberculosis (TB) and sexually transmitted infections (STIs) by 2019 | New indicator | Develop draft integrated action plan to respond to the social and structural drivers of HIV, TB and STIs | Consolidate inputs and finalise the draft document | Consolidation of inputs in to the draft integrated action plan was undertaken and the plan was finalized | No deviation | Not applicable |  |

Rights of Persons with disabilities

| Strategic Objectives | High-level outputs | Performance indicator | Estimated performance 2018/19 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reasons for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To promote, protect and empower persons with disabilities through the development and implementation of legislation, policies and programmes | Legislative and policy framework strengthened | Draft Policy on Social Development Services to Persons with Disabilities | Submit Policy on Social Development Services to Persons with Disabilities to Cabinet for approval and gazette for public comments | Submit draft Policy on Social Development Services to Social Protection, Community and Human Development (SPCH) cluster and FOSAD clusters | Submit draft Policy on Social Development Services to Social Protection, Community and Human Development (SPCH) cluster and FOSAD clusters | The Policy was not presented to (SPCHD) cluster and FOSAD clusters. However, the Policy was presented at EXCO on route to MINMEC as required (on the report) before presenting the Policy to Social Cluster | EXCO made recommendation for the Policy to be revised before tabling at MINMEC. The prerequisite for tabling the Policy at MINMEC and Social Cluster is EXCO approval. | The Policy will be processed at various structures for approval in the new financial year. |  |
|  |  | Strategic Framework to support implementation of the White paper on the Rights of Persons with Disabilities (WPRPD) | Develop 2 National Strategic Frameworks to support implementation of the WPRPD | Submit National Strategic Framework on Disability Rights awareness campaigns submitted for Cabinet Approval | National Strategic Framework on Disability Rights awareness campaigns submitted for Cabinet approval | Validation and improvement process towards a Final Draft of the National Strategic Framework on Disability Rights Awareness Campaigns still in progress | Human Resources Capacity constraints | The Policy will be processed at various structures for approval in the new financial year. |  |
|  | UN Convention on the Rights of Persons with Disabilities (UNCRPD) and WPRPD implementation monitored and evaluated | Number of reports on the implementation of the WPRPD and UNCRPD | One report on implementation of the WPRPD produced | One compliance report on implementation of the WPRPD; and one periodic report on the UNCRPD, submitted to Cabinet for approval | Second Progress Report on Implementation of the WPRPD published and released | One compliance report on implementation of the WPRPD approved at branch level One periodic report on the UNCRPD approved by Cabinet | Late submissions from departments delayed the cabinet approval process for compliance report. This was a risk identified. | The compliance report on Implementation of the WPRPD will be submitted to Cabinet for approval in Q1 of 2019/20 |  |

Programme 5: Social Policy and Integrated Service Delivery

Special Projects and Innovation

| Strategic Objectives | High-level outputs | Performance indicator | Estimated Performance in 2017/18 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reasons for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Facilitate management and coordination of cross-cutting functions for DSD and Social Cluster | Social Sector Public Employment Programmes coordinated | Social Sector plan phase IV through the EPWP | Convene 32 Social Sector coordination forums | Develop phase IV of the Social Sector Plan through the EPWP | Communicate final draft of phase IV of the Social Sector Plan through the EPWP to stakeholders | The EPWP Phase IV Plan was finalised. The Plan was discussed with the Social Sector National Programme Managers, comprising of Department of Social Development, Public Works, Health, Sports and Recreation, and the Civilian Secretariat at a National Steering Committee Meeting held in March 2019 in Gauteng | No deviation | Not applicable |  |

Population and Development

| Strategic Objectives | High-level outputs | Performance indicator | Estimated Performance in 2017/18 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reasons for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Promote and support the implementation of the Population Policy | Population Policy implementation monitored and evaluated | Number of progress reports on the implementation of the White Paper on Population Policy and the ICPD PoA | Produce 10 reports on the implementation of the Population Policy | Produce 9 reports on the implementation of the White paper on Population Policy and ICPD PoA | ICPD +25 synthesis report | ICPD+25 synthesis report was compiled | No deviation | Not applicable |  |
|  |  |  |  |  | ASRHR Framework Strategy monitoring report | ASRHR Framework Strategy monitoring report produced | No deviation | Not applicable |  |
|  |  |  |  |  | PPD EXCO report | PPD EXCO report compiled | No deviation | Not applicable |  |
|  | Policy to promote the demographic of youth dividend for South Africa | Policy paper prospects and recommendations for the demographic youth dividend for South Africa | New indicator | Finalise Draft Policy Paper on demographic youth dividend | Finalise draft policy paper | Zero draft policy paper produced | No deviation | Not applicable |  |

NPOs Compliance Monitoring and Funding Coordination

| Strategic Objectives | High-level outputs | Performance indicator | Estimated Performance in 2017/18 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reason for deviation | Corrective Action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Create an enabling environment for NPOs to deliver effective services by 2019 | DSD Sector Funding Policy developed | DSD Sector Funding Policy | Submit DSD Sector Funding Policy for approval | Facilitate the implementation of the DSD Sector Funding Policy | Consultations with relevant stakeholders to facilitate the implementation of the DSD Sector Funding Policy | Facilitated the implementation of the DSD Sector Funding Policy through the consultative engagement sessions with key stakeholders. | No deviation | Not applicable |  |
|  | Reviewed dispensation for State-civil society partnership in the delivery of social welfare and community development services | DSD-NPO Partnership Model | Submit Partnership Model for State, NPOs and relevant stakeholders for approval | Facilitate the implementation of the DSD-NPO Partnership Model | Consultations with relevant stakeholders towards the National implementation of the DSD-NPO Partnership Model facilitated | Facilitated the implementation of the DSD-NPO Partnership Model through consultative engagement sessions with key stakeholders. | No deviation | Not applicable |  |
|  | Regulatory framework for NPOs revised | NPO Act amended | Table NPO Amendment Bill in Parliament | Submit the NPO Bill to Cabinet | Submit the NPO Bill to Cabinet | The NPO Bill was not submitted to Cabinet | The SEIAS Certification not concluded. SEIAS certification is a prerequisite for development of policies and Bill before submitting to Cabinet. | The target has been reviewed in the new financial year |  |

Social Mobilisation and Community Empowerment

| Strategic Objectives | High-level outputs | Performance indicator | Estimated Performance in 2017/18 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reason for deviation | Corrective Action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Facilitate and coordinate community development efforts to build vibrant and sustainable communities by 2019 | Regulated and uniform Community Development Practice | Community Development Practice Policy | Facilitate implementation of the Community Development Practice Policy | Facilitate implementation of the Community Development Practice Policy | Report on the establishment of provincial forums on the Community Development Practice Policy | Report on the establishment of provincial forums on the Community Development Practice policy was produced. | No deviation | Not applicable |  |
|  | Guidelines on community mobilisation and implementation developed | National guidelines for community mobilisation and implementation | National guidelines for community mobilisation and intervention | Facilitate implementation of the guidelines | Conduct workshops on the implementation of the guidelines in 3 provinces | The target was achieved in the third quarter | No deviation | Not applicable |  |
|  | Youth development facilitated | Social Development Youth Policy | Submit the Social Development Youth Policy for approval | Facilitate the implementation of the Social Development Youth Policy | Conduct workshops in 3 provinces | Target was achieved in the second quarter | No deviation | Not applicable |  |
|  | Youth development facilitated Implementation of Policy framework for management of Community Based Workers (CBWs) | Social Development Youth Strategy | Submit Social Development Youth Strategy for approval | Facilitate the implementation of the Social Development Youth Strategy | Develop and submit workshop reports | The Directorate changed the approach and held Roundtables discussion with all nine provinces to discuss both the policy and the strategy. Roundtable discussion report was developed and submitted. | No deviation | Not applicable |  |
|  | Youth development facilitated Implementation of Policy framework for management of Community Based Workers (CBWs) | Number of youth attending national youth camp | 1 000 youth attending national youth camps | 1 800 youth attending national youth camps | Applicable in the third quarter |  |  |  |  |

Poverty Alleviation, Sustainable Livelihood and Food Security

| Strategic Objectives | High-level outputs | Performance indicator | Estimated Performance in 2017/18 | Annual target 2018/19 | 4th Quarter Target 2018/19 | 4th Quarter Actual Outputs 2018/19 | Reason for deviation | Corrective Action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contribute to poverty eradication and elimination of hunger through support to community-driven programmes and the provision of food and nutrition security services by 2019 | Facilitate the establishment and support of income-generating sustainable livelihood initiatives for communities | Number of cooperatives linked to economic opportunities | 600 Cooperatives linked to economic opportunities | 1000 Cooperatives linked to economic opportunities | 200 Cooperatives linked to economic opportunities | 117 Cooperatives linked to economic opportunities | Introduction of National Treasury Classification Circular affected Cooperatives, since they have to operate under Goods and Services. Most of them are not compliant with SCM processes. | Capacity building of Cooperatives on SCM processes and compliance |  |
|  |  | Developmental Model for Community Nutrition and Development Centres(CNDCs) | - | Develop a Developmental Model for CNDCs | Final Developmental Model for CNDCs | The Developmental Model for CNDCs was finalized through consultation process with provinces. | No deviation | Not applicable |  |
|  | Integrated Food and Nutrition Security Plan implemented | Integrated Food and Nutrition Security Plan | Facilitate the implementation of the Integrated Food and Nutrition Security Plan in 9 provinces | Assess the implementation of the Integrated Food and Nutrition Security Plan | Consolidation and submission of assessment report | Assessment report on the implementation of the Integrated Food and Nutrition Security Plan has been consolidated from the provincial responses | No deviation | Not applicable |  |
|  |  | Number of vulnerable individuals accessing food through CNDCs | 80 000 vulnerable individuals accessing food through CNDCs | 415 000 vulnerable individuals accessing food through CNDCs | Provide food to 103 750 vulnerable individuals through CNDCs | Food was provided to 413 069 vulnerable individuals | The over achievement is due to high demand for food by vulnerable individuals in the country. | Not applicable |  |

PART C: ACRONYMS AND ABBREVIATIONS

Abbreviations for Entities

NDA	National Development Agency

SASSA	South African Social Services Agency

Department of Social Development Abbreviations and Acronyms

APP	Annual Performance Plan

ASRHR	Adolescent Sexual Reproductive Health Rights

AU	African Union (Formerly OAU)

CNDCs	Community Nutrition and Distribution Centres

CSG	Child Support Grant

CWP	Community Work Programmes

DDG	Deputy Director General

DPME	Department of Planning, Monitoring and Evaluation

DSD	Department of Social Development

EC	Eastern Cape

ECD	Early Childhood Development

EPWP	Extended Public Work Programme

FS	Free State

GBV	Gender Based Violence

GP	Gauteng Province

HRCF	Human Resource Consultative Forum

HWSETA	Health and Welfare Sector Education and Training Authority

ICT	Information and Communication Technology

IJS	Integrated Justice System

IMC	Inter-Ministerial Committee

IPPF	International Planned Parenthood Foundation

JCPS	Justice, Crime Prevention and Security

KZN	KwaZulu-Natal

LP	Limpopo Province

M & E	Monitoring and Evaluation

MINMEC Minister and Members of the Executive Committee’s Council

MP	Mpumalanga Province

NC	Northern Cape

NDMP	National Drug Master Plan

NISIS	National Integrated Social Information System

NPO	Non-Profit Organization

NSP	Nutrition Security Plan

NW	North West

OVC	Orphaned and Vulnerable Children

PASA	Population Association for South Africa

PED	Population Environment and Development

PSS         Psychosocial Support Services

SBC          Social Behaviour Change

SDGs         Sustainable Development Goals

SDS          Social Development Sector

SHRP       Social Sector Human Resource Plan

SLA          State Law Advisors

SPCHD    Social Protection, Community and Human Development

SRD        Social Relief of Distress

SSP         Social Service Practitioners

ToR         Terms of Reference

UAPS	 Union for African Population Studies

UN	   United Nations

UNCPD    United Nations Commission on Population and Development

USA          United State of America

VEP	  Victim Empowerment Programme

VSS           Victim Satisfaction Survey

WC             Western Cape

WPRPD      White Paper on the Rights of

Persons with Disabilities