PROGRAMME 4: WELFARE SERVICES POLICY DEVELOPMENT AND IMPLEMENTATION

Rights of Persons with disabilities

| Strategic Objectives | High-level outputs | Performance indicator | Estimated performance 2018/19 | Annual target 2019/20 | 1st Quarter Target 2019/20 | 1st Quarter Actual Outputs 2019/20 | Reasons for deviation | Corrective action | Overall progress |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To promote, protect and empower persons with disabilities through the development and implementation of legislation, policies and programmes | White Paper on the Rights of Persons with Disabilities (WPRPD) implemented | Policy instruments (tools, guidelines, policy briefs, discussion papers and research reports) developed to support domestication of international treaties and implementation of WPRPD | Frameworks on Disability Rights Awareness Campaigns, as well as Framework on Self-Representation by Persons with Disabilities released for public comment. National Guidelines for Public Participation developed. | Frameworks on Disability Rights Awareness Campaigns, as well as Self-Representation by Persons with Disabilities developed | Applicable in the second quarter | Draft Structure for Framework on Disability Rights Awareness Campaigns completed. Draft Framework on Self-Representation by Persons with Disabilities developed. | The delays in obtaining Cabinet approval of the National Frameworks on Universal Access and Design and Reasonable Accommodation have delayed finalization of the subsequent draft frameworks, which will not be submitted to the NDRM for validation. | National Frameworks on Universal Access and Design and Reasonable Accommodation to be re-routed to Ministry Women, Youth and Persons with Disabilities before end of Aug 2019. |  |
|  |  | National Disability Rights Machinery strengthened | New Indicator | Disability Inclusion embedded in Government-wide Institutional Arrangements | Framework for National and Provincial Disability Inclusion Institutional Arrangements finalised | Consultations with national government departments as well as provinces have been concluded. | Finalisation of the draft Framework delayed due to National Macro-Organisation of Government process | Draft Framework will be finalized by end of August following announcement on reconfiguration of government departments |  |
|  |  | Performance reports on implementation of WPRPD developed | Annual Progress Report on Implementation of the White Paper on the Rights of Persons with Disabilities produced. One Periodic report on implementation of the UNCRPD developed | Annual Progress Report on Implementation of the White Paper on the Rights of Persons with Disabilities developed. | Design and develop model for automated reporting. | Department of Justice and Constitutional Development (DJoCD) and Office of the United Nations High Commissioner for Human Rights were consulted on aligning the national disability reporting system within the ‘OHCHR National Recommendation and Tracking’ Database and locating disability inclusion within the broader international reporting system. | The project was initially seen as a disability sector pilot, however an opportunity to align the national reporting system has presented itself. There are delays due to alignment with DJoCD reporting system. Aligning national reporting system will slow down the process but is more sustainable in the long term | Possibility of approaching the Office of the United Nations High Commissioner for Human Rights to support the project on a pilot basis being explored. |  |
|  | Strengthening legislative and policy framework to provide persons with disabilities and their families with equitable access to social development services | Policy and legal instruments that support services to persons with disabilities and their families developed | Policy on Social Development Services to Persons with Disabilities submitted to the FOSAD SPCHD cluster | Draft Policy on Services to Persons with Disabilities and their families submitted for approval for public comment | Policy on Services to Persons with Disabilities and their families submitted for approval to gazette for public comments | IGNORE - DSD WELFARE SERVICES TARGET |  |  |  |
|  | Persons with disabilities and their families empowered to drive disability inclusion in their communities | Community-Based Disability Inclusive Development Programme piloted | New Indicator | Community Based Disability Inclusive Development Programme (CBID) developed | Baseline survey and activity plan on CBID developed in two provinces | IGNORE - DSD WELFARE SERVICES TARGET |  |  |  |