## Slide 1: FORESTRY AND FISHERIES BRANCH 2018/19 Annual Performance Report
PRIVATE AND CONFIDENTIAL

## Slide 2
FORESTRY

## Slide 3: Forestry
Strategic Objective: Ensure increased production and productivity in prioritised areas as well as value chains |  | 
Performance indicator | Annual target 2018/19 | Programme Annual Progress and Analysis
Number of hectares planted TUPs | 550 ha | 586,16 hectares were planted in the Kwazulu-Natal (100), Eastern Cape (419,62) and Limpopo (66,54) regions Reason for over-achievement: Eastern Cape, Limpopo and Mpumalanga experienced rainfall above normal average and temperatures below normal average (favourable rainfall conditions). Another reason provided by Limpopo + Mpumalanga Region was enough seedlings were available for planting whilst the partnership with DRDAR also played a critical role in speeding up site preparations for planting in the Eastern Cape Region.
Re-commissioning of WC state forest plantations | Establishment of six legal entities | Six legal entities were not established. However, the draft trust deed was discussed with communities for possible adoption. Challenge: No positive outcome came from the meeting held on 11-13 March 2018. Corrective measure: The six communities requested to be given more time to look into the Draft Trust Deed before adopting it.
    = Achieved
    = Partially achieved
    = Not achieved
    = No
    milestone

## Slide 4: Forestry
Strategic Objective: Lead and coordinate government food security initiatives |  | 
Performance indicator | Annual target 2018/19 | Programme Annual Progress and Analysis
Agro-forestry Strategy Framework implemented | Project plans on the two pilot sites implemented | Project plans on the two pilot sides (Limpopo and Mpumalanga) have been implemented.
Strategic Objective: Ensure the conservation, protection rehabilitation and recovery of depleted and degraded natural resources |  | 
Number of hectares of state indigenous forests rehabilitated | 300 ha of state indigenous forests | 300.44 ha of state indigenous forests were rehabilitated.
    = Achieved
    = Partially achieved
    = Not achieved
    = No
    milestone

## Slide 5: 2018/19 FORESTRY PERFORMANCE
Chart: 2018/19 Forestry Performance
| Achieved | Partially Achieved | Not Achieved
Forestry | 0.75 | 0 | 0.25

## Slide 6
FISHERIES MANAGEMENT

## Slide 7: Fisheries Management
Strategic Objective: Strategic Objective: Ensure increased production and productivity in prioritised areas as well as value chains |  | 
Performance indicator | Annual target 2018/19 | Programme Annual Progress and Analysis
Increase the number of FTE job opportunities (Working for Fisheries Programme) | 1 092 jobs (544 FTEs) 597 female jobs (328 female youths and 12 females with disabilities) 488 male jobs (268 male youths and 10 males with disabilities) | Not achieved. 30 jobs (27.72 FTEs) 16 female jobs (3 female youths and 0 females with disabilities; 14 male jobs (2 male youths and 0 males with disabilities. Challenge: Only 1 project (Hamburg Aquaculture project) was active during the financial year. The WfFP did not have staff during the reporting period and as a result, no new projects could be initiated.
Number of aquaculture catalyst projects (identified and listed under Operation Phakisa) supported | Four Operation Phakisa projects supported | 16 aquaculture projects were supported 12 Exceeded annual target due to the increased demand due to the EIA that was approved in Saldanha Bay during the financial year.
Small-scale aquaculture support programme developed and implemented | Small-scale aquaculture support programme concept note | Small-scale Aquaculture Support Programme Inception report was developed Challenge: Small-scale Aquaculture Support Programme concept note was not done due to delays in Supply Chain processes on the appointment of the service provider to develop the concept note.
    = Achieved
    = Partially achieved
    = Not achieved
    = No
    milestone

## Slide 8: Fisheries Management
Strategic Objective: Strategic Objective: Ensure increased production and productivity in prioritised areas as well as value chains |  | 
Performance indicator | Annual target 2018/19 | Programme Annual Progress and Analysis
Aquaculture Development Act developed and implemented as per Operation Phakisa | Aquaculture Development Bill/ Act implementation plan | Aquaculture Development Bill/Act implementation plan was not developed. Challenge: The implementation plan can only be developed once the President has signed off on the Bill into Act. The process is currently under Parliament processes.
Number of aquaculture research projects conducted | One new research on economics of new candidate species for aquaculture conducted (Sea urchin) | One new research on economics of new candidate species for aquaculture was Conducted (Sea urchin) and report has been compiled and approved.
 | One new research project on production systems for new candidate species for aquaculture conducted (Scallops) | An exploratory survey of Algoa Bay was conducted in April 2018 by contracted divers to establish the population density and to collect 30 scallops parentstock/broodstock, as no live scallops could be found in False Bay. During the survey in April 2018, no live parentstock/broodstock was found in Algoa Bay and only empty shells were found. The natural populations of scallops will need to recover and timeframes for recovery could span a number of years unless a population is detected elsewhere along the South African coast. Challenge: No live broodstock can be located in the areas known to have scallop populations.
    = Achieved
    = Partially achieved
    = Not achieved
    = No
    milestone

## Slide 9: Fisheries Management
Strategic Objective: Strategic Objective: Ensure increased production and productivity in prioritised areas as well as value chains |  | 
Performance indicator | Annual target 2018/19 | Programme Annual Progress and Analysis
Number of aquaculture research projects conducted (cont) | One aquatic animal health research project (Epizootic Ulcerative Syndrome) | One aquatic animal health research project (Epizootic Ulcerative Syndrome) was conducted and report has been compiled.
 | One research project on climate change: Assessment of temperature, deoxygenation and acidification on aquaculture | One research project on climate change: Assessment of temperature, deoxygenation and acidification on aquaculture was conducted and report has been compiled.
    = Achieved
    = Partially achieved
    = Not achieved
    = No
    milestone

## Slide 10: Fisheries Management
Strategic Objective: Lead and coordinate government food security initiatives |  | 
Performance indicator | Annual target 2018/19 | Programme Annual Progress and Analysis
Commercial fishing rights allocated | Allocate rights in the abalone sector | Rights in the abalone sector were not allocated however exemption was granted to existing long term abalone right holders for the 2018/19 abalone season, starting 1 November 2018 until 31 July 2019. The delegated authority decided not to allocate rights in the abalone sector during 2018/19.
 | Revised policies and application forms for 12 fishing sectors which expire in 2020 | 1st Draft General Policy on the Allocation of Commercial Fishing Rights completed and consulted internally Challenge: The new requirement to conduct Socio-Economic Impact Assessment System (SEIAS) by the DPME included additional requirements that resulted in planned milestones not being achieved. The Revised Application forms are dependent on the finalisation of the policy
 | Support the (FRAP 2015/2016) appeals process | The appeals in the Netfish and KwaZulu-Natal Sardine Beach-Seine fishing sectors were finalised on 25 April 2018, The appeals in the Seaweed fishing sector were finalised on 8 June 2018. The appeals of the WCRL Offshore and Zones A-B of WCRL Nearshore was finalised on the 20 September 2018. The appeals in the WCRL Nearshore sector- Zones D-F were concluded on the 4 & 16 October 2018. The appeals in the Hake Inshore Trawl sector were concluded on 7 December 2018.
    = Achieved
    = Partially achieved
    = Not achieved
    = No
    milestone

## Slide 11: Fisheries Management
Strategic Objective: Lead and coordinate government food security initiatives |  | 
Performance indicator | Annual target 2018/19 | Programme Annual Progress and Analysis
Small-scale Fisheries Policy implemented | Rights allocated to registered small-scale fisheries cooperatives | The small-scale fishing rights were allocated in Northern Cape. Challenge: The tip off process caused the delay in finalizing the list of small scale fishers in the western cape and there were delays of co-operative registration with CIPC for the EC and KZN
Sustainable management of fish stocks | Recovery plans for 2 sectors: abalone and west coast rock lobster | The inter area-schedule was finalised in consultation with the exemption holders. Applications for permits for the 2018/19 fishing season received, considered. WCRL Inter-area schedule was signed off on 07 November 2018, and the permits issued thereafter. The Minister upheld the 2018/19 Abalone TAC appeal and reset the fishing season from 9 April 2019 to 9 January 2020.
 | Research reports and TAC/TAE recommendations for 2 sectors: abalone and west coast rock lobster | Research reports and TAC/TAE recommendations compiled for the Abalone and WCRL sectors
    = Achieved
    = Partially achieved
    = Not achieved
    = No
    milestone

## Slide 12: Fisheries Management
Strategic Objective: |  | 
Performance indicator | Annual target 2018/19 | Programme Annual Progress and Analysis
Number of inspections conducted | 4 500 compliance and enforcement measures in the six prioritized fisheries sectors: hake, abalone, rock lobster, linefish, pelagic and squid implemented | A total of 4 698 compliance and enforcement measures in the six prioritised fisheries sectors: hake, abalone, rock lobster, linefish, pelagic and squid implemented. The over- achievement was due to the Fishery Control Officers (FCOs) performing the function of the catch data monitors which resulted in additional inspections being conducted.
Number of joint operations conducted with partners including Operation Phakisa Initiative 5 | 40 operations | A total of 91 joint operations conducted An over achievement is imputed to Operation Phakisa Oceans Economy activities that had been initiated with the other Law Enforcement Agencies. Due to a lack of resources, MCS participated in a number of smaller operations to address illegal activities which led to an over-achievement
Number of investigations conducted in terms of the Marine Living Resources Act | 280 investigations | A total of 281 investigations conducted
    = Achieved
    = Partially achieved
    = Not achieved
    = No
    milestone

## Slide 13: OVERALL SUMMARY OF 2018/19 PROGRAMME 1 PERFORMANCE
% Achieved | % Partially achieved | % Not achieved | % No milestone
53% (9/17) | 12% (2/17) | 35% (6/17) | -
Chart: 
| On target | work in progress | Off target | No milestone
Sales | 53 | 12 | 35 | 0