## Finance
DEPARTMENT OF MILITARY VETERANS- FINAL MANAGEMENT REPORT 2020/21 | [20 empty] | Select Department Name | 2007-04-07
[18 empty] | Yes |  | 1 | The Presidency | 2007-05-07
Audit Findings Action Plan Monitoring Tool - Issues raised by AGSA | [19 empty] | 3 | Foreign Affairs | 2007-07-07
|  |  | BACK TO COMBINED | [15 empty] | 0% - No progress | 4 | Home Affairs | 2007-08-07
40% - Task partially complete
Exception number and audit finding title | Description | Action Plan Description |  | Root Cause | Start Date | Completion Date | Person Responsible | Position | Progress | Narrative | Rank | Count | Factor | Score | Progress | Probability | Weighted Score |  | 60% - Task progressing well | 6 | Public Works | 2007-10-07
[7 empty] | Name | [11 empty] | 80% Task virtually complete | 7 | Government Communication and Information System | 2007-11-07
|  | * Describe activities in point form to address issue (use lower case) |  |  | * Select planned start and completion dates |  | * Select title and enter name (use lower case) | * Select position | *Select progress of activity | *Enter any pertinent comments | 1 | #REF! | #REF! | #REF! |  |  | #REF! |  | 100% - Task complete | 8 | National Treasury | 2007-12-07
1. Logistical Information System (LOGIS) user access management procedure was not formally documented (COMAF 2) | The user access management procedure that the Department of Military Veterans (DMV) should use as a guide for managing user access on Logistical Information System (LOGIS) was not formally documented. Lack of user access management procedure may result may result in user access on LOGIS not being consistently and adequately managed, this may lead to nauthorised access being granted. |  | The draft policy is now available for input by MANCO and recommendation for approval by EXCO | Consultation on the policy took longer than expected | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 40% - Task partially complete | Policy to be finalised before 31 March 2022 |  | 1 | #DIV/0! | #DIV/0! | #REF! | #REF! | #DIV/0!
2. Logistical Information System (LOGIS) user modification process was not adequately implemented (COMAF 2) | The completed user modification request forms ((“LOG21 Maintain Security (User) Profiles”) for some transactions were not adequately completed; as the forms did not indicate the functions that needed to be modified. |  | None | None | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 40% - Task partially complete | None
3. Segregation of duties on Logistical Information System was not adequately implemented (COMAF 2) | The segregating duties on the Logistical Information System (LOGIS) were not adequately implemented due to the following: a) The LOGIS functions were not adequately configured, as the user type profiles had conflicting functions. Refer to Annexure for further user type profiles which had conflicting functions. b) The RACF ID “VW5006” was allocated with the user type 3 and 4 profiles on the LOGIS; as a result, the user was able to perform both administrative and user functions on the LOGIS. |  | a) No further action to be implemented. b) The user will remain with one user type i.e. User Type 3. User type 4 will be deleted with immediate effect to remove the conflict/s. c) No further action to be implemented. d) The CFO delegation of authority will be aligned with the financial delegations. Management will also add the Accounting Officer to approve payments above R1 million or the Accounting Officer may opt to delegate in writing the LOGIS approval process to optimise the processing period. The correction/s will be done by 06 July 2021, as the LOGIS System is offline for maintenance purposes. | Inadequate human capacity | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | The CFO delegation of authority is aligned with the financial delegations.
4. The SCM policy have not been updated with the latest changes in legislation (acts and regulations) and treasury instructions. (COMAF 3) | During the audit of procurement and contract management, it was noted that the Supply Chain Management (SCM) policy for the department was last updated on the 28th of February 2017. |  | a) Management should review and update the SCM policy annually to incorporate changes and new requirements to ensure that the risk of non-compliance in procurement and contract management is mitigated. b) Controls in place for the review and updating of policies should be enhanced. | Consultation process took longer than expected | 2021-09-01 | 2021-12-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
5. Difference between Irregular Expenditure schedule, Fruitless and Wasteful Expenditure schedule and the Annual Financial Statements. (COMAF 04) | The department had inadequately implemented the process of password resets on Active Directory (AD) as ITSM (SITA Service Desk) logged incident request for the following transaction could not be provided to the audit team. |  | System administrator account privileges provide unrestricted access to files, directories, and resources with full read / write / execute privileges. Therefore, the Government Information Technology Officer (GITO) should ensure that activities performed by system administrators on AD are consistently and adequately monitored during the SITA SLA meetings; and the evidence of monitoring is retained for reference purposes. | Corrected immediately and AFS figure was reinstated | 2021-09-01 | 2021-12-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
6. Fixed Assets under investigation (COMAF 5) | The accounting officer for a department is responsible for the management, including the safeguarding and the maintenance of the assets of the department. |  | We are in agreement with the observation and finding by AGSA. It is for the same reason that we have reported that we have appointed a service provider to assist with the verification process formanagement to close off this issue on assets under investigation. The physical verification is done and we are now busy with the reconciliation or matching with the Assets Register. | Service provider was appointed but could not deliver | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 60% - Task progressing well | Finance scheduled to visit all DMV offices in February 2022 including provincial office to perform a thourough verificaion and make recommendations to the A/CFO.
7. Determination test for fruitless and wasteful expenditure not performed (COMAF 11) | In terms of section 38 (1)(a)(i) of the Public Finance Management Act, 1999 (Act No1 of 1999): The accounting officer for a department must ensure that the department has and maintains effective, efficient and transparent systems of financial and risk management and internal control |  | We are in agreement with the finding. This is due to current capacity challenges in the department concerning both Human Resource Capacity and Skill/s. The skills challenge is being challenged through training from the Office of the Accountant General. Human Resources Capacity is being addressed through the renewal of the DMV organogram. | Insufficient huma capacity | 2021-09-01 | 2022-01-31 | Z Gcasamba | Acting CFO | 100% - Task complete | All cases emanating from previous financial years were submited to Nexus forensic investigation for determination and recommendation due to inadequate capacity within the department to perform such. A report was since issued and shared with AGSA
8. High Level inconsistencies identified in the Financial Statements. (COMAF 14) | The Public Finance Management Act 1 OF 1999 section 40(1)(a) states that: ‘The accounting officer for a department (a) must keep full and proper records of the financial affairs of the department, trading entity or constitutional institution in accordance with any prescribed norms and standards. (b) prepare financial statements for each financial year in accordance with generally recognized accounting practice.’ |  | This was to state that we are willing to adjust the AFS. | Corrected immediately and AFS figure was reinstated | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
9. Suppliers not paid within 30 days (COMAF 16, 19, 21 & 45) | In terms of Treasury Regulation (TR) 8.2.3: Unless determined otherwise in a contract or other agreement, all payments due to creditors must be settled within 30 days from receipt of an invoice or, in the case of civil claims, from the date of settlement or court judgment. |  | Corrective steps/controls implemented to address the finding and risk: Processes have been put. | Still remains a challenge | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 60% - Task progressing well | We are enhancng internal controls in this area
10. High level inconsistencies identified in the Financial Statements. (COMAF 23) | The Public Finance Management Act 1 OF 1999 section 40(1)(a) states that: The accounting officer for a department (a) must keep full and proper records of the financial affairs of the department, trading entity or constitutional institution in accordance with any prescribed norms and standards. (b) prepare financial statements for each financial year in accordance with generally recognized accounting practice. |  | Corrective Action: We are more than willing to amend the mistake on the AFS. | Corrected immediately and AFS figure was reinstated | 2021-09-01 | 2021-12-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
11. Payables not recognised. (COMAF 22) | During the audit of the annual financial statements (AFS) we identified that ‘payables not recognised’ in relation to goods and services provided to the Department of Public Works (DPW) were incorrectly recorded in the payables summarised manual. The payables summarised manual therefore disagreed with the DPW reconciliation. As a result, the ‘payables not recognised’ disclosed in the AFS are overstated. |  |  | Corrected immediately and AFS figure was reinstated | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
12. Recording of Key Management Emoluments (COMAF 25) | During the audit of the Key management personnel disclosure note (Note 34), it was noted that the prior period correction relating to the disclosure of the family members of the key management personnel, was not disclosed as a prior period error as required by MCS. |  |  | Corrected immediately | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
13. Supply chain management: NonCompliance with National Treasury Instruction no.11 (COMAF 26) | In terms of the National Treasury Instruction No: 11 of 2020/21: Procurement in response to national state of disaster regarding COVID-19 pandemic and repeal of instruction no: 5 of 2020/21:  Paragraph 6.1 – All institutions are required to report procurement transactions for the periods indicated in Table 1 by the deadlines provided. All procurement transactions related to the emergency procurement for COVID- 19 PPE items, fabric masks as well as other goods, works or services that were procured to prevent an escalation of the national state of disaster, declared on 15 March 2020 (the Disaster) or to alleviate, contain or minimize the effects of the Disaster, must be reported. This includes, inter alia, expenditure for quarantine and isolation services, humanitarian relief, etc. |  | We have now created a database to track all Covid 19 procured items for the ease of tracking and reporting. | SCM was not aware of the requirement and have since made the correction | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 40% - Task partially complete | Department is progressing well
14. Control weakness in the review process of Overtime (COMAF 28) | HIGH OVERTIME RATES The Department will compensate employees for higher rates whereby the Heads (General Manager’s/Senior General Manager’s) have approved in writing for employees to work overtime on a Sunday/Public Holiday, or any other day between 20h00 to 06h00. The Department will pay the employee concerned the applicable rate for the overtime worked as prescribed in PSCBC Resolution 3 of 1999 Part VII and 1 of 2007. |  | Control measures are in place to ensure that we compensate employees accordingly. | Inadequate controls in the area of overtime. | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 40% - Task partially complete | In-progress
15. Recurring fruitless and wasteful expenditure not prevented (COMAF 29) | In terms of section 38(1)(c)(ii) and 38(1)(h)(iii) of the Public Finance Management Act, 1999 (Act No1 of 1999): The accounting officer for a department must take effective and appropriate steps to prevent unauthorised, irregular, fruitless, and wasteful and losses resulting from criminal conduct. The accounting officer for a department must take effective and appropriate disciplinary steps against any official in the service of the department, trading entity or constitutional institution who makes or permits an unauthorised expenditure, irregular expenditure or fruitless and wasteful expenditure. |  |  | Most fruitless and wastefull are as a result of no shows during work travel. The departmet has since approved its S&T policy with strong controls on management of S&T | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Most fruitless and wastefull are as a result of no shows during work travel. The departmet has since approved its S&T policy with strong controls on management of S&T.
16. Submissions to the B-BBEE Commission not performed as required by B-BBEE regulation No.12 (COMAF 30) | In terms of B-BBEE regulation 12(2): the sphere of government, public entity or an organ of state must file the audited annual financial statements and annual report compiled in terms of section 13G(1), with the Commission, in the prescribed FORM B-BBEE 1 within thirty (30) days of the approval of such audited annual financial statements and annual report. |  | We subsequently received the BBBEE compliance certificate but could not lodge the submission with the BBBEE Commission. We will use the 2019/20 BBBEE and lodge the reports with the Commission by 31 July 2021. | In-progress | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 40% - Task partially complete | In-progress
17. Subsequent event not disclosed in the AFS (COMAF 34) | If a department receives information after the reporting date, but before the financial statements are authorised for issue, about conditions that existed at the reporting date, it shall update disclosures that relate to these conditions, in the light of the new information. |  |  | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
18. Incorrect disclosures included under irregular expenditure note (COMAF 35) | During the audit of the irregular expenditure we noted that under sub-note 23.6 ‘Details of the non compliance where an institution is involved in an inter-institutional arrangement’, which would be the note 31.9 in the specimen annual financial statements (referred to in the guidance above), the department disclosed an amount of R12 026 000 for rental paid for the DMV Head Offices on an expired contract. This irregularity arose as a result of the lease agreement transaction where the department is required by law to make use of the Department of Public Works (DPW) to procure office accommodation for them. |  | We are in agreement with the finding from AGSA. This finding is now informed by the Frequently Asked Questions (FAQ) that were issued post the submission date of the 31 May 2021. This was contrary to the advice obtained during the CFO forum held on the 26 March 2021. We will however be guided by the FAQ document as it purports to drive consistency in across government on the preparation of AFS. We will adjust the AFS should AGSA grant DMV the permission to do so. | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
19. Suppliers in which close family members of role players have and interest (COMAF 36) | In terms of section 38(1) (h) (i) of the Public Finance Management Act The accounting officer for a department must take effective and appropriate disciplinary steps against any official in the service of the department who contravenes or fails to comply with a provision of the Act. In terms of the Treasury Regulations 16A8.4 “If a supply chain management official or other role player, or any close family member, partner or associate of such official or other role player, has any private or business interest in any contract to be awarded, that official or other role player must: a) Disclose that interest; and b) Withdraw from participating in any manner whatsoever in the process relating to that contract”. |  | Corrective steps/controls implemented to address the finding and risk: The Assistant Directors are not included in the category of financial disclosure. The following categories disclose their financial interests; SMS, MMS, all finance and SCM officials. | Under investigation | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 20% - Task Started | Under investigation
20. Incorrect supplier awarded with bid (COMAF 37) | In terms section 6 (8) of the Preferential Procurement Regulations 2017: The contact must be awarded to the tender scoring the highest points. |  | Management is willing to add this non-compliance matter on the checklist for further handling and corrective action to be onsidered. | Under investigation | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 20% - Task Started | Under investigation
21. Internal control deficiencies identified in the quotations register (COMAF 38) | During the audit of procurement and contract management controls deficiencies were identified relating to the quotations register, which is a manual register (excel document), used by the department to maintain a record of request of quotations (RFQs) and the related quotations received. |  |  | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
22. Accruals Overstated (COMAF 39) | During the audit of the accruals note with reference to Transfer Payments relating to Tertiary Education, it was identified that the following learner was duplicated in the schedule supporting the disclosure note and as a result the accrual amount disclosed is overstated. |  |  | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
23. Asset verification and reconciliation not performed (COMAF 40) | In terms of the Department of Military Veterans Asset Management Policy: -10.6.1 “The department will perform one full asset verification per annum”. -11.1.3 “On a monthly basis, the assets register will be reconciled to the general ledger, the register will be sufficiently detailed to provide an adequate trail its useful lifespan”. -20.5 The key responsibilities of the Asset Manager, amongst others include,” To manage asset counts, plan all assets counts i.e., number of locations per site or provincial offices”. |  | Due to the lack of capacity, authority was obtained to utilize an external service provider. The service provider is yet to conclude the process and this remains a concern on the side of management. | Service provider was appointed but could not deliver | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 60% - Task progressing well | Finance scheduled to visit all DMV offices in February 2022 including provincial office to perform a thourough verificaion and make recommendations to the A/CFO.
24. Control weakness in the review process of Periodic Payments (COMAF 42) | In terms of section 38 (1)(a)(i) of the Public Finance Management Act, 1999 (Act No1 of 1999): The accounting officer for a department must ensure that the department has and maintains effective, efficient and transparent systems of financial and risk management and internal control. |  |  | All documentation sent out to stakeholders are reviewed by the acting CFO | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
25. Fruitless and Wasteful Expenditure register misstatements (COMAF 43) |  |  |  | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
26. Irregular expenditure note - Items not condoned but removed understated (COMAF 44) | With reference to Public Finance Management Act, 1999 (Act No. 1 of 1999) (PFMA) In terms of the Public Finance Management Act Section 38 and 40: 38. General responsibilities of accounting officers (1) The accounting officer for a department, trading entity or constitutional institution (a) must ensure that that department, trading entity or constitutional institution has and maintains (i) effective, efficient and transparent systems of financial and risk management and internal control, |  | We have since updated the formulae on the related worksheets in order ensure correctness of the information to be disclosed. | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
27. Overstatement of irregular expenditure under assessment in relation to remuneration to audit committee members (COMAF 47) | In terms section 40(1) (a) of the PFMA The accounting officer for a department must keep full and proper records of the financial affairs of the department in accordance with any prescribed norms and standards. In terms of section 38 (1) (c) (ii) of the PFMA The accounting officer for a department must take effective and appropriate steps to prevent unauthorized, irregular and fruitless and wasteful and losses resulting from criminal conduct.  Treasury Regulation 20.1 provides the following definitions: “Official member” means a person as defined in section 8(1) of the Public Service Act, 1994 (Proclamation No. R.103 of 1994), a member of Parliament or a judge, as well as a person employed by a body that was established by an Act of Parliament and that receives its funds wholly, or in part, from the National Revenue Fund, where such a person represents the department or body where he or she is employed as a member of a commission or committee. “Non-official member” means a person who is not an official member. |  |  | Lack of policy on employees doing business with the state | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 80% Task virtually complete | Draft policy is being consulted and will be finalised before the end of the year
28. Understatement of accruals (COMAF 51) | In terms of Section 40 (1)(a) of the Public Finance Management Act, 1999 (Act No1 of 1999), The accounting officer for a department, (a) must keep full and proper records of the financial affairs of the department, trading entity or constitutional institution in accordance with any prescribed norms and standards. (b) must prepare financial statements for each financial year in accordance with generally recognized accounting practice; |  |  Corrective steps/controls implemented to address the finding and risk:  Name and surname (responsible official who will implement the corrective steps/controls):  Position (position of the responsible official who will implement the corrective steps/controls):  Date (date when the corrective steps/controls will be implemented): | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
29. Payables not recognised (COMAF 52) | In terms of Section 40 (1)(a) of the Public Finance Management Act, 1999 (Act No1 of 1999), The accounting officer for a department, (a) must keep full and proper records of the financial affairs of the department, trading entity or constitutional institution in accordance with any prescribed norms and standards; (b) must prepare financial statements for each financial year in accordance with generally recognized accounting practice; c) During the completeness testing of payables we identified the following learners that were not included payables note. This results in a projected understatement of payables amounting to R10 236 440. |  | A) We agree for items 1 and 3 that an omission on our part was committed and we would like to adjust the AFS (R62 085.00). For items 2, 4, 5 and 6, the invoices were already paid for and therefore no need for adjustment of Payables. B) We agree and we will effect the adjustment of R7967.29. C) We agree with the finding and we will adjust the AFS if permitted to do so. | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
30. Understatement of rental accruals (COMAF 53) | During the audit of rental accruals, we noted that there were no accruals raised for the Bloemfontein and Cape Town offices in relation to office space used during the year. |  | DMV management will develop its own schedule for accruals and payables for office rental to ensure that accruals and payables related to office rentals are always correct. | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
31. Overstatement of Lease Commitments (COMAF 54) | During the audit of Lease Commitments, it was noted that the lease commitment disclosure note number 22.1 is misstated for the buildings and other fixed structures for the separation as per MCS chapter 13 paragraph 22. The requirement is for the total future minimum lease payments at the reporting not later the one year (within 12 months) and later than one year and note later than five years from the reporting date. |  | We agree with the above findings. At the time of submission of the AFS, the Northern Cape Lease Agreement was not yet provided to the Department. We have since received a copy during June 2021 and we would like to adjust the calculation in accordance with the agreed contract period that runs from 01 September 2020 till 31 August 2025. This will allow us not to report prior year errors during the next audit cycle. We also request to adjust thediscrepancies identified on the lease commitments in terms of the two reporting periods i.e. Less than 12 months and more than one year but less than five years. | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
32. Items not evaluated for local content (COMAF 56) | Paragraph 7.1.1 of the Preferential Procurement Policy Framework Act, no 5 of 2000 states that; bids in respect of services, works or goods that have been designated for local production and content, must contain a specific bidding condition that only locally produced goods, services or works or locally manufactured goods with a stipulated minimum threshold for local production and content will be considered. |  | To remedy this, the SCM compliance checklist will be strictly enforced to avoid this repeat finding. | SCM checklist not strictly enforced | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 40% - Task partially complete | SCM checklist strictly enforced
33. Understatement of Performance Bonus estimate (COMAF 57) | During the audit of the Employee Benefits Performance Bonus, a mathematical error was noted on the total estimate for salary levels 13 – 16. The total of R193 137,42 as per the schedule differs with the auditor’s recalculation of R525 479.74. This is due to the fact that the bonus estimates amounts for salary level 13 were not included in the total. |  | In future, management is working towards filling the vacant post of the Director Finance, whose functions include compilation of AFS that are supported by validated and complete supporting schedules. | Corrected during the audit of 2020-21 AFS | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 100% - Task complete | Done
34. Misstatements identified in the asset register (COMAF 58) | During our asset verification testing, we selected assets from the asset register to trace to the floor to verify existence. However, we noted that the following assets could not be traced for existence. Based on the discussion held with the asset official, it was indicated that the assets have been stolen, however these assets are still recorded in the asset register. This misstatement results in an overstatement of the movable tangible asset amount recorded in the notes to the annual financial statements by R47 877,28 and a projected amount of R2 863 979. Furthermore, this also results in the understatement of the disposal amount by R47 877,28. |  | We agree with the findings under item 1 but the laptop with tag number DMV-4002696 was amended by AGSA to reflect tag number DMV4002146. Having noted the finding, we have since added same items on the investigations register for major assets. We have not yet resolved the microwave and we wish AGSA to keep this for the next audit cycle for management to have done proper investigation. | Service provider was appointed but could not deliver | 2021-09-01 | 2022-03-31 | Z Gcasamba | Acting CFO | 60% - Task progressing well | Finance scheduled to visit all DMV offices in February 2022 including provincial office to perform a thourough verificaion and make recommendations to the A/CFO.

## Corp Services
DEPARTMENT OF MILITARY VETERANS- FINAL MANAGEMENT REPORT 2020/21 | [20 empty] | Select Department Name | 2007-04-07
[18 empty] | Yes |  | 1 | The Presidency | 2007-05-07
Audit Findings Action Plan Monitoring Tool - Issues raised by AGSA | [19 empty] | 3 | Foreign Affairs | 2007-07-07
|  |  | BACK TO COMBINED | [15 empty] | 0% - No progress | 4 | Home Affairs | 2007-08-07
40% - Task partially complete
Exception number and audit finding title | Description | Action Plan Description |  | Root Cause | Start Date | Completion Date | Person Responsible | Position | Progress | Narrative | Rank | Count | Factor | Score | Progress | Probability | Weighted Score |  | 60% - Task progressing well | 6 | Public Works | 2007-10-07
[7 empty] | Name | [11 empty] | 80% Task virtually complete | 7 | Government Communication and Information System | 2007-11-07
|  | * Describe activities in point form to address issue (use lower case) |  |  | * Select planned start and completion dates |  | * Select title and enter name (use lower case) | * Select position | *Select progress of activity | *Enter any pertinent comments | 1 | #REF! | #REF! | #REF! |  |  | #REF! |  | 100% - Task complete | 8 | National Treasury | 2007-12-07
1. Policies have not been approved. (COMAF 12) | During the planning phase we requested updated policies form the department (RFI 10 of 2020/21), and a number of the policies submitted per the register were old policies in effect for periods beyond their review periods. Some of the policies which were provided/submitted by the department were not approved, and only draft versions were submitted, which may as a result not be fully enforceable |  | The review and approval of policies will be followed up in the following financial year. Management should ensure that the policies have gone through all the relevant processes in time to be approved before the review date of the previous policy falls due. | Consultation procces took longer | 2001-04-21 | 1931-03-22 | Siyengo | C-Director Research and Policy | 80% Task virtually complete | The task is progressing very well as most policies were approved during the year.
2. Organisational Structure not aligned with the Strategic Plan. (COMAF 10) | During the planning phase of the audit, it was noted that the organization structure is not aligned to the service delivery model as its noted as a risk as well in their strategic plan : The current structure does not capacitate this high-level reality that will enable the legislative mandate of the department to the full. Phase 2 of the organisational structure has been under review for numerous years and still in progress as at year-end. The above could result in possible non-compliance with the requirements of the Public Service Regulations and impact on service delivery objectives if not addressed. |  | As it is an external Service Provider who needs to be appointed, the Department is not able to commit to a timeline at this stage as it will be dependent on the Terms of Reference which needs to be agreed upon. | The Military Veteterans Act is under review which then delayed the process to finaliuse the review of the organisational structure | 31/03/21 | 31/12/21 | M Makhonza | HR Head | 60% - Task progressing well | The finding remain until such time management is able to address the finding
3. Business agreement and Service Level Agreement was not reviewed (COMAF 8) | The BA stated that “BA will be reviewed annually or in line with the strategic and/or annual performance plan to confirm the correctness/validity of the BA”. However, the BA was last approved in December 2012 and the officials who have signed and agreed on the BA terms were no longer employed by Department of Military Veterans (DMV) and State Information Technology Agency (SITA).  The SITA primary SLA which was signed by both parties in September 2014 was found to be outdated due to: o the annexures which were part of the primary SLA were different to annexures which were separately submitted to auditors. The primary SLA had four (4) annexures and the annexures which were separately submitted were 10. o the 14% was used to calculate VAT on the pricing schedule of the 4 annexures which were part of the SLA. |  | Management takes note of the finding. The BA and SLA have been reviewed and the legal opinion was provided from both parties. A separate Addendum will be made available for the current services the DMV has contracted for with SITA. The services will therefore not form part of the Primary SLA as they will be defined in their specific Annexure documents. Management however does not agree that services were governed inadequately because separate Annexures were provided for each service rendered by SITA. | Consultation procces took longer | 1921-08-31 | 1921-09-30 | O Masekwameng | GITO | 100% - Task complete | The Businesses agreement and service level agreement have been reviewed and signed .
4. No formal process to measure information and communication technology return on investment and benefit realisation (COMAF 8 | The development of formal processes which will be followed to measure ICT return on investment and benefits realisation was delayed by finalisation of Corporate Governance ICT Framework and ICT Strategic Plan. The ICT management wanted to finalise the ICT Framework and ICT Strategy and thereafter develop other processes based on the approved Corporate Governance ICT Framework and ICT Strategic Plan. |  | Management takes note of the finding. The ICT Strategy was only finalised in the previous financial year. The ICT is currently in the process of developing various plans to support the implementation of the plan including negotiation off budget. Develop the ICT implementation plan that will incorporate processes which will be followed to measure ICT return on investment and benefits realisation | Consultation procces took longer | 1921-04-30 | 2021-12-21 | O Masekwameng | GITO | 100% - Task complete | The Standard operating procedure to address this area has been completed and finalised.
5. Software licenses not adequately managed (COMAF 8 | The software licence agreement between the Department of Military Veterans (DMV) and Microsoft was not in place. As a result, the department was running on Windows 7, which was no longer receiving security patches and support from the Microsoft. It was further noted that the software licence agreement between the DMV and McAfee antivirus had expired in August 2020 and have not been renewed since its expiry. |  | The recommendation is also noted and management will ensure that available licenses and software are managed appropriately | Inadequate funding | 31/03/21 | 2022-03-31 | O Masekwameng | GITO | 60% - Task progressing well | Procurement of software licences is underway.
6. Anti-virus software updates not adequately deployed (COMAF 7) | The anti-virus software updates were not adequately deployed, as the audit team was unable to confirm whether the following workstations were updated with the latest antivirus software:  DESKTOP-48R51J5  |  | Agreed with the finding | Capacity constraints | 31/03/2119 | 2022-03-31 | O Masekwameng | GITO | 100% - Task complete | • A list is provided in the monthly reports on workstaions that are conneting to the ePo. • The workstations that are updated DATS automatically and manually are reported on in the monthly report. • The department has a clear WSUS and Antivirus process in place.
7. Patch management process was not adequately implemented (COMAF 7) | It was noted that seventy-nine (79) workstations were running on Windows 7 Operating System, which was no longer being supported and receiving patches from Microsoft since January 2020. Furthermore, the audit team was unable to confirm the Operating System/s running on “Bafanam”‘s workstations. As Operating Systems reach their end-of-life (EOL), vendors stop offering support. Therefore, security and stability decrease, allowing attackers to exploit found vulnerabilities that will never receive a patch or security update |  | The DMV line managers responsible will be engaged to ensure that workstations which are incompatible with antivirus are replaced | Capacity constraints | 31/03/21 | 31/12/21 | O Masekwameng | GITO | 100% - Task complete | • A screen shot was provided for workstations that were patched. • A function in WSUS - monthly reports are provided on all workstations and servers on their patch progress. • Screenshots will be provided on request.
8. Inactivity timeout setting on Active Directory not configured (COMAF 7) | The inactivity timeout setting was not configured on Active Directory. The users can leave their workstations unattended and forget to lock them. This may result in unauthorised access to the department's information systems. |  | Management takes note of the finding and has addressed it. Email (DOMAIN LOCK SCREEN SETTING REQUEST | Capacity constraints | 31/03/21 | 31/12/21 | O Masekwameng | GITO | 100% - Task complete | The inactive timeout setting has been set to be activated after 15 minutes.
9. Lack of information and communication technology awareness training (COMAF 7) | The audit team had only received evidence of the security awareness that took place on the last day of the audit cycle, 31 March 2021 and no other Information and Communication Technology (ICT) awareness trainings were conducted during 2020/21 financial year. As a result, the following security awareness trainings were not conducted:  Training staff on secure authentication  Training staff on identifying social engineering attacks  Training staff on sensitive data handling  Training staff on causes of unintentional data exposure  Training staff of identifying and reporting incidents |  | The education and awareness plan will be updated and conducted throughout the 2021/22 financial year. | Capacity constraints | 31/03/21 | 31/03/2022 | O Masekwameng | GITO | 100% - Task complete | The user awareness training was conducted through out the year. The training covered the following areas ( Password construction and management guideline , Email Accounts on Mutliple devices , Protection from Malware , Password reset reminders)
10. Logon violations on the Active Directory were not monitored (COMAF 7) | The logon violations on Active Directory (AD) were not monitored during 2020/21 financial year. The control weakness was also reported during the 2018/19 and 2019/20 audit cycles. |  | Mail sent for the above finding for the logging attempts and reset done from the AUDITING rule enabled attached as evidence.  Document with screen shot of the AUDITING ENABLED active attached as evidence.  The Auditing enablement function is has been activated on Active Directory.  The reports will be signed periodically. | Capacity constraints | 31/12/21 | 30/03/22 | O Masekwameng | GITO | 60% - Task progressing well | The department is aware of this limitation, however, implemented a temporary solution in the form of Active Directory Plus for management and reporting solution that enables instant reports on all activities. The procurement of a fully equipped and licensed management and motoring application is underway. | not address
11. The firewall management processes were not adequately designed (COMAF 7) | The approved network and firewall procedure document was not adequately designed as previously reported, due to following weaknesses:  The metadata, which would have accompanied each rule descriptors for the DMV firewall was not documented.  The minimum firewall configuration settings to block unnecessary services, spoofing, illegal/ bogus addresses were not outlined on the procedure document. As a result, the audit team was unable to confirm whether the firewall was adequately configured. |  | The DMV is in the process of procuring a firewall solution that will be managed internally though SITA | Capacity constraints | 1931-04-21 | 31/03/22 | O Masekwameng | GITO | 80% Task virtually complete | Management partially agrees with the finding. Though the department will take corrective measures to address some of the identified gaps as per recommendation, note should be taken that some information cannot be captured on the procedure due to security measures, but the role and function is supervised through the SLA and reports are produced and submitted, periodically. | not address
12. Firewall activities were not monitored (COMAF 7) | There was no evidence to confirm that firewall rulesets and incoming and outcoming traffic was regularly monitored during 2020/21 financial year, as previously reported. |  | The DMV to specify the rules to be logged on the syslog server. To also ensure that SITA provides reports consistent | Capacity constraints | 2021-03-03 | 31/03/22 | O Masekwameng | GITO | 80% Task virtually complete | Management partially agrees with the finding. Though the department will take corrective measures to address some of the identified gaps as per recommendation, note should be taken that some information cannot be captured on the procedure due to security measures, but the role and function is supervised through the SLA and reports are produced and submitted, periodically.
13. Disaster Recovery Plan not adequately designed (COMAF 5) | During the 2018/19; 2019/20 and 2020/21 financial years it was noted that the department had developed the Disaster Recovery Plan (DRP) document to “provide guidance to DMV Information Technology (IT) department in recovering the ICT infrastructure and systems in the event of a major ICT disaster, in line with the Recovery Time Objectives (RTO) defined by business.” However, the DRP document was in draft and the following weaknesses were noted: |  | Management within the ICT does not accepts the finding. The overall DMV BCP is the responsibility of the Accounting Officer. The ICT will ensure to align to the BCP as soon as it is available. | Capacity constraints | date not provided | Date not provided | O Masekwameng | GITO | 80% Task virtually complete | A Tasking Letter incorporating a comprehensive Business Impact Analysis, BCP and DRP implementation plan has been submitted to SITA for implementation.
14. Personnel and Salary system (PESRAL) policy and procedure documents were in draft (COMAF 1) | The user access management policy document which the Department of Military Veterans (DMV) was utilising as a guide for managing user access on Personnel and Salary (PERSAL) system was still in draft and under review to address the weaknesses which was previously reported on user access management processes. |  | Not in agreement, the Acting Director: HRM was formally appointed and all responsibilities pertaining to the post of Director: HRM rests on the Acting appointment. | Capacity constraints | 31/03/21 | 2022-03-31 | M Makhonza | HR Director | 80% Task virtually complete | Policy to be approved before the end of the financial year.
15. User access rights on Personnel and Salary system were not reviewed (COMAF 1) | The user access management policy document which the Department of Military Veterans (DMV) was utilising as a guide for managing user access on Personnel and Salary (PERSAL) system was still in draft and under review to address the weaknesses which was previously reported on user access management processes. |  | Not in agreement, the Acting Director: HRM was formally appointed and all responsibilities pertaining to the post of Director: HRM rests on the Acting appointment | Capacity constraints | 1921-04-30 | 2022-03-31 | M Makhonza | HR Director | 80% Task virtually complete | The process of revising the ICT Security policy is underway which will address the identified gaps.
16. Activities of the system controller on Personnel and Salary system were not monitored (COMAF 1) | The review of user access rights on Personnel and Salary (PERSAL) system, which will ensure that PERSAL access rights commensurate with the users’ job responsibilities, was not performed during 2020/21 financial year, as previously reported. |  | The Policy Review has been concluded and is currently in draft which will be presented to MANCO in July 2021 Not in agreement, the Acting Director: HRM was formally appointed and all responsibilities pertaining to the post of Director: HRM rests on the Acting appointment. | Shortage of personnel | 1921-09-30 | 1921-12-31 | M Makhonza | HR Director | 100% - Task complete | Persal system controller was appointed during the year. | not address
17. Password reset controls on Active Directory were not adequately implemented (COMAF 4) | The department had inadequately implemented the process of password resets on Active Directory (AD) as ITSM (SITA Service Desk) logged incident request for the following transaction could not be provided to the audit team: |  | Management comments outstanding. The updated audit finding was re-issued on 03 August 2021. | Capacity constraints | 1921-09-30 | 1921-12-31 | O Masekwameng | GITO | 100% - Task complete | Calls are logged at SITA call desk then referred to on sight technicians to be reset.
18. Disagreement misstatement: Overstatement of leave entitlement balance due to control weakness in the review process of periodic payments (COMAF 48) | it was noted that vacation leave transactions were not captured in time within the financial year on the Persal System for the following employees, and were as a result not taken into accounting when calculating the leave entitlement balance disclosed in the financial statements: |  | agreed and resolved | Capacity constraints | 1921-04-30 | 1921-09-30 | M Makhonza | HR Director | 100% - Task complete | Done

## IA&RM
DEPARTMENT OF MILITARY VETERANS- FINAL MANAGEMENT REPORT 2020/21 | [20 empty] | Select Department Name | 2007-04-07
[18 empty] | Yes |  | 1 | The Presidency | 2007-05-07
Audit Findings Action Plan Monitoring Tool - Issues raised by AGSA | [19 empty] | 3 | Foreign Affairs | 2007-07-07
|  |  | BACK TO COMBINED | [15 empty] | 0% - No progress | 4 | Home Affairs | 2007-08-07
INTERNAL AUDIT & RISK MANAGEMENT | [18 empty] | 20% - Task Started
40% - Task partially complete
Exception number and audit finding title | Description | Action Plan Description |  | Root Cause | Start Date | Completion Date | Person Responsible | Position | Progress | Narrative | Rank | Count | Factor | Score | Progress | Probability | Weighted Score |  | 60% - Task progressing well | 6 | Public Works | 2007-10-07
[7 empty] | Name | [11 empty] | 80% Task virtually complete | 7 | Government Communication and Information System | 2007-11-07
|  | * Describe activities in point form to address issue (use lower case) |  |  | * Select planned start and completion dates |  | * Select title and enter name (use lower case) | * Select position | *Select progress of activity | *Enter any pertinent comments | 1 | #REF! | #REF! | #REF! |  |  | #REF! |  | 100% - Task complete | 8 | National Treasury | 2007-12-07
EX 1. Internal Audit -No external assessments conducted - Internal Audit Function (COMAF 1) | Since its establishment (for over 5 years) the internal audit function has not been externally reviewed by an independent assessor as required by the International Auditing Standard 1312 External Quality Assessment. This external assessment evaluates the internal audit department’s conformance with the Standards and assesses the efficiency and effectiveness of the internal audit department. This results in non-compliance with the instructions provided by National Treasury, Treasury Regulation 3.2.6 as well as the international Auditing Standards IIA 1312. Since the internal audit function has not been assessed, this may also lead to a poor control environment due to increased risk that internal controls may not be properly evaluated by internal audit to ensure effectiveness thereof. |  | The department only staffed its internal audit activity later in 2014 with only two officials and the focus was to market the unit and develop the required policies and procedures. The unit performed its first internal audit assignments in 2015-16 financial year to date. The first external quality assurance review will be due after 5 years, i.e in 2020 in this instance. As required by standard 1300, in order for the internal audit activity to perform External Quality Assurance review, it must have performed internal quality assurance reviews. The DMV internal audit activity has successfully achieved this by performing peer to peer reviews and evaluations of the internal audit activity by Audit Committee and the Accounting officer on an annual basis. | Capacity constraints | 2021-04-01 | 2022-03-31 | M Mufamadi | DD IA | 20% - Task Started | Request was sent to National Treasury for the state of readiness review.
EX 2. Internal Audit - Insufficient capacity in the internal audit function (COMAF 2) | During the assessment of the internal audit function the following was identified indicating that the internal audit function may not be adequately resourced relative to the size of the department: i) In terms of the internal audit and risk management approved structure there are only two (2) permanent positions in the internal audit unit with one administrative staff member. The unit also has two interns who are not members of the Institute of Internal Auditors South Africa and still have limited experience. ii) The Chief Audit Executive (CAE) was the project leader in the internal audits during the year. As the CAE is also involved in the audit assignments instead of mainly performing a directing and oversight function of the whole internal audit unit it could impact on sufficient reviews in the unit as there is only one other senior official (Deputy Director) in the IA division. |  | There is a plan in place to appoint a service provider to assist in rendering internal audit services to the department. New positions are also proposed in the new structure to ensure adequate capacity within the internal audit unit. | The design of the organisational structure only catered for 2 individuals in the Internal Audit Unit. A proposed structure is in place aiming at addressing insufficient capacity. The department is in a process to appoint an internal audit service provider to address the capacity challenges faced by the unit. | 2021-09-01 | 2022-03-31 | M Mufamadi | DD IA | 80% Task virtually complete | The department is in a process to appoint a service provider before the end of the financial year.

## SES
DEPARTMENT OF MILITARY VETERANS- FINAL MANAGEMENT REPORT 2020/21 | [20 empty] | Select Department Name | 2007-04-07
[18 empty] | Yes |  | 1 | The Presidency | 2007-05-07
Audit Findings Action Plan Monitoring Tool - Issues raised by AGSA | [19 empty] | 3 | Foreign Affairs | 2007-07-07
|  |  | BACK TO COMBINED | [15 empty] | 0% - No progress | 4 | Home Affairs | 2007-08-07
40% - Task partially complete
Exception number and audit finding title | Description | Action Plan Description |  | Root Cause | Start Date | Completion Date | Person Responsible | Position | Progress | Narrative | Rank | Count | Factor | Score | Progress | Probability | Weighted Score |  | 60% - Task progressing well | 6 | Public Works | 2007-10-07
[7 empty] | Name | [11 empty] | 80% Task virtually complete | 7 | Government Communication and Information System | 2007-11-07
|  | * Describe activities in point form to address issue (use lower case) |  |  | * Select planned start and completion dates |  | * Select title and enter name (use lower case) | * Select position | *Select progress of activity | *Enter any pertinent comments | 1 | #REF! | #REF! | #REF! |  |  | #REF! |  | 100% - Task complete | 8 | National Treasury | 2007-12-07
1. limitation misstatement; PPI 203- validity of compensation benefits provided: upporting information not provided for audit purposes (COMAF 13) | The files requested (as per RFI 20) were provided for audit but did not included the information stated above. Upon enquiry with management it was stated that the documents were there at time of processing the applications, but this information could not be provided for audit purposes. As a result, we could not verify the validity of the compensation benefits provided to these military veterans as the affidavits would provide appropriate evidence that the applicant had witnesses of his/her injury, trauma or disease that is linked to military services. In the absence of affidavits alternative procedures could not be performed to ensure that the payments were valid, therefore resulting in an overstatement of the achieved number. | 1 | Not in agreement with the finding: Each file of the applicants has two checklists the one is completed by the applicant to ensure that all required documents are made available to the DMV. The other checklist is for the DMV to confirm whether all documents are available before approving applicants for medical assessments. All the military veterans listed by AG were contacted to check if they have copies of what they sent to us, and they all indicated that they provided DMV with original documents. They have sent the attached affidavits confirming under oath that their documents were there and in their files because they also saw their files during the assessments. During the Medical Panel Review, section 10 (5) (c) of the approved compensation policy states that the medical panel must utilize the medical reports from the medical practitioners to determine the amount to be paid. Two members of the panel evaluate and read aloud the findings. In addition to this, to strengthen the task at hand, another member of the panel is allocated to read the Military Veterans file and the affidavits aloud to all members in the panel for every file before the final score is allocated. There is no way that a score would be allocated without hearing what witnesses said. It is on this statements and affidavits from the military veterans that I can confirm without any doubt that the documents were in the files when they were submitted to AG. | Capacity and manual system | 2021-03-31 | 2021-06-23 | Caroline Mongale | Director Health | 100% - Task complete | The Healthcare and Wellness Unit agreed with Auditor General to create the DMV/AG Checklist as attached to ensure that all documents in the files are accounted for and avoid any document lossess. The 2021/22 Audit for the Compensation benefit has been started and the two entities are testing the Checklist. | N/A
2. AOPO : Programme 2: limitation misstatetement of PPI 203 and overstatement of PPI 207as well as non-compliance with the Mil vet benefit regulations. (COMAF 15) | ii) PPI 207: Total number of military veterans provided with access to healthcare services The following military veteran was granted access to healthcare despite being convicted of a criminal offence and serving a prison sentence of 20 years after 27 April 1994. ID |  | In Agreement with the finding | Capacity and manual system | 2021-07-01 | 31/12/21 | Coroline Mongalo | Director Health | 100% - Task complete | In the current financial year, all military veterans appliying for the healthcare benefit are requested to provide an affidavit about their criminal records when appliying for the benefit. To date, those who do not meet the criteria on the DMV Regulations are not approved to receive the benefit | N/A
3. Limitation misstatement: AOPO_ PPI 207 Healthcare and PPI 206 Education (COMAF 46 | It was identified that the military veterans listed below received counselling treatment during the year but had not been included in the register of military veterans authorized to access healthcare services and were therefore not included in the actual achievement reported in the annual performance report for PPI 207: Military veterans provided with access healthcare . |  | Addressed | Capacity and manual system | 31/03/21 | 31/06/21 | Corolane Mongalo | Director Health | 80% Task virtually complete | There is a challenge of dependency on the South African Military Healthcare Services reports. In most instances, some of the military veterans who receive service, are listed 30 days after reported. The Healthcare Unit is monitoring the process closely to ensure all military veterans who received services are accounted for in all quarters.
4. Control Deficiency: Health Care- Standard operating procedure not sufficiently to support compliance with set regulations. (COMAF 24) | The above provisions allow for a military veteran who had been authorized in terms of the Ministerial Authority, and registered on the National Military Veterans Database and accessed medical services at SAMHS to be granted an authorization letter and become registered on the Health Care Database |  | Not in agreement. with the finding | Capacity and manual system | 31/03/21 | 2021-09-06 | Caroline Mongalo | Director Health | 100% - Task complete | Information was submitted
5. Control deficiency: Adoption of the Healthcare SOP before approval (COMAF 31) | we noted that the 2021/22 Healthcare Standard Operating Procedure (SOP) was implemented at the start of the 2020/21 financial year, however it was only formally approved on 23 April 2021. From the assessment performed of the Healthcare SOP, it was noted that no provision was made that recommends or suggests the retrospective implementation of the SOP which indicates that the new procedures contained in the 2021/22 Healthcare SOP, were adopted before the finalisation of the consultation process and ultimate approval of the revised Healthcare SOP. |  | I am not in agreement with the finding From February 2020, the Unit has been engaging with the SAMHS management as they were not pleased with the number of healthcare claims rejected, on the basis of military veterans authorized. Management report of Department of Military Veterans 92 through ministerial authority, in consideration of this challenge the CD Health approved the attached workflow processes in August 2020. The new work flow processes are always identified and are subsequently added to the SOP, to assist in continuous management of risks and strengthen controls, hence the annual reviews. | Capacity and manual system | 31/03/21 | 2021-12-06 | Caroline Mongale | Director Health | 100% - Task complete | SOP was approved in April 2021 therefore finding was resolved and wont recurr in the 2021-22 audit.
6. Limitation mistatement: PPI 206 Education (COMAF 46) | The files submitted for audit either missing the education support checklist that would provide evidence on the outcome of the adjudication including the overall approval of the application by the appropriate official |  | I am in agreement with the finding for the following reasons, I cannot deny nor agree since the incumbent at the time was Ms L. Sothondoshe, who is now rotated to Housing environment and she could provide better explanation. | Capacity and manual system |  | No date indication | P.Dzuguda | Acting Director - Education | 80% Task virtually complete | The reserve forces were sourced from the DOD to assist with general administration of the Education benefit.
7. Material adjustment to APR: AOPO-Programme 2(PPI 201: Number of military veterans who are verified and captured on the National veterens Database. (COMAF 33) | I identified material misstatements in the annual performance report submitted for auditing. These material misstatements were in the reported performance information Programme 2 – socio-economic support. As management subsequently corrected only some of the misstatements, I raised material findings on the reliability of the reported performance information. Those that were not corrected are reported above. - As a result, the aggregate of the four reported figures, that have been reported as the annual achievement per the 2020/21 APR, contains military veterans that have been duplicated and thereby resulting in an overstatement of the reported achievement by 309 units. |  | Based on the audit procedures performed on the completeness of PPI 201, we identified that the following military veteran, were not included in the reported figure which creates a projected understatement of 41 Directorate will start reporting once only for each registered military veteran, that being the date of his/her registration, not the date of updating of his/her profile. This reporting approach will eliminate reporting of movements against individual Military Veteran across quarters as the database does not allow for a military veteran to be registered more than once. | Capacity and manual system | 2001-09-21 | 1931-03-22 | M Matsafu | Chief Director Data base | 100% - Task complete | Done | In progress
8. Non-compliance: Payment to schools not in operation as per with department of basic education database (COMAF 49) | We performed a procedure of comparing the schools paid by DMV to the Department of Basic Education database. In performing this comparison we identified that payments made as bursaries for beneficiaries, which amounted to R201 520.29, were paid to schools that were indicated to not be in operation as per Department of Basic Education database as detailed below: |  | Not in agreement with the finding | Capacity and manual system | 2001-09-21 | 1931-03-22 | P Dzuguda | Acting Director Education | 100% - Task complete | Only schools that are the database for the department of education are compensated.
9. Employee costs: Disagreement - Critical positions vacant for more than (twelve) months (COMAF 50) | During the audit of Employee Costs, it was noted that the following funded positions remained vacant for a period more than 12 months: Deputy Director – General: Socio Economic Support : Deputy Director – General: Corporate Services : Chief Director: Beneficiary Support |  | The Chief Director: Beneficiary Support post has been filled since 17 February 2020. The DDG posts are currently vacant and as a result of the Covid-19 Lockdown levels the Department had challenges in filling them in time. However, the two (2) DDG posts were advertised in March with a closing date of 19 March 2021 and are in the process of being filled subject to the availability of the Ministers who should constitute the Selection Panel something which is exogenous of the DMV (Administrators). | Capacity and manual system | 31/03/21 | 1931-03-22 | M Matsafu | CD Database | 60% - Task progressing well | The position of Chief Director Beneficiary support services was filled in February 2020. The posiiton of DDG SESS is yet to be filled. | in progress
10. Backups were not performed on the Military Veterans Beneficiaries Database (COMAF 5) | The backup solution was only implemented in June 2021, which is outside the financial year under review. As a result, the backups were not performed for Military Veterans Beneficiaries Database (MVBD) during 2020/21 financial year. The weakness was also reported during 2018/19 and 2019/20 financial years. |  | Management does not accept the finding. The DMV has recently implemented a Backup solution and the IDMS back up is done regularly as part of the file server. (See attached) | Capacity and manual system | 1-4-2021 | 31-3-2022 | M Matsafu | CD Database | 40% - Task partially complete | The ICT Service Continuity Plan was developed and currently on draft.
11. Military Veteran Beneficiaries Database user access and change management controls were not adequately designed and implemented (COMAF 6 | The Military Veterans Beneficiaries Database (MVBD) is based on the Microsoft Access to manage military veterans’ beneficiaries. The MVBD is a shared folder and the user access to the folder is managed by ICT department. |  | The Department of Military Veterans is currently in the process of implementing a solution that will provide more advanced features than the current Access Database. The new solution will provide the capability that will allow the monitoring of all activities by anyone who will have access to the system in a form of logs and robust audit trail to all activities performed in the system. Our manual process has a clear segregation of duties by those who perform activities in the Access database. | Capacity and manual system | 2021-03-03 | 31/03/22 | M Matsafu | CD Database | 100% - Task complete | The firewall process was revised to close the identified gaps to ensure the proper monitoring by the firewall administrators.
12. Number of Military Veterans provided with newly built houses per year (COMAF 32) | During the performance of our audit procedures on the validity of the reported figure for PPI 202: ‘Number of Military Veterans provided with newly built houses per year’ per the annual performance report (APR), we identified that the military veterans listed in the table below, took occupation of the newly built houses during the 2019/20 financial year, however they were incorrectly reported in the 2020/21 financial year |  | Quality assurance and validation should be enhanced to ensure that correct supporting portfolio of evidence is submitted at all times. | The manual system of submitting and verification process of the department is contributing to errors and omissions and the implementation of the Integrated Database Management system will assist in the collection of authentic data, efficient quality assurance verification and overall improvement in information manag | 2021-08-01 | Continuous | L Sothondoshe | Acting CD SESS | 40% - Task partially complete | On-going improvements in the filing system and the capturing of all the applications. Development of an eletronic system to reduce inconcistencies is critical. SITA dependency will inform progress. |  | 1 | #DIV/0! | #DIV/0! | #REF! | #REF! | #DIV/0!
13. Policies have not been approved. (COMAF 12) | During the planning phase we requested updated policies form the department (RFI 10 of 2020/21), and a number of the policies submitted per the register were old policies in effect for periods beyond their review periods. Some of the policies which were provided/submitted by the department were not approved, and only draft versions were submitted, which may as a result not be fully enforceable. The following serves as examples where drafts were submitted: For example- The housing policy , UAM procedures for BAS. |  | Housing policy once finalised will be ratified with internal stakeholders with guidance from the Policy unit | The department was previously not well capacitated to develop policies and this has since been addressed with the appointment of the officials in the policy unit | 2021-08-01 | 2022-03-31 | L Sothondoshe | Acting CD SESS | 20% - Task Started | The Housing policy is in draft and is being discussed in the Housing sub workstream with different external stakeholders to assist the department with finalisation of the policy. |  | 1 | #DIV/0! | #DIV/0! | #REF! | #REF! | #DIV/0!

## ESM
DEPARTMENT OF MILITARY VETERANS- FINAL MANAGEMENT REPORT 2020/21 | [20 empty] | Select Department Name | 2007-04-07
[18 empty] | Yes |  | 1 | The Presidency | 2007-05-07
Audit Findings Action Plan Monitoring Tool - Issues raised by AGSA | [19 empty] | 3 | Foreign Affairs | 2007-07-07
|  |  | BACK TO COMBINED | [15 empty] | 0% - No progress | 4 | Home Affairs | 2007-08-07
40% - Task partially complete
Exception number and audit finding title | Description | Action Plan Description |  | Root Cause | Start Date | Completion Date | Person Responsible | Position | Progress | Narrative | Rank | Count | Factor | Score | Progress | Probability | Weighted Score |  | 60% - Task progressing well | 6 | Public Works | 2007-10-07
[7 empty] | Name | [11 empty] | 80% Task virtually complete | 7 | Government Communication and Information System | 2007-11-07
|  | * Describe activities in point form to address issue (use lower case) |  |  | * Select planned start and completion dates |  | * Select title and enter name (use lower case) | * Select position | *Select progress of activity | *Enter any pertinent comments | 1 | #REF! | #REF! | #REF! |  |  | #REF! |  | 100% - Task complete | 8 | National Treasury | 2007-12-07
1. Possible non-compliance from payments made to officials of the association (COMAF 55) | During the audit of compliance with laws and regulations the following matters were identified in terms of the South African National Military Veterans Association (SANMVA) established in terms of the act for management to consider: 1. It was identified that the Secretary General (SG) of SANMVA was indicated to be part of the staff establishment of the Department of Military Veterans (DMV), however based on subsequent follow-up it was indicated that the SG’s position is an additional post to the DMV’s establishment. |  | Agreed with comments | Delays in the finalisation of SANMVA affairs | 2001-09-21 | 1931-03-22 | D Mathole | Acting CD | 80% Task virtually complete | SANMVA is scheduled to hold its conference to ensure that its outstanding affairs are addressed. A business plan will be presented to the department with a clear description of the association business model as well as its planned activities for the during the term.

## Graph Summary
Implemetation Status
Management Response Actions | FINANCE | CORPORATE SERVICES | SES | ESM | IA & RM | TOTAL | %
Implemented | 21 | 9 | 7 |  |  | 37 | 54.4118
In -progress | 13 | 9 | 6 | 1 | 2 | 31 | 45.5882
Not implemented | [5 empty] | 0 | 0
TOTAL | 34 | 18 | 13 | 1 | 2 | 68 | 100