## Slide 1
Presentation to the Portfolio Committee on Higher Education, Science and Technology
Briefing by the DHET on the Certification Status: NC(V), NATED and GETC:ABET Level 4
18 February 2020

## Slide 2: Presentation Outline
DHET Mandate for examinations
Working Definitions
Examination Cycles and Key Activities
Progress and status of the certification backlog statistics
Key obstacles to eliminating the certification backlogs
Certification backlog Roll out Plan aimed at addressing the obstacles
Update on progress of the new Integrated Exams IT System (IEITS)
Challenges experienced in the development and deployment of the IEITS
Conclusion

## Slide 3: DHET Mandate for Examinations
The DHET mandate emanates from Chapter 6A, Section 41B, Sub-Section (4) (f) and Section 41G Sub-section (1) – (5) of the Continuing Education and Training (CET) Act, (Act No 16 of 2006).
The CET Act of 2006 empowers the Department with the authority to conduct, administer and manage the GETC, NATED Report 190/1 and NC (V) examinations and assessment processes.
DHET serves as the national assessment body for both TVET and CET national qualifications
For TVET sector-
  (NC (V)) Level 2-4 - Annual + Supplementary
  Report 190/1 Engineering Studies N1-N6 - Trimester
  Report 190/1 Business Studies N4-N6 - Semester
  GCC – Labour and Mining X 2
  Business Languages(NSC) x1
For CET-
  GETC-(ABET Level 4) x 2

## Slide 4: Working definitions
Definition
Certification is defined as the process to issue all eligible candidates who met the minimum certification requirements for various qualifications and are certified within three months (business days) after results have been approved by the quality assurers.
Candidates may achieve minimum certification requirements in their first / one exam sitting or over multiple exam sittings. The bulk of the students fall within the first examination. An example of a multiple sitting candidate is where a NATED candidate passes the three (3) subjects in the first trimester (April) examinations and completes the fourth (4th subject in the second trimester (August) examinations.
Certification criteria is as follows:
NC(V) qualification candidates (L2 to L4) have to pass all 7 subjects at the same level. Candidates must pass preceding levels to obtain Level 3 and L4 certificates.
NATED qualification candidates (N1 to N6) have to pass a minimum of 4 subjects at the same level. Candidates must pass the preceding levels from N1 to obtain N2 and N3 certificates.
Similarly, Candidates must pass the preceding levels from N4 to obtain N5 and N6 certificates.
GETC:ABET candidates have to pass a minimum of 5 subject and total of 120 credits.
First Issue Certification backlog / outstanding certificates - Definition
Certification backlog is defined as all eligible candidates who met the minimum certification requirements for various qualifications and were unfortunately not yet issued with certificates within the three months after results have been approved by the quality assurers.

## Slide 5: Examinations Cycles and key activities
The Department runs 12 examinations cycles in an academic year.
Legend
DR-Dry Run
EC-Exam conduct
ER - Exam Result release
C-Certification processes
GL-Go live
* - 2021
Qualification | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |  | Sep | Oct | Nov | Dec | Quality Assuror
GETC/CET Level4 (2 exams per year) |  |  | C | GL*) |  | EC | ER |  |  | C |  | EC & DR | ER | Umalusi
NATED: Engineering Studies N1 to N6 (3 Exams per year) |  |  | C | EC | ER |  | EC | C |  | ER & GL |  | EC & DR | ER & C | DHET delegated by QCTO: N1, N2, N4 to N6 Umalusi: N2 (Resulting only) & N3
NATED: Business Studies N4 to N6 (2 exams per year) |  |  | C |  |  |  | ER | GL |  | C |  | EC & DR | ER | DHET delegated by QCTO
NC(V) (2 exams per year including supplementary) L2 to L4 |  |  | EC& C | ER & GL* |  |  | C |  |  |  |  | EC & DR | ER | Umalusi
NATED: Business Languages N3 (1 exam per year) |  |  | C |  |  |  |  |  |  |  |  | EC & DR | ER | Umalusi
Government Competence Certificates (GCC) [2 exams per year) |  |  | C | GL* |  |  | ER |  |  | C |  | EC & DR | ER | DoL & DME

## Slide 6: Progress and status of the certification backlog statistics
Qualification | Previous Reporting to PCHET in Pretoria (5 February 2020) |  | Current Reporting to PCHET (18 February 2020) | 
 | Date of Report Extract | Backlog Candidate Records and Exam Cycles | Date of Report Extract | Backlog Candidate Records and Exam Cycles
GETC/ABET | 30 Jan 20 | 66 072 (200211 to 201906) | 14 Feb 20 | 65 890 (200211 to 201906)
NATED: Business Studies | 15 Jan 20 | 29 524 (199211 to 201906) | 15 Feb 20 | 29 473 (199211 to 2019060
NATED: Engineering Studies | 15 Jan 20 | 19 780 (199211 to 201904) | 13 Feb 20 | 21 638 (199211 to 201908)
NC (V): First Issue Subject or Full Certificates | 15 Jan 20 | 444 (200711 to 201903) | 12 Feb 20 | 410 (200711 to 201903)
NC (V): Full Certificates Based on report from Umalusi | 17 Dec 19 | 7 878 (200811 to 201903) | 13 Feb 20 | 7 866 (200811 to 201903)
Note: The stats may fluctuate due to the following:
The stats may fluctuate as SITAT is busy refining the scripts and system certification backlog.
Instability of the examination information system to process the eligible candidates for certification
SITA is busy refining the examination information system certification backlog report
The 201908 exam cycles outstanding certificates has been included in the backlog totals as they now meet the certification backlog criteria.
The candidates who had outstanding raw marks as at the last reporting time which have since been summited by the TVET colleges who are now eligible for certification are included in the totals.
The candidates who had irregularities as at the previous report date and have since been cleared by the irregularity committee and now eligible for certification are included in the totals.

## Slide 7: Key obstacles to eliminating the certification backlogs
Part submission of both Internal and External marks by colleges and provinces before resulting for Nated R190/1 ; NC(V) and GETC qualifications
System functionality and alignment across the full system
Understanding of Business Rules for certification by students at all points of data processing

## Slide 8: Certification Backlog Rollout plan
TASK | AFFECTED CANDIDATES (ESTIMATES) | RESPONSIBILITY | TARGET DATES | IMPACT | STATUS
Perform analysis of not approved certification data records and correct any data anomalies on the exam IT system. | TBC | DHET/SITA | February to 31 August 2020 | High | Analysis of the non approved certification data records is ongoing
Manually go through each of the records reported in the SITA outstanding certificates report and query list from Colleges and request a certificate where the certification criterion has been met. | TBC | DHET/TVET colleges | February to 31 August 2020 | Medium | Ongoing
Oversee the management of examination irregularities | TBC | DHET/TVET colleges | Current | High | Ongoing – SITA reports
Oversee the process of capturing of outstanding marks | TBC | TVET Colleges/DHET | Current | Low | Ongoing
Provide guidance on business rules (.i.e. policies) application and processes clarity where required. | 0 | DHET | February to 31 August 2020 | High | TE Memo to colleges and planned road shows to regions

## Slide 9: Certification Backlog Rollout plan
TASK | AFFECTED CANDIDATES (ESTIMATES) | RESPONSIBILITY | TARGET DATES | IMPACT | STATUS
Continue to collect and analyse data from colleges and also use technologies such as e-Query system. | TBC | DHET – Exams | Ongoing | Low | Ongoing
Oversee provision of Portfolio of Evidence whereby TVET college/exam centre/PEDs made changes to candidate raw marks post the resulting or certification processes. | TBC | TVET Colleges and PEDs supported by DHET | 30 May 2020 | High | Ongoing
Desktop verification of certification backlog per public examination centre(campus) | TBC | DHET | March to 31 September 2020 | High | ongoing
Development of new exam IT system in partnership with private IT service provider | 0 | DHET/IT service provider | 31 March 2021 | Medium | Functional, integration and User Acceptance Testing by system user community in process

## Slide 10: New Exam System update
Integrated Examinations Information Technology System (IEITS)
DHET has been working with a private service provider for the development of the new examinations IT solution for the past three years.
Currently, system requirements and specifications for NC(V) L2 and NATED N4-N6 examination processes (i.e. student registrations, capturing of marks, resulting and certification) have been documented and tested with the user community and Umalusi.
The focus is now on the finalisation n/interfaces with key stakeholders such as Umalusi, SAQA, SITA printing bureau, Department of Home Affairs (DHA),Department of Labour (DoL), Department of Minerals and Energy (DMR), Government Printing Works (GPW), TVET Colleges, enhancements, data migration from the legacy system as well as development of training manuals.
The deployment of the new solution is planned to be implemented in a staggered approach per qualification over a four-months’ period to ensure business continuity.

## Slide 11: New IT System update
Integrated Examinations Information Technology System (IEITS)
The deployment of the new solution is planned to be implemented in a staggered approach per qualification over a four-months’ period to ensure business continuity, it is envisaged that the deployment will now commence in August 2020.
The deployment of the solution go-live move from June to August 2020 due to comprehensive quality gates for Functional Acceptance Testing (FAT), User Acceptance Testing (UAT), data migrations and audits on the data take on processes.
It is expected that most qualifications will be executed on the new IT system for the November 2020 exams.

## Slide 12: Challenges in the development of IEITS
Challenge | Risk | Mitigation
Changes in policies – relaxation of HE admission requirements | Strengthening of specifications | Testing of functions with relevant stakeholders Change management strategy and rollout – meeting with change champions – March 2020
Introduction of new qualifications – NASCA & GETCA | Interface of old and new requirements | Testing of functions with relevant stakeholders Change management strategy and rollout – meeting with change champions – March 2020

## Slide 13: Conclusion
The DHET, SITA and UMALUSI certification team, continue to collaborate in an endeavor to improve the system and processes to eliminate the certification backlog in the sector.
The new integrated exam IT system is designed to deal with the certification backlog as most of the business intelligences are embedded in the system. Major gains will be the capacity of the new exams system to combine candidate information across examination cycles, and indicate the outcome to determine whether the candidate qualifies for a certificate or not .

## Slide 14
Thank You