## Slide 1: SITA Commitment to Backlog Day Zero, Backlog Reduction Planning and SITA Role in the New Exam System
18 February 2020

## Slide 2: Content
Objectives
Progress and status of the certification backlog statistics
Approach to get to Backlog Day Zero
Principles / Critical Success Factors
New System Go Live Dates and Backlog Day Zero Target Timeline
Detailed Planning
  General Education and Training Certificate / Adult Education and Training - GETC/AET
  National Accredited Technical Education Diploma - NATED
  National Certificate Vocational - NC(V)
Stakeholder Roles and Responsibilities
Role of SITA in the New Exam System
Programme Governance Structure
Programme Delivery Team Structure
Programme Team Staffing Considerations
Conclusion

## Slide 3: Objectives
Communicate SITA Executive commitment on Backlog Day Zero
Provide an update on the certification backlog statistics
Present a plan of action to reduce the backlog to Backlog Day Zero and the responsibilities of the associated key stakeholders
Communicate the role of SITA in the new exam system

## Slide 4: Progress and status of the certification backlog statistics
Qualification | Previous Reporting to PCHETST (5 February 2020) |  | Current Reporting to PCHETST (18 February 2020) | 
 | Date of Report Extract | Backlog Candidate Records and Exam Cycles | Date of Report Extract | Backlog Candidate Records and Exam Cycles
GETC | 30 Jan 20 | 66 072 (200211 to 201811) | 14 Feb 20 | 65 890 (200211 to 201906)
NATED: Business Studies | 15 Jan 20 | 29 524 (199211 to 201906) | 15 Feb 20 | 29 473 (199211 to 201906)
NATED: Engineering Studies | 15 Jan 20 | 19 780 (199211 to 201904) | 13 Feb 20 | 21 638 (199211 to 201908)
NC (V): First Issue Subject or Full Certificates | 15 Jan 20 | 444 (200711 to 201903) | 12 Feb 20 | 410 (200711 to 201903)
NC (V): Full Certificates Based on report from Umalusi | 17 Dec 19 | 7 878 (200811 to 201903) | 13 Feb 20 | 7 866 (200811 to 201903)
Note: The stats may fluctuate as the scripts and system reports to address the backlog are refined and records are processed.

## Slide 5: Approach to get to Backlog Zero
Phase 1: Resolve Currently Identified Candidate Record Issues (Data Analysis and Alignment)
Phase 2: Deep Data Analysis and Cleansing – for each qualification
Enhance System Functionality (Ongoing)
Result and certify backlog candidate records (Ongoing)
Dedicated Programme Manager and with focused Programme resources that will be crossed utilized and rolled over to work on activities where quicker reduction benefits can be achieved
Other consideration – Source Data Analytics service from industry
Previous Approach | Revised Approach
No dedicated programme manager | Dedicated programme manager reporting directly to Executive: HSO
Team members are dispersed | Team members reporting to programme manager with focus primarily on backlog
Programs written in Natural to extract and analyse data from Adabas. Extracted data also analysed using Excel or SQL (the latter to a lesser extent) – this is time consuming | Data will be ported to from Adabas to MS SQL and primary analysis will be done using SQL. This is where we believe we can fast track the analysis and in turn the reduction
The currently capability is predominantly a legacy type team | Increase currently legacy capability and establish SQL capability
A Different Approach

## Slide 6: Principles / Critical Success Factors
Not everything will be resolved by the system
Records that cannot be resolved by the system must be resolved through business decisions
First prize will be Backlog Day Zero to be achieved before new system is implemented
Dedicated DHET and SITA officials to be allocated to the Backlog Day Zero Programme
Swift dataset turnaround times by all stakeholders and communication / resolving candidate records that have not been approved by Umalusi
Timely business decisions and business rules

## Slide 7: New System Go Live Dates and Backlog Day Zero Target Timeline
Long Term
Medium Term
Short Term
Feb
2020
Mar
2020
Apr
2020
May
2020
Jun
2020
Jul
2020
Aug
2020
Sep
2020
Oct
2020
Nov
2020
Dec
2020
Jan
2021
Feb
2021
Mar
2021
Apr
2021
GETC
Backlog Go-Live
NCV
Backlog Day Zero
NCV
System Go - live
NATED Business Studies
Backlog Day Zero
NATED Business Studies
New System Go - live
NATED Engineering Studies
Backlog Day Zero
NATED Engineering Studies
New System Go - live
Backlog Day Zero planned to be two weeks before go-live of a qualification on the new system
--- Data integrity checks and audit are done as part of migration to the new system, which also serves as quality assurance---
GETC
Backlog Day Zero
NCV
Phase 1 Reduction
NATED Business Studies
Phase 1 Reduction
NATED Engineering Studies
Phase 1 Reduction
GETC
Phase 1 Reduction
NATED Engineering Studies
Significant Reduction*
GETC
Significant Reduction*
NATED Business Studies
Significant Reduction*
NCV
Significant Reduction*
* Significant Reduction target is approximately 80% of currently identified

## Slide 8: Milestone Planning: GETC
GETC
29
Feb
2020
31
Mar
2020
30
Apr
2020
31
May
2020
30
Jun
2020
31
Jul
2020
31
Aug
2020
30
Sep
2020
31
Oct
2020
30
Nov
2020
31
Dec
2020
31
Jan
2021
29
Feb
2021
31
Mar
2021
30
Apr
2021
Short Term
Medium Term
Long Term
Phase 1: Reduce Currently Identified Outstanding
Phase 2: Onboard Team
Phase 2: Deep Data Cleansing
Conduct Resulting and Certification (Ongoing)
Backlog Day Zero
New System Go-Live
Enhance system programs

## Slide 9: Milestone Planning: NATED Business Studies
NATED Business Studies
29
Feb
2020
31
Mar
2020
30
Apr
2020
31
May
2020
30
Jun
2020
31
Jul
2020
31
Aug
2020
30
Sep
2020
31
Oct
2020
30
Nov
2020
31
Dec
2020
31
Jan
2021
29
Feb
2021
31
Mar
2021
30
Apr
2021
Short Term
Medium Term
Long Term
Phase 1: Reduce Currently Identified Outstanding
Phase 2: Onboard Team
Phase 2: Deep Data Cleansing
Conduct Resulting and Certification (Ongoing)
Backlog Day Zero
New System Go-Live
Enhance system programs

## Slide 10: Milestone Planning: NATED Engineering Studies
NATED Engineering Studies
29
Feb
2020
31
Mar
2020
30
Apr
2020
31
May
2020
30
Jun
2020
31
Jul
2020
31
Aug
2020
30
Sep
2020
31
Oct
2020
30
Nov
2020
31
Dec
2020
31
Jan
2021
29
Feb
2021
31
Mar
2021
30
Apr
2021
Short Term
Medium Term
Long Term
Phase 1: Reduce Currently Identified Outstanding
Phase 2: Onboard Team
Phase 2: Deep Data Cleansing
Conduct Resulting and Certification (Ongoing)
Backlog Day Zero
New System Go-Live
Enhance system programs

## Slide 11: Milestone Planning: NC (V)
NC(V)
29
Feb
2020
31
Mar
2020
30
Apr
2020
31
May
2020
30
Jun
2020
31
Jul
2020
31
Aug
2020
30
Sep
2020
31
Oct
2020
30
Nov
2020
31
Dec
2020
31
Jan
2021
29
Feb
2021
31
Mar
2021
30
Apr
2021
Phase 1: Reduce Currently Identified Outstanding
Phase 2: Onboard Team
Phase 2: Deep Data Cleansing
Conduct Resulting and Certification (Ongoing)
Backlog Day Zero
New System Go-Live
Enhance system programs
Short Term
Medium Term
Long Term

## Slide 12: Stakeholder Roles and Responsibilities
DHET | SITA | Umalusi
Provide business rules Make business decisions Capture outstanding marks (raw marks) Provide Portfolio of Evidence for raw mark changes Address outstanding Irregularities Execute system functionality for resulting and certification Submit datasets to Umalusi for all qualifications Analyse and resolve candidate records not approved by Umalusi (Proposal 5 day turnaround) Quality assure candidate records: NATED Resulting N1, N4 to N6 NATED Certification N1, N2, N4 to N6 Develop and execute communication strategy | Provide system functionality to meet business requirements Align data (excluding raw marks) Support DHET to execute system functionality for resulting and certification Submit datasets to Umalusi Analyse and resolve candidate records not approved by Umalusi (Proposal 5 day turnaround) Develop / update and execute programs for reporting and resolution purposes | Quality assure candidate records: GETC Resulting and Certification L4 NC (V) Resulting and Certification L2 to L4 NATED Resulting N2&N3 and Certification N3 Approve / not approve and provide return datasets - including reasons for non-approval where required (Proposal 5 day turnaround time)

## Slide 13: Role of SITA in the New Exam System
Services to be rendered:
  Providing advice and information related to the current exam system to the DHET Service Provider
  Extracting data from the current exam systems and make it available to the DHET Service Provider to port it to the new exam system
  Hosting new exam system on the SITA cloud infrastructure
  Change management and training services
Services not rendered (may be rendered after end of DHET service provider contract)
  System maintenance and enhancement services
  Functional application support services

## Slide 14: Programme Governance Structures
Structure | Core Constituents | Responsibility | Meeting & Reporting Frequency
Portfolio Committee | PCHETST (Lead) DHET SITA Umalusi | Oversight | Meeting – as required Reporting – monthly
Programme Steering Committee | DHET: DG (Lead) DHET SITA Umalusi | Policy Direction Setting & Monitoring | Meeting – fortnightly Reporting – monthly
Program Management | SITA: HSO: Executive (Lead) SITA Programme Manager Technical Leads | Managing programme Monitor progress | Meeting – weekly Reporting – weekly
Programme Delivery | SITA Programme Manager (Lead) Technical Leads Programme Team | Execute program | Meeting – daily

## Slide 15: Programme Delivery Team Structure
1 x Data Quality
1 x Data Quality Lead
SITA Executive
1 x Programme Manager
1 x Technical Lead
1 x Functional Application Support Lead
1 x DBA Lead (Natural and SQL)
1 x Senior Software Developer
1 x Software Developer
1 x Consultant FAS
1 x Specialist FAS
1 x Senior DBA SQL
1 x Senior Software Developer
1 x Software Developer
1 x Consultant FAS
1 x Specialist FAS
1 x Senior DBA SQL
1 x Senior Software Developer
1 x Software Developer
1 x Consultant FAS
1 x Specialist FAS
1 x Senior DBA SQL
1 x Senior Software Developer
1 x Software Developer
1 x Consultant FAS
1 x Specialist FAS
1 x Senior DBA SQL
1 x Super User Lead
1 x Super User
1 X Super User
1 x Super User
1 x Super User
GETC
NATED
Business
Studies
NATED
Engineering
Studies
NC(V)
Natural
Natural & SQL













= Currently Allocated
1 x Advisor




## Slide 16: Programme Team Staffing Considerations
SITA Internal
  Allocations/ secondments will be done with immediate effect
  The current allocations for the Technical lead, Software Developers, DBA lead, Specialist FAS resources and Data Quality lead are all resources operating within the current legacy environment
DHET
  DHET has agreed to allocations/secondments. There is one resource available for immediate allocation and the DHET qualification leads will be made available at programme set time frames.
External
  Referrals / Headhunting skilled / qualified resources / staff
  Recruitment from Industry

## Slide 17: Conclusion
DHET: Director General and SITA Executive Caretaker and Accounting Authority to direct the Backlog Day Zero Programme
DHET TVET Branch Head and SITA Executive: Hosting and Secure Operations to drive Backlog Day Zero Programme

## Slide 18: Thank You Questions

## Slide 19: GETC Outstanding Breakdown, Problem Areas and Key Actions
GETC |  |  | 
Initial Problem Area Identified | Key Actions | Responsibility | Potentially Outstanding
Certification request created and extract. To be processed. | Follow up on unprocessed datasets | DHET and SITA | 17 797
Certification request created and extract. To be processed. | Follow up on unprocessed datasets | DHET and SITA | 5 896
Outstanding irregularities that must be finalised | Finalise irregularities | DHET and SITA | 1 204
Candidate records are not being successfully processed due to e.g. data alignment and candiates not yet linked | Conduct root cause analysis and determine course of action with responsibilities | DHET and SITA | 33 297
Marks not yet captured | Convert outstanding marks from 200211 to 201806 to absent and process. DHET to capture marks for 201811 onwards | DHET and SITA | 7 696
Potentially Outstanding |  |  | 65 890

## Slide 20: NATED Business Studies Outstanding Breakdown, Problem Areas and Key Actions
Business Studies |  |  | 
Initial Problem Area Identified | Key Actions | Responsibility | Potentially Outstanding
Record consolidated to a next exam cycle where candidate offered subjects but previous year (s) offerings not yet certified | Unconsolidated, certify in year, consolidate and certify consolidated | DHET & SITA | 13 355
Certificate issued to candidate and subsequently cancelled. | DHET to confirm the reason for action and whether certificate should be resissued or replaced | DHET & SITA | 1 186
Candidate records are not being successfully processed due to e.g. data alignment | Conduct root cause analysis and determine course of action with responsibilities | SITA | 13 448
Candidate record incorrectly consolidated to next exam cycle though the candidate did not offer any subjects or had an improvement in the next exam cycle | Unconsolidate and certify in year | DHET & SITA | 1 325
Candidate record is consolidated to the current year, which is not yet certified | Unconsolidated, certify the current year, consolidate and certify | DHET & SITA | 159
Potentially Outstanding |  |  | 29 473

## Slide 21: NATED Engineering Studies Outstanding Breakdown, Problem Areas and Key Actions
Engineering Studies |  |  | 
Initial Problem Area Identified | Key Actions | Responsibility | Potentially Outstanding
Record consolidated to a next exam cycle where candidate offered subjects but previous year (s) offerings not yet certified | Unconsolidated, certify in year, consolidate and certify consolidated | DHET & SITA | 6 122
Candidate record is ready to be certified | Extract and certify | DHET & SITA | 2
Certificate issued to candidate and subsequently cancelled. | DHET to confirm the reason for action and whether certificate should be resissued or replaced | DHET & SITA | 734
Candidate records are not being successfully processed due to e.g. data alignment | Conduct root cause analysis | SITA | 8 310
Candidate record incorrectly consolidated to next exam cycle though the candidate did not offer any subjects or had an improvement in the next exam cycle | Unconsolidated and certify in year | DHET & SITA | 3 029
Candidate record cannot be consolidated due to previous year not yet certified | Certify previous exam, consolidate to next exam and certify | DHET & SITA | 3 208
Candidate record is consolidated to the current year, which is not yet certified | Unconsolidated, certify the current year, consolidate and certify | DHET & SITA | 233
Potentially Outstanding |  |  | 21 638

## Slide 22: NC(V) First Issues Outstanding Breakdown, Problem Areas and Key Actions
NCV (First Issues) |  |  | 
Initial Problem Area Identified | Key Actions | Responsibility | Potentially Outstanding
Main and supplementary exam not consolidated due to outstanding marks | Capture outstanding mark and consolidate | DHET and SITA | 31
Previous exam not certified | Unconsolidated, consolidate and certify | DHET and SITA | 5
Candidate record incorrectly consolidated to a year where subjects were not offered or no improvement achieved | Unconsolidated and certify | DHET and SITA | 1
Further analysis required | Conduct root cause analysis and determine course of action with responsibilities | DHET and SITA | 373
Potentially Outstanding |  |  | 410

## Slide 23: NC(V) Full Issues Outstanding Breakdown, Problem Areas and Key Actions
NC(V) Full Certificates |  |  | 
Initial Problem Area Identified | Key Actions | Responsibility | Potentially Outstanding
First issue was cancelled after being issued and not re-issued | Investigate reasons for cancellation and whether certificate must be issued gain. | DHET | 283
Pass indicator on master file not aligned | Align pass indicator | SITA | 2 405
Full certificate created but not yet extracted | Extract certificate and submit to Umalusi for processing | DHET and SITA | 28
Full certificate created extracted but not yet processed | Process certificate | DHET and SITA | 898
Candidate does not meet certification requirements according to master record | Confirm candidate academic history versus certification record | SITA | 1 586
Candidate record consolidated but not yet certified | Conduct root cause analysis and determine course of action with responsibilities | DHET and SITA | 131
Further analysis required | Conduct root cause analysis and determine course of action with responsibilities | DHET and SITA | 2 280
Subject total on document and master misaligned | Align master and document totals | SITA | 255
Potentially Outstanding |  |  | 7 866