## Slide 1: PRESENTATION TO THE PORTFOLIO COMMITTEE DCDT PERFORMANCE FOR QUARTER 1 OF THE 2020/21 FINANCIAL YEAR 18 AUGUST 2020

## Slide 2
PRESENTATION OVERVIEW
DCDT Vision, Mission & Mandate
2020/21 Quarter 1 Programme Performance
2020/21 Quarter 1 Financial Performance
Progress against the Audit Action Plan

## Slide 3
DCDT VISION, MISSION & MANDATE
VISION:
A leader in enabling a connected and digitally transformed South Africa
MISSION:
Leading SA’s inclusive digital transformation journey through creating an enabling environment towards a digital society to foster socio-economic growth
MANDATE:
To lead South Africa’s digital transformation to achieve digital inclusion that must result in economic growth through creating an enabling policy and regulatory environment

## Slide 5
SIGNIFICANT ACHIEVEMENTS AGAINST
PLANNED QUARTER 1 TARGETS (1)
Workplace Skills Plan (WSP)
  Workplace Skills Plan (WSP) developed, approved and submitted to PSETA and MICT SETA
Country Positions to support the Digital Economy
  Draft RSA position developed for World Telecommunications Standardization (WTSA) Assembly and the BRICS ICT Ministerial Meeting
Digital Economy Masterplan
  Draft Digital Economy Masterplan developed
ICT SMME Strategy
  Concept document on the market access for local IP & innovation by SMMEs developed
Feasibility study for Phase 2 funding conducted
  Appointment and contracting of a service provider has been concluded as planned
Establishment of Cybersecurity Incident Response Team (CSIRT)
  Consultations has commenced with key stakeholders (MTN, Vodacom, Telkom, Cell C and Liquid Telecoms)

## Slide 6
SIGNIFICANT ACHIEVEMENTS AGAINST
PLANNED QUARTER 1 TARGETS (2)
National e-Government Strategy and Roadmap
  Engagements held with SITA & DPSA to align the implementation of the e-Govt roadmap.
  The Department drafted the e-Services portal concept document as well as Governance structure for the monitoring and reporting of uploading e-Services on National e-Services Portal.
Digital and Future Skills
  A draft Digital and Future Skills Implementation Programme has been developed and consulted with relevant stakeholders
Integrated Digital Economy and Society Indicator Model
  A Framework for the Integrated Digital Economy and Society Indicator Model was developed

## Slide 7
AREAS OF UNDER-ACHIEVEMENT
AGAINST QUARTER 1 TARGETS (1)
The Department did Not Achieve 17 of its 31 planned quarterly targets as reflected below. Details on the challenges experienced are presented in the tables on the subsequent slides:
Organisational structure
  The Department was unable to develop the Service Delivery Model as planned
Integrated DCDT Digitisation Strategy
  The Business needs analysis and development of the business architecture were not concluded
Country Position for UPU
  RSA Position for PAPU-20 was not developed, approved and advanced as planned
South African Broadcasting Corporation SOC Ltd Bill
  Public consultation was not conducted on the Bill as planned
Data & Cloud Policy
  Draft Data & Cloud Policy was not submitted to Cabinet for public consultations approval
Implementation of PC4IR Report
  The 4IR PMO was not fully capacitated to facilitate implementation of PC4IR Report
SOE Oversight
  Fourth Quarterly analysis reports of entities for 2019/20 was developed, however, approval and submission to Minister could not be confirmed with prescribed evidence
Performance Management System for ICASA Councillors
  The signing of the Performance Agreements between the Minister and Councillors was not concluded as planned

## Slide 8
QUARTER 1
AREAS OF UNDER-ACHIEVEMENT (2)
SABC’s implementation of the Turnaround Plan
  Analysis of the Quarterly Report on SABC’s implementation of the Turnaround Plan was not conducted
Postbank Bill
  Public consultation did not take place as planned
State ICT Infrastructure Company Bill
  Business Case for the State ICT Infrastructure Company was not finalized and submitted for approval
State IT Company Bill submitted to Parliament
  Business Case for the State IT Company was not finalized and submitted for approval
National Radio Frequency Plan
  WRC-19 Outcomes report, impacting South Africa, was developed, however, was not issued to ICASA
Provision of broadband services to 970 connected sites, monitored and sustained
724 of the planned 850 connected sites were monitored
Digital Transformation Centre (DTC)
DTC Agreement was developed, however, it was not finalized and signed by relevant stakeholders
Policy Direction on 5G Spectrum
Detailed analysis of the ICASA 5G study report was not concluded

## Slide 9
ADMINISTRATION
PROGRAMME PURPOSE: Provide strategic leadership, management and support services to the department. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
Organisational structure, aligned to strategy, revised and approved for implementation | Draft Service Delivery Model developed | A memo requesting the Minister to approve the review of the Organisational Structure was submitted | Not achieved | As per direction from Minister, a consolidated approach with other Departments affected in the NMOG process is to be explored. Furthermore, the Department is engaging DPSA on the provision of technical support in this regard.
Workplace Skills Plan (WSP), aligned to DCDT mandate, developed and implemented | Workplace Skills Plan (WSP), aligned to DCDT mandate, developed and approved | Workplace Skills Plan (WSP) for PSETA and MICT SETA developed, approved and signed off by the DG. | Achieved | N/A
Integrated DCDT Digitisation Strategy developed and implementation of priority interventions monitored | Business needs analysis of the new Department conducted focusing on prioritized interventions | No Achievements | Not achieved | Branch workshops to determine business needs analysis were delayed due to the lockdown. Branch workshops have commenced in quarter 2, through MS Teams.
Integrated DCDT Digitisation Strategy developed and implementation of priority interventions monitored | Business architecture report developed | No Achievements | Not achieved | Branch workshops to determine business needs analysis were delayed due to the lockdown. Business architecture will be informed by the business needs analysis which is underway

## Slide 10
PROGRAMME PURPOSE: Ensure alignment between South Africa’s foreign policy and international activities in the field of ICT. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
3 Country Positions developed to support the Digital Economy focused on BRICS, UPU and WTSA | Draft RSA Position for World Telecommunications Standardization (WTSA) Assembly developed | Draft position prepared and key issues identified for engagement | Achieved | N/A
 | Draft RSA Position for BRICS ICT Ministerial Meeting developed | Draft Position developed and circulated for inputs/consultations internally. | Achieved | N/A
 | RSA Position for PAPU-20 developed, approved and advanced | Position developed through engagement with stakeholders. | Partially Achieved | PAPU Plenipotentiary Conference which was scheduled for June 2020 has been postponed due to COVID-19 and the lockdown. The position paper will be advanced when PAPU Plenipotentiary conference is convened
ICT INTERNATIONAL RELATIONS & AFFAIRS (1)

## Slide 11
PROGRAMME PURPOSE: Ensure alignment between South Africa’s foreign policy and international activities in the field of ICT. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
BRICS Institute for Future Networks establishment coordinated | Drafting of a designation of the BRICS Institute for Future Networks facilitate | Legal instrument drafted. Inputs received from MERAKA (CSIR). | Achieved | N/A
2 Partnership agreements, focusing on the Digital Economy, signed, and implementation monitored | Relevant Partners identified | The relevant Partners have been identified. |  | 
 |  |  | Achieved | N/A
ICT INTERNATIONAL RELATIONS & AFFAIRS (2)

## Slide 12
ICT POLICY DEVELOPMENT AND RESEARCH (1)
PROGRAMME PURPOSE: Develop ICT policies and legislation that support the development of an ICT sector that creates favourable conditions for accelerated and shared economic growth. Develop strategies that increase the adoption and use of ICT by the majority of South Africans to bridge the digital divide. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
South African Broadcasting Corporation SOC Ltd Bill submitted to Cabinet for approval to introduce to Parliament | Public consultation conducted on draft South African Broadcasting Corporation SOC Ltd Bill | None | Not Achieved | The Bill was not submitted to Cabinet for public consultation approval, due to COVID-19 related priorities – which impacted on the public consultation.
Data & Cloud Policy submitted to Cabinet for approval | Draft Data & Cloud Policy submitted to Cabinet for public consultations approval | Policy amended with inputs from key stakeholder departments. Draft SEIAS submitted to DPME and feedback received for further amendments. | Not Achieved | Key stakeholders did not timeously respond due to COVID-19 lockdown which affected accessibility DPME also took longer than expected to provided feedback to DCDT on the SEIAS Cluster and Cabinet submission is being expedited in Q2
Digital Economy Masterplan developed, and implementation facilitated | Draft Digital Economy Masterplan developed | Draft Digital Economy Masterplan developed | Achieved | N/A

## Slide 13
ICT POLICY DEVELOPMENT AND RESEARCH (2)
Programme Purpose: Develop ICT policies and legislation that support the development of an ICT sector that creates favourable conditions for accelerated and shared economic growth. Develop strategies that increase the adoption and use of ICT by the majority of South Africans to bridge the digital divide. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
Digital Economy Masterplan developed, and implementation facilitated | Draft Digital Economy Masterplan developed | Draft Digital Economy Masterplan developed | Achieved | N/A
Implementation of PC4IR Report facilitated and monitored | 4IR PMO capacitated to facilitate implementation of PC4IR Report | 4IR PMO capacitated; 6 positions filled. | Partially Achieved | Couldn’t fill in the remaining 4 positions due to lack of suitable candidates The 4 remaining positions have been re-advertised to widen the search
ICT SMME Strategy revised, and its implementation facilitated | Concept document on the market access for local IP & innovation by SMMEs developed | Concept document on the market access for local IP & innovation by SMMEs developed | Achieved | N/A

## Slide 14
ICT ENTERPRISE AND PUBLIC ENTITY OVERSIGHT (1)
PROGRAMME PURPOSE: Oversee and manage government’s shareholding interest in the ICT public entities and state-owned companies. Facilitate the growth and development of small, medium and micro enterprises in the ICT sector. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
Service Delivery performance and compliance of SOEs against strategic plans and relevant prescripts monitored | Fourth Quarterly analysis reports of entities for 2019/20 developed and submitted | Quarter 4 analysis reports of entities for 2019/20 developed and submitted | Not Achieved | Evidence submitted did not meet the requirements stipulated in the Proposed Portfolio Of Evidence (POEs) for the Quarter One Target to Qualify as Fully Achieved
Implementation of the Performance Management System for ICASA Councillors facilitated | Signing of Performance Agreements between the Minister and Councillors, facilitated | None | Not Achieved | The programme of the Portfolio Committee, which is required to approve the Performance Management System of ICASA, was disrupted due to the COVID-19 outbreak. The Agreements could not be signed in the absence of the approved Performance Management System, hence such approval will be prioritised.
Quarterly analysis report on SABC’s implementation of the Turnaround Plan, developed | Quarterly analysis report on SABC’s implementation of the Turnaround Plan developed | The Monitoring Task Team of SABC commenced in the first quarter of 2020/21 financial year. | Not Achieved | The Monitoring Task Team of SABC commenced in the first quarter of 2020/21 financial year. The first quarterly analysis report will only be submitted in the second quarter

## Slide 15
ICT ENTERPRISE AND PUBLIC ENTITY OVERSIGHT (2)
PROGRAMME PURPOSE: Oversee and manage government’s shareholding interest in the ICT public entities and state-owned companies. Facilitate the growth and development of small, medium and micro enterprises in the ICT sector. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
Postbank Bill submitted to Parliament | Public Consultation conducted on the Postbank Bill | Public consultation did not take place as planned; however, the Postbank Bill was submitted to Cluster. | Not Achieved | Due to COVID-19 lockdown, Cluster Meetings did not take place as planned which delayed the submission of the Bill to Cabinet for public consultation approval. Cabinet approval for public consultation will be expedited in Q2
State ICT Infrastructure Company Bill submitted to Parliament | Business Case for the State ICT Infrastructure Company Bill submitted for approval | Draft Business Case developed but to be finalised in order to comply with the guidelines from DPSA and Treasury | Not Achieved | Due to delays in finalising the Business Case, the Department has solicited the services of GTAC to help with the review and finalisation of the Business Case, which should be completed by end of Q2
State IT Company Bill submitted to Parliament | Business Case for the State IT Company Bill submitted for approval | Draft Business Case developed but to be finalised in order to comply with the guidelines from DPSA and Treasury | Not Achieved | Due to delays in finalising the Business Case, the Department has solicited the services of GTAC to help with the review and finalisation of the Business Case, which should be completed by end of Q2

## Slide 16
ICT INFRASTRUCTURE SUPPORT (1)
PROGRAMME PURPOSE: Promote investment in robust, reliable, secure and affordable ICT infrastructure that supports the provision of a multiplicity of applications and services. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
National Radio Frequency Plan revised in line with WRC-19 Outcomes | WRC-19 Outcomes report, impacting South Africa, developed and issued to ICASA | WRC-19 outcomes impacting South Africa have been developed. Submitted to Minister for approval & submission to ICASA for update of the NRFP. | Not Achieved | Covid-19 lockdown restrictions delayed the submission of the memo to Minister regarding the issuing the Outcomes Report to ICASA. Memo had to be re-submitted digitally
Provision of broadband services to 970 connected sites, monitored and sustained | Q4 (2019/20) monitoring report developed on the provision of broadband services to 850 connected sites | 724 connected sites were monitored. Of the outstanding sites 179 had infrastructure completed during Q4 (2019/20). | Partially Achieved | All planned sites not connected due to: Unreliable power supply at some of the sites. Technical challenges (network configurations). COVID-19 lockdown restrictions. All planned sites should be connected by end of Q2
Feasibility study for Phase 2 funding conducted | Appointment and contracting of a service provider | The service provider has been appointed. | Achieved | N/A

## Slide 17
ICT INFRASTRUCTURE SUPPORT (2)
PROGRAMME PURPOSE: Promote investment in robust, reliable, secure and affordable ICT infrastructure that supports the provision of a multiplicity of applications and services. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
Digital Transformation Centre established and operationalised | DTC Agreement finalized and signed by relevant stakeholders | Host country agreement has been signed. Cabinet memo is in the process of being finalised. Agreement for the physical hosting of the DTC is being concluded. | Not Achieved | Department had to factor in Cabinet approval which was not initially planned for. This impacted on the finalisation and signing of the Agreement. The Agreement will be signed by relevant stakeholders post Cabinet approval.
1 additional CSIRT established | Consultations conducted with identified industry sector stakeholders | Engagements have taken place with the mobile operators in respect of the establishment of a sector CSIRT. Operators currently involved are MTN, Vodacom, Telkom, Cell C and Liquid Telecoms. | Achieved | N/A
Draft Policy Direction on 5G Spectrum developed | Analysis of preliminary findings and recommendations conducted | High-level Analysis of the ICASA 5G study report was done. High-level briefing done to Minister. Letter to ICASA sent on status of analysis of report. | Partially Achieved | Detailed analysis to be expedited in Quarter 2.

## Slide 18
ICT INFORMATION SOCIETY AND CAPACITY DEVELOPMENT (1)
PROGRAMME PURPOSE: Develop and implement strategies to build capabilities to bridge the digital divide. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
National e-Government Strategy and Roadmap implemented, monitored and reported, towards digitalisation of government services | Monitoring and Reporting Mechanism on the Uploading of e-Services on National e-Services Portal, in collaboration with SITA, developed | Engagements held with SITA & DPSA to align the implementation of e-Govt roadmap in which e-Services portal is one of the deliverables. DCDT drafted the e-Services portal concept document as well as Governance structure for the implementation and monitoring and reporting of uploading of e-Services on National e-Services Portal. | Achieved. | N/A
Implementation of the Digital and Future Skills Programme, in line with National Digital and Future Skills Strategy, facilitated and monitored | Draft Digital and Future Skills Programme developed | Draft Digital and Future Skills Implementation Programme plan, to be consulted with stakeholders developed. | Achieved | N/A

## Slide 19
ICT INFORMATION SOCIETY AND CAPACITY DEVELOPMENT (2)
PROGRAMME PURPOSE: Develop and implement strategies to build capabilities to bridge the digital divide. |  |  |  | 
Annual Target | Quarterly Target | Actual Performance | Status | Explanation of Variance
Training Programme on AI related skills, focusing on the youth, developed and implemented | Training assessment workshop conducted with relevant stakeholders | A two-day webcast training assessment work was conducted on 22-23 June 2020 with relevant stakeholders. | Achieved | N/A
Blueprint for Digital Technology diffusion developed | Letter of Intent with Smart City Alliance in collaboration with GIZ as a stakeholder signed | The letters related to Smart City Alliance were signed by relevant stakeholders | Achieved | N/A
Integrated Digital Economy and Society Indicator Model developed | Framework for the Integrated Digital Economy and Society Indicator Model developed | Framework for the Integrated Digital Economy and Society Indicator Model developed | Achieved | N/A

## Slide 20
REVISION OF THE
2020/21 ANNUAL PERFORMANCE PLAN
2020/21 APP has been revised taking into consideration:
  Budget cuts (R111 million) incurred by the Department
  COVID-19 – as the 2020/21 APP was developed without taking into consideration the impact of COVID-19
Consideration was also given to the Department’s Contribution to the Economic Recovery Plan as well as implementation of the PC4IR Report recommendations
Majority of the Annual Targets have not been impacted as the Department is able to catch up the delays experience in Quarter 1.
The revised 2020/21 APP will be tabled before the end of August and subsequently presented to the Portfolio Committee.

## Slide 21
FINANCIAL INFORMATION
AS AT 30 JUNE 2020

## Slide 22
Adjusted appropriation budget of R3,2 billion after the special adjustment budget process.
Adjustment budget cuts in Goods & Services (R33 million) and BDM Project (R78 million).
APPROPRIATION BUDGET

## Slide 23
EXPENDITURE
Expenditure at 20,8% mainly consists of salaries, monthly commitments and transfers to the entities as spending on other items was affected by the level 5 lockdown. Payments for the previous financial year commitments on capital assets that could not be delivered by financial year-end.

## Slide 24
Transfers made in line with the pre-approved schedule with National Treasury.
International membership fees expenditure exceeded the budget due to the unforeseen significant depreciation of the rand against foreign currencies.
TRANSFERS

## Slide 25
PROGRESS AGAINST THE
AUDIT ACTION PLAN
2019/20 FINANCIAL YEAR
The audit findings from both former DoC and DTPS have been consolidated in the table above. The common findings related to matters on BBBEE verification, commitments & accruals and related parties. Those matters related to the AFS have been resolved.

## Slide 26
THANK YOU