## Slide 1
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
SIU Presentation
Emergency Procurement and
Implementation of the
40km Borderline Infrastructure Project
between the
Republic of South Africa and Zimbabwe
25/08/2020

## Slide 2: Slides Index
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
  Background
  Scope of the investigation
  General finding of the investigation
  Recommendations
  Conclusion

## Slide 3: BACKGROUND
On Monday the 16th of March 2020 Minister issued a directive to the Director-General (DG) of the Department, directing him to appoint a service provider using emergency procurement processes in relation to the erection and repair of the borderline fence at the Beitbridge Border Post.
The Directive from the Minister referred to Section 27 (2) of the Disaster Management Act of 2002. According to the minister, the purpose of issuing the directive was to secure the border in order to prevent the spread of COVID 19.
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za

## Slide 4: BACKGROUND
On the 25th of April 2020, the Minister requested the Department’s Anti-Corruption Unit to conduct the investigation in the procurement process followed in the erection of the fence.
DPW approached SIU for assistance and members of SIU were seconded to DPW.
The investigation commenced on the 28th of April 2020 after concluding the secondment agreement between SIU and the Department.
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za

## Slide 5
SCOPE OF THE INVESTIGATION

## Slide 6: SCOPE OF THE INVESTIGATION
Determine whether DPWI followed a fair and transparent SCM process as prescribed by Section 217 of the Constitution during the appointment of the contractor and consultant.
Determine whether any feasibility study was conducted for the service of erecting a 40km fence.
Determine whether there was value for money.
Determine whether the work performed were in line with what the client department (SANDF) requested.
Determine any acts of criminality.
Determine if the SIU should consider motivating for a proclamation.
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za

## Slide 7
GENERAL FINDINGS OF THE INVESTIGATION

## Slide 8: GENERAL FINDINGS OF THE INVESTIGATION
The investigation revealed procurement irregularities perpetrated during the infrastructure delivery process, as well as possible acts of fraud. The irregularities identified include:
Irregular application of emergency procurement.
Irregular appointment of the Contractor and the Principal Agent (PA).
The effecting of an advance payment of R21, 8 million to the Contractor and R1.8million to the Principal Agent within days of their respective appointments, was irregular as no material was delivered and construction had not commenced.
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za

## Slide 9: GENERAL FINDINGS OF THE INVESTIGATION
The Department failed to test the market in this regard to at least determine the reasonableness of the Contractor’s pricing. The procurement framework of bid specification, evaluation and adjudication was not properly followed.
National Bid Adjudication Committees’ (NBAC) who adjudicated on the appointment of the PA and Contractor, failed to ensure that proper SCM processes were followed.
The appointment of the Contractor was predetermined.
The above-mentioned process failed to achieve the objectives of a competitive, transparent, reasonable and fair procurement process, making it irregular in terms of Section 217 of the Constitution as well as Treasury and departmental regulations in this regard.
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za

## Slide 10: GENERAL FINDINGS OF THE INVESTIGATION
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
An assessment conducted by the Professional Review Team, of the items in the Bill of Quantities (BOQ), Drawings, and Specifications and the work ‘as built’ indicated that they were not aligned. The assessment also found that the fence is not in compliance with the Drawings and the Specifications.
The Value for Money Assessment conducted by the PICC technical task team indicated significant anomalies. The total project cost, which includes both construction and engineering fees, for the Contract was R40.4million.

## Slide 11: GENERAL FINDINGS OF THE INVESTIGATION
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
Although the contracted amount was ostensibly calculated at 2016 prices based on an earlier contract, the evaluation indicated that some of the items quoted were in fact not based on these 2016 prices. This includes site establishment costs exceeding R1 million, which should not have been charged, and excessive units rates for specific items. Using the 2016 Contract rates – at which this project was contracted, the assessment found that the overall total project cost should have amounted to R26.1 million was therefore overpriced by R14.3million.

## Slide 12: GENERAL FINDINGS OF THE INVESTIGATION
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
An assessment using market related prices for materials actually used on site and revised fees for engineering services provides for a total project cost of R23 388 023.97. This indicates that project cost was exceeded by an amount of R17 047 891.01.
No proper review of the BOQ’s was conducted by the DPWI, and this consequently resulted in the contract price being inflated. This also reflects the real risk to the DPWI of having failed to test the market. The 2020 market comparison also indicates that the 2016 rates were inflated at the time.

## Slide 13: GENERAL FINDINGS OF THE INVESTIGATION
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
Poor construction practices compromised the effectiveness of the fence as a deterrent for crossing the South African border with Zimbabwe. The barbed wire coils were stretched beyond its recommended effective limit, also making it easier to scale the fence. These factors undermined the effectiveness of the fence to mitigate border threats.
The significant elements of the Border Fence Project were not implemented at all. For example, the design of the fence had a final height of 2.2m and the final actual height of the fence reached no more than 1.8m on either side of the border and making it more easily scalable.

## Slide 14: GENERAL FINDINGS OF THE INVESTIGATION
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
During the SIU site visit on the 4th and the 5th of May 2020, we recorded at least 115 breaches of the fence which may have resulted in an untold number of unlawful crossings between South Africa and Zimbabwe.
The construction of the fence is also in material breach of the conditions of the Provisional Site Clearance Certificate (PSCC) including breaches of Environmental Regulations, as well deviations from the approved line of construction.
Given the non-compliance with aspects of the design specification and poor construction practices, the fence is not fit for purpose and current payments in this regard may already be regarded as Fruitless and Wasteful Expenditure.

## Slide 15
RECOMMENDATIONS

## Slide 16: RECOMMENDATIONS
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
Disciplinary charges have been recommended against fourteen (14) senior officials of the DPWI as a result of a range of alleged acts of misconduct perpetrated mainly during the procurement and construction phases of the Beitbridge Border Fence Project.
It is recommended that the department should register a criminal case of fraud against the Principal Agent, Main Contractor and designated officials for misrepresenting to the DPWI that project progress was achieved in order to justify a progress payment, when this was not the case, and for financial misconduct where appropriate.

## Slide 17: RECOMMENDATIONS
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
The Principal Agent and the Main contractor must be restricted from doing business with government subject to the application of the relevant due process.
It is recommended that the DPWI should report these material non-compliance with Environmental laws and to consult with the Department of Environment, Forestry and Fisheries (“DEFF”) so as to correct non-compliance in this regard.

## Slide 18: RECOMMENDATIONS
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
The Principal Agent failed to act in the interests of the Department and accordingly breached their fiduciary duties towards the DPWI. It is therefore recommended that their conduct accordingly be referred to the Council for the Built Environment (CBE) and the Engineering Council of South Africa (ECSA) for further investigation.
DPWI must ensure that appropriate training is conducted and awareness is created that the systems of Governance that regulates the activities of the Department has not been suspended as a result of Covid-19 related emergencies.

## Slide 19: RECOMMENDATIONS
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
Supply Chain Management should use the appointed Service Provider to conduct Due Diligence on Tender Processes.
Any further border fence initiatives should be located in the context of this programme in terms of an Integrated National Strategy, Best Practice and Border Management Master Plan, duly aligned to and noting the recently signed the Border Management Authority Act of 2020.

## Slide 20: CONCLUSION
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
DPW is implementing the recommendations from the report.
SIU will be approaching the Special Tribunal in order to cancel the contract and to recover the losses suffered by the state.

## Slide 21
Hotline: 0800 037 774 | Website: https://www.siu.org.za | E-mail: info@siu.org.za
THANK YOU
PRESENTED BY ADV. JL MOTHIBI
Hotline: 0800 037 774
Website: https://www.siu.org.za
E-mail: info@siu.org.za
Follow Us
@RSASIU