## Slide 1: Integrated progress report on the national rollout of the Sanitary Dignity Programme in Quintiles 1 – 3 Schools

## Slide 2: Enabling Environment
The Sanitary Dignity Implementation Framework is the main policy driver in as far as the implementation strategy.
It was approved by Cabinet in September 2020. Provinces were extensively consulted and engaged about the modalities of the framework to ensure their efficacy and full understanding of the framework.
The Monitoring and Evaluation Framework is scheduled to be finalized in November 2020, and is currently being consulted upon at Provincial level.
The Sanitary Dignity National Task Team (NTT) consistently meets every Quarter to examine and evaluate progress, and intervene where necessary. It comprises delegates from national department and provinces, including National Treasury.
National Treasury disbursed an allocation through equitable share to all 9 provinces, and they monitor the spending of the allocation. (See 3rd slide)
The Department monitors the implementation of the framework including monitoring the inclusion of women, youth & persons with disabilities at procurement level, whilst refining the SDIF value chain
Department of Women, Youth and Persons with Disabilities (DWYPD) convened capacity building workshops across all the provinces during 2019/2020 financial year in an effort to :

## Slide 3: Equitable share allocation
Sanitary Dignity Project |  | Medium term allocation |  |  | 
 | 2019/20 | 2020/21 | 2021/22 | 2022/23 | 
Total Allocation per Financial Year | 157 000 | 209 007 | 217 258 | 225 574 | 
Eastern Cape | 22 815 | 37 614 | 39 098 | 40 595 | 
Free State | 13 881 | 13 674 | 14 214 | 14 758 | 
Gauteng | 18 313 | 25 549 | 26 558 | 27 574 | 
KwaZulu-Natal | 27 032 | 48 912 | 50 843 | 52 789 | 
Limpopo | 20 999 | 32 749 | 34 042 | 35 345 | 
Mpumalanga | 15 984 | 19 308 | 20 071 | 20 839 | 
Northern Cape | 10 518 | 4 663 | 4 847 | 5 033 | 
North West | 14 908 | 16 427 | 17 075 | 17 729 | 
Western Cape | 12 551 | 10 110 | 10 509 | 10 911 | 

## Slide 4: ENABLING INFRASTRUCTURE
According to the assessment done before COVID-19 Lockdown, it revealed that schools in rural areas mostly have a huge gap in addressing water supply, sanitation and hygiene (WASH). DWYPD is working to address that in conjunction with the Department of Basic Education’s Sanitation Appropriate for Education (SAFE) initiative which was initiated by the President of the Republic. The SAFE initiative is conducting an assessment to determine the extent of the gap.
SAFE is also represented at the National Task Team.
Some Schools do not have bins for disposal of used menstrual products and that constitutes a health hazard. Free State is making good inroads in addressing the matter, targeting their rural areas.
Water tanks were delivered to some schools and the matter still needs to be evaluated in terms of impact and the number of schools that have been recipients.
An initiative is underway to come up with an ideal toilet that is appropriate, safe and hygienic which should ensure the dignity of girl learners. DWYPD, DBE & WaterAid are collaborating with other partners in the South African Coalition on Menstrual Health Management. A report will be ready during the 4th Quarter of 2020/21.
Women, Youth and Persons with Disabilities’ led & owned businesses are being encouraged to innovate and involve themselves in waste disposal initiatives.

## Slide 5: PROGRESS WITH IMPLEMENTATION
2020/21 financial year implementation was hampered by the COVID-19 Lockdown and as a result, no delivery was effected in schools.
During the 2nd Quarter, delivery to schools has taken place impressively in Western Cape, Gauteng, Free Sate and KwaZulu-Natal Provinces.
Eastern Cape, Limpopo and Mpumalanga have been delayed by procurement processes and will deliver in the 3rd Quarter. As a remedial plan the department advised that provinces should have a procurement plan that commences at beginning of the financial year, to ensure a seamless process with no interruptions in between.
The Eastern Cape has been interdicted from spending the 2019/20 budget due to what was referred to as defects during the procurement process. The expectation in line with the policy framework is that the procurement process must be unbundled within the value chain to benefit women, youth & persons with disabilities and not a sole service provider (monopolization) for the entire value chain.
DWYPD has met its Eastern Cape counterparts to ensure that such negative developments do not occur in future and that the 2020/21 procurement process be finalized in time within the procurement plan and the specifications must not be crafted to exclude emerging women, youth & enterprises for persons with disabilities.

## Slide 6: PROGRESS WITH IMPLEMENTATION (CONT…
The two most concerning Provinces are North West and Northern Cape.
The North West only used 25% of the 2019/20 budget and have not yet used the 2020/21 budget. Efforts by the departmental officials to ensure remedial interventions did not yield positive results.
This has resulted in the DG intervening directly with the HoD of Education.
The Northern Cape has not spent its 2019/20 and 2020/21 budget and no VALID reasons have been expressed through quarterly reports and reporting at the national Task Team (NTT).
The DG has also intervened in the matter by consulting with the DG of the Province.
During the 2019/20 financial year 1, 106 769 million learners received sanitary pads, which translates into 50.8% which was a good start, especially it having been a pilot year. (slide 7 illustrates the number of girls reached)

## Slide 7: PROGRESS WITH IMPLEMENTATION DURING 2019/20
Implementation | Mpumalanga | Gauteng | KwaZulu-Natal | Eastern Cape | North West | Limpopo | Free State | Western Cape | Northern Cape | Total
Beneficiaries |  |  |  |  |  |  |  |  |  | 
Target beneficiaries | 177 593 | 200 000 | 956 000 | 60 000 (They based the number of targeted beneficiaries on the allocation received & price of pads) | 93 000 | 538 701 | 64 395 | 90 000 | Not indicated | 3 835 689
Girls reached | 177 540 | 100 000 | 785 000 | None (Litigation matters) | 30 397 Only 25% of the budget was used | None (delays in procurement) | 13 832 | None (Late procurement & Lockdown before distribution) | None (No cooperation) | 1 106 769 = 50.8%

## Slide 8: CONCLUSION
DWYPD has a firm conviction that the Sanitary Dignity Programme will be a resounding success in 2020/21 and that challenges with some Provinces will be overcome because largely the programme is new and still has to settle well in some of the Provinces.
The DWYPD will ensure that the list of recipients widens exponentially, by working jointly with National Treasury in ensuring full spending as informed by procurement plans within provinces.
The consistent monitoring and evaluation of the programme will be a prime necessity, hence the development of a Monitoring & Evacuation framework supported by UNFPA.
Gauteng and Free State were leading in 2019/20 and in the current year regarding beneficiating women in the economic value chain by appointing women led and owned suppliers for supplying sanitary pads to schools.