## Slide 1: DRAFT TERMS OF REFERENCE – SERVICE PROVIDER
Background
The Committee placed an advert calling for written submissions from members of the public
A large volume of submissions were received via email and hard copies delivered to Parliament
This has necessitated that Parliament considers the procurement of a service provider to process the written submissions.
The process of procuring the external service provider is handled by Parliament’s Supply Chain Management (SCM).

## Slide 2: DRAFT TERMS OF REFERENCE – SERVICE PROVIDER
SERVICE PROVIDER AND SERVICES REQUIRED
An external service provider with relevant experience and proven track record, preferably a reputable research institution
Capacity to deliver within the set timeframe
a) Data capturing and indexing – synthesis of key views
The written public submissions must be captured into an indexed database.
Views expressed in the submissions to be summarised (reference should be made to the actual indexed identity)
A pdf version of the submission to be hyperlinked to each submission record

## Slide 3: DRAFT TERMS OF REFERENCE – SERVICE PROVIDER …cont
b) Data analysis and report writing
Analysis of written submissions and writing of a report on the substance of the submissions
The analysis to provide Parliament with information on who is for or against the Bill, their reasons and recommendations where applicable

## Slide 4: DRAFT TERMS OF REFERENCE – SERVICE PROVIDER …cont
Key deliverables
Indexed database of written submissions (hard copy and email submissions), with hyperlinks of pdf or actual submissions.
Analytical report of the public submissions
A presentation of the report to the PC on Health
Ensure that the confidentiality and integrity of the submissions made and report produced is maintained.

## Slide 5: DRAFT TERMS OF REFERENCE – SERVICE PROVIDER …cont
b) General requirements
The appointed service provider to provide an implementation plan/strategy (and associated timelines) on how they will index, capture and analyse public submissions into a report. The implementation plan/strategy to be presented at a briefing meeting
The service provider is expected to work closely with the core team of content advisors and researchers
Final draft to be presented to the Portfolio Committee on Health
The intention is not to subsume the Constitutional responsibility of the Committee. Members of the Committee will still have the opportunity to scrutinize each of the submissions received.

## Slide 6: DRAFT TERMS OF REFERENCE – SERVICE PROVIDER …cont
Work done internally:
Indexed database indicating name of the person/organisation who made the submission and contact details (Partially done)
Identification of individuals or groups who expressed interest to make oral presentations (Done)
Providing information on who is in favour of or against the Bill (Done)
Analysis of remaining substantive submissions and other submissions with motivations

## Slide 7: DRAFT TERMS OF REFERENCE – SERVICE PROVIDER …cont
Dealing with security issue:
There are two information security clauses built into the Request for Quotation (RFQ)
Deliverables (Number 4, page 5 of the RFQ): “Ensure that the confidentiality and integrity of the submissions made and report produced is maintained”.
Mandatory requirements (Number 9, page 6 of the RFQ): “The staffing requirement must ensure that the confidentiality and integrity of the submissions and the report is maintained”.

## Slide 8: DRAFT TERMS OF REFERENCE – SERVICE PROVIDER …cont
Timeframe for processing of information – proposed new dates:
Date of issue of the RFQ: 16 October (previous date: 10/09/2020)
Closing date and time: 27 October (previous date: 21/09/2020)
The appointed service provider to be briefed and expected to start work by 5 November 2020
The implementation plan / strategy and the report Framework are to be presented at the briefing meeting.
First draft report must be submitted by 20 January 2021
The final draft report must be submitted not later than 18 February 2021
Final draft report is to be presented to the Portfolio Committee on Health by Wednesday, 24 February 2021.