## Slide 1
PROGRESS REPORT ON THE IMPLEMENTATION OF THE NATIONAL SOLAR WATER HEATER PROGRAMME
TO THE PARLIAMENTARY PORTFOLIO COMMITTEE ON MINERAL RESOURCES AND ENERGY
14 OCTOBER 2020

## Slide 2
High Level Implementation View
High Level Status Report
Status on Delivery of Solar Water Heaters to Municipalities
Status on Installation of Solar Water Heaters
Status on Training of Learners
Challenges and Interventions:
  Technical
  Storage
  Installations
Conclusions
PRESENTATION OUTLINE

## Slide 3: HIGH LEVEL PROGRAMME PROCESS FLOW CHART

## Slide 4
HIGH LEVEL STATUS REPORT
No | Project Phase / Activity | Progress on each phase on activity
1. | Signing of the Framework Agreements between the Department and Municipalities including confirmation of residential areas and beneficiary households. | Completed
2. | Social Facilitation / Public Participation done across all phases. | Initial Social Facilitation was done (will be ongoing through the implementation phase)
3. | Technical Feasibility Assessment. | Completed in 14 of the18 municipalities. Findings were shared with municipalities for auctioning to enable installation.
4. | Delivery of the SWHs to participating municipalities | 70% of SWH units have been delivered to municipalities
5. | Appointment of Installation Service Providers | Phase 1 completed Finalizing Tender Documents for Phase 2
6. | Appointment of additional technical support capacity (Project Coordinators, Quality Assurance analysts and Community Liaison Officers) for municipalities | Completed
7. | Training – Product Specific and Learners training – Final TFA results are taken into consideration by the installation companies for roll out with their respective municipalities. | Work in progress
8. | Installation of Phase I - 33 000 systems | Work in progress. This phase is anticipated to be completed in December 2020.

## Slide 5
No | Municipality | SWHs allocated | Actual Units delivered | Status
1. | JB Marks | 5 000 | 5 000 | Completed.
2. | Mahikeng | 5 000 | 5 000 | Completed.
3. | The City of Matlosana | 5 000 | 5 000 | Completed.
4. | Bitou | 3 000 | 3 000 | Completed.
5. | The City of Cape Town | 5 000 | 5000 | Municipality doesn’t have a storage facility. Its systems were delivered & stored at SFF.
6. | Swartland | 2 000 | 2 000 | Municipality doesn’t have a storage facility. Its systems were delivered & stored at SFF.
7. | Cape Agulhas | 2 000 | 800 | Balance of 1 200 units are stored at SFF.
DELIVERY OF SOLAR WATER HEATERS TO MUNICIPALITIES

## Slide 6
No | Municipality | SWHs allocated | Actual Units delivered | Status
8. | Matzikama | 2 000 | 0 | Municipality is busy with security upgrades on identified storage facility. Delivery of units will take place after the completion of the security upgrades.
9. | Mossel Bay | 2 000 | 2 000 | Completed.
10. | Sol Plaatjie | 6 000 | 5 050 | Delivery of the balance of the systems is pending a resolution of dispute with the Supplier.
11. | Emthanjeni | 4 000 | 0 | Storage has been confirmed and delivery will take place soon.
DELIVERY OF SOLAR WATER HEATERS TO MUNICIPALITIES

## Slide 7
No | Municipality | SWHs allocated | Actual Units delivered | Status
12. | Polokwane | 10 000 | 10 000 | Completed.
13. | Ethekwini | 6 000 | 1 195 | Manufacturer is refusing to release the balance of the systems. Department is engaging with the manufacturer on the dispute.
14. | Mpofana | 5 000 | 0 | Storage facility has been identified but security is not adequate. Municipality has indicated budget constraints to install necessary security features. Delivery is yet to be scheduled.
15. | Makana | 6 000 | 6 000 | Completed.
16. | Elundini | 5 000 | 3 600 | Available storage is full. Delivery to commence once additional storage warehouse has been found.
DELIVERY OF SOLAR WATER HEATERS TO MUNICIPALITIES

## Slide 8
No | Municipality | SWHs allocated | Actual Units delivered | Status
17 | The City of Tshwane | 5 000 | 1 250 | The remaining systems to be delivered once additional storage is confirmed. Current storage is full. The City has not sourced additional storage.
18 | Ekurhuleni | 5 000 | Stored at NECSA | Programme is experiencing delays. The municipality has not confirmed storage facility.
Total |  | 87 000 | 61095 | 70% of the SWH units have been moved from the Manufacturer Warehouses
DELIVERY OF SOLAR WATER HEATERS TO MUNICIPALITIES

## Slide 9
It is projected that 33 000 systems will be installed by the end of December 2020 as part of Phase 1.
9 (nine) Installation Service Providers have been appointed to install 33 000 systems in all the participating municipalities.
In order to move with speed, the Department has allocated more than one service provider in some of participating municipalities.
The number of installation teams vary according to contracted allocation.
Training of Leaners which is part of the programme is underway and is expected to be completed by 30 November 2020.
INSTALLATION OF SWH SYSTEMS

## Slide 10
INSTALLATION SCHEDULE
No | Province | Municipality | Installation Company | Number of units Allocated for Installation | Period (12 Oct - 15 Dec 2020) | No. of Geysers to be installed per day | Installation period per month |  |  | Total
 |  |  |  |  | Number of days |  | 12-30 Oct (15 days) | Nov (21 days) | 1-15Dec (11 days) | 
1. | Northern Cape | Sol Plaatje | Mbalisto Energy | 2 079 | 47 | 44 | 664 | 929 | 487 | 2079
 |  | Emthanjeni | Gubhuza Trading | 750 | 47 | 16 | 239 | 335 | 176 | 750
 |  |  | Real Time Trading | 1009 | 47 | 21 | 322 | 451 | 236 | 1009
2. | North West | Mahikeng | Full Swing Trading 458 | 500 | 47 | 11 | 160 | 223 | 117 | 500
 |  |  | Thunzi Consulting | 1450 | 47 | 31 | 463 | 648 | 339 | 1450
 |  | City of Matlosana | Thunzi Consulting | 1450 | 47 | 31 | 463 | 648 | 339 | 1450
 |  |  | Full Swing Trading 458 | 500 | 47 | 11 | 160 | 223 | 117 | 500
 |  | JB Marks | Seabelo | 3500 | 47 | 74 | 1117 | 1564 | 819 | 3500
3. | Western Cape | City of Cape Town | Woesa | 827 | 47 | 18 | 264 | 370 | 194 | 827
 |  |  | Emzansi Consulting | 827 | 47 | 18 | 264 | 370 | 194 | 827
 |  | Swartland | Emzansi Consulting | 759 | 47 | 16 | 242 | 339 | 178 | 759
 |  | Matzikama | Emzansi Consulting | 759 | 47 | 16 | 242 | 339 | 178 | 759
 |  | Bitou | Emzansi Consulting | 1138 | 47 | 24 | 363 | 508 | 266 | 1138
 |  | Cape Agulhas | Emzansi Consulting | 500 | 47 | 11 | 160 | 223 | 117 | 500
 |  |  | Woesa | 500 | 47 | 11 | 160 | 223 | 117 | 500
 |  | Mossel Bay | Emzansi Consulting | 759 | 47 | 16 | 242 | 339 | 178 | 759

## Slide 11
INSTALLATION SCHEDULE
No | Province | Municipality | Installation Company | Number of units Allocated for Installation | Period (12 Oct - 15 Dec 2020) | No. of Geysers to be installed per day | Installation period in months |  |  | Total
 |  |  |  |  | Number of days |  | 12-30 Oct (15 days) | Nov (21 days) | 1-15Dec (11 days) | 
4. | Eastern Cape | Makana | Mbalisto Energy | 1366 | 47 | 29 | 436 | 610 | 320 | 1366
 |  |  | Real Time Trading | 910 | 47 | 19 | 290 | 407 | 213 | 910
 |  | Elundini | Gubhuza Trading | 1896 | 47 | 40 | 605 | 847 | 444 | 1896
5. | Kwa Zulu Natal | Ethekwini | Full Swing Trading 458 | 2276 | 47 | 48 | 726 | 1017 | 533 | 2276
 |  | Makana | Mbalisto Energy | 1366 | 47 | 29 | 436 | 610 | 320 | 1366
 |  |  | Real Time Traiding | 910 | 47 | 19 | 290 | 407 | 213 | 910
 |  | Mpofana | Gubhuza Trading | 1852 | 47 | 39 | 591 | 827 | 433 | 1852
6. | Gauteng | Tshwane | Mbalisto Energy | 1897 | 47 | 40 | 605 | 848 | 444 | 1897
 |  | Ekurhuleni | Emzansi Consulting | 1942 | 47 | 41 | 620 | 868 | 455 | 1942
7. | Limpopo | Polokwane | Lebone Engineering | 937 | 47 | 20 | 299 | 419 | 219 | 937
 |  |  | Thunzi Consulting | 1450 | 47 | 31 | 463 | 648 | 339 | 1450
 |  |  | Full Swing Trading 458 | 1297 | 47 | 28 | 414 | 580 | 304 | 1297

## Slide 12: PrOGRESS ON Training OF LEARNERS IN PARTICIPATING MUNICIPALITIES
Key training dates: All learner lists have been signed off by the DEL in compliance with Unemployment Insurance Fund (UIF). Assessment of Training Implementation Plans by CEF and Energy and Water SETA was conducted on 24th – 28th Aug 2020. Training Implementation Plans have been submitted to EWSETA for consolidation into one Master / Integrated Plan
State of readiness and notification of learners -
  Mahikeng Municipality: 27th/28th Aug 2020. Training commenced on 31 August 2020 – 30 learners completed training. The 2nd group started on 5 October 2020;
  City of Matlosana – Started but the municipality insists on having a group of 60 instead of 50 which is line with Covid-19 requirements;
  JB Marks – no venue that was approved based on the due diligence, 5 venues have been identified.
  Polokwane – Training is in progress and completing theoretical next week;
  Swartland learner training commenced last week and is expected to be completed on 13 & 14 October 2020.

## Slide 13: PrOGRESS ON Training OF LEARNERS IN PARTICIPATING MUNICIPALITIES
Key training dates: All learner lists have been signed off by the DEL in compliance with UIF
State of readiness and notification of learners -
  Tshwane Municipality: 27th/28th Aug 2020. Training commences on 31 August 2020 – 30 learners completing this week and 2nd group starting next week);
  Mpofana Municipality – Induction in progress;
  Makana Municipality – Induction in progress;
  Elundini Municipality – Induction in progress;
  Mosselbay Municipality – Induction in progress
  Elundini Municipality – Induction in progress
  Emthanjeni Municipality – Recruitment in progress, training to commence on 5th October 2020.
  Ethekwini Municipality – Recruitment in progress, training to commence on 5th October 2020.
  Sol Plaatje Municipality – Recruitment in progress. Training commences on 5th October
  Cape Aghulas and Matzikama municipalities have very few learners currently being confirmed. Still recruiting.
  All other municipalities expected to commence mid October 2020.
It is anticipated that training for first phase will be completed 30th November 2020.

## Slide 14: CHALLENGES AND INTERVENTIONS (Technical specification)
Water quality was found to be too hard in some areas. Hardness causes scale to build up in tubes, thus affecting the efficiency of heating water by the geysers.
Integrity of the household roofs. In some areas, the roof supporting beams were identified as inadequate to hold the weight of the geyser with full of water.
Cracked walls on the beneficiary houses were identified. The cracks create a problem in that once a geyser is installed on the roof, the load by the geyser may accelerate the crack.
In some areas houses with asbestos roofs were identified. Asbestos has been declared unsafe.
Intervention on above challenges
  The affected municipalities are being engaged to replace these households with houses that have appropriate roofs.
  Municipalities have been given the reports to act on the recommendations.
  Affected municipalities should enhance potable water treatment process which has financial implications.
  Additional material to support the geyser is required in those identified houses to address identified high risk.

## Slide 15: CHALLENGES AND INTERVENTIONS (STORAGE)
Storage payments remain a high risk due to the dispute with the contracted suppliers’ demands, to date 70% of the procured goods have been removed from the suppliers.
Some municipalities are also battling with provision of storage facilities and/or secure storage facilities citing budget constraints;
Unavailability of storage facility or storage with insufficient capacity and/or no secure storage at municipalities;
Municipalities with budget constraints to provide secure storage facilities are requesting the Department to waive some security measures increases the risks – theft:
Interventions
  The Minister’s intervention in some of the disputes has resulted in additional storage being made available and as such delivery was significantly enabled.
  The Director Generl is leading the process of engaging with suppliers to address all pending storage issues and resolve disputes.
  The Department & CEF are engaging affected municipalities and assessing requests by some municipalities to waive some security requirements.
  As a last resort, the Department may have to reallocate the SWHs from municipalities that are not able to provide storage facilities to municipalities that are ready.

## Slide 16
Demand that training of the learners must precede actual installation and that learners be the ones to install instead of the appointed employees of service providers.
Procurement of additional consumables to adapt the piping and the SWHs as most houses are not built in line with building codes
Demand for 30% of the project to be allocated to local business.
  No social facilitation and at times lack of support from responsible local authority.
Interventions
  The Department addressed the gap on additional consumables by approving the appointment of installation service providers to procure the additional material as and when needed but under strict controls.
  Ministry is continuously engaging some of the local authorities where there are challenges.
CHALLENGES AND INTERVETIONS (INSTALLATION)

## Slide 17
The Department would like to assure the Committee that efforts are being made to ensure that SWH geysers are installed without any further delays.
Parliamentary Portfolio Committee on Mineral Resources and Energy to note the status of the SWHs Programme as summarised in next slide.
CONCLUSIONS

## Slide 18
CONCLUSIONS - HIGH LEVEL STATUS REPORT
No | Project Phase / Activity | Progress on each phase on activity
1. | Signing of Framework Agreements between the Department of Municipalities and Confirmation of residential areas and beneficiary households; | Completed
2. | Social Facilitation / Public Participation done across all phases | Initial Social Facilitation was done (will be ongoing throughout the implementation phase)
3. | Technical Feasibility Assessment | Completed in 14 of the 18 municipalities. Findings were shared with municipalities for auctioning to enable installation.
4. | Delivery of the SWHs at participating municipalities | 70% of SWH units have been delivered to municipalities
5. | Appointment of Installation Service Providers | Phase 1 completed. Finalizing Tender Documents for Phase 2
6. | Appointment of additional technical support capacity (Project Coordinators, Quality Assurance analysts and Community Liaison Officers) to municipalities | Completed.
7. | Training – Product Specific and Learners training – Final TFA results are taken into consideration by the installation companies for roll out with their respective municipalities | Work in progress.
8. | Installation of Phase I - 33 000 systems | Work in progress. This phase is anticipated to be completed in December 2020.

## Slide 19
THANK YOU