## Slide 1: DHET Certification Backlog Reduction Status
20 October 2020

## Slide 2: Content
Objectives
Progress and status of the certification backlog statistics
New system go live dates and Backlog Day Zero target timeline (Previously Presented to PCHETST)
New system go live dates and Backlog Day Zero target timeline (Revised)
Key interventions planned to be undertaken over next report period
Key application changes & interventions undertaken
Conclusion

## Slide 3: Objectives
Provide a progress update on the certification backlog statistics
Present a revised timeline on the certification backlog (this is as communicated to PCHETST via DHET on 18 September 2020)

## Slide 4: Progress and status of the certification backlog statistics
Note: The stats may fluctuate as the scripts and system reports to address the backlog are refined and records are processed.
Qualification | 18-Feb-20 | 14-Oct-20 | % Reduction
GETC:ABET L4 | 65 890 | 10 517 | 84%
Business Studies | 29 473 | 7 691 | 74%
Engineering Studies | 21 638 | 19 327 | 11%
NC(V) First Issues | 410 | 7 | 98%
NC(V) Full Certificates | 7 866 | 2 542 | 68%
Total | 125 277 | 40 084 | 68%
The initially planned 80% reduction by end June 2020 could not be met, the key reasons being:
COVID-19 lockdown. Although online platforms were used by SITA for internal meetings, work sessions took much longer to complete and they were impacted by the rolling load shedding. Additionally the COVID-19 lockdown also hampered the planned collaboration efforts between SITA and DHET
Changes in the current exam cycles. Some team members were required to expend additional effort to prepare for the impact of cancelled examinations on remaining examinations e.g. systematic roll-over of candidates and to enable e-booklets for virtual standardisation meetings going forward
Lengthy data and program root cause analysis and resolution
SITA has subsequently revised the target dates given the challenges outlined above

## Slide 5: New system go live dates and Backlog Day Zero target timeline (Previously Presented to PCHETST)
Long Term
Medium Term
Short Term
Feb
2020
Mar
2020
Apr
2020
May
2020
Jun
2020
Jul
2020
Aug
2020
Sep
2020
Oct
2020
Nov
2020
Dec
2020
Jan
2021
Feb
2021
Mar
2021
Apr
2021
GETC
Backlog Go-Live
NCV
Backlog Day Zero
NCV
System Go - live
NATED Business Studies
Backlog Day Zero
NATED Business Studies
New System Go - live
NATED Engineering Studies
Backlog Day Zero
NATED Engineering Studies
New System Go - live
Backlog Day Zero planned to be two weeks before go-live of a qualification on the new system
--- Data integrity checks and audit are done as part of migration to the new system, which also serves as quality assurance---
GETC
Backlog Day Zero
NCV
Phase 1 Reduction
NATED Business Studies
Phase 1 Reduction
NATED Engineering Studies
Phase 1 Reduction
GETC
Phase 1 Reduction
NATED Engineering Studies
Significant Reduction*
GETC
Significant Reduction*
NATED Business Studies
Significant Reduction*
NCV
Significant Reduction*
* Significant Reduction target is approximately 80% of currently identified

## Slide 6: New system go live dates and Backlog Day Zero target timeline (Revised)
Long Term
Medium Term
Short Term
Feb
2020
Mar
2020
Apr
2020
May
2020
Jun
2020
Jul
2020
Aug
2020
Sep
2020
Oct
2020
Nov
2020
Dec
2020
Jan
2021
Feb
2021
Mar
2021
Apr
2021
Backlog Day Zero planned to be two weeks before go-live of a qualification on the new system
--- Data integrity checks and audit are done as part of migration to the new system, which also serve as quality assurance---
NATED
Engineering Studies
NATED
Business Studies
NCV Full
GETC
NATED
Engineering Studies
NATED
Business Studies
GETC
80% Reduction of Backlog as Communicated on 18 February 2020
95% Reduction of Backlog as Communicated on 18 February 2020
Principles / Critical Success Factors to Backlog Day Zero
Not everything will be resolved by the system
Records that cannot be resolved by the system must be resolved through business decisions
First prize will be Backlog Day Zero to be achieved before new system is implemented
Dedicated DHET and SITA officials to be allocated to the Backlog Day Zero Programme
Swift dataset turnaround times by all stakeholders and communication / resolving candidate records that have not been approved by Umalusi
Timely business decisions and business rules
Qualification | October 2020 | November 2020 |  | December 2020
GETC-ABET | Secondary focus |  |  | 
NATED Business Studies | Primary Focus |  | Secondary | 
NATED Engineering Studies | Secondary |  | Primary Focus | 
NC(V) First Issues | Secondary Focus |  |  | 
NC (V) Full Certificates | Primary Focus |  | Secondary Focus | 
GETC

## Slide 7: Key interventions undertaken
Identified candidate records that were already certified but listed as outstanding due to system indicators being incorrectly set and likewise some candidate’s indicating that they are deserving a certificate but are not (CET & NATED)
Made key adjustments on the functionality of the systems
  Created SQL database and SQL scripts to support analysis and updates (CET)
  Created functionality to process (resulting and extracting) candidates for multiple examination cycles as opposed to one exam cycle at a time (CET)
  Enhanced the evaluation program to do an audit on the external adjustments on written marks to ensure alignment when creating certification requests in order to reduce the Umalusi rejection rate (NCV)
  Created functionality to display all ID numbers linked to a sequence numbers to enable quicker analysis (NATED Business Studies)
  Enhanced current extracting and analysis programs to list the outstanding candidates (NATED)
DHET, Umalusi & SITA agreed to process candidates where multiple mark changes were applied after the initial resulting. Initially only a single mop-up was catered for and resulted in QAA rejections (NCV)
Onboarding a functional specialist who is familiar with the DHET exam systems and process
Installation of the Natural Engineer tool that will assist with simplifying the complexities that exist in the old Natural/Adabas system

## Slide 8: Key interventions planned to be undertaken over next report period
Investigate the feasibility of using the SITA modern big data analytics platform to analyse data, which is now in a production ready state and requires key activities such as configuration, data population and confirmation/ implementation of business rules
Enrich the user and technical functionality to process outstanding candidate records quicker based on data and system root cause analysis, including setting the candidates to indicators such as active and inactive
Further enhance the NATED outstanding reporting programs to reduce the administration in preparing management reports and quicker resolution of candidate records

## Slide 9: Conclusion
As mentioned above, during detailed analysis, there are candidates being identified that already being certified or do not qualify for certification but their system indicators are showing incorrectly. The team is busy aligning these indicators as and when they are identified. Thus these candidates will reflect correctly and the will not be receiving certificates
As much as progress was impacted due to COVID-19, the adjusted roadmap shows that we plan to achieve 95% reduction by 31 March 2021
SITA understands that the outstanding certificates have an adverse implication on candidates and is therefore committed to resolving any system or data matters preventing candidates from receiving their certificates

## Slide 10: Thank You Questions