## Slide 1: Portfolio Committee 03 November 2020
PROGRESS REPORT ON SECTION 139 INTERVENTIONS

## Slide 2: Purpose
To provide progress on the implementation of the Section 139 Provincial Executive Council resolutions.

## Slide 3: Introduction
Limpopo Province’ Executive Council Decisions to invoke Section 139 interventions were taken in respect of the following municipalities:
Pre-2016 Local Government Elections Thabazimbi Local Municipality: Feb 2016
Post- 2016 Local Government Elections
Modimolle Mookgophong Local Municipality: 2018
Fetakgomo Tubatse Local Municipality: 2018
Mogalakwena Local Municipality 2019
The presentation provides progress on the implementation of the Executive Council resolution in the four municipalities.

## Slide 4
Thabazimbi Local Municipality

## Slide 5
Thabazimbi Local Municipality experienced institutional challenges in 2015 and a Rapid Assessment Team was established to provide a fair objective report on the state of affairs of the municipality.
After considering a progress report on Thabazimbi as per CoGHSTA intervention from August 2015 to January 2016, the Executive Council resolved that the Thabazimbi Local Municipality be placed under Section 139(1) (b) of the Constitution of the Republic of South Africa.
The Executive Council resolved that:
- CoGHSTA should appoint an Administrator who will assume the responsibility of Accounting Officer
- The municipality should invoke Section 152(1) and Section 152(2) of the MFMA by directing the Administrator to apply for stay of legal proceedings
- National Treasury should be requested to undertake forensic investigation of all municipal activities to unearth financial irregularities.
The intervention was duly approved by the Minister, and the NCOP also visited the Thabazimbi on April 15, 2016
Background

## Slide 6
An Administrator was appointed with a sole responsibility of stabilizing the municipality, with clearly outlined responsibilities.
The Administrator was supported by officials from COGHSTA, MISA, COGTA and Provincial Treasury.
The Administrator had difficulty in obtaining information and cooperation from the municipal staff, affecting his ability to play the role as expected.
After the August 3, 2016 local government elections, the municipality, constituted a new council, governed by a coalition made up of the DA, EFF, Residents Association and FF Plus.
In August 2016 the Municipality had a number of assets removed by sheriff of the court from 8 warrants which had been issued from 2015 to 2016.
Progress

## Slide 7
A Financial Recovery Plan(FRP) was developed with the support of various role players and approved by Council on 17 July 2016.
Provincial Treasury seconded a financial expert to help implement the FRP.
COGHSTA enlisted the services of the state attorney to file papers on behalf of the municipality to invoke Section 152(1) and section (152(2) of the MFMA. The order was granted in favour of the municipality.
National Treasury was engaged to conduct a forensic investigation, and preliminary discussions were held with administrator, and documentation also submitted. National Treasury could, however, not conclude the forensic investigation due to lack of sufficient records/ information in the municipality
A placement policy was developed to guide the placement process, and a register implemented to curb staff absenteeism which was a serious challenge.
The municipality was also supported to develop several sector plans through the assistance of DBSA and Anglo American namely Water Services Development Plan, Roads Master Plan, Electricity Master Plan, Pothole Repair Plan, Stormwater Management Plan
Progress

## Slide 8
The municipality wrote to the Ministers of Cooperative Governance and Traditional Affairs (COGTA) and Finance, acknowledging that things have not improved despite the various support initiatives provided, including the intervention instituted by the provincial government.
Following several engagements between CoGTA, National Treasury and Limpopo Provincial Government, a decision was taken to institute an inclusive support package in line with section 154 of the constitution and rescind resolution to invoke section 139 intervention.
The support package, amongst others, sought to ensure finalisation of outstanding matters which includes the following:
  Forensic Investigation
  Implementation of the Financial Recovery Plan.
  Filling of positions of the Municipal Manager, CFO and Director: Community Services as well as other vacant critical posts within the municipal establishment.
  Development, approval and implementation of the procedure manual and record management system.
  Conducting a skills audit amongst staff and development of training process.
  Reversal of the placement process which caused the municipal budget to skyrocket
Exco further approved a support of a financial loan totaling R25 million to support the municipality and that the Provincial Treasury manage the funds, and develop relevant systems to ensure that the money is used for the intended purposes.
SUPPORT PACKAGE INLINE WITH SECTION 154 OF THE CONSTITUTION

## Slide 9
Senior Managers were duly appointed, and this led to the stabilization of the municipality. There has however been a high turnover of senior managers in the municipality as most worked for less than six months and moved to other municipalities.
This has resulted in an improved audit outcome for the 2018/19 Financial Year as the municipality was able to submit AFS on time and further received a qualified audit opinion from a disclaimer.
The municipality was however riddled with council instability that led to the replacement of the mayor.
The municipality is supported by MISA to improve on MIG expenditure.

## Slide 10
Despite its high Eskom Debt and financial challenges, the municipality was among the first to sign and honour a repayment agreement with Eskom and Magalies Waterboard, avoiding service interruptions and saving on interest.
Although it still has financial challenges, the municipality has stabilized resulting in it being to implement MIG programme after it was regazetted to Waterberg District Municipality from 2015/16.
These gains may however be lost due to the suspension of the municipal manager in June 2020.
The main challenge and lesson learnt from Thabazimbi intervention was the need to establish a team to support the “Administrator” so as not to rely on municipal official.

## Slide 11
Modimolle Mookgophong Local Municipality

## Slide 12: Background
COGHSTA conducted a rapid assessment in the municipality due to a number of challenges that were identified in the municipality.
In particular, it was during the meeting between the municipality’s Political Management Team, Senior Management and COGHSTA on 01 February 2018 following the inability of the municipality to pay salaries on 25 January 2018 that an agreement was reached for the provincial government to conduct a rapid assessment in the municipality.
The rapid assessment was subsequently conducted from 08 to 09 February 2018 ,and the team was constituted by officials from COGHSTA, Provincial Treasury and SALGA Limpopo.
The team conducted a desktop study using the available reports and further interviewed several officials.

## Slide 13: Findings of the rapid assessment
High vacancy rate at senior management level as well as instability of the senior management team.
The salary bill for the staff was very high estimated at R8m with additional R3m of third parties payments. The total employee cost was 35% including council remuneration.
Poor HR management(poor leave management, incomplete placement process, non-functional LLF, inadequate segregation of duties,etc)
The financial statements indicated that the municipality incurred a deficit of R29 055 478 during 2015/2016. The municipality’s liabilities exceeded its assets by R75 233 666.
The municipality was bankrupt - Solvency ratio of less than 1:1 (total liabilities exceed total assets)

## Slide 14: Findings…cont’d
Municipality | 2012/13 | 2013/14 | 2014/15 | 2015/16 | 2015/16 second set | 2016/17
Modimolle | Adverse | Disclaimer | Qualified | Qualified | Qualified | Disclaimer
Mookgophong | Qualified | Qualified | Qualified | Qualified | Adverse | 
Poor management of grants: R83 million of unconditional grants received by the municipality was used for other purposes and were not cash backed, with a possibility that the amount could be withheld from the 2018/19 equitable share of R100.8 million, leaving the municipality with only R17.8.
Municipality owed creditors in excess of R350million(R366.6 as at May 2018) and the 2018/19 budget was not funded
The municipality owed Eskom R269.6 million, Magalies Water R15 million and Department of Transport R10 418 386.00.
Government Departments owed municipality R13 604 500.31 of undisputed amounts.

## Slide 15: Findings…. Cont‘nd
Based on the findings of the assessment, the Limpopo Provincial Executive Council resolved on 30 May 2018 that:
The Modimolle-Mookgophong Local Municipality be placed under Section 139 of the Constitution of the Republic of South Africa, 108 of 1996 as part of an intervention to stabilize the municipality.
The Department of Co-operative Governance, Human Settlements and Traditional Affairs and Provincial Treasury should work on the financial resources to implement the intervention; and
The Provincial Treasury should undertake a forensic investigation on all municipal activities to determine the extent of the challenges and remedial actions necessary to be undertaken.
An application be made to the High Court on behalf of the Modimolle-Mookgophong Municipality in terms of Section 152 of the Municipal Finance Management Act 56 of 2003 for the stay of all legal proceedings including execution of legal process against the Municipality.
The Minister approved the intervention, and the NCOP Select Committee on Cooperative Governance and Traditional Affairs, Water and Sanitation and Human Settlements also visited the municipality and engaged with various stakeholders on the intervention.

## Slide 16: Progress on the intervention
Institutional Arrangements
The Department appointed an Administrative Head to give effect to the implementation of EXCO resolution and to address the following issues :
  Development and implementation of a financial recovery plan.
  Appointment of senior managers.
  Finalisation of all outstanding transitional measures resulting from the merger of former Mookgophong and Modimolle Local Municipalities.
  Stabilise the financial situation in the municipality, including ensuring that the municipality honours its repayment agreement with Eskom and Magalies Water Board to avoid service delivery interruptions.
  Oversee the Forensic Investigation and any other investigations to be undertaken by Treasury and other organs of state in the municipality.
  Any other issues from the rapid assessment report.
The Administrative Head was supported by a team of specialists, constituted as follows:
  Human Resource and Labour Management Specialist
  3 Financial Experts(1 seconded by National Treasury and 2 by Provincial Treasury)
  1 Technical Expert(seconded by MISA)
COGHSTA further provided the following services when required by the municipality: Information Technology Specialists, Legal Services and Planners

## Slide 17: Progress on the intervention
    Development and implementation of a financial recovery plan:
    A Financial Recovery Plan was drafted, consulted with various stakeholders including councilors and tabled in Council on 02 August 2018. It was approved by the MEC and adopted by Council on the 21st February 2019.
    Departmental Heads were given the responsibility to update the FRP monthly for implementation.
    A progress report on the implementation of the FRP was tabled at EXCO on the 20/03/2019 and recommended that the Mayor must report to the MEC on a monthly basis as required stipulated in Sections 145 and 146 of the MFMA.
    The municipality is therefore expected to continue implementing the report to improve the financial situation of the municipality.

## Slide 18: Progress on the intervention
Appointment of senior managers:
The top echelon structure of the municipality has six (6) positions.
When the intervention was invoked, the municipality had four(4) vacancies at senior management level.The positions of Municipal Manager, Chief Financial Officer (CFO), Senior Manager: Technical Services and Senior Manager: Planning and Economic Development were vacant .
The positions of Chief Financial Officer and Planning & Economic Development Manager were filled during that period.
There were challenges with the Technical Services Manager position as the Council resolved to appoint an internal candidate who did not meet legislated minimum requirements. The MEC declined concurrence and advised council to re-advertise the position. The position was re-advertised and had since been filled.
The municipal manager’s position is still outstanding due to legal challenges.
It should also be noted that during the intervention period, the Municipal council requested the MEC to second the Administrator as an Acting Municipal Manager. The approval was duly granted and this improved the accountability and efficiencies in the management of the municipal affairs.

## Slide 19: Progress on the intervention
Stabilise the financial situation in the municipality:
An IT audit conducted by COGHSTA team identified several deficiencies that led to instances were money withdrawn from the municipal bank account could not be accounted for.
As a result, all payments were approved by the administrator to ensure accountability and compliance to payment arrangement. The CFO, Senior Manager: Corporate Services, Divisional Manager: Expenditure and administrator were introduced as signatories to the bank replacing erstwhile signatories.
All user rights of users of the financial system were revoked. The process to allocate user rights was centralised in the Divisional Manager: Expenditure with the administrator as the approving allocation of all user rights.
The payment system in respect of capital projects was revised to include MISA officials and the administrator as the approving authority. MISA officials were tasked with the responsibility to authenticate all certificates before any payment can be approved for payment.
A system was introduced that on receipt of any conditional grant, the funds were moved to investment accounts to ring-fence its utility. As at the end of the intervention, all unused conditional grants were available and controls in place to ensure that they are not used for other things other than their conditions.
This led to an improved financial situation in the municipality and the municipality was able to honour some of the critical obligations like paying ESKOM, Water Boards, salaries and third party payments.

## Slide 20: Progress on the intervention
Forensic Investigation :
The forensic investigation company was appointed by National Treasury to conduct investigations into various allegations of irregularities.
The suspected irregularities pertained to twenty eight (28) service providers appointed by the municipality, and payments made for the period 01 July 2017 to May 2018.
The findings and recommendations of the forensic investigation were presented to the Executive Committee of the municipality by the MEC on 02 September 2019 for tabling in Council and implementation of the recommendations.

## Slide 21: Progress on the intervention
Finalisation of all outstanding transitional measures resulting from the merger of former Mookgophong and Modimolle Local Municipalities
The placement process was audited and a placement audit report was compiled. The placement audit report served in the local labour forum and was repudiated by trade unions.
An intervention from the South African Local Government Association (SALGA) was solicited to address the purported contradiction between the Transfer Agreement Collective Agreement and the Section 12 Notice.
A re-audit of the placement process was agreed to in the local labour forum after address by Salga. The re-auditing was conducted by officials from the department and is 100% complete.
Draft placement letters were prepared but could not be issued due to pushback by trade unions, particularly shopstewards from Modimolle. Subsequent to the re-auditing, five hundred and eleven (511) placement letters were issued. The process could not be concluded at the end of the intervention due to poor support from Council.
The service provider to review and develop the organisational structure was appointed. Engagement session with the service provider took place during May 2019. The matter of review of the organisational structure was presented to the local labour forum for consultation. A project execution plan was agreed to and information collection was ongoing.

## Slide 22: PAYMENT OF CREDITORS OF MODIMOLLE–MOOKGOPHONG LOCAL MUNICIPALITY
The Provincial Executive Council approved funding of an amount of R70 million for immediate relief to the municipality for business continuity and provision of basic services.
The funds were not transferred to the municipality, but COGHSTA and Limpopo Provincial Treasury was vested with the responsibility to facilitate and process payments of creditors as per approved list of creditors.
A verification team was established comprising of Limpopo Provincial Treasury and CoGHSTA to conduct invoice verification before any payment could be effected.
Based on the outcome of the invoice verification process, creditors amounting to R68 322 554.28 were paid, and R1 677 446.66 remained unspent as at 31 March 2019.
The biggest challenge was unavailability of supporting documents(appointment letters, contracts, delivery notes, etc) , resulting in some claims not being paid,
13 Companies were paid including Eskom, SARS, Magalies Water and the Auditor General South Africa and this contributed to stable business continuity and provision of basic services as part of intervention at the municipality.

## Slide 23: Termination of the Intervention
    Following the Constitutional Court Judgement that declared the Municipal Systems Amendment Act invalid, the municipal council resolved to relieve the acting municipal manager(head of intervention team) of her responsibility and appoint an internal official as an acting municipal manager.
    This was despite the fact that the judgement was not retrospective and the municipality could still use her services until the legal challenge pertaining to the appointment of municipal manager is resolved.
    Having considered the municipal resolution and progress made since the intervention, the Executive Council resolved to terminate the intervention and proceed to support the municipality through Section 154.
    On the other hand, the one –year contracts of both the head of team and HR specialist (shared resource with Fetakgomo Tubatse) was due to expire. For the duration of their contracts, the team members continued to support the municipality.
    The municipality is therefore currently supported like other municipalities in terms of Section 154 of the Constitution.

## Slide 24: Overall State of the municipality
    The municipality is still faced with serious financial challenges. The billing and collection rate for September 2020 is 65%. The decline in revenue collection is attributed to the COVID – 19 pandemic and non-payment of services by residents in townships were the municipality is not the licensed to provide electricity. The Eskom Debt is increasing, as at 30 September 2020 the debt owed amounted to R600 393 438, which is an increase from when the intervention started. This is because the municipality reneged on the initial agreement with ESKOM (negotiated by the head of intervention team). The mediation process benefitted Musina which now has an agreement that is being honoured and therefore saving on interest.
    Overall Financial Health is a concern, the municipality is partially implementing the Financial Recovery Plan.
    The municipality is however stable as there as not been any labour unrest.
    There is a decline in MIG Expenditure, and the municipality is supported by COGHSTA and MISA to improve on conditional grants.
    Placement Matters: The placement process has been concluded and placement letters were issued to all officials on 01 July 2020. The focus now is on addressing appeals.

## Slide 25: Conclusion

## Slide 26
Fetakgomo Tubatse Local Municipality

## Slide 27: BACKGROUND
Following presentations of the state of affairs of Fetakgomo Tubatse Local Municipality by the Member of Executive Council CoGHSTA; the Provincial Executive Council resolved to place the municipality under Section 139(1)(b) of the Constitution of the Republic of South Africa, 108 of 1996.
The decision was informed by the administrative, financial and institutional instability that plagued the municipality.
Placing the Municipality under section 139 was a way of supporting it to stabilise and be able to provide services to communities as required by the constitution of the republic.
The intervention was not approved by the Minister due to the fact that the notice was submitted after the 14 day period as legislated.
The delay on submission of the notice to the Minister was due to the fact that guided by the Guidelines on Section 139 interventions the department issued a notice to the municipality for submissions on the Executive Council resolution, which led to the delay in submission to the Minister.
Although the Minister disapproved the intervention, the Provincial Government continued to support the municipality.

## Slide 28: Appointment of Intervention Team
The Department established intervention support team comprising of officials from the department (head of team), human resource specialist(shared resource with Modimolle Mookgopong) and provincial treasury(financial expert). Similar to other areas, the intervention team would be supported by other units in COGHSTA and Treasury when a need arise.
The team leader assumed the responsibility of the Accounting Officer for the municipality following the resignation of the municipal manager and a request by the municipal council.
The team as expected to address the following issues at the municipality:
  Development and implementation of a financial recovery plan in the municipality.
  Appointment of senior managers
  Finalisation of all outstanding transitional measures resulting from the mergers
  Oversee the Forensic Investigation and any other investigations to be undertaken by Treasury and other organs of state in the municipalities
  Development and implementation a turn-around strategy
  Oversee the implementation of the recommendations of the VBS Forensic Investigations report and any other investigations in the municipality.
  Address any other issues required to stabilize and improve the financial situation of the municipality in line with the Limpopo Provincial Government’s development priorities.

## Slide 29: PROGRESS
A draft Financial Recovery Plan (FRP) was developed by the intervention support team.
The draft FRP was considered by the Executive Committee of Fetakgomo Tubatse municipality on 11 April 2019 and was due for consideration by the municipal Council on 25 April 2019 which could not sit due to disagreements between councilors, and was not adopted by Council.
Despite the revised FRP not having been approved by Council, management of the municipality guided by the Intervention team had started implementing the FRP which included cost containment measures.
The total cash available in the bank as at 30 June 2019 was R94 117 54.85 inclusive of conditional grants amounted to R69 415 409.00.
The difference between the total available cash of R94 117 504.85 and conditional grants of R69 415 409.00 was at R24 702 095.85. The total cash in the bank was what was available for the municipality as own cash that it could use to pay for all operational costs and any capital expenditure serviced by the municipality.
The results of June 2019 showed that a disciplined implementation of the Financial Recovery Plan will yield results though at a very small scale and at this rate, it will take a long time for the municipality to be completely financially sustainable.

## Slide 30: PROGRESS
The successful preparation and approval of the adjustment budgets 2018/19 and 2019/20, enforcing cost containment measures
Building capacity within the Budget and Treasury department as well as minimisation of ad-hoc procurement requests and scope creep;
Establishment of a functional Audit Steering Committee and Establishment of a Compliance monitoring team;
Establishment of a MSCoA Committee; Revival of the IT Committee; Implementation of Risk Registers; Improvement in the Internal Controls Environment; 2019 Interim Annual Financial Statements for the period ending 31 March 2019 were prepared in accordance with GRAP standards and in line with mSCOA requirements.

## Slide 31: PROGRESS…..cont’d
Disciplinary Cases-VBS Matter
  The municipal Manager and acting Chief Financial Officer resigned before disciplinary hearings could be concluded.
VBS Creditors Claim
  The municipality appointed Verveen Attorneys to lodge and process a claim for the repayments of investment deposits made to VBS Mutual Bank against the appointed VBS Liquidator.
  The municipality submitted a claim against the VBS Mutual Bank to the VBS Liquidator on 11 April 2019 and is awaiting the conclusion of the liquidation process.

## Slide 32: Conclusion
The support team finalised its work on the 30 June 2019 due to the Constitutional Court Judgment which prohibits the MEC from seconding personnel to act in senior management positions in the municipalities.
The Department continued to support the municipality to resolve the placement and salary parity issues through engagements with the Executive Committee.
The role of the department was mainly to explore the various options for the council to consider to address the placement impasse resulting from undue promotions in the then Tubatse Municipality as follows:
  Option 1: Reversal of promotions with retrospective recovery
  This option entails reversing all promotions (and by implication reversal of the irregular expenditure) and recovering salaries unduly earned as a result of unlawful promotions. To effect this option, municipal council must review the decision of promoting some employees by approaching the courts. Option 1 is characterised by little legal implications and might lead to possible labour unrests as organized labour would possibly resist this approach.
  Option 2: Reversal of promotion without retrospective recovery
  This option entails reversing all promotions and foregoing salaries unduly earned. Similar to option 1, the municipality must review the decision of promoting some employees by approaching the courts. Municipal council would have to write off the salaries paid so as to regularise the expenditure incurred. This option is characterised by little legal implication and possible backlash from trade unions (labour unrests).
The municipal council resolved for option one (1) and requested administration to obtain legal opinion, and the municipality is currently sourcing the legal opinion.
Not much progress was made after the withdrawal of the team due to the instability of Council and the high vacancies at senior management level.

## Slide 33: Conclusion
Due to Council instability, there was a delay in filling of senior management posts which affected the functionality of the municipality-
There is an improvement in this regards in that all senior management positions are filled except position of Corporate Services which is vacant. The municipal manager resumed duty on 01 August 2020.

## Slide 34
Mogalakwena Local Municipality

## Slide 35: Background
The Member of Executive Council tabled a report on the state of the Mogalakwena local Municipality in the Provincial Governance and Administration cluster, and highlighted serious institutional and political challenges which impact on service delivery and governance.
The Cluster subsequently mandated the MEC to establish a multidisciplinary team to conduct rapid assessment in the municipality in accordance with Section 106 of the Local Government: Municipal Systems Act, No.32 of 2000.
The Rapid Assessment Team was established constituted by officials from CoGHSTA , Provincial Treasury and MISA.
The multidisciplinary task team conducted assessment in the municipality during October 2019 analyzing reports and interviewing both officials and Risk and Audit Committee Chairpersons.
Based on the findings of the assessment, the Provincial Executive Council took a resolution dated 04 December 2019 to place Mogalakwena Local Municipality under Section 139 (1) (b) of the Constitution of the Republic of South Africa, 108 of 1996.
COGHSTA issued notices to the Minister for Cooperative Governance and Traditional Affairs, the National Council of Provinces and the Provincial Legislature as required by Section 139 (2)(b) of the Constitution.
The municipality was also notified of the EXCO resolution. The municipal council noted and accepted the intervention.
The Minister approved the intervention within the 28-day period as prescribed by legislation and the National Council of Provinces has also noted the intervention.

## Slide 36: BACKGROUND….cont’d
Institutional Arrangements:
An intervention team was established to implement the intervention. The following team members are based full-time in the municipality for the duration of the intervention: Head of intervention team: Mr Boshielo F(COGHSTA), Finance Specialists: Mr Netshisaulu P(PT) and Ms Papiah M(PT).
A Human Resource and Labour Management Specialist was appointed but unfortunately declined the offer. The Department had to restart the recruitment process. The process of appointing a replacement is at an advanced stage(SSA clearance received recently), the official will also be based full-time in the municipality.
A multi-departmental monitoring and evaluation team has been established to monitor the implementation of the intervention plan, as well as to support the intervention team in various matters identified by the intervention team during its operations.
The key areas of the intervention are outlined hereunder:
Recruitment process :
  The decision to commence any recruitment process as well as the management of all the steps during the recruitment processes.
  Ratify all the decisions in terms of the recruitment process before implementation.
Labour Relations:
  Appointment of teams to handle disciplinary processes, Implementation of bargaining agreement(s) and Ratify all the decisions before implementation
Financial Management:
  The decision/request to deviate from SCM process or to use Regulation 32 to procure.
  Management of the supply chain management processes in line with the applicable legislative provisions.

## Slide 37: BACKGROUND
Financial Management:
Payment of service providers for capital projects and other key operational services like roads maintenance, grass cutting, bush clearing, waste management,
Verification of all invoices for conditional grants prior payment by teams constituted by Municipality, CoGHSTA, Provincial Treasury, MISA, Transferring Authority.
Sign-off financial management reports to any institution/stakeholder.
Ratify all the decisions in so far as the supply chain management process, payments after the verification processes and other key decisions relating to financial management before implementation.
Council Support
Coordination of Executive Committee and Council structures,
Sign-off all reports to Council
Ratify the decisions of Council before implementation to ensure adherence to legal and policy prescripts.
Additional Areas
Should other areas be identified as high risk areas by the intervention team, such will be added to the list and be communicated to the municipality for immediate implementation.

## Slide 38: PROGRESS TO DATE
The intervention team has been appointed and is relatively on course to achieve its objectives of stabilizing the municipality.
An intervention plan has been developed, and identifies key activities per functional area as identified during the rapid assessment.
The team is generally receiving support from councilors, management, workers and various governance structures.
Of critical importance is that the municipality suspended the following officials as part of implementing consequence management: Municipal Manager. Corporate Services Director, Deputy CFO, Acting Manager SCM, Deputy Manager Technical Services, PMU Manager and four(4) members of the Bid Evaluation Committee on various allegations of misconduct.
As from June 2020, the municipality with the support of CoGHSTA, embarked on the process of consulting internal stakeholders to review and obtain inputs and comments on the current organizational structure. The following departments are reviewed: Municipal Manager Office, Planning and Economic Development, Community Services & Transport and Safety.
The process of resuscitating the Local Labour Forum (LLF) is bearing some fruits, the municipality held ordinary LLF meetings on the 3rd and 6th July 2020.

## Slide 39: PROGRESS TO DATE
Financial Management –
An action plan has been developed to address the UIF incurred and to prevent future UIF incurred by the municipality.
The SCM strategy has been developed to prevent future UIF.
A centralized email address for ESKOM Accounts was created to curb fruitless and wasteful expenditure.
The FRP has been finalized with the support of National Treasury, Provincial Treasury and COGHSTA and approved by the MEC on the 14 October 2020.
All invoices submitted to the intervention head for concurrence were checked by the financial experts thus ensuring that invoices are paid for work done ,supplies delivered or services rendered.
Invoices from the capital projects and other maintenance related services are continuously subjected to the verification by the internal audit and MISA.

## Slide 40
The following three examples are cases in point of improved internal controls:
stopping the prepayment of R 11 million to a contractor for goods (water pipes) not in possession of the Municipality which were allegedly produced and in custody of a company in Mozambique.
The supply of water through water tanker services to Masodi village for period of three days with no proof of services being rendered and without SCM process being followed for the total amount of R 700 000.
Stopping and subjecting the transaction to an internal audit for an overtime payment of R 204 000 for the electrician allegedly having worked for 676 hours of overtime in two months.
Reviewed and implemented SCM internal control process to ensure that all SCM regulations are complied with and the intervention team sign off on critical stages of the procurement process (opening of bids, administrative evaluation, and tender appointment)

## Slide 41: PROGRESS TO DATE
Improving Governance and the operation of Council
Council and EXCO meetings are being held on regular basis. The increase in the number of the Special Council meetings during May - June months was necessitated by the need for the Council to approve special Covid 19 budget adjustments as well dispensing with the disciplinary processes relating to the senior managers
The council committees are also meeting on regular basis to consider reports to the Ordinary Council meetings. However, these committees are not receiving reports on time from the Management which is an area that needs to be improved.
Committees are beginning to effectively play their oversight role by visiting capital projects.
One of the key deliverables of the intervention team is to ensure that all council resolutions are implemented by the Management. In this regard the implementation of the council resolutions is monitored on an ongoing basis through a resolution register.

## Slide 42: 3. Progress Report on the Intervention cnt…
Audit committee is functional and are holding meetings as per annual calendar. The Committee was also exposed to the AG presentation on Mogalakwena audit report on the 25th May 2020.
Both the Audit Committee and Auditor General reports where tabled in Council for the first time.
MPAC acted on this council resolution by holding series of meetings with the user departments regarding the UIF and a report was compiled with recommendations. The report was duly tabled in Council.
The implementation of the council resolutions is monitored on an ongoing basis through resolution register as a standard agenda item to executive management meetings.
Unlocking service delivery bottlenecks : The intervention team received and addressed numerous service delivery queries and challenges such as project stoppages, contractual disputes, payments disputes and non-delivery of basic services such as provision of water, blockage of sewage, potholes, non-collection of waste and re-gravelling of roads

## Slide 43: Progress Report on the Intervention cnt…
  Strengthening recruitment process
  A placement committee has been established to ensure optimal utilization of the human resources. Some of the municipal employees are misplaced and these affected people will be placed to the right jobs through a well-coordinated, fair and transparent process.
  Lockdown curtailed the finalization of the recruitment process on critical positions of the municipality.
  The Manager Community Services assumed duty on the 1st April 2020.
  The Acting Manager Technical Services was sourced from the Waterberg District Municipality. Shortlisting of the candidates for the position of Manager Technical Services was finalized in April 2020. There were delays with interviews due to lockdown and the municipality is busy with the screening process
  Motivation for the following critical positions has been approved: the researcher for the MPAC, the SCM Manager, three interns through Financial Management Grant, and the Divisional Head Budget and Treasury. The filling of these positions will improve the institutional capacity of the municipality to deliver services.

## Slide 44: OVERALL CONCLUSIONS
There is significant progress made on stabilizing the municipality following the Provincial Executive Council decision to intervene and the appointment of the intervention team.
This is to a large extent based on the support and cooperation by the key political and administrative teams in the municipality.
There is however an increase in senior management vacancies following the resignation of Senior Manager Planning and Economic Development and the Chief Financial Officer.
The MEC regularly updates Council on progress made on the intervention plan, as well as to encourage council and its structures to strengthen oversight to ensure good governance and accountability.

## Slide 45: LESSONS LEARNT FROM THE INTERVENTIONS
The role of “Administrator/Head of Intervention Team” versus the role of a municipal manager in terms of legislated functions in the case of Section 139(1)(b) should be legally defined.
The “Administrator” must be supported by a full-time team so as not to rely on municipal officials, and this requires budgets to appoint additional staff where required.
The success of an intervention depends on support from both Council and staff. Modimolle Mookgophong team faced a lot of threats and poor support from council, affecting ability to attain critical milestones.
It requires more than 12 months to get a dysfunctional municipality to be fully functional.

## Slide 46: RECOMMENDATIONS
It is hereby recommended that the Portfolio committee notes the report

## Slide 47: Thank You!