## Slide 1: GREATER TZANEEN MUNICIPALITY
PORTFOLIO COMMITTEE ON COOPERATIVE GOVERNANCE
03 November 2020

## Slide 2: CONTENTS
Governance and Institutional Capacity
Management
UIF
Cash Flow
Revenue Collections
Covid Expenditure
Provision of Basic Services
Performance Per Project
Progress Report on Petition from Letsitele Residents
Local Economic Development
Spatial Development Framework and IDPs
Eskom Debt

## Slide 3
1. Governance and Institutional Capacity

## Slide 4: FUNCTIONALITY OF COUNCIL
Council meets at least once per quarter save for special meetings as an when required.
Council must retain and improve administrative capacity in order to maintain the current level
of functionality.
Councillors receives all reports which serves in EXCO when they are dispatched for EXCO
meeting. This is done to give each councillor adequate time to prepare. After EXCO shall have
considerer the reports, they then serve in Council.
Council directly receives reports from Audit Committee and MPAC.
Councillors do provide oversight over administration, though there is still a room for
improvement
4

## Slide 5: ORGANS OF COUNCIL
EXCO holds at least one meeting each month and have special meetings whenever there is need.
Portfolio committees each hold a meeting at least once a month in terms of the year programme. It does happen that a portfolio committee not meet if the are no relevant issues to serve in Council.
Training and performance management of portfolio committees and committee members must be implemented to improve functionality.

## Slide 6: PARTICIPATION BY TRADITIONAL LEADERSHIP
Representatives of all seven traditional leaders in the municipality attend and participate in Council although participation is still at minimal levels.
The participation of the representatives of the traditional authorities are line with section 81 of the Municipal Structure Act, No. 117 of 1998.
The representative have been provided with tablets to ensure easy access to Council documents and are provided with out-of-pocket allowances amounting to R 2 756.00 for each representative.

## Slide 7: FUNCTIONALITY OF LOCAL LABOUR FORUM
Meetings of LLF are called each month in line with the Collective Agreement, however not all meetings are realised due to requests for postponement for one reason or another.
The participation by parties in the LLF is not as constructive as it should, meetings tend to be bogged down with non-substantives issues.
The is a need for clarification for the role of the LLF as well as the roles of each party within the LLF and the workplace.
Though there were work stoppages in the previous financial years, the was one in the current financial year it was about encashment of leave in August 2020.
Constant communication is being promoted to ensure that there is smooth relations between the employer party and unions.

## Slide 8: FILLING OF CRITICAL VACANCIES
All senior positions have been filled:
Municipal Manager : Mr B S Matlala
Chief Financial Officer : Ms P Makhubela
Director Corporate services : Mr W. Shibamba
Director Community Services : Mr A Nkuna
Director Electrical Engineering : Mr M S Lelope
Director Engineering Services : Mr C W Molokomme
Director Planning and Economic Development : Mr B M Mathebula

## Slide 9: FILLING OF CRITICAL VACANCIES
The municipality is gradually moving to achieve its equity targets in the various levels
of the organisation.
Attention will have to be focussed on new appointment to ensures that current gap
between the composition of staff complement and the set target is drastically reduced.
There is currently no disciplinary cases involving senior managers.

## Slide 10: TRAINING AND CAPACITY BUILDING
For 2019/2020 financial year 355 employees were trained on different training interventions , the training plan couldn’t be fully implemented due to lockdown regulations
The Municipality received mandatory grant from LGSETA amounting to R702 846.72, as well as discretionary grant amounting to R699 763.80
The implementation of 2020/2021 training plan in underway. The Municipality has taken officials at management and supervisory levels to change management training. Further implementation of the training plan will include taking employees through recognition of prior learning programme amongst others.
The training was conducted by DTM Consulting

## Slide 11: TRAINING AND CAPACITY BUILDING
Seven interns, who are beneficiaries of internship programme funded by National Treasury (Municipal Finance Management Internship Programme-MFMIP).
In 2019/2020 financial year, 25 employees of which 17 are women have been granted bursaries to pursue studies in various fields.
Capacity building programmes help close performance gaps which are due to lack of capacity in employees.

## Slide 12: 2. MANAGEMENT

## Slide 13
Municipality | Audit Opinion 2016/17 | Audit Opinion 2017/18 | Audit Opinion 2018/19
GTM | Unqualified | Qualified | Qualified
AUDIT OPINION: LAST THREE FYS

## Slide 14: STRATEGIES TO IMPROVE AUDIT OUTCOMES (GTM)
Weekly audit steering committee with management
Development and Implementation of audit action plan
The review of AFS was done
Annual review of all critical council polices
Mopani water debt repayment

## Slide 15: AUDIT FINDING FOR THE PAST 3 YEARS
Year | No of Finding | No Resolved | %
2016/17 | 67 | 53 | 80%
2017/18 | 43 | 28 | 65%
2018/19 | 25 | 17 | 68%

## Slide 16: MAJOR/KEY AUDIT FINDINGS 2018/2019
Audit findings | Progress to Date
Inappropriate estimation of useful lives of assets | Implemented
Inaccurate Performance Reporting | Implemented
Discrepancies in SCM Processes | Implemented

## Slide 17: FUNCTIONING OF GOVERNANCE STRUCTURES
 | YES/NO
Audit Committee | YES
Internal Audit | YES
Audit Steering Committee | YES

## Slide 18: 3.UIF

## Slide 19: UIF - AWAITING AGSA AUDIT for 19/20:
Irregular Expenditure for 2019/2020 amounts to R24 862 274.
Fruitless and Wasteful Expenditure for 19/20 amounts R3 717 605.32
Unauthorized Expenditure for 19/20 – None identified as of current date

## Slide 20: STATUS OF UIF INVESTIGATIONS
Current :
Waiting council write off and also taken for investigation to MPAC and Financial misconduct Board currently investigating
18/19 MPAC report concluded –some items referred to FMC-Board
Unauthorized Expenditure :
Was only accounting asset deprecation accounting journals for Annual financial statements .
There was no actual cash outflow or any external transactions

## Slide 21: Register of Irregular Expenditure 2019/20:
3. COMP NAME: | Theuwedi Trading Enterprise- R 7 789 879,17
SEC32: Finding | Irregular Expenditure : Wrong CIDB Criteria used on Bid Advert in 2017- not a construction project but and landfill site waste disposal treatment project .
Action plan Taken to resolve the finding : | 3 year Contract ends in Dec 2020, thus irregular expenditure will on contract end date This is landfill waste disposal operation project will be advertised correctly and not construction on CIDB The new bid appointed is complying audited in prior year.
4. COMP NAME: | Eternity star investment- Mopye High School access road- R3 679 012.16
SEC32: Finding | Irregular Expenditure : lowest priced bidder not appointed
Action plan Taken to resolve the finding | Original Appointed Contractor withdrew from project in 2019 , the project engineer recommended that bid evaluation appoint a contractor who will finish the road at market related priced on BOQ - a risk assessment was done.

## Slide 22: THE UIF BELOW IS CATEGORIZED INTO THE FOLLOWING:
1. Irregular Expenditure from prior years till 18/19- R 32 826 799
2. Unauthorized Expenditure from prior year 18/19 –
(only accounting asset deprecation journals no actual cash outflow): R 83 025 989
3. Fruitless ad Wasteful Expenditure from 18/19 - R 11 628 191

## Slide 23: Register of Irregular Expenditure 2019/20:(Con..)
4. COMP NAME: | Eternity star investment- Mopye High School access road- R3 679 012.16
SEC32: Finding | Irregular Expenditure : lowest priced bidder not appointed as per Ag finding in audit .
Action plan Taken to resolve the finding | Original Appointed Contractor withdrew from project in 2019 , the consulting engineer appointed to oversee the MIG road project. Consulting Engineer recommended that bid evaluation appoint a contractor who will finish the road at market related priced on BOQ - a risk assessment was done.

## Slide 24: Register of Irregular Expenditure 2019/20:(Con..)
5. COMP NAME: | Mulati Access Road: Tshiamiso Trading 135 : R 12 839 312,76 Letsopa projects : R 95 337,55
SEC32: Finding | Irregular Expenditure: no adequate Risk assement taken to award bidder 2 projects in similar periods on evaluation criteria
Action plan Taken to resolve the finding : | A risk assessment are currently being undertaken by project engineers on all bids: contractor’s capacity BOQ pricing- mathematical accuracy
Total 19/20 Irregular EXP | R 24 862 274,29

## Slide 25: Register of Fruitless Expenditure 2019/20:
1. COMP NAME: | Forest Fig Properties - NYDA Office Rental: R 2 262. 80
SEC32: Finding | Fruitless Expenditure: Interest –invoices submitted late by lessor
Action plan Taken to resolve the finding : | Meetings held with lessor to submit invoices timeously ,this has resolved the matter
2. COMP NAME: | Compensation Commission: R 70 751,90
SEC32: Finding | Fruitless Expenditure: Interest – invoice payment arrangement interest not reduced by Dept. of Labour
Action plan Taken to resolve the finding : | Meetings held, Payment arrangement made but all debt has been paid up to date

## Slide 26: Register of Fruitless Expenditure 2019/20:(Con…)
3. COMP NAME: | ESKOM -Bulk electricity Purchases bill R 2 556 264.48
SEC32: Finding | Fruitless Expenditure: Cashflow constraints
Action plan Taken to resolve the finding : | Current electricity Tariff review and billing system audit with DBSA to improve meter nd revenue data integrity ,Energy loss audit undertaken in 2019. Current independent Debt collection process effected with new comp appointed 2019 Meter reading and credit control more stringent Pilot project to read large farm and industrial meters remotely to mitigate Electricity theft and bridging

## Slide 27: Register of Fruitless Expenditure 2019/20: (Con…)
4. COMP NAME: | Auditor General : R 5 580.83
SEC32: Finding | Fruitless Expenditure: Interest – 1 invoice submitted late form AG from Dec 2019
Action plan Taken to resolve the Finding : | Meetings held with AGSA when sending invoices to include: CFO and CC: CFO secretary, Expenditure manager and account creditor
TOTAL Fruitless Expenditure 2019/20: | R3 717 605.32

## Slide 28: New defied fruitless and Wasteful expenditure identified in 18/19 AGSA audit:
4. COMP NAME: | Moruji Access Road : Readira Matlala/Nyapele JV : R5 180 296,49
SEC32: Finding | Fruitless Expenditure: Contactor in 2016/17 won court order to re-advertise road Original engineer consultant withdrew from project
Action plan Taken to resolve the Finding: | Road has been competed to date Costs were re-worked by new Engineer Makasela Consulting to market related priced on BOQ- ( P & G’s on BOQ )
TOTAL addional Fruitless Expenditure 2018/19 : | R5 180 296,49

## Slide 29
4. Cash Flow

## Slide 30
Revenue Estimates July to Sep 2020/2021
Revenue Estimates | July '20 | Aug '20 | Sep '20
Opening Balance 01 July 2019 | 70 215 765 | 108 892 483 | 104 140 687
Investment Recalled | - | 10 000 000 | -
Equitable Share | 186 277 000 | - | 
MIG | 39 500 000 | - | 32 662 000
INEP | - | - | -
FINANCE MANAGEMENT GRANT | - | 2 000 000 | 
EPWP | - | 1 784 000 | 
DBSA Loan Received | - | - | -
IIPSA Grant | - | - | -
Revenue - Customer Collections | 45 784 799 | 45 031 204 | 60 449 684
VAT refund | 1 461 694 | - | 13 970 239
Licencing | - |  | 
Other income | - |  | 
Forecast Monthly Income | 343 239 258 | 167 707 687 | 211 222 610
Cash Flow July to Sep 2020/21

## Slide 31
Cash Flow July to Sep 2020/21(Con…)
Expenditure Estimates | July '20 | Aug '20 | Sep '20
Investments made | 50 000 000 | - | -
Salaries | 17 686 404 | 17 352 459 | 17 993 720
Ward committees +EPWP | 498 375 | 498 375 | 495 375
Councillors Remeneration |  |  | 
Other Creditors | 5 258 617 | 697 812 | 968 500
Third Parties | 7 126 583 | 7 072 833 | 7 032 015
pension fund,SARS ,Med Aid | 5 935 039 | 6 191 441 | 6 776 237
Security/Speed Camera | 1 212 753 | 1 212 753 | 1 212 753
MIG PROJECTS | 13 138 736 | 15 831 406 | 6 618 377
INEP PROJECTS | - | - | -

## Slide 32
Cash Flow July to Sep 2020/21(Con…)
Expenditure Estimates | July '20 | Aug '20 | Sep '20
DBSA PROJECTS | 1 529 192 | 2 276 561 | 1 510 033
Eskom - | 118 480 519 | - | 10 000 000
FUEL | 1 275 222 | 1 125 270 | 865 274
retention to contractors | - | - | 327 000
Photocopier Machines | 252 101 | 252 101 | 252 101
Legal costs | 689 256 | 1 085 789 | 1 818 906
Water Tankers +Plant hire | 625 320 | 375 524 | 542 720
Consultants | 2 120 250 | 1 052 365 | 892 760
Telephone | 92 520 | 93 260 | 91 452
Travelling | 22 475 | 19 742 | 25 278

## Slide 33
Expenditure Estimates | July '20 | Aug '20 | Sep '20
Inventory Stores | - | 1 250 273 | 927 860
Expenditure on events | 4 352 | 7 253 | 3 250
Loan repayment | 319 651 | 319 651 | 3 032 748
AG Audit | - | - | -
Waste Management | 2 275 235 | 2 275 235 | 2 275 235
limpopo Provincial Government | 4 966 505 | 4 576 897 | 4 461 861
VAT Payment | 837 670 | - | 761 518
Crane truck purhcase | - | - | -
Repairs and mainatance |  | - | 1 165 283
Forecast Monthly expenditure | 234 346 775 | 63 567 000 | 70 050 255
Running bank balance month end | 108 892 483 | 104 140 687 | 141 172 355
Cash Flow July to Sep 2020/21(Con…)

## Slide 34: 5. Revenue collections

## Slide 35: REVENUE COLLECTION
Revenue | March 20 | April 20 | May '20 | June '20 | Total
Revenue - Customer Collections | 60 629 077 | 39 414 546 | 85 645 959 | 47 005 849 | 689 308 091
VAT refund |  |  | 6 351 617 | 102 240 | 33 773 817
Licencing | 3 917 472 | 233 255 | - | 7 423 399 | 51 140 568
Other income | 631 220 | 2 571 242 | 75 199 | 5 753 268 | 40 201 143

## Slide 36: SPECIFIC RECOMMENDATIONS ON REVENUE ENHANCEMENT AND COLLECTION
Settle discounts are being offered to customers in arrears (30%-45%) discounts
based on debt payment pattern of each consumer to enhance cash flow
Audit of electricity meters on the ground completed
Audit of water meters new developed areas where completed
Major refurbishment of electricity substations underway
Electricity tariff review underway
Revenue base of municipality being investigated to enhance income

## Slide 37: INDIGENT POLICY
The Municipality has the Indigent Policy in place and the policy is reviewed annually
The Indigent Policy is intended to guide the municipality to improve the lives of indigents and to improve access to Free Basic services.
There are 26 367 registered indigents in the process of validating all current indigents.

## Slide 38: SUPPORT PROVINCIAL AND NATIONAL GOVERNMENT PROVIDING TO THE MUNICIPALITY AND GRANT SPENDING
Assistance with the review of the Annual Financial statements from Provincial treasury
Assistance with the assessment of the budget from Provincial and National Treasury
Monthly District and Provincial MIG forums led by COGHSTA

## Slide 39: 6. COVID EXPENDITURE

## Slide 40: COVID EXPENDITURE TZANEEN LOCAL MUNICIPALITY
COST | COMMODITY/SERVICE
R 171,30 | HAND SANITIZERS
R 11 460,00 | Non-contact thermometers
R 19 100,00 | Non contact thermometers
R 93 500,00 | surgical masks
R 71 739,00 | 5l hand sanitiser
R 16 522,00 | 500ml hand sanitiser
R 4 000,00 | disposable gloves
R 20 000,00 | surgical masks
R 35 000,00 | COVID-19 Loud Hailing Maake Plaza

## Slide 41: COVID EXPENDITURE TZANEEN LOCAL MUNICIPALITY: (Con..)
R 49 560,00 | TENT AND TOILET FOR ROAD BLOCK COVID-19
R 289,50 | Plastic Bags For Pack Food For Covid 19
R 1 315,49 | Drums And Sanitizer For Covid 19
R 27 200,00 | 25l Surface Disinfectants
R 10 000,00 | 3ply Cloth Masks
R 13 565,00 | Heavy Duty Face Shieds
R 90 300,00 | Toilet And Tent Covid 19
R 70 000,00 | Awareness At Maake Plaza
R 24 500,00 | 500ml Hand Sanitiser
R 5 750,00 | Surgical Masks
R 18 000,00 | Non-contact Thermometer

## Slide 42: COVID EXPENDITURE TZANEEN LOCAL MUNICIPALITY: (Con..)
COST | COMMODITY/SERVICE
R 352 619,40 | Sanitasation Of Facilities And Offices
R 12 000,00 | Non-contact Thermometer
R 49 130,00 | Safety Screens Testing Grounds
R 1 347,00 | Masks Ffp1
R 5 000,00 | 500/2kg Sanitiser Alco Base Wipes
R 1 739,00 | 1lt Spray Bottles

## Slide 43: COVID EXPENDITURE TZANEEN LOCAL MUNICIPALITY: (Con..)
R 18 951,60 | Disinfectants Cleansing Wipes 2kg Alco Base
R 35 000,00 | Covid 19 Awareness 1-15 Jun
R 29 509,65 | Disinfectant Cleansing Wipes 5kg 1000sheets
R 4 108,70 | Work Light Energiser
R 900,00 | Aa 6x10 Batteries
R 13 750,55 | 3ply Cloth Masks
R 1 305,85 | Cleaning Materials Covid-19
R 8 000,00 | Tents For Hiring During Roadblock
R 35 000,00 | Covi-19 Awareness - Usave/Nkowankowa Dan
R 89 124,00 | Covid-19 Sanitization Of Gtm Offices
R 640 055,00 | OVERTIME TRAFFIC OFFICERS (Road Blocks)
R 1 879 527.84 | TOTAL As At Sept 2020

## Slide 44: 7. PROVISION OF BASIC SERVICES

## Slide 45: GTM BUDGET SPENDING July-Sept 2020
YEAR | % OF OPEX BUDGET SPENT TO 1 JULY TO SEPT 2020’ | % OF CAPITAL BUDGET SPENT1 JULY TO SEPT 20’
2020/21 | 13.16% | 21.65%

## Slide 46: ANNUAL OPERATING, CAPITAL AND GRANT BUDGET 20/21
Revenue Source | Allocation 2021/20 | Expenditure 2020/21 | Percentage
INEP | R10 000 000 | R0 | %0.00
EPWP | R7 134 000 | R1 236 137 | %17.32
MIG | R93 619 000 | R36 278 626 | %38.75

## Slide 47: GRANTS THAT WERE SURRENDERD TO NATIONAL TREASURY IN THE PAST 5 YEARS
YEAR | ROLL OVER APPLIED | ROLL OVER APPROVED | ROLL OVER NOT APPROVED
2017/2018 | R2 724 847 | - | R 2’724’847
2018/2019 | R 4 950 614 | R 4 950 614 | Nil
2019/2020 | R 18 007142 | R5 432 664 | Nil
THERE ARE NO GRANTS STOPPED DUE TO POOR PERFORMANCE OF CONTRACTORS |  |  | 

## Slide 48: GRANTS SPENDING AS AT 30 JUNE 2020
Description | YTD receipt | YTD spent | Total unspent | % Spent from receipt
EQUITABLE SHARES | 383,567,000 | 383,567,000 | 0 | 100.00%
FMG | 2,145,000 | 1,901,951 | 243,049 | 88.67%
INEP | 20,000,000 | 14,567 733 | 5,432 664 | 72.83%
MIG | 94,263,000 | 94,112 000 | 151 000 | 99.83%
EPWP | 5,749,000 | 5,749,000 | 0 | 100.00%
SETA | 1,083,116 | 793,361 |  | 73.25%
IIPSA | 10,000,000 |  |  | 0.00%

## Slide 49: SPECIAL BUDGET ADJUSTMENT PASSED ON 23 SEPT 2020 BY GTM COUNCIL
Descript | Approved Budget | Changes | Adjusted Budget
Revenue Budget | 1 492 904 434 | 96 542 000 | 1 589 446 434
Expenditure Budget | 1 360 799 620 | 83 042 378 | 1 443 841 998
Capital Budget | 130 738 050 | 24 309 720 | 155 047 770

## Slide 50: SPECIAL BUDGET ADJUSTMENT REASONS:
a) Government Gazette 43450 issued by National Treasury on 24 June 2020 in which Council is informed that the equitable share allocation will be increased from R414 million to R506 million and INEP grant reduced from R15 million to R10 million
b) Electricity tariffs as approved by Council on 29 July 2020, resolution no A2- FOR additional Electricity tariff increases of 1,72% amounting to R9.5million included
c) DBSA loan projects also readjusted in terms of loan conditions
d) Own income funding for : rental of office space (Covid compliance, roof fixing, purchasing of plants and IT network improvement

## Slide 51: SERVICE DELIVERY BACKLOG
Service Type | Total Households | Backlog | Percentage
Water service | 108 926 | 26 373 HH | 25.1%
Sanitation service | 108 926 | 1 836 HH | 1.7%
Electricity service | 108 926 | 2 366HH | 2.2%
About 239 households were connected for the first time to the electricity grid in the previous financial year

## Slide 52: WATER SUPPLY INTERRUPTIONS
Water supply interruptions in town and township occur because of insufficient bulk water sources.
DWS has reduced the volume of water from Ebenezer dam to Great Letaba river from 1.6m3 to 0.6m3 per second and that affects the level of Tzaneen Dam adversely
Lepelle Northern Water has reduced the volume of purified water supply to Polokwane and this affects water supply to Haenertzburg Village
The Municipality is implementing water tariffs which includes penalties in order to discourage high consumption.
Majority of villages within Greater Tzaneen Municipality rely on boreholes which are not a realizable source of water supply due to breakdowns, draught, power outages, theft and vandalism

## Slide 53: DETERIORATED ROADS FOR RECONSTRUCTION OR REHABILITATION
Road | Number | Classification | Distance
Moruji-Khetlhakong | D3184 | Provincial | 6km
R36-Mohlava Headkrall | D3763 | Provincial | 2km
Mohlava Cross-Moime Motseteng | D4157 | Provincial | 7km
Senakwe-Morapala | D3199 | Provincial | 12km
Thapane-Deerpark | D3175 | Provincial | 10km

## Slide 54: ACCELERATION OF PROVISION OF BASIC SERVICES
GTM allocates budget for the upgrading of roads from gravel to surfacing on annual basis
The Water Services Authority should consider upgrading the bulk water infrastructure to accommodate population growth e.g water and sewer plants
Acquiring alternative sources of funding for rollout of infrastructure development programmes

## Slide 55
8. Performance Per Project

## Slide 56
2019/20 INEP PROJECTS
Electrification Project
Project Name | Project Progress | Challenges
Motseteng | Physical Construction: 95% | Capacity constraints on Eskom network resulting in delays on the approval of designs & Energizing of households. Covid-19 Lockdown affected the execution of electrification projects
Lenyenye | Completed: 100% | 
Ntsako | Physical Construction: 97% | 
Mulati | Physical Construction: 97% | 
Mohlaba Cross | Physical Construction: 82% | 
Mavele | Physical Construction: 90% | 
Tshamahansi | Physical Construction: 50% | 

## Slide 57
2019/20 CAPITAL PROJECTS DBSA
Municipal Electrical Infrastructure
Project Name | Project Progress | Challenges
Install 2x20MVA Transformers Tzaneen | Physical Construction: 64% (Multi-Year Project) | Insufficient budgets available to fully execute scope. Resulting in scope reductions. Material Price Escalations Covid-19 Lockdown caused delays in the implementation of capital projects
Rebuilding 14 km of Overhead lines | Physical Construction: 87% | 
Installation of Highmast R36 Khujwana | Physical Construction: 77% | 
Installation of Streetlights R71 (Ashade) | Physical Construction: 95% | 
Replacement of Miniature Substation | Physical Construction: 100% | 
Installation of prepaid meters | Physical Construction: 100% | 

## Slide 58
2019/20 MIG PROJECTS
Project Name | Brief Scope of Works | Status & Physical Progress | Comments
Upgrading of Lenyenye Taxi Rank | Construction of 5 market stalls, taxi parking bays and civil services | 95% | The Contractor has completed the works and Practical Inspection was done on the 15/10/2020
Upgrading of Mulati Access Road | Upgrading of 5.8kms from Gravel to Interlocking Paving Blocks and related Stormwater management systems | N/A | Original Contractor was terminated. Project has been redesigned, and advertised is now on adjudication.
Construction of Mawa Block 12 Low level bridge | Construction of a 6No. 1500mm x 900mm precast portals culverts low level bridge, continuously reinforced concrete surfacing | 95% | The Contractor has completed Construction of the works. Practical Completion Inspection was conducted and the Contractor is attending to the Snag List.
Upgrading of Relela Access Road | Upgrading of 3km road from gravel to Interlocking Paving Blocks and related Stormwater management systems | 93% | The contractor has paved 2.5km of the road and they are currently busy with Construction of the remaining 500m paving, drains and edge beams.
Mmatapa to Leseka Access Road | Upgrading of 3km road from gravel to Interlocking Paving Blocks and related Stormwater management systems | 60% | The contractor experience delays during the rainy season which affected the completion date
Mopye High School Access Road | Construction of 2 km access road. Laying of 80mm interlocking paving blocks where gradients are less than 16% Casting Construction of Retaining walls (Gabion and masonry) Installation of road furniture | 72% | The contractor has completed 1.5km of paving (250m of concrete slab and of 1.25km concrete paving) and the are currently busy with layer works.
Nelson Ramodike High School Access Road | Upgrading of 5.6km gravel road to paving blocks and related Stormwater management systems | 63% | The contractor has paved 1km.They are busy with kerbing, paving and construction of V-drains, Construction of Layer works from chainage 2.5km to 5.6kms.

## Slide 59
2019/20 MIG PROJECTS
Project Name | Brief Scope of Works | Status & Physical Progress | Comments
Nelson Ramodike High School Access Road | Upgrading of 5.6km gravel road to paving blocks and related Stormwater management systems | 63% | The contractor has paved 1km.They are busy with kerbing, paving and construction of V-drains, Construction of Layer works from chainage 2.5km to 5.6kms.
Upgrading of Codesa to Hani Street | Upgrading of Nkowankowa Codesa street to Hani Street from gravel road to a paved road. This road is 1,73km long and 6m wide with the following pavement structure: Surfacing : 80mm Interlocking blocks on a 25mm Bedding sand | N/A | Original Contractor was terminated. Project has been redesigned, and advertised is now on adjudication.
Paving of Moseanoka to Cell C Pharare Internal Streets in Ward 28 | Construction of approximately 8.7km from gravel to paving blocks with stormwater management | Project is on Adjudication Stage | None
Paving of Risaba, Mnisi, Shando, to Driving School in ward 5 | Construction of approximately 6.2km from gravel to paving blocks with stormwater management | Project is on Adjudication Stage | None
Paving of Main road from Nduna, Mandlakazi, Efrika, Zangoma, Mpemyisi to Jamba Cross Internal Street (in ward 13) and Nwamitwa Bridge via Nhlengeleti School to Taxi Rank, Clinic via Lwandlamoni School to Nwamitwa/Mandlakazi Road (in Ward 12) | Construction of approximately 11km from gravel to paving blocks with stormwater management | Project is on Adjudication Stage | None
Erection of Apollo Lights | Construction and energizing of two(2) High Must Lights is Dan Village | 24% | The contractor is busy with delivery of the high mast lights. The Municipality is in the process of paying Eskom the connection fee.
All Projects are Implemented on multi year approach

## Slide 60: CURRENT PROJECT CHALLENGES
The current problematic projects are Mulati Access Road and Codesa to Hani Street both implemented by one Contractor. The challenge affecting the projects relate to contract amount dispute
Contracts were terminated and Court procession is set for 5 November to solicit an appropriate solution

## Slide 61: Project Schedule for current project challenges
Upgrading of Nkowankowa Codesa to Hani Street
No | Activity | Start Date | End Date | Duration(Days)
1. | Condition Assessment | 18/02/2020 | 19/02/2020 | 02
2. | Revise Project Close-Out report | 20/02/2020 | 21/02/2020 | 02
3. | Geotechnical Investigation | 24/02/2020 | 28/02/2020 | 05
4. | Review designs and drawings | 09/03/2020 | 11/03/2020 | 03
5. | Develop detailed Bill of Quantities and Cost Estimated | 12/03/2020 | 13/03/2020 | 02

## Slide 62: Project Schedule for current project challenges
Upgrading of Nkowankowa Codesa to Hani Street(Con..)
No | Activity | Start Date | End Date | Duration(Days)
6. | Consideration of designs and cost estate by GTM | 16/03/2020 | 17/03/2020 | 02
7. | Final Designs, Drawings | 18/03/2020 | 19/03/2020 | 02
8. | Tender Documentation | 23/03/2020 | 25/03/2020 | 03
9. | Tender Advert | 06/04/2020 | 05/05/2020 | 30
10. | Tender Awarding | 06/05/2020 | 05/08/2020 | 90
11. | Project Administration | 17/08/2020 | 15/12/2020 | 120
12. | Project Close-Out | 17/12/2020 | 17/12/2020 | 01

## Slide 63: Project Schedule for current project challenges
Upgrading of Mulati Access Road
No | Activity | Start Date | End Date | Duration(Days)
1. | Condition Assessment | 28/01/2020 | 29/01/2020 | 02
2. | Development Project Close-Out Report | 30/01/2020 | 05/02/2020 | 05
3. | Geotechnical Investigation | 06/02/2020 | 12/02/2020 | 05
4. | Review designs and drawings | 19/02/2020 | 21/02/2020 | 03
5. | Consideration of designs and cost estimate by GTM | 27/02/2020 | 28/02/2020 | 02

## Slide 64: Project Schedule for current project challenges
Upgrading of Mulati Access Road
No | Activity | Start Date | End Date | Duration(Days)
6. | Consideration of Designs and Cost Estimate by GTM | 27/02/2020 | 28/02/2020 | 02
7. | Final Designs Drawings | 02/03/2020 | 04/03/2020 | 02
8. | Tender Documentation | 09/03/2020 | 11/03/2020 | 03
9. | Tender Advert | 23/03/2020 | 24/04/2020 | 30
10. | Tender Evaluation and Awarding | 27/04/2020 | 28/07/2020 | 90
11. | Project Administration | 10/08/2020 | 12/04/2021 | 240
12. | Project Close-Out | 16/04/2021 | 16/04/2021 | 

## Slide 65
10. Progress Report On Petition From Letsitele Residents

## Slide 66
Introduction
A petition was received from residents of Letsitele and subsequent to that Greater Tzaneen Municipality appeared before the Parliamentary Portfolio Committee of COGTA on the 24th June 2020. the phenomenon of bush mechanics evolved with the opening of spare shop.
Purpose of the Report
Purpose of the report is to give feedback to the Parliamentary Portfolio Committee for COGTA on progress since 24 June 2020.
What has been done?
In our quest to address the issues raised in the petition, the following were done:
Roaming Cattle
An inspection was conducted by a designated Environmental Management Inspector and Traffic Officer. The feeder area for Letsitele town is agricultural farms, which in terms of geographical positioning are adjacent to the town and the following villages are at the periphery:

## Slide 67
Mariveni situated at a distance of about of about 3km;
Muati Mariveni situated at a distance of about 7km;
Mafarana situated at a distance of about 5KM;
Ntsako situated at a distance of about 5,8km and
Nkambako situated at a distance of abut 13km;
Due to the nature of the complaint, the size of the town and the traffic volumes in that area, permanent allocation of a traffic officer under current financial climate is not possible. We however have identified spotters with the solid waste division stationed at Letsitele. They are to immediately report any sighting of cattle in town to the Assistant Superintendent ( Law Enforcement). Arrangement will then be made to impound the cattle.
Informal Mechanics
During alert level 5 and 4 there were limited activities in Letsitele town, only the supermarket, butchery and bank were open. Alert level 3 has resulted in the re-opening of most businesses, the spares shop and ultimately the return of the informal mechanics.

## Slide 68
An inspection was conducted after appearing before the portfolio committee. The following was ascertained:
That operations of informal repairs have resumed;
That the numbers of the informal mechanics are still the same;
Are the operations still giving rise to a nuisance? And
That they are still trading from the same spot.
The mechanics are still three in number. They have since been issued with drip trays to prevent pollution. A refuse receptacle has also been made available to prevent littering in that area. Continued monitoring will be done to ensure that the informal mechanics do not operate their trade in a manner the gives rise to a nuisance.
The process of relocating them has not been initiated yet since this action has financial implications.
What the future plans?
Training of officers from each user division as peace officers so that they can, when there are contraventions issues fines has been temporarily put on hold due to restriction. The process of identifying contraventions and submitting proposed fines to be imposed to the Tzaneen Magistrate to approve and set codes is underway

## Slide 69: . LOCAL ECONOMIC DEVELOPMENT

## Slide 70: LED PROJECTS WHICH NEED SUPPORT
No | Name of Project | Progress | Amount
1 | Greater Tzaneen Farmers Facilitation Centre | Business Plan Completed | R15 000 000.00
2 | Greater Tzaneen Waste Management | Business Case Completed | R 1 200 000.00
3 | Agricultural Business Incubator | Business Plan Completed | R21 771 734.00
4 | Improving electrical capacity in industrial areas | Project in the LED Strategy | TBC
5 | Improving water service delivery | Project in the LED Strategy | TBC
6 | Fixing Roads in Industrial areas | Project in the LED Strategy | TBC
7 | Sepakoe Tea Estate | Project in the LED Strategy | TBC
8 | Honey Production | Project in the LED Strategy | TBC

## Slide 71: JOB CREATION TARGETS
NO | INITIATIVES | TARGET | JOBS CREATED
1. | CWP | 2200 | 2168
2. | EPWP | 502 | 1062
 | TOTAL | 2702 | 3200
The contracting service providers cater for women and youth employment

## Slide 72
11. Spatial Development Framework and IDPs

## Slide 73: REALISING THE GOALS OF LIMPOPO DEVELOPMENT PLAN AND NATIONAL DEVELOPMENT PLAN
NO | KEY FOCUS AREA | KPI FOR REPORTING | PROGRESS BY MUNICIPALITY
1. | Spatial Framework | Spatial Development Framework tabled to council | The SDF was approved by Council
2 | SPLUMA Implementation | Number of tribunal sittings held | One (1) meetings held for 2019/20FY
3 | SPLUMA Implementation | Number of land development applications adjudicated by the tribunal | Nine (9) applications received for 2019/20 FY
4 | SPLUMA Implementation | Number of SPLUM By-laws gazetted(enlist) | One (1) By- Law promulgated

## Slide 74
12. Eskom Debt

## Slide 75: ESKOM DEBT
The Municipality was owing Eskom a balance of R118 480 518.95 and the balance was settled by year end 2019/20. Paying Eskom puts pressure on the finances of the municipality and therefore from time to time the Municipality will lack behind. In this regards we will then have to make payments arrangements with Eskom.

## Slide 76
THANK YOU