Presentation to the Portfolio

Committee on

Communications:

2019/20

Annual Report

04

November

2020

PRESENTATION

OUTLINE

▪

Overview

▪

Progress

against

Audit

Action

Plan

▪

Auditor

-

General’s

Audit

Outcomes

▪

2019

/

20

Financial

Performance

▪

Significant

Achievements

during

the

Reporting

Period

▪

Arears

of

under

-

achievement

during

the

reporting

period

▪

Programme

Performance

for

2019

/

20

,

with

specific

focus

on

targets

not

achieved

OVERVIEW

❑

53

%

of

planned

targets

achieved

with

99

%

expenditure

❑

2

AG

Findings

in

Audit

Report

in

2018

/

19

vs

2

in

2019

/

20

❑

14

AG

Findings

in

Management

Letter

in

2018

/

19

vs

8

in

2019

/

20

❑

Previous

cases

of

irregular

expenditure

amounting

to

R

393

thousand

were

investigated

and

condoned

by

National

Treasury

during

the

financial

year

.

❑

The

Department

achieved

an

unqualified

audit

opinion

for

2019

/

20

financial

year

.

❑

At

the

end

of

the

financial

year

the

Department

addressed

94

%

of

audit

findings

raised

by

the

AGSA

.

| Finding | Details | Action Plan |
| --- | --- | --- |
| Supply Chain Management | Possible splitting of procurement of goods. | - Procurement of DTT promotional items split - The promotional item has been included in the procurement plan and a tender process will be followed. - Irregular expenditure to be investigated and consequence management to take place where necessary. |
|  | Procurement of assets not included in the procurement plan | - Oversight by management where a procurement plan was not updated accordingly. - Laptops were planned to be procured through SITA and orders were cancelled in the new FY due to suppliers unable to deliver. Departmental vehicles were procured through a transversal contract (RT-57). - Procurement was made following necessary SCM process. - Internal controls enhanced in SCM unit to ensure that a checklist put in place. |
|  | Approved reasons for deviation not justifiable. | - Suppliers not given sufficient time to respond to RFQ resulting in lack of proper planning. Deviation reasons not justified. - The SCM controls strengthened for requests to be submitted to SCM unit at least 7 days before event. - Irregular expenditure to be investigated and consequence management to take place where necessary. |

FINDINGS IN THE 2019/20 RELATING TO NON-

COMPLIANCE

BUDGET AND EXPENDITURE

|  | 2019/20 |  |  |  | 2018/19 |  |
| --- | --- | --- | --- | --- | --- | --- |
| Appropriation per programme R'000 | Final Appropriation | Actual Expenditure | Variance | % Spent | Final Appropriation | Actual Expenditure |
| Administration | 63 710 | 57 784 | 5 926 | 90,7% | 72 265 | 71 984 |
| Communications Policy, Research and Development | 14 412 | 7 185 | 7 227 | 49,9% | 10 646 | 9 162 |
| Industry and Capacity Development | 37 504 | 26 341 | 11 163 | 70,2% | 45 307 | 20 568 |
| Entity Oversight | 4 657 465 | 4 640 328 | 17 138 | 99,6% | 1 388 028 | 1 386 407 |
| Total | 4 773 091 | 4 731 637 | 41 454 | 99,1% | 1 516 246 | 1 488 121 |
|  | 2019/20 |  |  |  | 2018/19 |  |
| Economic Classification R'000 | Final Appropriation | Actual Expenditure | Variance | % Spent | Final Appropriation | Actual Expenditure |
| Compensation of employees | 86 791 | 61 700 | 25 091 | 71,1% | 80 916 | 73 643 |
| Goods and services | 48 835 | 34 148 | 14 688 | 69,9% | 52 902 | 32 051 |
| Transfers and subsidies | 1 430 318 | 1 430 238 | 80 | 100,0% | 1 381 768 | 1 381 748 |
| Payments for capital assets | 7 147 | 5 480 | 1 667 | 76,7% | 660 | 638 |
| Payment for financial assets | 3 200 000 | 3 200 071 | -71 | 0,0% | - | 40 |
| Total | 4 773 091 | 4 731 637 | 41 454 | 99,1% | 1 516 246 | 1 488 121 |

Overall spending at 31 March 2020 was 99% of the allocated budget. R3.2 billion paid to SABC as financial asset.

Communications Policy – Underspending mainly due to delays in the implementation of activities relating to the audio-visual and digital content strategy developed for the 4IR and Broadcasting Amendment Act. This resulted in savings in travelling, consultations, venues and facilities cost.

Industry & Capacity Development - Underspending mainly due to few outreach programmes implemented for the DTT project because of changes in the delivery model. This resulted in savings in travelling, rental and hiring, advertising and promotional items cost.

EXPENDITURE PER ECONOMIC

CLASSIFICATION

❑

COE

–

Underspending due to

posts that were not filled during the financial year.

❑

Goods & Services

–

Underspending mainly due to projects not implemented and

overall reduction in international and local travel and other items related to the

projects.

❑

Capital Assets

–

Delays in the delivery of orders placed for laptops

by suppliers

which was affected by the COVID

-

19

lockdown.

PERFORMANCE

INFORMATION

PERFORMANCE TRENDS 2018

-

19

&

2019

-

20

73

%

27

%

Overall Annual Performance of 2018

-

19

Achieved

Not achieved

53

%

47

%

Overall Annual Performance of 2019

-

20

Achieved

Not achieved

SIGNIFICANT ACHIEVEMENTS  DURING THE REPORTING PERIOD (1)

The Department achieved 53% of its planned 2019/20 annual targets (10 out of 19) while spending 99.3% of it budget allocation

- Intergovernmental Relations and Stakeholder Management

  - Worked closely with the DTPS to develop and advance the Country Position Paper for the International Telecommunications Union – World Radio Conference - 2019 (ITU-WRC-19)

  - Also worked with the DTPS to develop and advance the Country Position Paper at the 5th Brazil, Russia, India, China and South Africa (BRICS) Ministers of Communications Meetings in Brazil.

- Enterprise Development

  - The Department implemented the Enterprise Development Programme with the intention to empowerment of SMMEs in creative industries and audio-visual content industries (training & capacity building) and to coordinate and facilitate digital entrepreneurship environment in creative industries & audio-visual content industries.

# SIGNIFICANT ACHIEVEMENTS  DURING THE

REPORTING PERIOD (2)

- Broadcasting Digital Migration Programme

  - A revised delivery model was completed and approved by Cabinet on 13 December 2019, paving a way for the finalisation of the migration process pending the available required financial resources.

  - The recommendations include reprioritisation and sequencing of the BDM Programme in lieu of High Demand Spectrum release as well as making use of voucher system for qualifying indigent households.

- Reconfiguring the DTPS & DOC

  - Both Departments participated in the NMOG process and worked very closely together on joint projects as well as undertook resource sharing from both a financial and human resource perspective. Jointly developed the DCDT strategy as well as the start-up structure for the DCDT which was approved by the DPSA. The transfer of employees from the DCDT and the DOC to the newly established DCDT was also concluded.

# AREARS OF UNDER-ACHIEVEMENT DURING THE REPORTING PERIOD

The Department did not achieve 9 of its 19 planned 2019/20 annual targets, as reflected below:

- 98.8% of compliant invoices were paid within 30 days

- 2019/20 Strategic Risk reports approved, 2020/21Strategic Risk Assessment conducted, and strategic risk register updated

- Audio-Visual and Digital Content Strategy developed for the 4IR

- Broadcasting Amendment Bill submitted to Cabinet for approval

- PMO established and operationalised to support the Presidential Commission on Fourth Industrial Revolution

- Training of Audio-Visual SMME in three Provinces focussing on 4IR Skills and Enterprise Development

- Country-wide Implementation Plan on Analogue Transmission Services Switch-Off approved by Minister

- Report on BDM awareness and educational campaigns conducted in nine provinces

- 12 performance review and compliance monitoring reports of SOEs developed

14

Annual target

Status

Reason for Deviation

2019

/

20

WSP

and

2018

/

19

Annual

Training

Report

submitted

to

the

PSETA

Achieved

N/A

Reconfigured

department

established

to

deliver

on

the

new

mandate

Achieved

N/A

Unqualified

audit

outcome

on

2018

/

19

AFS

Achieved

N/A

100

%

of

all

compliant

invoices

paid

within

30

days

Not Achieved

Since

the

DoC

officials

moved

to

DTPS

premises,

the

transversal

systems

and

the

internet

have

been

overloaded

which

resulted

in

poor

functionality

transversal

systems

.

All

invoices

were

paid

although

some

were

paid

after

30

days

.

PROGRAMME 1: ADMINISTRATION (1)

Annual target

Status

Reason for Deviation

Implementation

of

the

approved

2019

/

20

Procurement

Plan

monitored

2020

/

2021

Procurement

Plan

submitted

to

National

Treasury

Achieved

N/A

2019

/

20

Strategic

Risk

reports

approved,

2020

/

21

Strategic

Risk

Assessment

conducted,

and

strategic

risk

register

updated

Not Achieved

Consultations

with

Programme

Managers

could

not

be

finalised

due

to

the

lockdown

.

The

consultations

were

finalised

in

Q

1

of

2020

/

21

financial

year

.

PROGRAMME 1: ADMINISTRATION (2)

Annual target

Status

Reason for Deviation

Audio

-

Visual

and

Digital

Content

Strategy

developed

for

the

4

IR

Not Achieved

A

Draft

White

Paper

on

Audio

and

Audio

-

visual

Content

Services

Policy

Framework

for

the

4

IR

was

instead

compiled

to

speed

up,

the

strategy

development

process

.

A

Draft

White

Paper

on

Audio

and

Audio

-

visual

Content

Services

Policy

Framework

was

approved

by

EXCO,

in

February

2020

,

for

processing

and

submission

to

Cabinet

for

approval

for

public

consultation

.

The

Audio

-

Visual

and

Digital

Content

Strategy

and

final

White

Paper

will

be

expedited

in

2020

/

21

FY

PROGRAMME 2:

COMMUNICATION POLICY,

RESEARCH AND DEVELOPMENT

PROGRAMME 2: COMMUNICATION POLICY, RESEARCH AND DEVELOPMENT

| Annual target |  | Status | Reason for Deviation |
| --- | --- | --- | --- |
| Broadcasting Amendment submitted to Cabinet for approval | Bill | Not Achieved | The Broadcasting Amendment Bill was approved by EXCO, in February 2020, for processing and submission to Cabinet for approval. The Amendment Bill planned for submission to Cabinet during 2020 /21 FY, as part of DCDT priority legislation. |
| PMO established and operationalised to support the Presidential Commission on Fourth Industrial Revolution |  | Not Achieved | The recruitment process to capacitate the PMO took longer than expected. Appointments of Snr Research Expert and five (5) Research Experts were concluded in the fourth quarter. Only one (1) Research Expert started in March 2019 and the other four (4) officials started on 1 April 2020. The recruitment of the remaining positions are in the process of being concluded. |

| Annual target | Status | Reason for Deviation |
| --- | --- | --- |
| Training of Audio-Visual SMME in three Provinces focussing on 4IR Skills and Enterprise Development | Not Achieved | The sourcing of suitable Service Providers to offer training on 4IR was a challenge and was therefore confirmed at a later period in the financial year. Training of Audio-Visual SMME on 4IR Skills is continuing as part of the implementation of the ICT SMME Development Strategy |
| Six engagements conducted on access to digital platforms for SMMEs | Achieved | N/A |
| A country-wide Implementation Plan on Analogue Transmission Services Switch-Off approved by Minister | Not Achieved | Although a high-level plan was submitted together with the revised BDM delivery model, a detailed plan could not be finalised pending the restructuring of roles and responsibilities of entities playing a role in the delivery of the BDM Programme. 18 |

# PROGRAMME 3: INDUSTRY AND CAPACITY DEVELOPMENT (1)

PROGRAMME 3: INDUSTRY AND CAPACITY

DEVELOPMENT (2)

## Annual target	Status	Reason for Deviation

Report on BDM awareness and Not Achieved Awareness and educational campaign educational campaigns conducted Plan was not adequately implemented in nine provinces in some of the provinces during a quarter 1 reporting period. Awareness Campaigns were not conducted in Western Cape (WC), KwaZulu-Natal and Gauteng (GP) due to the CSIR recommendations that places the WC, GP and KZN as the last provinces for Analogue Switch Off.

2 multilateral structures engaged Achieved N/A jointly with the DTPS

- ITU

- WIPO

Draft	WRC-19	Outcomes	report	Achieved	N/A

developed to inform the revision of the 2020 National Radio Frequency

Plan jointly with the DTPS

19

20

Annual target

Status

Reason for Deviation

12

performance

reviews

and

compliance

monitoring

reports

of

SOEs

developed

Not Achieved

Performance

reviews

and

compliance

monitoring

reports

were

developed

for

all

the

SOEs,

however,

the

analysis

reports

were

submitted

for

only

two

SOEs

FPB

(

and

SABC)

due

to

HR

capacity

constraints

.

12

SOE

QPR

sessions

coordinated

Achieved

N/A

PROGRAMME 4:

STRATEGY AND POLICY

ALIGNMENT

21

THANK YOU