## Slide 1: Portfolio Committee Presentation
02 November 2020

## Slide 2
Strategic Position
Vision:
Digitally skilled citizens
Mission: To drive national digital skills development, enhancing competence for sustainable socio-economic development in South Africa; and to radically advance the human capacity development in digital skills.

## Slide 3
2019/20 Highlights and Challenges
The new board was appointed with effect from 25 October 2019
The Ya-Rona Digital Ambassadors Programme was successfully launched in KZN
Successfully hosted the Digital Skills Summit, Research Colloquium and Hackathon
Strategic and Annual Performance Plans were prepared in line with the envisaged mandate
Challenges
Change in leadership in the middle of the financial year
Training disruptions due to Covid-19

## Slide 4
Summary of Performance
NEMISA has achieved Ten (10) of the eighteen (18) planned targets, being 55% of the total planned targets, and eight (8) of the planned targets were not achieved, being 45% of the total annual planned targets.
Detailed performance is outlined in sections to follow

## Slide 5
Programme 1:Administration
Strategic Objectives | Performance Indicator | Planned Target 2019/2020 | Actual Achievement 2019/2020 | Deviation from planned target to Actual Achievement for 2019/2020 | Comment on Deviations
Efficient business process support within the institute by developing strategies and plans. | Transformation and Change Strategy for NEMISA is developed, approved and implemented. | One Transformation and Change Strategy developed and approved. | A draft Transformation and Change Strategy has been developed. | The finalisation of the Strategy is deferred to 2020/21 to ensure that the Strategy is aligned to the New Strategic Plan. | Transformation and Change Strategy to be approved in 2020/21 and broadened to a Transformation and Change Strategy.

## Slide 6
Programme 2:Multi Stakeholder Collaboration
Strategic Objectives | Performance Indicator | Planned Target 2019/2020 | Actual Achievement 2019/2020 | Deviation from planned target to Actual Achievement for 2019/2020 | Comment on Deviations
Raise brand and digital skills awareness | Number of advocacy and awareness campaigns conducted by the institute and CoLabs. | 24 | 34 | 10 | Over performance is due to various opportunities where NEMISA was invited to participate in events.

## Slide 7
Programme 3: e-Astuteness Development
Strategic Objectives | Performance Indicator | Planned Target 2019/2020 | Actual Achievement 2019/2020 | Deviation from planned target to Actual Achievement for 2019/2020 | Comment on Deviations
Facilitate digital skills training through training interventions. | Number of e-literacy learners trained per annum. | 6500 | 5836 | -664 | 7805 individuals were trained however inadequate tools of recording trainees in attendance resulted in the underachievement.
 | Number of sector users trained per annum. | 2500 | 323 | -2177 | 5451 individuals were trained however inadequate tools of recording trainees in attendance resulted in the underachievement.
 | Number of ICT practitioners trained per annum. | 800 | 0 | -800 | 1074 individuals were trained however inadequate tools of recording trainees in attendance resulted in the underachievement.

## Slide 8
Programme 3: e-Astuteness Development
Strategic Objectives | Performance Indicator | Planned Target 2019/2020 | Actual Achievement 2019/2020 | Deviation from planned target to Actual Achievement for 2019/2020 | Comment on Deviations
Facilitate digital skills training through training interventions. | Number of e-leaders trained per annum. | 240 | 25 | -215 | 494 individuals were trained, however only 25 were classified as e-leaders hence the underperformance is attributed inadequate tools of recording trainees in attendance.
 | Number of senior Government employees participating in the programme on digital transformation for the public service. | 50 senior employees | 21 senior employees | -29 | 50 government employees were trained however, only 21 senior employees were classified as senior hence the underperformance is attributed to inadequate tools of recording trainees in attendance.
Provide broad learning access through the learning system to ensure digital skills massification. | Implemented a learning management system. | Phase 1 of the learning management system implemented. | Phase 1 learning management system implemented. | None | None
Enhancing Leadership’s understanding of the application of data, data analytics and Artificial Intelligence for strategic decision making. | Number of senior Government employees participating in a training workshop, on the application of data, data analytics and Artificial Intelligence for strategic decision making. | 60 senior employees | 25 senior employees | -35 | The underperformance is attributed to postponement of training scheduled for mid March due to the COVID-19 pandemic.

## Slide 9
Programme 3: e-Astuteness Development
Strategic Objectives | Performance Indicator | Planned Target 2019/2020 | Actual Achievement 2019/2020 | Deviation from planned target to Actual Achievement for 2019/2020 | Comment on Deviations
Enhancing Government employees’ understanding of the nexus of privacy, data protection and regulation e.g. POPIA, GDPR & Cybersecurity. | Number of Government employees participating in a training workshop on enhancing the understanding of the nexus of privacy, data protection and regulation. | 60 employees | 17 employees | -43 | The underperformance is attributed to postponement of training scheduled for mid March due to the COVID-19 pandemic.

## Slide 10
Programme 4:Knowledge for innovation
Strategic objectives | Performance Indicator | Planned Target 2019/2020 | Actual Achievement 2019/2020 | Deviation from planned target to Actual Achievement for 2019/2020 | Comment on deviations
Produce relevant research programmes to identify digital skills demands and gaps | Number of National environmental scans conducted | 1 | 1 environmental scan focusing on different sectors was conducted, and report compiled. | None | None
Contribute to research capacity | Number of Postgraduate research initiatives funded on key digital skills required for 4IR era | 3 Research reports on status of research initiatives funded | 3 Research reports developed | None | None
 | Number of non-degree research funded on key developments of ICT | 3 Research reports on status of research Initiatives funded | 3 Research reports developed | None | None

## Slide 11
Programme 4:Knowledge for innovation
Strategic objectives | Performance Indicator | Planned Target 2019/2020 | Actual Achievement 2019/2020 | Deviation from planned target to Actual Achievement for 2019/2020 | Comment on deviations
Facilitate knowledge transfer through the network | Number of national research colloquiums hosted | 1 | 1 National research colloquium hosted | None | None
 | Number of formal engagements held with ICT thought leaders | 6 | 13 | 7 | The over performance is due to opportunities that arose.
 | Host the Fourth Industrial Revolution (4IR) Symposium to develop 4IR plan of action for NEMISA | 4IR symposium hosted and 4IRPA for NEMISA developed | Hosted the 4IR symposium and developed the 4IRPA | None | None
 | Number of digital skills summits hosted | 1 | 1 | None | None

## Slide 12
Programme 5: Aggregation Framework
Strategic Objectives | Performance Indicator | Planned Target 2019/2020 | Actual Achievement 2019/2020 | Deviation from planned target to Actual Achievement for 2019/2020 | Comment on Deviations
Provide strategic direction by developing frameworks and policies that will guide in measuring impact. | Monitoring and evaluation framework developed and submitted to the board. | 1 Monitoring and evaluation framework developed and submitted to the board. | The monitoring and evaluation framework has been developed, aligned to the new strategic plan and submitted to the board. | None | None

## Slide 13
AFS Overview
Statement of Financial Performance | Approved budget | Final Budget | Actual Amounts | Difference | Ref | 
Revenue from exchange transactions |  |  |  |  |  | 
Exchange revenue | - | - | 443 026 | 443 026 |  | 
Interest received investment | - | - | 2 779 981 | 2 779 981 | 1 | 
Total revenue from exchange transactions | - | - | 3 223 007 | 3 223 007 |  | 
Revenue from non exchange transactions |  |  |  |  |  | 
Transfer revenue |  |  |  |  |  | 
Appropriation income | 95 347 000 | 95 347 000 | 112 266 904 | 16 919 904 | 2 | 
Total revenue | 95 347 000 | 95 347 000 | 115 489 911 | 20 142 911 |  | 
Expenditure |  |  |  |  |  | 
Personnel | -23 368 794 | -23 368 794 | -23 971 799 | -603 005 | 3 | 
Depreciation and amortisation | - | - | -1 882 883 | -1 882 883 |  | 
Goods and services | -71 978 206 | -71 978 206 | -91 094 665 | -19 116 456 | 4 | 
Total expenditure | -95 347 000 | -95 347 000 | -116 949 347 | -21 602 347 |  | 
Operating deficit | - | - | -1 459 436 | -1 459 436 |  | 
Deficit before taxation | - | - | -1 459 436 | -1 459 436 |  | 

## Slide 14
Budget Vs Actual Variance
1. Interest earned on the rolled over funds which was not included in the budget.
2. The difference is due to Commitments realised as non exchange revenue in the current year
3. The variance is due to temporary positions filled and funds utilised from commitments
4. The variance is due to prior year commitments realised as expenditure in the current year

## Slide 15
Key Notes to AFS
Note 2 : PPE
Note17 : Commitments
Note23 : Fruitless & Wasteful Expenditure
Note24 : Irregular Expenditure

## Slide 16
Non-compliance matters
Irregular expenditure
  Current year : R425 523
  Prior year identified in current year : R9,8 million
  Internal Audit will conduct internal investigation on Irregular expenditure
  Consequence management processes to be initiated upon conclusion of Internal Audit investigation
Fruitless & wasteful expenditure
  Current year : R10 482
  Internal Audit will conduct internal investigation on Fruitless & Wasteful expenditure
  Consequence management processes to be initiated upon conclusion of Internal Audit investigation

## Slide 17
Key AGSA Audit Matters
Validity of reported Performance Information
  This was due to collation of audit evidence for training conducted not aligned to the APP technical indicator descriptions (TID). Measures have been put in place to ensure improved collection of training evidence.
Financial Statement Disclosure Adjustments
  Disclosure of Lease Commitments. This was due to misinterpretation of timing of automatic lease extension per the lease agreement leading to incomplete disclosure of lease commitments per GRAP standards. This has already been addressed

## Slide 18: Thank you