## Slide 1: 06 November 2020
Briefing to the Portfolio Committee on Police
Situational Analysis, Leadership for Forensic Science Laboratory(Biology) and Project Plan on Processing DNA Backlog

## Slide 2: Outline
Section 1: Purpose
Section 2: Situational Analysis
Section 3: Leadership for Forensic Science Laboratory (Biology)
Section 4: Project Plan on Processing DNA Backlog

## Slide 3: Purpose
Section 1

## Slide 4: Purpose
The purpose of this presentation, is to brief the Portfolio Committee on Police, with regard to the Situational Analysis, leadership of FSL and the Project plan to address DNA backlog.

## Slide 5: Situational Analysis
Section 2

## Slide 6: SITUATIONAL ANALYSIS
Insufficient funding for Forensic Science Laboratory.
Instability of leadership and management.
Submission of high volume of DNA buccal samples in line with the implementation of the Criminal Law
(Forensic Procedures) Amendment Act No 37 of 2013 commonly known as the DNA Act.
The increasing workload and additional capacitation required to process all exhibits for analysis
Turnaround times in accordance with the international and national standards.
Challenges with the procurement of consumables and servicing of equipment to perform analysis.
No Health Risk Management Contract for vaccination of analysts.

## Slide 7: SITUATIONAL ANALYSIS
No competitive market (utilising same supplier for multiple years)
Utilization of closed system instruments affects rotation of suppliers
Load shedding
Water cuts
Covid-19 pandemic
Lack of internal skilled lab technician to render service and calibration of instruments/ equipment.

## Slide 8: Leadership: Forensic Science Laboratory
Section 3

## Slide 9: Governance Structure: Forensic Science Laboratory
  Component Head: FSL
  Section Head: Biology
  Regional Head: FSL - Eastern Cape
  Regional Head: FSL - KwaZulu-Natal
  Regional Head: FSL- Western Cape

## Slide 10: Governance Structure: FSL: BIOLOGY
Province | Biology | Process Activity | Total Number Commander
Pretoria: HQ | HQ Biology: Section Head | Section Management | 1
 | Case Management Section (Customer Service Centre) |  | 1
 | Responsibilities | Case Registration RI | 
 |  | Case Registration CI | 
 |  | Case dealing | 
 |  | Case Enquiries | 1
 |  | Case Dispatch | 1
 | Evidence Recovery (ER) Section |  | 1
 | Responsibilities | Evidence Recovery | 1
 |  | Samples crime exhibit submission | 1
 |  | Reference Buccal sample submission | 1

## Slide 11: Governance Structure: FSL: BIOLOGY
Province | Biology | Process Activity | Total Number Commander
Eastern Cape | Regional Biology: Section Commander |  | 1
 | Case Management: Commander |  | 
 | Responsibilities | Case dealing | 
 |  | Case Enquiries | 
 |  | Case Dispatch | 
 | Evidence Recovery: Commander |  | 1
 |  | Evidence Recovery | 
 |  | Sample Submission | 
Kwa ZuluNatal | Regional Biology: Section Commander |  | 1
 | Case Management: Commander |  | 
 | Responsibilities | Case dealing | 
 |  | Case Enquiries | 
 |  | Case Dispatch | 
 | Evidence Recovery (ER): Commander |  | 1
 | Responsibilities | Evidence Recovery | 
 |  | Sample Submission | 

## Slide 12: Governance Structure: FSL: BIOLOGY
Province | Biology | Process Activity | Total Number Commander
Western Cape | Regional Biology: Section Commander |  | 1
 | Case Management Section |  | 1
 | Responsibilities | Case Dealing | 
 |  | Case Enquiries | 
 |  | Case Dispatch | 
 | Evidence Recovery (ER) Section |  | 1
 | Responsibilities | Evidence Recovery | 
 |  | Samples crime exhibit submission | 
 |  | Reference Buccal sample submission | 

## Slide 13: Governance Structure: FSL: BIOLOGY
Province | Biology | Process Activity | Total Number Commander
Western Cape | Status Reporting Officer (SRO) Commander |  | 1
 | Responsibilities | Intelligence | 
 |  | Comparison | 
 | DNA Analysis Commander Regional Biology: Section Commander |  | 1
 | Responsibilities | Manual DNA Analysis: sub-section | 
 |  | Manual Sample Storage | 
 |  | Manual Isolation | 
 |  | Manual Quantitative Polymerase Chain Reaction (qPCR) | 
 |  | Manual Polymerase Chain Reaction (PCR) | 
 |  | Manual Capillary Electrophoresis (CE) | 
 |  | Semi-Automation Crime Index (CI) DNA Analysis: | 1
 |  | Semi-Automation CI Storage | 
 |  | Semi-Automation qPCR | 
 |  | Semi-Automation PCR | 
 |  | Semi-Automation CE | 

## Slide 14: Governance Structure: FSL: BIOLOGY
Province | Unit | Process Activity | Total Number Commander
Western Cape | Responsibilities | Semi-Automation Reference Index (RI) DNA Analysis | 1
 |  | Pre-Amplification | 
 |  | Post Amplification | 
 |  | STRgazer | 
 |  | Manual Data Analysis | 1
 |  | CI Data Analysis | 
 |  | RI Data Analysis | 

## Slide 15: Governance Structure: FSL: BIOLOGY
Province | Unit | Process Activity | Total Number Commander
Western Cape | DNA Report Officer (RO) and Review Section Commander |  | 1
 | Responsibilities | Report Writing | 
 |  | Serial Report Writing | 
 |  | Report Review | 
 |  | Serial Report Review | 

## Slide 16: Governance Structure: FSL: BIOLOGY
Province | Biology | Process Activity | Total Number Commander
Pretoria: HQ | Status Reporting Officer (SRO) Commander |  | 1
 | Responsibilities | Intelligence | 
 |  | Comparison | 
 | DNA Analysis Section Commander |  | 1
 | Responsibilities | Manual DNA Analysis: sub-section | 
 |  | Manual Sample Storage | 
 |  | Manual Isolation | 
 |  | Manual Quantitative Polymerase Chain Reaction (qPCR) | 
 |  | Manual Polymerase Chain Reaction (PCR) | 
 |  | Manual Capillary Electrophoresis (CE) | 
 |  | Semi-Automation Crime Index (CI) DNA Analysis | 1
 |  | Semi-Automation CI Storage | 
 |  | Semi-Automation qPCR | 
 |  | Semi-Automation PCR | 
 |  | Semi-Automation CE | 

## Slide 17: Governance Structure: FSL: BIOLOGY
Province | Unit | Process Activity | Total Number Commander
Pretoria: HQ | Responsibilities | Semi-Automation Reference Index (RI) DNA Analysis | 1
 |  | Pre-Amplification | 
 |  | Post Amplification | 
 |  | STRgazer | 1
 |  | Manual Data Analysis | 
 |  | CI Data Analysis | 
 |  | RI Data Analysis | 

## Slide 18: Governance Structure: FSL: BIOLOGY
Province | Unit | Process Activity | Total Number Commander
Pretoria: HQ | DNA Report Officer (RO) and Review Section Commander |  | 1
 | Responsibilities | Report Writing | 1
 |  | Serial Report Writing | 1
 |  | Report Review | 1
 |  | Serial Report Review | 1

## Slide 19: Project Plan on Processing DNA Backlog
Section 4

## Slide 20: Project Plan on Processing DNA Backlog
Biology HQ – Unassigned Entries | DNA HQ E = 14057 as of 2020-11-03 Plan to deal an average of 5 cases per day to a maximum of 40 analysts 40 X 5 = 200 = 1000 per week, current backlog to be depleted in 14 weeks. Incoming work = an average of 1000 cases per week. At the end of 14 weeks = 14000 cases. Overtime hours required resulting in 2000 cases completed in a 2 month period resulting in a carryover of +/- 12000 cases to the fourth quarter. Additional overtime in the fourth quarter will be needed to address this such that the carry over into the new financial year is minimal. RI HQ E = 43 068 as of 2020-11-03 | 
Biology HQ – Entries in Process | The total cases in process = 25 633. Expected incoming for the next 6 weeks = 6 000 cases Total cases expected to be handled by Biology for the next quarter = 31 633. | With the recovery plan Biology will reduce the current backlog and incoming cases in the following manner over the next 5 months: December – total reduction will be 20% January – total reduction will be 15% February – total reduction will be 15% March– total reduction will be 15% April – total reduction will be 20% May- total reduction will be 20%

## Slide 21: Project Plan on Processing DNA Backlog
Biology WC – Unassigned Entries | DNA WC E = 9956 as of 2020-11-03 Plan to deal an average of 5 cases per day to a maximum of 32 analysts 32 X 5 = 160 = 800 per week, current backlog to be depleted in 13 weeks. Incoming work = an average of 500 cases per week. At the end of 14 weeks = 7000 cases. Overtime hours required resulting in 2000 cases completed in a 2 month period resulting in a carryover of +/- 5000 cases to the fourth quarter. Additional overtime in the fourth quarter will be needed to address this such that the carry over into the new financial year is minimal. RI WC E = 22 585 as of 2020-11-03 RI Index backlog is currently about 1 month. WC has 3 lanes, with all Instruments running, the current backlog can be depleted in 10 working days. | December – total reduction will be 20% January – total reduction will be 15% February– total reduction will be 15% March – total reduction will be 20% April – total reduction will be 20% May- total reduction will be 20%
Biology WC – Entries in Process | The total cases in process = 13 933. Expected incoming for the next 6 weeks = 3 000 cases Total cases expected to be handled by Biology for the next quarter = 16 933. | With the recovery plan Biology WC will reduce the current backlog and incoming cases in the following manner over the next 5 months: December – total reduction will be 20% January – total reduction will be 15% February – total reduction will be 20% March – total reduction will be 20% April – total reduction will be 20% May- total reduction will be 20%

## Slide 22: Project Plan on Processing DNA Backlog
Biology WC – Unassigned Entries | DNA WC E = 9956 as of 2020-11-03 Plan to deal an average of 5 cases per day to a maximum of 32 analysts 32 X 5 = 160 = 800 per week, current backlog to be depleted in 13 weeks. Incoming work = an average of 500 cases per week. At the end of 14 weeks = 7000 cases. Overtime hours required resulting in 2000 cases completed in a 2 month period resulting in a carryover of +/- 5000 cases to the fourth quarter. Additional overtime in the fourth quarter will be needed to address this such that the carry over into the new financial year is minimal. RI WC E = 22 585 as of 2020-11-03 RI Index backlog is currently about 1 month. WC has 3 lanes, with all Instruments running, the current backlog can be depleted in 10 working days. | December – total reduction will be 20% January – total reduction will be 15% February– total reduction will be 15% March – total reduction will be 20% April – total reduction will be 20% May- total reduction will be 20%
Biology WC – Entries in Process | The total cases in process = 13 933. Expected incoming for the next 6 weeks = 3 000 cases Total cases expected to be handled by Biology for the next quarter = 16 933. | With the recovery plan Biology WC will reduce the current backlog and incoming cases in the following manner over the next 5 months: December – total reduction will be 20% January – total reduction will be 15% February – total reduction will be 20% March – total reduction will be 20% April – total reduction will be 20% May- total reduction will be 20%

## Slide 23: Project Plan on Processing DNA Backlog
Biology EC – Unassigned Entries | DNA EC E = 7 258 as of 2020-11-03 Plan to deal an average of 5 cases per day to a maximum of 8 analysts 8 X 5 = 40 = 200 per week, current backlog to be depleted in 36 weeks. Incoming work = an average of 300 cases per week. At the end of 14 weeks = 7000 cases. Overtime hours required resulting in 2000 cases completed in a 2 month period resulting in a carryover of +/- 5000 cases to the fourth quarter. Additional overtime in the fourth quarter will be needed to address this such that the carry over into the new financial year is minimal. RI E = 22 585 as of 2020-11-03 RI Index backlog is currently about 1 month. WC has 3 lanes, with all Instruments running, the current backlog can be depleted in 10 working days. | December – total reduction will be 20% January – total reduction will be 15% February– total reduction will be 15% March – total reduction will be 20% April – total reduction will be 20% May- total reduction will be 20%

## Slide 24: Way Forward
Forensic Science Laboratory is committed to providing quality forensic products to support the Criminal Justice System and victims of crime, especially gender-based violence incidents.
Forensic Science Laboratory is committed to maintain effective and efficient, financial, risk management and internal control measures, to support service delivery to the victims of crime.
Forensic Science Laboratory will continue to cooperate with and support internal and external stakeholders, in an integrated and multidisciplinary approach, to address serious and violent crimes, including any priorities of the JCPS.

## Slide 25
THANK YOU