PROGRESS REPORT ON PAAP IMPLEMENTATION NGAKA MODIRI MOLEMA DISTRICT MUNICIPALITY

| Completed |  |  | In Progress |  |  | Not Complete |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Legend: MR = Management Report AR = Annual Report |  |  |  |  |  |  |  |  |
| PAAP NMMDM AS AT 17 NOVEMBER 2020 |  |  |  |  |  |  |  |  |
| Municipality | No. of findings per MR | No. of findings addressed per MR |  | Completed Percentage per MR | No. of Qualifications per AR |  | No. of Qualifications addressed per AR | Completed Percentage per AR |
| NMMDM | 218 | 158 |  | 66% | 17 |  | 15 | 91% |

| Qualification per Audit Report |  |  |  |  |
| --- | --- | --- | --- | --- |
| No | Qualification component | Brief audit finding | Status |  |
|  |  |  | Current Year | Prior Year |
| 1 | Property, plant and equipment | Overstatement of PPE due to pre-payment wrongly included in PPE & Non-compliance to GRAP 17 |  |  |
| 2 | VAT receivable | Overstatement of VAT receivable due to limitation of scope |  |  |
| 3 | Inventories | Understatement of Inventories due to VIP toilets classified as WIP |  |  |
| 4 | Receivables from exchange transactions | Understatement due of receivables due to omission of VAT payments owed by Sedibeng Water |  |  |
| 5 | Payables from exchange transactions | Understatement of payables due to incorrect calculations of retention. Plus limitation of scope |  |  |
| 6 | Accumulated surplus | Limitation of scope |  |  |
| 7 | Contracted services | Limitation of scope – Water Tankering expense information |  |  |
| 8 | Repairs and maintenance | Limitation of scope |  |  |
| 9 | General expenses | Overstatement of accounting fees and understatement of PPE due to misclassification |  |  |
| 10 | Distribution Water losses | Limitation of scope |  |  |
| 11 | Commitments | Overstatement of commitments due to limitation of scope |  |  |
| 12 | Prior-year adjustments | Limitation of scope |  |  |
| 13 | Unauthorized expenditure | Understatement due to calculations and limitation of scope |  |  |
| 14 | Irregular expenditure | Understatement due to calculations and limitation of scope |  |  |
| 15 | Contingencies | Understatement of contingencies due to contingencies register being incomplete |  |  |
| 16 | Cash flow statement | Limitation of scope |  |  |
| 17 | Current assets | Materially misstated due to cumulative understatements |  |  |