## Slide 1: COMMUNITY WORK PROGRAMME AUDIT OUTCOMES
PORTFOLIO COMMITTEE
Dr B Siswana
Deputy Director-General
27 November 2020

## Slide 2: 2018/2019 FY AUDIT OUTCOME reoccurring findings emerge:
Reoccurring findings emerge: | Progress to date
Not address the root causes: Deficiencies in implementation model results in operational inefficiencies has contributed to recurrent negative audit outcomes for the programme | Redesign of the Implementation Model to improve operational efficiencies and service delivery (Outcome Based Approach). Model options considered by TMC and submission with recommendations made to Executive Authority for decision making. A review of the systems, processes and people-centred model
Lack of adequate record keeping, internal control processes and supervision | A Document Management SOP has been developed to guide the record management process. NPO Governance Compliance Matrix developed and monitored monthly covering the following: expenditure, agreed deliverables and progress per business plan. Documents outlining procurement processes including invoices, delivery notes and purchase orders diligently kept and accessible for audit, shared with DCOG monthly.. Participants Registers / Records at site level updated monthly.
CWP leadership instability | Full-year appointment of Branch Head to begin process of stabilising and turnaround the programme Contract appointment of Chief Director, Finance to streamline audit and finance migration to the office of the CFO

## Slide 3: 2018/2019 FY AUDIT OUTCOME reoccurring findings emerge:
Reoccurring findings emerge: | Progress to date
Lack of attention or requisite expertise within the finance department; | Integration process underway with the office of CFO to strengthen finance functionality. Objective review of capacity requirements, and confirmation of ideal organogram to be guided by the outcome remodelling process. Chief Director on contract basis to Assist CWP Finance
No indication of corrective actions; and | CWP Management is implementing the IMT and progress monitored by DCoG Internal Audit Unit on an ongoing basis. CWP Management has prioritized implementation of the recommendations as outlined in the IMT and monitored by Internal Audit.
Lack of sense of urgency in implementing recommendations. | 

## Slide 4: PERFORMANCE AUDIT FINDINGS INCLUDED
Root Causes identified on Planning & Reporting | Progress to date
a) Performance indicators in the CWP operational plan | All Performance Indicators were reviewed and updated considering the findings by AGSA, (p82 & 83 of the current 2020/21 AAP)
b) Progress on some of the CWP’s performance targets not monitored. | CWP Management convenes quarterly PCFs & Provincial M&R forums to monitor the implementation of CWP at site level.
c) Progress reports from the NPOs are not aligned to the deliverable in the Service Level and Transfer Agreements. | CWP Management developed the SLA Checklist, which is being accounted for by NPOs on quarterly basis, including Site Visits by Management using a standardized template to validate and verify all work done by NPOs.

## Slide 5: PERFORMANCE AUDIT FINDINGS INCLUDED:
Root Causes identified on CWP Finance | Progress to date
NPOs reported financial performance based on budget figures different from the CWP budget allocations. Some NPOs overspent on their budget allocation for 2018/2019 financial year. The NPO overspent on PPE without obtaining approval from DCoG. Expenditure incurred prior to the approval of spending. Absence of/inadequate portfolio of evidence to support expenditure incurred. | Developed a reporting template which is aligned to the CWP budget allocation where NPOs report on a monthly basis and the Finance Unit analyses and feedback to NPOs to correct where gaps are identified. CWP Management investigated the NPOs overspending and established that the reporting not aligned to budget allocation and resulting in the status misinterpreted as overspending

## Slide 6: ROOT CAUSES AND SUMMARY ON CWP KEY FINDINGS: Training & Service Level Agreement
Root Cause identified on Training | Progress to date
Information / Attendance Registers not uploaded; Training not conducted for some NPOs and Underspending reasons not provided on Training; No approval policy/standard operating procedure for training of CWP; Training documents not submitted with claims; No site business plan/not approved by DCoG; & Procurement plans not approved; A 5% retention fee was not retained | Single Portal was created and system improvement to facilitate & access enabled (address (a) & (d); All nine (9) NPOs conducted training in the 2019/20 fy, and have spent their training budget. Training Standard Operating Procedure (SOP) in place, reviewed and submitted for 2020/21 approval; Training Checklist developed for 2019/20 fy and all submissions aligned to it to ensure that all training conducted is accounted for. All sites are currently aligning their 20/21 Site Business Plans to Covid-19 Deliverables, including Procurement Plans & Training Plans as annexures; 5% retention fee is withheld for all payments made to NPOs to date; NPO Annual Performance Assessments are currently being conducted to determine the performance by NPOs.

## Slide 7: CWP WAGES
Root Cause identified on Wages | Progress to date
Accuracy and Occurrence of wage amounts cannot be confirmed | Interim arrangements with SASSA currently in place for monthly verification and validation of participants. Finalisation of this interface currently going through approval processes. b) Medium Term CWP Management together with SITA are developing a web-based Information Management System that enable verifications and validations to remedy the findings; The CWP Management has resolved to prioritize systems integration with systems of other Departments (DHA, National Treasury, SASSA and PERSAL) to remedy the existing findings; Work in Progress and the plan is to pilot from December. Engagements between CWP, SITA and other departments (DHA, National Treasury, SASSA) have been concluded and we are waiting for confirmation of implementation dates from SITA. c) In the long term The CWP IMS is intended to have a full integration with systems of other departments (i.e. DHA (Deceased), DPSA(PERSAL), National Treasury and Bank Serv Africa, STATS SA, and SASSA).

## Slide 8: CWP WAGES
Root Cause identified on Wages | Progress to date
Participants not registered for COID, UIF | UIF is paid timeously to DOL from May 2020 due to additional capacity added. CWP Management has engaged the Department of Labour to solicit support to assist NPOs with the challenges they experience with regard to COID Assessments. The process is currently underway, in preparation for a workshop
UIF & COID contributions not paid within the required deadline | 
Deceased participants on payroll and CWP MIS – participants with PERSAL numbers | & e) Management formalized identified Financial irregularities due to Persal & Deceased and recouped from PM Fees due (See the next slide). There is progress here with arrangements entered into with DPSA for a monthly verification and validation for proactive identification of participants with PERSAL numbers. Contact with DHA made and SITA assisting with the Finalisation of the Interface in MIS and later into the IMS.
CWP MIS –participants with PERSAL numbers | 

## Slide 9: SUMMARY OF DECEASED & PERSAL PARTICIPANTS’ FINANCIAL IRREGULARITIES
CATEGORY | AMOUT IDENTIFIED | AMOUNT CLEARED / RECOUPED / UNDER INVESTIGATION
AGSA PERSAL PARTICIPANTS | R4 711 695.50 | CLEARED * - R2 200 910.50 RECOUPED** - R2 510 785.00
AGSA DECEASED PARTICIPANTS | R581 015.00 | CLEARED - R479 669.00 RECOUPED - R101 346.00
Total | R5 292 710.50 | R5 292 710.50
PERSAL PARTICIPANTS | R7 198 927.00 | Cleared - R1, 276, 017.00 Recouped - R5, 925,910.00
DECEASED PARTICIPANTS | R448 223.00 | cleared - R420, 885.00 Recouped - R2,738.00
TOTAL | R7 647 150.00 | R7, 647, 150.00
**Recouped = Amounts deducted from NPOs
*Cleared = NPOs were able to provide acceptable POE

## Slide 10: CWP ASSETS
Root Cause identified on Training | Progress to date
No assets verification reports, inventory list and Discrepancies with Asset Management; | Annual Asset Verification is a process that takes place at the end of the financial year in preparation for the AFS. CWP assets verification was planned to start in April and required travelling across the republic however with the current National Lock Down, this process was negatively affected. The appointment of the Service Provider to assist with the asset verification process was suspended for 2019/20 fy and will be re-advertised for a shorter period in alignment to the remodeling process including handover. The process of taking this forward is currently underway Management requested NPOs to submit the required updated registers for all assets procured, but credibility of the information submission by NPOs is still in question and require physical verification which could not be done prior to submission of AFS.
b) Discrepancies with Asset Management | 
c) Verification – Tracing from floor to asset register – Major, Minor assets existence not confirmed | 
d) Additions – Assets not barcoded e) Inaccurate description f) Incorrect classification | 

## Slide 11: ROOT CAUSES AND SUMMARY OF KEY FINDINGS: CWP Pre-Payments & Project Management Fees :
Root Causes identified | Progress to date:
Non-functional NPO payments. Portfolio of evidence not provided for the expenses incurred. Procurement made by the NPOs not in accordance with the NPO’s SCM Policies. No evidence that unutilized funds by certain NPOs were paid back to DCoG. NPO payments not in accordance with payment supporting evidence. Supporting evidence not provided to support the quarterly performance reports. Monthly and Quarterly performance reports not submitted for audit purposes. Advances to Non-Profit Institutions not supported Overstatement of Prepayments, Project Management Fee Goods & Services; Project Management fees not supported | Developed and implemented Record Management System for submission of information by NPOs. Letters of non-compliance were written to NPOs to ensure compliance and accountability. One on one interaction with NPOs was held to further follow up on areas identified as non-compliance. NPO Annual Performance Assessment are currently being conducted to confirm performance by NPOs. Matter is referred to Investigations for quantifying and validating for accountability & transparency; There is an approved PM Fee guidelines which is currently being aligned to SLA Addendum for signing once concluded;

## Slide 12: SUMMARY OF THE SUSPENSE ACCOUNT
NO | NPO | NO OF DOCUMENTS | NOT RESOLVED | ON HAND | DOCUMENTS %
1 | THEMBALETHU | 0 | - | - | 0%
2 | SAYM | 31 | 1,269,014.48 | 1,478,520.68 | 5%
3 | BAFF | 25 | - | 150,185.06 | 4%
4 | INSIKA | 164 | 930,818.88 | - | 26%
5 | SEBOKA | 0 | - | - | 0%
6 | 3L DEV | 73 | 966,645.46 | 483,866.45 | 12%
7 | JOUBERT | 0 | - | - | 0%
8 | IKETSETSE | 239 | 2,240,024.96 | - | 38%
9 | AFSA | 77 | - | 350,411.25 | 12%
10 | ICEMBE | 21 | 151,036.00 | - | 3%
TOTAL |  | 630 | 5,557,539.78 | 2,462,983.44 | 100%

## Slide 13
                Historical 2019/20
Direct Engagements will NPOs
Deadline set for 30 November
All outstanding amounts deducted from Q3 payments
Letters to that Extent sent to affected NPOs ( 4/8)
              Current 2020/21
Monthly Reports
Quarterly reports
All NPO’s up to date
SUSPENSE ACCOUNTS FINALISATION

## Slide 14: CWP FORENSIC INVESTIGATIONS

## Slide 15
2020/11/26
The following are the forensic investigations commissioned by the Department into the Community Work Programme to date, as well as the associated expenditure:
FORENSIC INVESTIGATIONS COMMISSION BY THE DEPARTMENT
No. | Investigation name | Financial Year | Expenditure (R)
1. | Investigation into the appointment and awarding of Tenders to the Implementing Agents for the Community Work Programme (CWP) and procurement processes of goods/services procured by the Implementing Agents | 2015/16 | 821, 057.68
2. | Forensic Investigation into the Community Work Programme (CWP) | 2016/17 & 2017/18 | 7, 486, 494.69
3. | Community Work Programme Forensic Investigation | 2019/20 | 8, 585, 976.20
 | Total |  | 16, 893, 528.57

## Slide 16
2020/11/26
Investigation into the appointment and awarding of Tenders to the Implementing Agents for the Community Work Programme (CWP) and procurement processes of goods/services procured by the Implementing Agents.
Investigation mandate
To investigate the procurement processes followed to select and award tenders to the Implementing Agents for the CWP and the possible irregular expenditure incurred by the appointed Implementing Agents when procuring good and services on behalf of the Department.
FORENSIC INVESTIGATION 1

## Slide 17
2020/11/26
Forensic Investigation into the Community Work Programme (CWP)
Investigation mandate
Perform a detailed analysis on the Project Management Fees (PM Fees) per IA with a view to identifying inconsistencies and trends by the IAs when invoicing the Department for PM Fees;
Review and analysis of payment batches and identification of irregular expenditure;
Detailed review of the CWP-MIS application–this requirement, which was added to the scope via deviation, was performed by a team of Information Technology (IT) auditors, payment specialists and data analysts;
Verify the completeness of the CWP Asset Register by performing a detailed analysis of all the payment batches for all IAs for the period 1 April 2014 to 31 March 2016
FORENSIC INVESTIGATION 2

## Slide 18
2020/11/26
The following is a summary of the findings raised as they relate to the mandate, recommendations as well as the current status of implementation of those recommendations.
FORENSIC INVESTIGATION 2
Finding | Recommendation | Status of implementation of the Recommendation
Asset Management – no clear definition as to what constitute an asset | The Department should consider: Developing an asset policy, which should include the definition and recognition criteria. Conducting physical verification of assets with the purpose of properly documenting each asset with barcoding and identification of location as well as safeguarding and valuation. | The project is underway to attend to all asset related matters from the previous years to date. Both the CFOs office and CWP Management are putting in place mechanism to ensure that all the assets are accounted, recorded and classified accordingly. The expected outcome is a credible asset register.

## Slide 19
2020/11/26
FORENSIC INVESTIGATION 2
Finding | Recommendation | Status of implementation of the Recommendation
Processing of payments | The CWP should exercise stricter control on the verification and validation of the PM Fee claims to ensure that the IAs comply with the SLA requirement | The SLA checklist has been developed as a compliance tool
CWP-MIS | Management should investigate internal (i.e. through enhanced system functionality) and external (i.e. through the use of additional software) options for the automation of the balancing and reconciliation functions for the salary payments managed by CWP-MIS. The current manual processes and reliance upon human inspection of data lack the robustness and expected levels of quality assurance for the volumes of financial entries being processed. The MIS system should also interface with the Home Affairs system for further verification of participants. | SITA in partnership with CWP is currently working on a project to enhance CWP MIS with effective controls and systems (Copy is attached)

## Slide 20
2020/11/26
Community Work Programme Forensic Investigation
Investigation mandate
Arising from the Auditor-General’s material irregularities raised in the 2018/19 audit report, the Department commissioned a legal forensic investigations on all issues directly and/ or indirectly linked to the material irregularities in respect of the CWP. The material irregularities issued by the Auditor-General covered the following areas:
  Payment to deceased participants;
  Payment to Persal participants;
  Project Management Fees not supported, prior year (2014-2018); and
  Project Management Fees not supported, current year (2018/19).
FORENSIC INVESTIGATION 3

## Slide 21
2020/11/26
The following is a summary of the findings raised as they relate to the mandate, recommendations as well as the current status of implementation of those recommendations.
FORENSIC INVESTIGATION 3
Finding | Recommendation | Status of implementation of the Recommendation
Various findings: Overpayment on Project Management Fees; Undue Vat benefit; and Pre-payments unsupported by evidence | A total of R39 714 864.20 paid to the sighted NPOs for amongst others, overpayments on project management fees, undue VAT benefit and prepayments unsupported by evidence must be recovered. | Work in progress
Consequence management against officials | The Accounting Officer should take disciplinary action against the sighted officials for failing to ensure that there is a system of financial management and control; prevention of fruitless and wasteful expenditure; failure to withhold retention fees. | Six officials have been suspended.

## Slide 22
2020/11/26
FORENSIC INVESTIGATION 3
Finding | Recommendation | Status of implementation of the Recommendation
Payment to Deceased participants | See Slide 9 of the presentation | See Slide 9 of the presentation
Payment to Persal participants | See Slide 9 of the presentation | See Slide 9 of the presentation

## Slide 23
2020/11/26
FORENSIC INVESTIGATION 3
Finding | Recommendation | Status of implementation of the Recommendation
Non-compliance with the VAT Act | DCoG must report this irregularity to SARS for non-compliance with the Vat Act | Work in progress

## Slide 24: IRREGULAR APPOINTMENT OF NPOs Progress: Auditor General and High Court pronounced on the matter. However, on the latter the process is suspended till 31 March 2021.

## Slide 25
RECOMMENDATIONS
It is recommended that the Portfolio Committee notes CWP Progress Report on Audit Findings.

## Slide 26: Thank You