## Slide 1: Update on Management of the Temporary Disability Grant Project
3 February 2021

## Slide 2: Presentation Outline
Recap on the TDG
Contextual Analysis
High level project plan
Progress to date
Specific Interventions
  Queue management
  Automation
  Communication
Risks and Mitigation
Recommendation

## Slide 3: Recap on the Temporary Disability Grants
A Disability grant (DG) is awarded in terms of the Social Assistance Act, 2004
Medical assessment is a prerequisite for an application for a disability grant
Assessment model is medical not social
Grants provided to those who are unable to work as a result of the functional limitation caused by the disability or medical condition: not provided for chronic conditions, or conditions which are manageable with treatment
Temporary disability grants provided for a period of 6 to 12 months, after which the grant lapses in terms of Social Assistance Act.

## Slide 4
SASSA made a presentation to the portfolio Committee on the 20th January 2021. The objective of the presentation was to report to the Portfolio Committee on how SASSA plans to address the challenges relating to the TDGs, reapplication for lapsed grants, and the management of queues.
The Committee raised amongst others, the following issues and requested SASSA to provide detailed plan (interventions):
Lapsing of TDG grant without the capacity for reassessments
  Reinstatements of lapsed TDG
  Queue Management
    Poor queue management &
    Criminals queuing and selling spaces
    Overcrowding and social distancing
    Lack of visibility for volunteers
Contextual analysis

## Slide 5
Issues Raised By The Committee (cont…)
  Communication
    Lack of Information on the process to be followed
    Referral Forms for disability grants not available on the website
    SASSA website not user friendly, no guidance on how people can apply
  SASSA’s Capacity to manage client numbers
    Availability of community halls and service centers
    Restricted access to health facilities
    Limited availability of doctors
    Ability of clients to make appointments
    Call centre accessibility ( not reachable)
    Office Space and restricted number of persons that can be serviced including staff that can be in the office
In addition the Committee raised the issue of long queues at SAPO
Contextual analysis (Cont…)

## Slide 6
The Presentation to the Committee today serves to provide an update as requested and focuses on
  operationalizing the plan that was presented to the Committee on the 20th January 2021;
  Addressing the issues that were raised by the Committee; and
  Giving update on progress to date
Contextual analysis (Cont…)

## Slide 7: Summary of Lapsed TDGs
SASSA has a total of 214 473 TDGs which were extended beyond the period for which they were approved for the period from February to December 2020, under the Disaster Management Act. The cost of these extensions is approximated at R1,8 billion which was funded from the existing allocation:
Province | Feb | Mar | April | May | June | July | Aug | Sep | Oct | Nov | Dec | Total
Eastern Cape | 1 111 | 1 258 | 1 235 | 785 | 873 | 1 493 | 1 407 | 1 378 | 992 | 424 | 190 | 11 146
Free State | 1 159 | 1 464 | 1 694 | 1 398 | 1 458 | 1 798 | 1 567 | 1 236 | 1 177 | 688 | 723 | 14 362
Gauteng | 1 565 | 3 682 | 4 199 | 3 403 | 4 137 | 3 971 | 3 439 | 2 743 | 3 066 | 1 430 | 1 759 | 33 394
KwaZulu-Natal | 2 586 | 4 130 | 4 498 | 4 001 | 5 060 | 4 976 | 4 464 | 3 691 | 3 115 | 1 922 | 2 441 | 40 884
Limpopo | 1 378 | 2 151 | 2 430 | 2 082 | 2 539 | 2 314 | 2 062 | 2 161 | 1 792 | 872 | 1 552 | 21 333
Mpumalanga | 1 152 | 1 693 | 1 831 | 1 396 | 1 520 | 1 533 | 1 386 | 1 271 | 1 213 | 659 | 735 | 14 389
North West | 826 | 1 587 | 1 591 | 1 218 | 1 175 | 1 436 | 1 547 | 1 016 | 902 | 588 | 595 | 12 481
Northern Cape | 1 888 | 1 435 | 1 841 | 1 363 | 1 586 | 1 151 | 1 515 | 924 | 918 | 803 | 737 | 14 161
Western Cape | 3 573 | 6 476 | 6 847 | 5 791 | 5 390 | 6 262 | 5 082 | 3 869 | 4 125 | 3 143 | 1 765 | 52 323
Total | 15 238 | 23 876 | 26 166 | 21 437 | 23 738 | 24 934 | 22 469 | 18 289 | 17 300 | 10 529 | 10 497 | 214 473

## Slide 8: National Summary: Reinstatements
 |  | Grants Re-instated |  |  |  | 
Province | TDGs Lapsed | 59 years | TDG + grant in aid | Procurators | Administrators | Revised Target
Eastern Cape | 10 679 | 257 | 67 | 4 | 2 | 10 349
Free State | 12 941 | 714 | 35 | 20 | 4 | 12 168
Gauteng | 33 394 | 1 484 | 515 | 49 | 5 | 31 341
KwaZulu-Natal | 40 884 | 2 021 | 1 136 | 81 | 9 | 37 637
Limpopo | 21 615 | 676 | 540 | 79 | 3 | 20 317
Mpumalanga | 15 019 | 547 | 1 159 | 54 | 1 | 13 258
Northern Cape | 14 385 | 511 | 336 | 28 | 11 | 13 499
North West | 12 210 | 591 | 759 | 24 | 0 | 10 836
Western Cape | 52 323 | 2 494 | 1 532 | 238 | 38 | 48 021
Total | 213 450 | 9 295 | 6 079 | 577 | 73 | 197 426
Objective: Reinstatements of selected categories of Grants completed in February 2021

## Slide 9: Progress To Date: TDG
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 5.3 | 6.2 | 16 | 19.2 | 10.4 | 6.8 | 6.2 | 5.5 | 24.5
Eastern Cape
Free State
Gauteng
KwaZulu-Natal
Limpopo
Mpumalanga
Northern Cape
North West
Western Cape
10,349
12,168
31,341
37,637
20,317
13,258
12,114
10,836
48,021
6,195
7,509
6 696
12,163
7,862
5,628
6,695
10,310
22,958
5,696
2,773
2,022
9,134
6,534
3,953
2,941
5,321
4,098
Target (%)
Booked 26/01
Assessed 26/01
Eastern Cape
Free State
Gauteng
KwaZulu-Natal
Limpopo
Mpumalanga
Northern Cape
North West
Western Cape
10,975
12,951
33,394
40,884
21,615
15,019
14,006
12,481
53,323
5,314
3,443
5,693
8,903
4,713
3,081
5,005
3,136
11,550
1,735
2,300
1,091
4,779
2,453
647
1,215
1,853
796
Target (%)
Booked 20/01
Assessed 20/01
5.3%
6.2%
16%
19.2%
10.4%
6.8%
6.2%
5.5%
24.5%
Chart: 
| 1st Qtr | 2nd Qtr | 3rd Qtr | 4th Qtr
Sales | 5.1 | 6 | 15.6 | 19.1 | 10.1 | 7 | 6.5 | 5.8 | 24.8
5.1%
6%
15.7%
19.1%
10.1%
7%
6.5%
5.8%
24.8%

## Slide 10
Medical Assessments
8 hour
40 assessments
(12 minutes per client)
session
80 assessments
(6 minutes per client)
Increased to
8 hour
session
Doctors to supplement the capacity in the public health sector are contracted by SASSA after following an open procurement process
Dependent on detailed referrals and client history
Contracted doctors remunerated at R164,80 per assessment: total cost for the assessments will this project will not exceed R32 307 557.
Funds are available under the allocation for medical assessments

## Slide 11: National Summary: Reinstatements
 |  | Re-assessments Estimated - Projections |  |  | 
Province | Number of Lapsed TDG | Revised baseline | Completed Assessments | Confirmed bookings | Bookings to be finalised by March 2021
Eastern Cape | 10 679 | 10 349 | 5,696 | 6,195 | 
Free State | 12 941 | 12 168 | 2,773 | 3,623 | 9,571
Gauteng | 33 394 | 31 341 | 2,022 | 6 696 | 22,623
KwaZulu-Natal | 40 884 | 37 637 | 9,134 | 12,163 | 16,340
Limpopo | 21 615 | 20 317 | 6,534 | 7,862 | 5921
Mpumalanga | 15 019 | 13 258 | 3,693 | 5,628 | 3,937
Northern Cape | 14 385 | 13 499 | 2,941 | 6,695 | 3,863
North West | 12 210 | 10 836 | 5,321 | 5,310 | 
Western Cape | 52 323 | 48 021 | 4,098 | 22,958 | 20,965
Total | 213 450 | 197 426 |  |  | 
Objective: To complete the reassessments by 31 March 2021
It should be noted that generally not every one will qualify and some will not present themselves for assessment. Historically, 80% of applications will present themselves for Assessments
2 tertiary hospitals in GP (North Rand) do not take the referrals – and this is where majority of assessments are done – Paper based assessments will be used to mitigate the challenge. This measure is already being implemented in WC

## Slide 12: Risks and Mitigation Strategies

## Slide 13: Management Plan CDG Re-applications
CDG where child turned 18 years in the course of 2021 were extended under the Disaster Management rules – total of 11 243
So far we have completed 70% of the re-assessments
Introduced paper-based assessments - Arrangements made for previous medical to be used for SASSA doctors to complete paper based assessments (CDG child not required to undergo new assessment, except in cases where there is no medical, or the medical is inconclusive)
care giver have been called to complete the processing of the applicants
Due to DHA not accepting new applications for IDS, SASSA has made a concession and negotiated with SAPO to open bank accounts using a birth certificate.

## Slide 14: Potential Risks
Item No | RISKS | Mitigations
1. | Risk of not completing all lapsed TDG grant by end of March 2021 | Number of operating days and hours increased to include weekends (overtime). Hybrid Assessment model implemented (health/private doctors) Weekly Monitoring and monitoring corrective actions where provinces are lagging behind Continue beyond March 2021, supplement with SRD where possible
2. | Limited availability of community halls | SASSA offices utilised as assessment sites where health is unable to help assessments at alternative facilities other than the usual health facilities. SASSA trucks used to mitigate the pressures with the facility. Ongoing Robust engagements with local stakeholders such mayors etc
3. | Fatigue of health professionals (Limited availability of doctors ) | Alternative supplementary medical assessment system currently being concluded. folder review medical assessment with telephonic follow up where file does not provide sufficient information..

## Slide 15
Item No | RISK | Mitigations put in place
4. | Temporary closure of offices due to risk exposure – staff contracting acting the virus | Rotation of staff at offices and ensuring that we constantly have PPE Deployment staff from regional and district offices to alternative sites to support local offices Communication to clients on closure of offices and diverting clients to alternative sites
5. | Limited number of people that can be accommodated at service points | Staff rotation introduced assessments at alternative facilities other than the usual health facilities
6. | Criminals queuing and selling spaces | Booking system introduced Number of operating days and hours increased to include weekends (overtime). Referral forms availed online Alternative venues utilized to reduce congestion

## Slide 16: PLANS TO OPERATIONALISE THE INTERVENTIONS

## Slide 17: High Level Project Plan: Target Date for Completion: 31 March 2021
Theme |  | Time frame | Progress
Reinstatements of lapsed TDGs |  | Complete re-instatement of selected TDGs by February 2021 | The reinstatements for selected beneficiaries have been completed 59 years: 9 295 TDG + grant in aid: 6 079 TDG + procurator: 577 TDG + Administrator: 73
Reassessments of Lapsed TDGs completed |  | Complete reassessments of 80% of lapsed grants by end of March 2021 (157,940) 01 February 2021 | 38,484 reassessments have been completed countrywide 75,434 TDG applicants have been booked for assessments as at 26 January 2021 Introduce paper based assessments to fast-track re-assessment.
Reassessments of lapsed CDGs |  | Reassessments all of 11 243 Care Dependency Grants to be concluded by end of March 2021 | 75% of CDG re-assessments have been completed

## Slide 18: High Level Project Plan: Target Date for Completion: 31 March 2021
Theme (Sub-theme) |  |  | Time frame | Progress
Queue Management | Poor queue management |  | Queue management strategy is being implemented immediately | Generally there has been improvement with managing of queues across the country compared to the past few weeks. Express queues have been created for persons with special needs Management teams were dispatched to the different sites to assess the situation and ensure that there are mitigation actions implemented Telephone booking implemented Volunteers deployed to manage queues and have been given name tags and Bibs for visibility Referral letters provided at queue level and also through electronic channels
 | Overcrowding and lack of social distancing |  |  | 
 | Lack of visibility of volunteers |  |  | 

## Slide 19: High Level Project Plan: Target Date for Completion: 31 March 2021
Theme |  | Time frame | Progress
Communication | General poor communication | Improve Communication to citizens, including beneficiaries and stakeholders with immediate effect | Appointed a Communication Agency to supplement SASSA on Communication challenges General communication using local media ramped up. Communication the focus at National, Provincial and Local level through multiple channels – formal and social media Community radio stations activated and in print media. Adverts on print media since December 2020 Engagements with provincial and local JOCS weekly Loudhailers procured for all SASSA offices
 | Stakeholder engagements |  | SASSA commenced engagements with organisations working with persons with disabilities, Consult on modalities to improve communication for persons with disabilities traditional authorities, Churches and Other NGos

## Slide 20: High Level Project Plan: Target Date for Completion: 31 March 2021
Theme |  | Time frame | Progress
Communication | Referral Forms for disability not available on the website SASSA website not user friendly | Completed in January 2021 Completed in 15 February 2021 | Referral forms uploaded on SASSA website
 | Lack of Information on the process to be followed on the website and social media |  | Updated website and Social media channels Further modification of the website is in progress to ensure urgent and emergency issues reflect on the landing page

## Slide 21: High Level Project Plan: Target Date for Completion: 31 March 2021
Theme |  | Time frame | Progress
SASSA’s Capacity to manage client numbers within the universal access design principle | Availability of community halls and service centers | 31 January 2021 To continue throughout project – additional facilities and doctors to be arranged as and when necessary | Additional facilities secured to serve as service points for TDG. For example in WC – 11 SASSA offices are also used as sites for assessments Engagements with the Health practitioners to conduct file assessments supplemented by telephonic interviews In Mpumalanga, for example, hospitals have put site tents dedicated to assist SASSA clients
 | Restricted access to health facilities Referral forms uploaded on SASSA website (GP) |  | 
 | Limited availability of doctors |  | 
 | Ability of clients to make appointments | Completed | Manual booking system (telephonic and in-person) implemented in all local offices as presented under queue management

## Slide 22: High Level Project Plan: Target Date for Completion: 31 March 2021
Theme |  | Time frame | Progress
SASSA’s Capacity to manage client numbers | Call centre accessibility (not reachable) Upgrading the call centre to respond to respond to disability needs | 18 January 2021 | Appointed a service provider to supplement SASSA’s capacity for 6 months 300 call centre agents appointed and trained. There is improvement. Regional landlines: increased the hunting lines in regions Long term: modernization of the call centre
 | Office Space and restricted number of persons that can be serviced including staff that can be in the office due to Covid-19 protocols |  | Compliance to Covid-19 protocols of 50% Alternative sites (e.g. community halls) and venues used for other staff and deployed to assessments sites and SAPO Mobile Trucks are also used with full teams We have additional chairs in some offices for dignity and assist with social distancing

## Slide 23: High Level Project Plan: Target Date for Completion: 31 March 2021
Theme | Time frame | Progress
In addition the Committee raised the issue of long queues at SAPO | Ongoing | Introduced Queue Management System based on the last numbers of the IDs Staggering of SMS Cash flow projections to ensure availability of resources
 | We request the Portfolio Committee to allow SASSA and SAPO to jointly present a detailed plan on Grant payments | 

## Slide 24: Programme of Action (Feb – March 2021)
Communication and Marketing will be accelerated in February – March 2021 focusing on:
  Priority Focus on TDG (Process to apply for TDG; What to do when you cannot get to a SASSA Office; How to make contact with a SASSA Office; Where to complain when you cannot get a service, FAQ on TDG, SRD, etc)
  Social media activations and improvements
  Internal Communication and Staff information
  Stakeholder Engagement: Share information with Constituency offices; targeted Loudhailing, especially in rural areas; information sharing through email)
  Exploration of Retailers & Banking Infrastructure - as points of information
  Web Management: Update Website and ensure it has a user-friendly landing page

## Slide 25: OTHER DETAILED SPECIFIC INTERVENTIONS

## Slide 26: Automation
Legislative restrictions are being addressed through draft regulations which are out for public comment : target date for implementation : 1 April 2021.
Automation of grant application processes is available for grants for older persons, CSG and FCG. The plans are to expand the on-line applications to include disability related grants in the 2021/22 financial year; consider electronic assessment forms for medical officers; utilisation of multiple access channels – including cell phone access
A service provider is onsite to augment call centre processing capacity is assisting with introduction of some automated elements in the call centre environment by end of March 2021:
  Chatbots
  Clearing of email enquiries and complaints
  Call answering for the national number – including afterhours.
An interim process for collection, verification and uploading of new policy mandates for funeral policies under Regulation 26A put in place since September 2020. This process will limit direct client interaction with SASSA (reduce foot traffic at local offices)
SASSA is building on the successes of the Covid-19 R350 SRD grant digitization platform to automate other grant types including disability grants

## Slide 27: Communication: Campaign Progress
Integrated Communication Plan Developed for 04 December 2020 – 31 January 2021
The following activations have been initiated and ongoing:
Digital Information Campaign: information SASSA digital platforms (social media, web, whatapp) on latest SASSA development;
Community Media Activated – Live read, Voice-overs on Temporary Disability Grant;
Community Education: Information campaign targeting high frequency areas with multimedia support; Talk shows; community media;
Staff Information: provide update to staff on SASSA operations and social grant

## Slide 28
ALWAYS ON
*The above messaging is not exhaustive and is meant to be added to and layered.
PRIORITY
Primary:
Temporary Disability Grants
Secondary:
SRD Grants
KEY MESSAGING PER FOCUS AREA
3-PRONGED APPROACH: JAN – MARCH
CRISIS
Information and communication requiring rapid response.
Payment Dates (last
& 1st week of the month)
COVID Safety (once
a week)
Paypoint Safety (once a week)
Grant & general info (once
a week)
Notes: Change image

## Slide 29: Key Messages for activations (December 2020 – February 2021)
Activations focused on the following messages
  SRD Appeals Cut off Date
  SRD Extension to January 2021
  Temporary Disability Grants Lapse
  Care Dependency Grant Lapse
  Financial Literacy: SASSA services are free; Use grant card to transact; keep PIN safe
  Broad Social Grants Information (Types of Grants; Current status of disability grant (temporary/permanent); means test; grant amounts

## Slide 30
SASSA Radio Schedule
SASSA conducted Live reads December 2020 - January 2021

## Slide 31: Recommendation
It is recommended that the Portfolio Committee note;
  Plan to operationalizing the interventions that were presented to the Committee on the 20th January 2021; and
  update on progress to date.

## Slide 32: Thank You Enkosi Dankie