## Sheet1
EXPROPRIATION BILL PROJECT PLAN 2020/21
ESTIMATED COMPLETION DATE: 30 JULY 2021
TASK | DESCRIPTION | SOURCE DOCUMENT(S) | RP | CONTACT DETAILS | START DATE | END DATE | DURATION | STATUS | REASON FOR NON-COMPLETION (if not completed) | REVISED COMPLETION DATE
Introduction & Tabling | Intoduction and tabling of the Expropriation Bill to Parliament. | ATC 145-2020-10-14 | DPWI | Mr Cobus Coetzee (CLO) Cobus.Coetzee@dpw.gov.za | 14/10/2020 | 14/10/2020 | 1 Day | Completed
Process planning | Presentation on the processing of legislation | Briefing note & presentation 2020-10-26 | Committee Secretary | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 26/10/2020 | 26/10/2020 | 1 Day | Completed
Tagging | Classification of the Bill into Section 76 Bill through Joint Tagging Mechanism (JTM) | Classification of Bill document [B23-2020] | JTM | Ms Phumelele Ngema pngema@parliament.gov.za | 28/10/2020 | 29/10/2020 | 2 Days | Completed
Referral to NHTL | 4.1. Referral of the Bill to the National House of Traditional Leaders (NHTL) in accordance with section 18(1) of the Traditional Leadership and Governance Framework Act, 2003 (Act No. 41 of 2003) | ATC 161-2020-11-06 | Bills Office | Mr Neil Bell nbell@parliament.gov.za | 2020-06-11 | 2020-06-11 | 1 Day | Completed
| 4.2. Submission of NHTL comments | Submission documents | NHTL | Mr Abram Sithole SitholeaM@cogta.gov.za | 2020-06-11 | 2020-06-12 | 30 Days | Pending
Briefing by the Department | Briefing on the Expropriation Bill | Presentation on the Expropriation Bill | DPWI | Mr Cobus Coetzee (CLO) Cobus.Coetzee@dpw.gov.za | 24/11/2020 | 24/11/2020 | 1 Day | Completed
Motion of desirability | Adoption of the motion of desirability | Adopted minutes of the meeting | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 24/11/2020 | 24/11/2020 | 1 Day | Completed
Call for public comments | Call for public comments through radio, print and social media | Advertisement | Committee Secretary | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 25/11/2020 | 2020-10-12 | 10 Days | Pending
| Request quotation for advert from service provider | Quotation | Committee Secretary | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 25/11/2020 | 25/11/2020 | 1 Day | Completed
| Send advert to Language Services for translation | Advert mock-up | Committee Secretary | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 25/11/2020 | 26/11/2020 | 2 Days | Pending
| Submit political aplication to HC for approval | Political application | Committee Secretary | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 26/11/2020 | 26/11/2020 | 1 Day | Completed
| Send request for creation of whatsapp line | Active whatsapp line | Committee Secretary | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 25/11/2020 | 2020-02-12 | 3 Days | Pending
| Send a request to ICT for email setup | Active email expropriationbill@parliament.gov.za | Committee Secretary | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 25/11/2020 | 26/11/2020 | 2 Days | Completed
| Send a request to PCS for radio, website and social media advertising | Radio promo, website video promo and social media adverts | Communications Officer | Ms Faith Ndenze, fndenze@parliament.gov.za | 2020-02-12 | 2020-10-02 | 5 Days | Pending
| Collate and submit report on written submissions | Submissions Report | PC on PWI Support |  | 2020-10-12 | 2021-12-02 | 60 Days | Pending
Oral submissions to Parliament | Meetings for oral submissions | Submission documents | Committee Secretary | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 15/2/2021 | 19/2/2021 | 5 Days | Pending
Public Hearings | Public Hearings rollout to all 9 provinces: | PH Report | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 25/2/2021 | 25/6/2021 |  | Pending
| 10.1. Limpopo |  | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 2021-02-01
| 10.2. Mpumalanga |  | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 2021-03-01
| 10.3. North West |  | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 2021-03-01
| 10.4. Gauteng |  | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 2021-04-01
| 10.5. Free State |  | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 2021-04-01
| 10.6. KZN |  | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 2021-05-01
| 10.7. Eastern Cape |  | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 2021-05-01
| 10.8. Northern Cape |  | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 2021-06-01
| 10.9 Western Cape |  | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 2021-06-01
Report | Adoption of the report and submission to the National Assembly through ATC | Report on Expropriation Bill | PC on PWI | Ms Nola Matinise, -83 709 8397 Nmatinise@parliament.gov.za | 30/07/2021 | 30/07/2021