## Slide 1: 2020/21 Q2 Performance Report
Presentation to Portfolio Committee
2 March 2021

## Slide 2
STRATEGIC FOCUS
Impact statement:
Accelerated use of digital technologies to improve quality of life.
Vision:
A world class innovative Skills Institute to ensure an empowered South African citizenry with 4IR capabilities.

## Slide 3
OVERALL PERFORMANCE SUMMARY
NEMISA has achieved 4 of the 11 planned targets set for quarter. This implies that NEMISA only achieved 36%. Detailed performance is outlined in programme development sections.

## Slide 4: PROGRAMME 1: ADMINISTRATION
Programme 1: Administration |  |  |  |  |  |  |  |  | 
No | Annual Target | Q2 Target | Achievement | % Targeted Progress | % Actual Progress | Year-to-date Achievement | Challenges | Corrective Action | Status
1.1 | Approved Transformation and Change Strategy | Draft Transformation and Change Strategy developed and approved by EXCO | Had SETCOM solutions workshop amongst the relevant Board members and EXCO managers saw the joint development of the draft Transformation and Change Strategy. | 50% | 50% | Had SETCOM solutions workshop amongst the relevant Board members and EXCO managers saw the joint development of the draft Transformation and Change Strategy. | None | None | Achieved
1.2 | Multi-Media Production house business plan submitted to board for approval and online interface launched | Draft Business plan developed | The target has been achieved. After several discussions between the Acting CEO, the acting Head of training and the production managers, Multi-Media Production house business plan has been developed. It has been submitted to the PAAC Board subcommittee tor noting and/or recommendations | 50% | 50% | Multi-Media Production house business plan has been developed | None | None | Achieved

## Slide 5
PROGRAMME 2:MULTI STAKEHOLDER COLLABORATION
Programme 2: Multi-stakeholder Collaboration |  |  |  |  |  |  |  |  | 
No | Annual Target | Q2 Target | Achievements | % Targeted Progress | % Actual Progress | Year-to-date Achievement | Challenges | Corrective Action | Status
2.1 | 2 MoUs | 1 MoU with Government institution | An MoU with DCDT has been concluded however it is not counted as the deliverables in the MoU are about the normal budget allocation made to NEMISA by DCDT as a shareholder | 50% | 0% | An MoU with DCDT has been concluded however it is not counted as the deliverables in the MoU are about the normal budget allocation made to NEMISA by DCDT as a shareholder | None | NEMISA is working at signing MoUs with other Government Institutions in Q3 | Not Achieved

## Slide 6
PROGRAMME 3: E-ASTUTENESS DEVELOPMENT
Programme 3: e-Astuteness Development |  |  |  |  |  |  |  | 
Annual Targets | Q2 Targets | Actual Achievement | % Targeted Progress | % Actual Progress | Year-To-Date Achievement | Challenges | Corrective Action | Status
30 000 citizens trained in basic digital literacy | 5 000 | 580 | 17% | 2% | 580 | Agenda item | Agenda item | Not Achieved
150 learners trained in creative media courses | Report on training conducted | Quarter 2 progress report was developed on 10 qualifications rolled out of the creative media courses. 116 students participated in these qualifications. | 50% | 50% | Quarter 2 progress report was developed on 10 qualifications rolled out of the creative media courses. 116 students participated in these qualifications. | None | None | Achieved
1 creative media course developed | Creative media course drafted and submitted to board for inputs | This target was not achieved “Digital Story-Telling on Mobile Device “is the new creative media course that has been identified for development. The specifications for course have been submitted to PAAC Board subcommittee. | 100% | 0% | “Digital Story-Telling on Mobile device” is the new creative media course that has been scoped for development and its specifications submitted to the PAAC Board Committee. | The draft was not ready for submission at the time of finalising Q2 report. Only specifications and the scope of the course were submitted to the PAAC. | The new creative media course developed is a Skills Programme “Digital Story Telling using a Mobile Device”. The scope and specification have been determined. The training manual will be written by 10 December for submission to PAAC by January 2021 | Not Achieved

## Slide 7
PROGRAMME 3: E-ASTUTENESS DEVELOPMENT
3.4 | 800 citizens trained on specialist technology | 150 | 42 | 19% | 5% | 42 | Refer to table 1 on page 15 | Refer to table 1 on page 15 | Not Achieved
3.5 | 500 employees within government departments and institutions participating in digital transformation advocacy and awareness campaigns | 100 | 82 | 20% | 16% | 82 | Refer to table 1 on page 15 | Refer to table 1 on page 15 | Not Achieved
3.6 | Learning management system (LMS) integrated onto cloud platform with 10000 registered users | LMS reconfigured onto cloud 1500 registered users on the cloud platform | The LMS has been configured onto the cloud and can be accessed from the official site https://dsp.nemisa.co.za.Debugging and testing checks are being performed. The delays from Q1 has had a domino effect on this target and hence 1500 users could not be registered onto the LMS. | 50% | 40% | The LMS has been configured onto the cloud and can be accessed from the official site https://dsp.nemisa.co.za | The delays from the SCM processes to obtain an ISP (Internet Service Provider) Q1 has had a domino effect on this target and hence 1500 users could not be registered onto the LMS. | Registration of users will definitely be closely monitored and accelerated in Q3. | Not Achieved
 | Programme 3: e-Astuteness Development |  |  |  |  |  |  |  | 
No | Annual Targets | Q2 Targets | Actual Achievement | % Targeted Progress | % Actual Progress | Year-To-Date Achievement | Challenges | Corrective Action | Status

## Slide 8
PROGRAMME 3: E-ASTUTENESS DEVELOPMENT
COMMENTS ON DEVIATIONS AND INTERVENTIONS FOR PROGRAMME 3 |  |  |  | 
 | Outcomes | Output indicators | Deviation between planned target and actual achievement | Intervention that will be put in place
3.1 | Digitally skilled citizens | Citizens trained in digital literacy | CoLabs underachieved by 88.4% and only managed to train 580 participants due to the delay in finalizing the Annual Business Plans and the restrictions due to the pandemic. Intermediaries are not able to utilize their venues to full capacity and are conducting training sessions in smaller groups. Only 4 CoLabs contributed to the training. | Facilitators were trained to roll out face-to-face and blended training under Level 1, especially in areas with limited or no connectivity. Facilitators are also being trained to facilitate online courses. Facilitators of other CoLabs participated in the online version of the Mobile Digital Literacy course of Limpopo CoLab to gain an understanding of their approach. Onboarding of the 2 CoLabs that have not yet signed the agreement will be prioritized. The online Mobile Digital Literacy course will be rolled out to all CoLabs by the start of the 3rd Quarter using the NEMISA LMS.
3.3 | 1 creative media course developed | Creative media course drafted and submitted to board for inputs | The underachievement is 100% as the target for the quarter was to achieve a developed media course and submit to the Board | The new creative media course developed is a Skills Programme “Digital Story Telling using a Mobile Device”. The scope and specification have been determined. The training manual will be written by 10 December for submission to PAAC by January 2021
3.4 | Increased 4IR participants | Sector users trained in specialist technology | CoLabs underachieved by 72% and one CoLab was responsible for training 42 sector users in specialist technology. | Limpopo CoLab is currently building an online support portal for participants in the IBM training.
3.5 | 500 employees within government departments and institutions participating in digital transformation advocacy and awareness campaigns | Digital transformation advocacy and awareness campaigns conducted | CoLabs underachieved by 18% CoLabs trained 82 of government departments and institutions in digital transformation awareness | The development of a virtual digital transformation workshop is also underway, using the material developed by the Western Cape CoLab.

## Slide 9
PROGRAMME 4:KNOWLEDGE FOR INNOVATION
Programme 4: Knowledge for Innovation |  |  |  |  |  |  |  |  | 
No | Annual Target | Q2 Target | Achievement | % Targeted Progress | % Actual Progress | Year-to-date Achievement | Challenges | Corrective Action | Status
4.1 | 1 Hackathon hosted | Hackathon concept document submitted to board for approval | This target has been achieved. The Concept document for the Data Science Hackathon to held concurrently in all 9 provinces as a 3 day event in February 2021 has been approved by Board. | 50% | 50% | Concept document for the Data Science Hackathon has been approved by Board | None | None | Achieved

## Slide 10
PROGRAMME 5: AGGREGATION FRAMEWORK
Programme 5: Aggregation Framework |  |  |  |  |  |  |  |  | 
 | Annual Target | Q2 Target | Actual Achievement | % Targeted Progress | % Actual Progress | Year-to-date Achievement | Challenges | Corrective Action | Status
5.1 | Monitoring and evaluation framework implemented | Online aggregation system tested | The site is being tested. 4 online courses have been uploaded. NEMISA staff and board members were invited to join the site and try one of the available courses. Since no other users have been registered onto the site, the M&E reports could not be generated from the online aggregation reports. However, M&E reports were generated from our other training provider LMS’s. | 50% | 0% | The site was not tested in Q2 as no report for this was produced to support if any testing was done | The M & E runs on concurrently with the LMS system and there were SCM delays for appointing a service provider for the LMS. | Testing of the site will be prioritised for Q3 | Not Achieved

## Slide 11
There was a total of 48 employees for the quarter.
The following appointments were made in quarter 2:
  Manager: Supply Chain Management
  Specialist: Risk and Compliance
Occupational levels | Approved headcount
Top Management (level 14- 15) | 3
Senior Management (level 13) | 4
Professional qualified (level 11-12) | 7
Skilled level (6-10) | 26
Semi-skilled (1-5) | 8
Total | 48
INSTITUTIONAL DEVELOPMENT

## Slide 12
  NEMISA made a surplus of R1 182 081.00 (Q1: 1 394 608) for the quarter.
  NEMISA is in a good financial health situation.
  The company liquidity is good.
  NEMISA current ratio is 0.99:1 this is the same as the industry norm of 1:1.
  The company is solvent.
  NEMISA debt ratio is 1.1:1, which indicates NEMISA cashflow is sufficient to fund long and short-term liabilities.
FINANCIAL INFORMATION

## Slide 13
Direct programmatic expenditure: Direct expenditure relates to the In-house training unit, implementing the digital skills programme and strengthening the current digital skills CoLab activities.
FINANCIAL INFORMATION
Description | Budget | Actual | Variance
Direct expenditure | R13 378 912 | R1 848 607 | 86%
Breakdown of Direct expenditure
E-Astuteness expenditure: CoLab UL R490 575 and CoLab UWC R490 575
Learner Management system: Website hosting R172 500
In-House Unit: R439 767
YaRona project: R255 190
The variance of 86% is due to training placed on hold due to COVID19 restrictions

## Slide 14
FINANCIAL INFORMATION
Overhead and other expenditure :Overhead and other expenditure relates to administration expenditure that are incurred in running the operations on the entity.
Description | Budget | Actual | Variance
Overhead expenditure | R12 423 000.00 | R11 613 140.00 | 7%
The significant variances of underspending relate to travel and accommodation reduced due to COVID 19 restrictions, catering for meetings due to virtual meetings conducted and EXCO Professional fees/consultants relating to legal services for contracts not utilised.

## Slide 17: THANK YOU