## Slide 1: PRESENTATION TO MOD&MV Q2 & Q3 PERFORMANCE INFORMATION REPORT (FINANCIAL AND NON-FINANCIAL) (JULY – DECEMBER 2020) Acting Director-General: DM MGWEBI (Lt Gen) (rtd) 9 March 2021

## Slide 2: PRESENTATION OUTLINE
Purpose of the presentation
Mandate of the Department
DMV Approved Budget Programme Structure
Executive Summary on Financial Performance
Spend vs Budget by Programme by Economic Classification
Overall Q2 and Q3 Performance Analysis
2020/21 Performance Information
Performance against set targets per Programme
  Programme 1: Administration
  Programme 2: Socio-Economic Support (SES)
  Programme 3: Empowerment and Stakeholder Management (ESM)
Human Resource Management
COVID-19 Report Intervention

## Slide 3: PURPOSE OF THE PRESENTATION
The purpose of the presentation is to appraise the Portfolio Committee on Defence and Military Veterans about the Department’s Q2 and Q3 2020/21FY performance against the Annual Performance Plan 2020/21FY

## Slide 4: MANDATE OF THE DEPARTMENT
Legislative mandate derived from the Military Veterans Act 18 of 2011:
To provide national policy and standards on socio-economic support to military veterans and their dependants, including benefits and entitlements to help realise a dignified, unified, empowered and self-sufficient community of military veterans.

## Slide 5: DMV APPROVED BUDGET PROGRAMME STRUCTURE

## Slide 6
2020/21FY Q2 and Q3
PERFORMANCE INFORMATION

## Slide 7: EXECUTIVE SUMMARY: OVERALL Q2 PERFORMANCE ANALYSIS
During Q2 the Department targeted 14 performance areas and 8 targets were achieved. This brought the overall achievement of targets against plan to 57% for Q2 with a variance of 43%. Underneath is the comparative analysis of the non-financial performance per programme during Q2 of the 2020/21FY.
Q2 Departmental Performance = No. of targets achieved x 100 Total no of targets = 8 x 100 14 = 57% DMV recorded 57% during Q2
 | Administration | SES | ESM | Total
Targets Planned | 04 | 05 | 05 | 14
Targets achieved | 04 | 02 | 2 | 08
Performance rating | 100% | 40% | 40% | 57%

## Slide 8: EXECUTIVE SUMMARY: OVERALL Q3 PERFORMANCE ANALYSIS
During Q3 the Department targeted 13 performance areas and 6 targets were achieved. This brought the overall achievement of targets against plan to 46% for Q3 with a variance of 54%. Underneath is the comparative analysis of the non-financial performance per programme during Q3 of the 2020/21FY.
Q3 Departmental Performance = No. of targets achieved x 100 Total no of targets = 6 x 100 13 = 46% DMV recorded 46% during Q3
 | Administration | SES | ESM | Total
Targets Planned | 03 | 05 | 05 | 13
Targets achieved | 01 | 02 | 03 | 06
Performance rating | 33% | 40% | 60% | 46%

## Slide 9: EXECUTIVE SUMMARY: OVERALL PERFORMANCE ANALYSIS (Q1-Q3)
Chart: Q1-Q3 Overall Performance
| Q1 | Q2 | Q3
Targets Planned | 10 | 14 | 13
Targets achieved | 3 | 8 | 6
Performance rating | 0.3 | 0.57143 | 0.46154
Notes: Q3 performance lower than Q2 performance due to what we have already seen in slide 11.

## Slide 10
PERFORMANCE ON FINANCIAL INFORMATION

## Slide 11
BUDGET VS SPENT Q2
Chart: MILLIONS
| Admin | SES | ESM | Total
Budget | 123527 | 311404 | 111142 | 546073
Expenditure | 50027 | 47180 | 25761 | 122968
% Spent | 0.40499 | 0.15151 | 0.23178 | 0.22519

## Slide 12
BUDGET VS SPENT Q3
Chart: Millions
| Administration | Socio Economic Support | Empowerment And Stakeholder Management | Total
Budget | 138851 | 238392 | 103099 | 480342
Actual Expenditure | 90708 | 106091 | 40740 | 237539
% Spent | 0.65328 | 0.44503 | 0.39515 | 0.49452
% Target

## Slide 13
SPEND VS BUDGET BY PROGRAMME BY ECONOMIC CLASSIFICATION
Q2
Q3

## Slide 14
Budget vs Spend – Key Benefits as at 31 December 2020

## Slide 15
PERFORMANCE AGAINST SET TARGETS PER PROGRAMME

## Slide 16
The Legend Colour Coding | 
Target achieved | 95% - 100%
Target partially achieved | 50% - 94%
Target not achieved | 0% - 49% (less than 50%)

## Slide 17: Q1-Q3 PERFORMANCE ANALYSIS: PROGRAMME 1: ADMINISTRATION
Programme Performance = No. of targets achieved x 100 Total no of targets
Administration Q1 – Q3 2020/21FY |  |  | 
 | Q1 | Q2 | Q3
Targets Planned | 03 | 04 | 03
Targets achieved | 02 | 04 | 01
Performance rating | 67% | 100% | 33%

## Slide 18: PROGRAMME 1: ADMINISTRATION PERFORMANCE INDICATORS AND TARGETS
Indicator ID | Output Indicators | Annual Target | Q1 Target | Q1 Output – Validated | Q2 Target | Q2 Output – Validated | Q3 Target | Quarter 3 Output – Validated | Deviation | Comments |  | Overall progress of indicator (Green, Amber or Red)
 |  |  |  |  |  |  |  |  |  | Reason for Deviation | Corrective Action | 
PPI: 101 | Unqualified audit opinion | Unqualified | - | - | Unqualified | Unqualified | - | - | N/A | N/A | N/A | Achieved in Q2
PPI: 102 | Percentage of legitimate invoices paid within 30 days | 90% | 90% | 69% | 90% | 87% | 90% | 97,7% | 7.7% | Mainly due to composition of invoices paid during Q3 weighted towards payment of benefits where invoice handling processing has since been revised resulting in improvement performance. | Proper tracking of invoices should be closely monitored. This will assist with aligning this target with FOSAD target to 100% payment of suppliers within 30 days. | 
PPI: 103 | Approved ICT Strategy | Approved ICT Strategy | Consultation with Stakeholders | The draft strategy has been developed and is currently being consulted with the business units of the Department | Development of ICT Strategy | The draft strategy has been developed and is on route for approval | Approval of ICT Strategy | ICT Strategy was not approved as planned as a result of receiving more inputs during the approval phase. | Approval of ICT Strategy | The draft strategy was developed, during Q2.The ICT Steering committee decided that the strategy should be consulted with branches again. | ICT is in the process of incorporating the inputs received and the strategy will be presented for approval in Q4. | 
Notes: PPI 103 and 104 still no POE

## Slide 19: PROGRAMME 1: ADMINISTRATION PERFORMANCE INDICATORS AND TARGETS (1)
Indicator ID | Output Indicators | Annual Target | Q1 Target | Q1 Output – Validated | Q2 Target | Q2 Output – Validated | Q3 Target | Quarter 3 Output – Validated | Deviation | Comments |  | Overall progress of indicator (Green, Amber or Red)
 |  |  |  |  |  |  |  |  |  | Reason for Deviation | Corrective Action | 
PPI: 104 | Approved Human Resources Management Strategy | Approved Human Resources Management Strategy | Consultation with Stakeholders | 1st round of consultations under way within the Directorate | Development of HRM Strategy | The draft HRM Strategy has been developed | Approval of HRM Strategy | HRM Strategy was not approved as planned as a result of receiving more inputs during the approval phase | Approval of the HRM Strategy | Concern was raised by other MANCO members particularly from SES that they were not “consulted”. | Same sent to the members | 

## Slide 20: PERFORMANCE ANALYSIS: PROGRAMME 2: SES
SES Q1-Q3 2020/21FY |  |  | 
 | Q1 | Q2 | Q3
Targets Planned | 0 | 05 | 05
Targets achieved | 03 | 02 | 02
Performance rating | 0% | 40% | 40%
Programme Performance = No. of targets achieved x 100 Total no of targets

## Slide 21: Q3 PERFORMANCE ANALYSIS: PROGRAMME 2: SES (1)
Indicator ID | Output Indicators | Annual Target | Q1 Target | Q1 Output – Validated | Q2 Target | Q2 Output – Validated | Q3 Target | Quarter 3 Output – Validated | Deviation | Comments |  | Overall progress of indicator (Green, Amber or Red)
 |  |  |  |  |  |  |  |  |  | Reason for Deviation | Corrective Action | 
PPI: 201 | Number of Military Veterans who are verified and captured on the National Military Veterans ’ Database | 70 000 (5 325) | 64 675 (1 332) | (208) | 67 336 (1 331) | (210) | 68 668 -1 331 | 430 | -901 | Due to the use of manual system, staff was unable to process applications from home as a result of Covid-19 Restrictions. Registration of Statutory Force members was deferred to prepare files for NSF | -Implementation of automated system and the provision of Laptops & Phones. -Statutory Force members applications will be processed again during Q4 | 
*PPI: 202 | Number of Military Veterans provided with newly built houses per year | 355 | - | - | - | - | - | 146 |  | Due to COVID- 19 that forced the CD to reduce staff as well as the capacity challenges the set targets could not be met I accordance with the original plans worsened the situation | Consultations with the DHS were undertaken to deliver for the FY 2020/21 with targets set for the 9 provinces. The COVID -19 is having an impact in how the plans will be delivered. Invoices are being followed up with GP and other provinces. | Not planned for Q3
*PPI: 203 | Number of Military Veterans approved for compensation | 100 | - | - | - | - |  |  | N/A | N/A | N/A | Not planned for Q3
*PPI: 204 | Number of Military Veterans approved for pension | Target was discontinued | - | - | Finalising the enabler: Policy | 0 | 0 | Finalizing the enabler: Regulations | Finalising the enabler: Regulations | - The policy formulation process is underway and not yet finalized - COVID-19 has a negative impact in the stakeholder consultative processes | - Consultations with the various stakeholders are being resuscitated to ensure the fast tracking of the policy development. - The process is envisaged to be accelerated with advent of level one of lockdown | 
Notes: PP1 202 not planned for the quarter but it is reported for tracking performance towards the annual performance

## Slide 22: Q3 PERFORMANCE ANALYSIS: PROGRAMME 2: SES (2)
Indicator ID | Output Indicators | Annual Target | Q1 Target | Q1 Output – Validated | Q2 Target | Q2 Output – Validated | Q3 Target | Quarter 3 Output – Validated | Deviation | Comments |  | Overall progress of indicator (Green, Amber or Red)
 |  |  |  |  |  |  |  |  |  | Reason for Deviation | Corrective Action | 
*PPI: 205 | Number of Military Veterans approved for transport | Target was discontinued | - | - | Finalising the enabler: Policy | 0 | 0 | Finalizing the enabler: Regulations | Finalising the enabler: Regulations | - The policy formulation process is underway and not yet finalised. - COVID-19 has a negative impact in the stakeholder consultative processes. | - Consultations with the various stakeholders are being resuscitated to ensure the fast tracking of the policy development - The process is envisaged to be accelerated with advent of level One of lockdown | 
*PPI: 206 | Number of bursaries provided to Military Veterans and their dependants per year | 3 500 | - | - | - | - | - | N/A | N/A | N/A | N/A | Not planned for Q2
PPI: 207 | Total number of Military Veterans with access to health care services | 18 500 (500) | 18 250 (250) | (56) | 18 325 (75) | (172) | 18 435 (123 ) | 35 (48) | Demand Driven and target decreased due to COVID-19 impact. | Continuous Monitoring | Continuous Monitoring | 
PPI: 208 | Number of Military Veterans and dependents provided with dedicated counselling and treatment. | 400 | 250 | 93 | 50 | 63 | 114 | 64 | Demand driven and demand decreased due to COVID-19 restrictions. | Continuous Monitoring | Continuous Monitoring | 
Notes: PP1: 208 - the sheet named Q3 has 98 beneficiaries not 114 as reported in the SES Q3 report

## Slide 23: PERFORMANCE ANALYSIS: PROGRAMME 3: ESM
ESM: Q1-Q3 2020/21FY |  |  | 
 | Q1 | Q2 | Q3
Targets Planned | 04 | 05 | 05
Targets achieved | 01 | 02 | 03
Performance rating | 25% | 40% | 60%
Programme Performance = No. of targets achieved x 100 Total no of targets

## Slide 24: Q3 PERFORMANCE ANALYSIS: PROGRAMME 3: ESM (1)
Indicator ID | Output Indicators | Annual Target | Q1 Target | Q1 Output – Validated | Q2 Target | Q2 Output – Validated | Q3 Target | Quarter 3 Output – Validated | Deviation | Comments |  | Overall progress of indicator (Green, Amber or Red)
 |  |  |  |  |  |  |  |  |  | Reason for Deviation | Corrective Action | 
PPI: 301 | Number of Memorial Lectures coordinated for Military Veterans | 9 | Consultation with relevant stakeholders | 0 | 3 | 0 | 3 | 2 (35th anniversary of Barny Molokoane; Reburial and memorial lecture of the late Vuyisile Mini) | -1 | Covid-19 lockdown as the nature of the roll-out of the benefit involves contact with clients in both walk-ins and outreach programs in the provinces. | -Utilize electronic platform to circumvent operational challenges brought about by the Covid-19 lockdown. | 
PPI: 302 | Percentage of approved burial claims paid within 30 days | 100% | 100% | 100% | 100% | 98% | 100% | 99% | -1% | Applicant’s bank details failed to verify successfully on National Treasury’s electronic bank verification system | Encourage beneficiaries to submit correct and authentic documentations. | 
PPI: 303 | Number of Military Veterans and their dependants provided with skills development programmes | 1 000 | 250 | 0 | 250 | 87 | 250 | 283 | 33 | Newly adopted proactive approach of taking services to the provinces (Operation Hlasela). | - | 
PPI: 304 | Number of Military Veterans businesses provided with access to business facilitation programmes | 110 | 30 | 3 | 40 | 98 | 70 | 121 | 51 | Proactive approach of the Business Unit | - | 

## Slide 25: Q3 PERFORMANCE ANALYSIS: PROGRAMME 3: ESM (2)
Indicator ID | Output Indicators | Annual Target | Q1 Target | Q1 Output – Validated | Q2 Target | Q2 Output – Validated | Q3 Target | Quarter 3 Output – Validated | Deviation | Comments |  | Overall progress of indicator (Green, Amber or Red)
 |  |  |  |  |  |  |  |  |  | Reason for Deviation | Corrective Action | 
PPI: 305 | Number of Military Veterans provided with employment opportunities | 20 | - | - | 5 | 0 | 5 | 0 | -5 | Prioritisation of Skills Development Operation Hlasela in Provinces | Engagements with relevant stakeholders for employment opportunities | 
PPI: 306 | Number of Military Veterans memorial sites erected per year | 3 | - | - | - | - | - | - | - | - | - | -

## Slide 26: HUMAN RESOURCE STATUS
Transformation/Equity Statistics: Total permanent employees |  |  |  |  |  |  |  |  |  | 
Ser No |  |  | African |  | Coloured |  | Asian |  | White | 
 |  |  | Male | Female | Male | Female | Male | Female | Male | Female
1 | Race distribution of members |  | 63 | 56 | 2 | - |  | 1 | 3 | 2
2 | Gender distribution of members |  | 63 | 56 | 2 | - |  | 1 | 3 | 2
3 | Number of disabled members |  | 1 | - | - | - | - | - | 1 | -
4 | Number of members in the Programmes | P1 | 34 | 37 | - | - | - | 1 | 2 | 1
 |  | P2 | 9 | 11 | - | - | - | - | 1 | 1
 |  | P3 | 20 | 8 | 2 | - | - | - | - | -
5 | Total | 127 | 63 | 56 | 2 | - | - | 1 | 3 | 2
 | Comments/Deviations: None |  |  |  |  |  |  |  |  | 
Transformation/Equity Statistics: Total contract employees |  |  |  |  |  |  |  |  |  | 
Ser No |  |  | African |  | Coloured |  | Asian |  | White | 
 |  |  | Male | Female | Male | Female | Male | Female | Male | Female
1 | Race distribution of members |  | 24 | 36 | - | - | - | - | - | -
2 | Gender distribution of members |  | 24 | 36 | - | - | - | - | - | -
3 | Number of disabled members |  | - | - | - | - | - | - | - | -
4 | Number of members in the Programmes | P1 | 8 | 24 | - | - | - | - | - | -
 |  | P2 | 13 | 9 | - | - | - | - | - | -
 |  | P3 | 3 | 3 | - | - | - | - | - | -
5 | Total | 60 | 24 | 36 | - | - | - | - | - | -
 | Comments/Deviations: |  |  |  |  |  |  |  |  | 

## Slide 27: HUMAN RESOURCE STATUS
Transformation/Equity Statistics: Total interns |  |  |  |  |  |  |  |  |  | 
Ser No |  |  | African |  | Coloured |  | Asian |  | White | 
 |  |  | Male | Female | Male | Female | Male | Female | Male | Female
1 | Race distribution of members |  | 9 | 7 | - | - | - | - | - | -
2 | Gender distribution of members |  | 9 | 7 | - | - | - | - | - | -
3 | Number of disabled members |  | - | - | - | - | - | - | - | -
4 | Number of members in the Programmes | P1 | 8 | 6 | - | - | - | - | - | -
 |  | P2 | 1 | 1 | - | - | - | - | - | -
 |  | P3 | - | - | - | - | - | - | - | -
5 | Total | 16 | 9 | 7 | - | - | - | - | - | -
 | Comments/Deviations: The department currently has 16 Interns, which is contrary to DPSA guidelines of 5%. |  |  |  |  |  |  |  |  | 

## Slide 28: REPORT ON COVID -19 INTERVENTIONS (1)
Reported Covid-19 pandemic Cases
During this quarter 27 employees were affected by Covid-19 pandemic:
  7 positive cases were reported.
  1 death
  19 employees came into contact with a person who tested positive (employees quarantined for 10 days)
PPE
The department procured PPEs for both the DMV HQ and Provincial Offices. Only PPEs for Limpopo and KZN Provinces have been received.
SANITIZATION OF DMV OFFICES
To date the department has sanitized:
    Procured service provider – 22 May 2020
    Scientology Volunteer Ministers – 22 June 2020; 13 and 24 July 2020.
    The Provincial Offices were also sanitized during the month of July 2020 by the Scientology Volunteer ministers.
SCREENING AND SOCIAL DISTANCING
Screening of employees or visitors entering the DMV building is taking place on a daily basis. The Health and Wellness Officer monitor the register daily.
Social Distancing signs are placed inside and outside the building. The committee and the security personnel ensure that employees and visitors adhere to social distancing.
FINANCIAL IMPLICATIONS
The department allocated funds to fight or deal with COVID-19 pandemic. To date the department has spent an amount of R302 776. 90 for internal PPE purposes.

## Slide 29
THANK YOU