## Slide 1
PROGRESS REPORT TO THE PORTFOLIO COMMITTEE ON POLICE
IMPLEMENTATION OF THE DIVISION
FORENSIC SERVICES TURNAROUND STRATEGY AND DNA BACKLOG
12 NOVEMBER 2020 TO 05 MARCH 2021

## Slide 2: Outline
Section 1: Purpose
Section 2: Progress Report: Implementation of the Turnaround Strategy (Corporate Renewal Strategy)
Section 3: Progress on DNA backlog
Section 4: Critical Success Factors
Section 5: Way Forward

## Slide 3: Purpose
Section 1

## Slide 4: Purpose
The purpose is to provide progress report to the Portfolio Committee on Police on the implementation of the Division Forensic Services Turnaround Strategy (Corporate Renewal Strategy) and DNA backlog from 12 November 2020 to 05 March 2021.

## Slide 5: Progress Report: Implementation of the Turnaround Strategy (Corporate Renewal Strategy)
Section 2

## Slide 6: Progress Report Implementation of the Turnaround Strategy (Corporate Renewal Strategy)(1)
Deliverables | Progress
Facilitate the optimal use of forensic services and products by clients (Visible Policing, Detective Service, Courts) | (4) Forensic Services Awareness conducted through internal communication nodal point (Ivory Analysis, Primer Residue, Chain of Custody & Data Base Buccal sample). Weekly DNA backlog management meetings conducted to monitor progress (12). Monthly feedback provided to the Detective Service and the National Prosecuting Authority (NPA) on priority cases (3). Presentation on the optimal use of forensic services products, to Crime Combating Forums (61).
Optimise the financial and SCM process supporting the provision of forensic services | Division Forensic Services operational baseline budget has been increased with R250m from R317 717 000,00 to R563 393 000,00. Funding certificates submitted on 2020-05-28 to the Division: Supply Chain Management (SCM), for activation of procurement processes. Number of contracts awarded = 13: Supply, delivery, installation of water purifying system (2 years); Installation of Roll top covers and rubberising of loading bins for vehicles (2 years); Manufacturing supply, fitment customised steel canopies drawer systems (2 years); Conduct forensic wildlife DNA testing (2 years); Silica membrane based purification kit, genomic DNA (2 years); 2 contracts for Raman Spectrometer (3 years); Supply & delivery of bomb disposal coveralls (3 years); Conversation of ten vehicles into CBRN vehicles (2 years); 2 contracts for Consumables (FTA cards, filter tips, plastic pipettes, POP4, Proteinase K, Centrifuge Tubes) (2 years); Supply and delivery of proficiency tests (2 years); Archiving and retrieval of documents (2 years).

## Slide 7: Progress Report Implementation of the Turnaround Strategy (Corporate Renewal Strategy)(1)
Deliverables | Progress
Optimise the financial and SCM process supporting the provision of forensic services | Number of contracts to be awarded = 2-which will serve at the Departmental Bid Adjudication Committee on 2021/03/8 Number of contracts in evaluation stage = 8. The Eastern Cape DNA laboratory contract was advertised, for 14 days and currently awaiting appointment of engineers. The building will have to be converted to accommodate the establishment of a manual and semi-automated DNA processing system. The building is a non –devolved facility and written approval for the conversion had to be obtained from DPW prior to the awarding of the bid. Approval was obtained on 2021/02/26 together with approval of the plans as submitted by the bidder. The Bid Evaluation Committee will reconvene on 2021/03/16 when a final presentation will be submitted by the recommended bidder where after a submission will be forwarded to the SAPS BAC. Dedicated overtime of R18 500 000,00 allocated to Forensic Science Laboratory for prioritisation of DNA backlog processing project. (12) Weekly contract management and procurement committee meetings are conducted to monitor progress on procurement files and outstanding contracts.

## Slide 8: Progress Report Implementation of the Turnaround Strategy (Corporate Renewal Strategy)(2)
Deliverables | Progress
Capacitate the Division: Forensic Services with adequate staff to meet the demands for forensic products | 175 post promotions were advertised and are awaiting approval Forensic Services and Detective Services have merged into Division. 17 posts from the 175 are to be withdrawn due to lack of pool of candidates etc 158 recommendations have been received 132 posts are in the operational environment and will be announced with effect from 1 April 2021 26 posts are in the support environment have been placed on hold until the matching and placing exercise has been finalized Enlistment of 150 new entry level Forensic Analysts (Warrant Officer) 150 posts have been approved in the 2021/22 financial year Enlistments to take place with effect from 1 July 2021. 13 posts were advertised, awaiting approval 3 internal: (Staff Officer/Driver/PA): filled effective date 01 October 2020 and 10 external: (FSA/Messenger/Data Typist/Administration Clerks), 9 to be filled 01 April 2021 and 1 withdrawn. 17 General Worker posts were advertised 9 filled on 01 October 2020, and 8 to be filled 01 April 2021. 69 re-enlistment applications considered Only 33 applications received (8 Constables / 7 Sergeants / 18 Warrant Officers). 11 medicals authorized to date (Const and Sgt). 22 applications are under consideration.
Modernise and maintain specialised forensic equipment & methods | (4) Contracts approved for maintenance, service and calibration of equipment: - 2 contracts for Raman Spectrometer; - Supply, delivery, installation of water purifying system - Manufacturing supply, fitment customised steel canopies drawer systems Technical Advisory Committee established for benchmarking and piloting of new modern and specialised forensic equipment, methods to meet international standards and current priority is focused on Mobile DNA Laboratory capacity. Research and feasibility study is being conducted. Three Rapid DNA equipment validation process finalised and ready for utilisation within Forensic Science Laboratory.

## Slide 9: Progress Report Implementation of the Turnaround Strategy (Corporate Renewal Strategy)(3)
Deliverables | Progress
Establish specialised forensic process optimisation and development capacity to support the need for forensic products | Enlistment of 150 new entry level Forensic Analysts (Warrant Officer) 150 posts have been approved in the 2021/22 financial year Enlistments to take place with effect from 1 July 2021. Number of members trained on ETDP = 32 Number Forensic Science Laboratory Learning Programmes i.t.o Organisational Standard = 38 Number of Forensic Science Laboratory Learning Programme on TAS = 60 Number of Forensic Analysts trained = 1360 Number of mentorship programme = 50 Number of members completed mentorship programme = 1323 Weekly Priority Committee meetings for consideration of critical procurement files, to support the need for forensic products and address the DNA backlog.

## Slide 10: Progress Report Implementation of the Turnaround Strategy (Corporate Renewal Strategy)(3)
Deliverables | Progress
Enhance management of forensic items, exhibit and record storage | Monthly stocktaking certificates submitted by store managers. Announced and unannounced compliance inspections conducted at critical facilities and environments, to support performance and mitigate audit findings. Archiving and retrieval of documents contract acquired for 2 years. 37 technical audits conducted. Weekly 1st and 2nd level inspections conducted by commanders. FSL-Admin system enhancement in progress by the Division: Technology Management Services (TMS) and SITA. 24 Hour CCTV coverage and monitoring, at critical sites. 24/7 Access Control System implemented, at all critical sites.

## Slide 11: Progress Report Implementation of the Turnaround Strategy (Corporate Renewal Strategy)(4)
Deliverables | Progress
Maintain forensic facilities in accordance with ISO standards and OHSACT, in order to ensure value for money | Health Risk Management Contract awarded and 4 872 medical surveillance and vaccinations conducted out of 10 104 authorisations, according to the programme of the Service Provider. SHE Compliance Representatives appointed, to ensure compliance on a daily basis. SHE committees are convened, as prescribed to ensure compliance. Fumigation of facilities conducted on a quarterly basis (1 x fumigation conducted). Decontamination of facilities affected by COVID-19 was conducted, within 24-hours, to ensure reoccupation of the critical facilities for Forensic Science Laboratory. Waste Removal conducted on quotation basis and all waste being removed by the appointed service provider and monitored by management.
Modernise IT systems to support optimal processing of forensic exhibit material and records | Forensic Services has 20 systems to provide the modernised IT systems support to the environment. FSL Admin system enhancement by Division: TMS and SITA underway, to provide electronic track and trace capacity, according to the project plan. On the 25th February2021: Demonstration of the developed Forensic Exhibits Management on FSL Admin was conducted to Division: Forensic Services management. Monthly progress report is submitted.

## Slide 12: DNA Progress
Section 3

## Slide 13: Project Plan on Processing DNA Backlog (1)
Biology HQ – Unassigned entries | DNA HQ E = 14 057 Plan to deal with an average of 5 cases, per day, to a maximum of 40 analysts. 40 X 5 = 200 = 1 000 per week, current backlog to be depleted in 14 weeks. Incoming work = an average of 1 000 cases, per week. At the end of 14 weeks = 14 000 cases. Overtime hours required resulting in 2 000 cases completed in a 2 month period, resulting in a carry over of +/- 12 000 cases to the fourth quarter. Additional overtime in the fourth quarter will be needed to address this, to ensure that the carry over into the new financial year, is minimal. RI HQ E = 43 068 | Status: On 2021-02-10 there were 23 294 unassigned entries (9 237 increase). On 2021-02-10, there were 43 892 RI HQ “E” entries (824 increase).
 |  | Progress: Short term plan= 42 quantification kits approved on quotation (35 in PTA and 7 at W/C) Medium term= ±4mil for quantification kits pending treasury outcome to sustain PTA and W/C for a period of 3months operation. Long term: bidding process in progress, validation and training to be effected after awarding. Outstanding vaccination of 393 forensic analysts being prioritised. COVID-19 pandemic disruptions leading to closure of laboratories and buildings decontaminated.

## Slide 14: Project Plan on Processing DNA Backlog (2)
Biology HQ – Entries in process | The total cases in process = 25 633. Expected incoming for the next 6 weeks = 6 000 cases. Total cases expected to be handled by Biology for the next quarter = 31 633. | Status: On 2021-02-10 there were 36 347 DNA and RI HQ “A” entries in process. (10 714 increase)
 |  | Progress: Short term plan= 42 quantification kits approved on quotation (35 in PTA and 7 at W/C) Medium term= ±4mil for quantification kits pending treasury outcome to sustain PTA and W/C for a period of 3months operation. Long term: bidding process in progress, validation and training to be effected after awarding. Outstanding vaccination of 393 forensic analysts being prioritised. COVID-19 pandemic disruptions leading to closure of laboratories and buildings decontaminated.

## Slide 15: Project Plan on Processing DNA Backlog (3)
Biology WC –Unassigned entries | DNA WC E = 9 956 Plan to deal with an average of 5 cases, per day, to a maximum of 32 analysts. 32 X 5 = 160 = 800 per week, current backlog to be depleted in 13 weeks. Incoming work = an average of 500 cases, per week. At the end of 14 weeks = 7 000 cases. Overtime hours required, resulting in 2 000 cases completed in a 2 month period, resulting in a carry over of +/- 5000 cases to the fourth quarter. Additional overtime, in the fourth quarter, will be needed to address this, to ensure that the carry over into the new financial year, is minimal. RI WC E = 22 585, on 2021-02-10. RI Index backlog is currently, about 1 month. WC has 3 lanes, with all Instruments running, the current backlog can be depleted, in 10 working days. | Status: On 2021-02-10 there were 12 024 DNA WC “E” unassigned entries (2 068 increase). On there were 20 849 RI WC “E” unassigned entries (1 736 decrease)
 |  | Progress: Short term plan= 42 quantification kits approved on quotation (35 in PTA and 7 at W/C) Medium term= ±4mil for quantification kits pending treasury outcome to sustain PTA and W/C for a period of 3 months operation. Long term: bidding process in progress, validation and training to be effected after awarding. Outstanding vaccination of 393 forensic analysts being prioritised. COVID-19 pandemic disruptions leading to closure of laboratories and buildings decontaminated.

## Slide 16: Project Plan on Processing DNA Backlog (4)
Biology WC – Entries in process | The total number of cases in process = 13 933. Expected incoming, for the next 6 weeks = 3 000 cases. Total cases expected to be handled by Biology, for the next quarter = 16 933. | Status: On 2021-02-10 there were 28 869 DNA and RI HQ “A” entries in process ( 14 936 increase).
 |  | Progress: Short term plan= 42 quantification kits approved on quotation (35 in PTA and 7 at W/C) Medium term= ±4mil for quantification kits pending treasury outcome to sustain PTA and W/C for a period of 3 months operation. Long term: bidding process in progress, validation and training to be effected after awarding. Outstanding vaccination of 393 forensic analysts being prioritised. Unavailability of PPE and procurement process at an advanced stage. COVID-19 pandemic disruptions leading to closure of laboratories.

## Slide 17: Project Plan on Processing DNA Backlog (5)
Biology EC – Unassigned entries | DNA EC E = 7 258 cases Plan to deal with an average of 5 cases, per day, to a maximum of 8 analysts. 8 X 5 = 40 = 200 per week, current backlog to be depleted in 36 weeks. Incoming work = an average of 400 cases per week. At the end of 36 weeks = 14 400 cases. Overtime hours required, resulting in 400 cases completed in a 2 month period, resulting in a carry over of +/- 14000 cases to the fourth quarter. Additional overtime, in the fourth quarter, will be needed to address this, to ensure that the carry over into the new financial year, is minimal. In addition to the above, plans will be made to transfer at least 50% of these entries to the other 3 regions, dependent on how the plan unfolds, per region. KZN should be in a better position to assist the EC, from January 2021. HQ and WC can also start assisting towards the end of the financial year. | Status: On 2021-02-10 there were 3 200 unassigned entries (4 058 decrease)
 |  | Progress: Unavailability of polyester swabs for Evidence Recovery and procurement process is at an advanced stage. Outstanding vaccination of 393 forensic analysts being prioritised. COVID-19 pandemic disruptions leading to closure of laboratories and buildings decontaminated.

## Slide 18: Project Plan on Processing DNA Backlog (6)
Biology EC – Entries in process | Total number of cases in process = 116. Expected incoming for the next 6 weeks = 3 000 cases. Total number of cases expected to be handled by Biology for the next quarter = 16 933. | Status: On 2021-02-10 there were 256 entries, in process (140 increase)
 |  | Progress: Unavailability of PPE and procurement process at an advanced stage. Unavailability of polyester swabs for Evidence Recovery. Outstanding vaccination of 393 forensic analysts being prioritised. COVID-19 pandemic disruptions leading to closure of laboratories and buildings decontaminated.

## Slide 19: Project Plan on Processing DNA Backlog (7)
Biology KZN – Unassigned entries | DNA KZN E = 3 898 cases Plan to deal with an average of 5 cases, per day, to a maximum of 8 analysts. 8 X 5 = 40 = 200 per week, current backlog to be depleted in 36 weeks. Incoming work = an average of 300 cases, per week. At the end of 14 weeks = 7 000 cases. Overtime hours required, resulting in 2 000 cases completed in a 2 month period, resulting in a carry over of +/- 5 000 cases to the fourth quarter. Additional overtime, in the fourth quarter, will be needed to address this, to ensure that the carry over into the new financial year, is minimal. RI E = 22 585 cases, on 2021-02-10. RI Index backlog is currently about 1 month. WC has 3 lanes, with all Instruments running, the current backlog can be depleted, in 10 working days. | Status: On 2021-02-10 there was 4 406, unassigned entries (508 increase) Progress: Unavailability of PPE and procurement process at an advanced stage. Unavailability of polyester swabs for Evidence Recovery. Outstanding vaccination of 393 forensic analysts being prioritised. COVID-19 pandemic disruptions leading to closure of laboratories and buildings decontaminated.

## Slide 20: Project Plan on Processing DNA Backlog (8)
Biology KZN – Entries in process | Total number of cases in process = 40. Expected incoming for the next 6 weeks = 2 400 cases. Total cases expected to be handled by Biology for the next quarter = 2 440. Due to the last 12 months downtime, as a result of the lack of consumables, Biology can now address all incoming work, including the backlog, with the utilisation of overtime hours. After a 2 month period, if members receive their vaccines as required, the total cases on hand should be approximately 5% of the total, depicted above. | On 2021-02-10 there were 34 entries in process (06 decrease)
 |  | Progress: Unavailability of PPE and procurement process at an advanced stage. Unavailability of polyester swabs for Evidence Recovery. Outstanding vaccination of 393 forensic analysts being prioritised. COVID-19 pandemic disruptions leading to closure of laboratories and buildings decontaminated.

## Slide 21: CRITICAL SUCCESS FACTORS
Section 4

## Slide 22: Critical Success Factors
Awarding of all outstanding contracts, especially for consumables that are critical in addressing the DNA backlog, according to the project plan.
Approval for EC Forensic Science Laboratory was obtained on 2021/02/26 together with approval of the plans as submitted by the bidder. The Bid Evaluation Committee will reconvene on 2021/03/16 when a final presentation will be submitted by the recommended bidder where after a submission will be forwarded to the SAPS BAC.
Maintain regular meetings with internal and external stakeholders, to identify and prioritise their needs.
Prioritisation and finalisation of all 393 vaccination of outstanding forensic analysts.
Prioritisation and finalisation of electronic track and trace system capability that is on phase 2.

## Slide 23: Way Forward
Section 5

## Slide 24: Way Forward
The Division: Forensic Services supported by all relevant role players is committed to providing quality forensic products and address DNA backlog through a multi-disciplinary action plan.
Multi-disciplinary steering committee convened on 04 March 2021 to develop multi-disciplinary action plan supported by partnership policing to prioritise and finalise DNA backlog.

## Slide 25
Thank you