## Slide 1: Preparations for the 2021 Local Government Elections: SALGA Framework for the Transition
PC COGTA 6 APRIL ‘21

## Slide 2: LOCAL GOVERNMENT TRANSITION: 2016-2021 TO 2021 - 2026
PRE-ELECTIONS
Voter Registration
Proclamation of Election Date
DURING ELECTIONS
Ward & PR Elections
Declaration of Election Results
POST-ELECTIONS
Inaugural Council Meetings (Metros & Local)
Inaugural Council Meetings (Districts)
Nomination of Candidates
2016 – 21 TERM OF OFFICE
2021- 26 TERM OF OFFICE

## Slide 3: PROBLEM STATEMENT
Municipalities would require support during the transition - pre, during and post the elections;
SALGA and COGTA agreed to partner in providing support to municipalities during the transition;
SALGA NEC on 31 March ‘21 approved a Framework for the Transition - to guide municipalities through the transition;
The Framework includes the governance support to be provided to municipalities prior to, during and after the election.

## Slide 4: PRE - ELECTIONS
 | DELIVERABLES | PRODUCTS (OUTPUT)
1. | Develop a comprehensive Councillor Induction Programme | Councillor Induction Manual
2. | Develop and roll out guidelines as governance support | Appointment and terms of reference for MEOs Funding of municipal activities related to elections Preparation of Mayco/Exco handover reports Protocol related to overall administration of municipalities during transition Extent of delegation of powers to heads of administration during transition Role of MM during transition
3. | Develop Social Plan for Councillors | Development of Register of Assets in possession of Councillors Guidelines on Withdrawal from Pension Funds Guidelines on Gratuity Payment and related matters Remuneration and benefits to incoming and outgoing councillors

## Slide 5: PRE - ELECTIONS
 | DELIVERABLES | PRODUCTS (OUTPUT)
4. | Develop of “Day 1” Guidelines | Convening the Inaugural Council meeting and related Agenda Convening of Mayoral / EXCO Lekgotla and related Agenda Appointment of Municipal and Senior Managers Briefing of Municipal Staff by Mayor, Mayco/Exco Establishment and functioning of Mayco / Exco Relationship between Local and District Municipalities Relationship between councillors and officials Roles and responsibilities of TROIKA Delegations of Authority Rules of Order Ward Committee establishment and election Framework
5. | Local Government (Pre-Elections) Profiling Campaign | Increase awareness about local government (governance, mandate, powers & functions) Showcase the value chain of municipal services Create and increase awareness around service delivery of municipalities in the past 20 years

## Slide 6: POST- ELECTIONS
 | DELIVERABLES | PRODUCTS (OUTPUT)
1. | Roll out comprehensive Councillor Induction Programme across all 9 provinces | Councillor Induction Programme
2. | Roll out Social Plan for Councillors | Support to municipalities on Withdrawal of former Councillors from Pension Funds – in line with guideline Facilitate Gratuity Payment and related matters Remuneration guidance for incoming and outgoing councillors

## Slide 7: POST-ELECTIONS
 | DELIVERABLES | PRODUCTS (OUTPUT)
3. | Roll out “Day 1” Guidelines | Convening the Inaugural Council meeting and related Agenda Convening of Mayoral / EXCO Lekgotla and related Agenda Appointment of Municipal and Senior Managers Briefing of Municipal Staff by Mayor, Mayco/Exco Establishment and functioning of Mayco / Exco Relationship between Local and District Municipalities Relationship between councillors and officials Roles and responsibilities of TROIKA Delegations of Authority Rules of Order Ward Committee establishment and election Framework
5. | Local Government (Post-Elections) Profiling Campaign | Increase awareness about the convening of first council meetings and related process of the election of TROIKA Profile newly elected councillors, Mayors, Speakers, Chief Whips, Mayco/Exco members

## Slide 8: RECOMMENDATIONS
It is recommended that the PC COGTA:
NOTE the support to be provided to municipalities pre, during and post the 2021 Local Government Elections.

## Slide 9: Thank You