(

i

)

State of readiness for 2021 Local Government Elections

(

ii

)

Closing out report of S189 process

TABLE OF CONTENTS

•

(

i

)

State of readiness for Local Government Elections

•

(

ii) S189 Closing out report

2

(

i

)

State of readiness for LGE

3

4

1.1

PURPOSE OF SUBMISSION

–

SECTION (

i

)

The

purpose

of

this

submission

is

to

appraise

the

Portfolio

Committee

on

Communications

(

PCC

)

about

the

state

of

readiness

of

the

SABC

.

4

# 1.2 BACKGROUND

- The 2021 local government elections come at a difficult time for South Africa as the country and the world are grappling with the COVID19 pandemic.

- The 2021 municipal polls will be held on the 27th October 2021, as announced by the President recently. The SABC’s plan for the 2021 local government elections is in line with the Broadcasting Act which requires the SABC to encourage the development of South African expression by providing content in all South African official languages, a wide range of programming that offers a plurality of views and a variety of news, information, and analysis from a South African point of view; and to advance the national and public interest.

- The Electronic Communications Act also requires the SABC to provide fair and equitable coverage of elections, monitored by the Independent

Communications Authority of South Africa.

55

6

1.3

SABC READINESS

•

The

SABC’s

comprehensive

business

continuity

plans

and

solutions

to

mitigate

Covid

-

19

,

will

be

leveraged

for

the

Local

Government

Elections

.

The

SABC

will

use

established

technologies

that

have

been

deployed

in

the

previous

elections

to

ensure

a

smooth

and

successful

operations

.

The

SABC

further

leverages

off

its

close

relationship

with

the

Independent

Electoral

Commission

(

IEC

)

which

delivers

both

the

infrastructure

and

linking

solutions

at

the

various

Result

Operation

Centers

(

ROC

)

.

The

Operational

Centers

are

based

in

all

Provinces

headquartered

at

the

ROC

in

Tshwane

.

•

The

SABC

will

deploy

resources

to

the

IEC

centres,

which

will

include

mobile

units

that

will

be

used

within

the

IEC

centers

or

can

be

deployed

elsewhere

in

the

regions

.

•

The

SABC

assures

the

committee

about

its

ability

and

capability

to

deliver

a

successful

Local

Government

Elections

(

LGE

)

.

6

(

ii) S189 CLOSE OUT

REPORT

7

8

2.1

PURPOSE OF SUBMISSION

–

SECTION (ii)

The

purpose

of

this

submission

is

to

provide

the

Portfolio

Committee

on

Communications

PCC

)

(

with

an

update

on

the

conclusion

of

the

Section

189

process

.

8

# 2.3 THE JOB EVALUATION PROCESS

After the completion of the Section 189 process that ended on 31 December 2020, the SABC started the process of transitioning into the new optimal structure to enable the Target Operating Model. This process was preceded by an organisation-wide job evaluation exercise which ensured that all new jobs are evaluated, advertised and filled at the correct levels. The outcomes of this process were implemented in line with our prevailing HR policies. The primary purpose of the job evaluation process was to set the SABC on a road to self-correct its remuneration bill as well as uphold the principle of equal remuneration for the work of equal value.

This was achieved through the full utilisation of the current pay scale by making almost all offers within the pay scale ranges including Entry Zone, contrary to the initial decision/practice (13yrs old practice) of making all offers at the midpoint of the pay scale. This old practise of making all offers at midpoint of the pay scale, resulted in increasing the overall compensation bill. The job evaluation process has helped in benchmarking our roles with the industry, creating parity in scale codes and remuneration throughout the organisations, and rectified past anomalies in salaries and scale codes. The job evaluation process has helped in reducing the overall compensation bill.

1010

11

2.4

THE JOB EVALUATION PROCESS

-

CONTINUATION

11

Table

1

:

Total

Retrenchment

Terminations

–

31

March

2021

Termination

Voluntary

Forced

Grand Total

Grand Total

346

275

621

The

total

number

of

employees

that

will

leave

the

organisation

at

end

of

March

2021

is

621

,

of

which

346

are

voluntary

.

This

cohort

of

voluntary

employees

refer

to

all

those

employees

who

chose

severance

as

the

first

option

and

decided

not

to

participate

in

any

alternative

seeking

and

recruitment

process

.

The

number

of

employees

exiting

is

higher

than

originally

anticipated,

primarily

due

to

:

i

)

(

the

impact

of

alternative

lower

jobs

to

employees’

retirement

benefits

and

fund

value

;

)

(

ii

no

competency

match

and

qualification(s)

for

many

employees

;

)

iii

(

language

requirements

for

African

Language

news

programming

were

not

met

;

)

(

iv

and

unfilled

positions,

including

those

that

became

vacant

during

the

notice

month

.

This

has

resulted

in

a

total

of

468

vacancies

within

the

new

structure

.

The

vacancy

committee

will

review

these

vacancies

and

only

critical

positions

will

be

filled

to

ensure

the

salary

bill

is

not

increased

.

12

2.4

THE JOB EVALUATION PROCESS

-

CONTINUATION

12

Table

2

:

Severance

Analysis

for

31

March

2021

The

final

number

of

employees

who

exited

the

Corporation

on

31

March

2021

was

621

,

with

a

total

severance

cost

of

about

R

164

million,

which

will

be

recovered

within

5

months

.

The

Total

Guaranteed

Remuneration

Package

(

TGRP

)

of

those

621

positions

is

about

R

457

million

per

year

.

This

means

that

our

total

salary

bill

target

of

R

700

million

reduction

will

be

fully

realised

over

a

3

-

year

period

(

by

2023

/

24

)

as

the

annual

salary

increase

freeze

of

at

most

3

years

is

implemented,

plus

the

3

alternatives

proposed

by

management

.

This

potential

savings

will

however

be

reduced

when

the

current

468

vacancies

are

filled

.

Management

will

ensure

only

critical

vacancies

are

filled

to

mitigate

any

risk

of

an

increase

in

the

compensation

bill

.

Number

TGRP Savings in 2021/22

Cost of

Severance

Break

-

even

Months

Annual TGRP

621

292 636 897

164 376 509

4

19

,

457 013 406

13

2.4

THE JOB EVALUATION PROCESS

-

CONTINUATION

13

A

follow

-

up

report

will

focus

on

:

(

i

)

the

workforce

profile

post

Section

189

;

(

ii

)

the

integration

of

new

structures

;

and

(

iii

)

the

four

(

4

)

alternatives

that

must

still

be

agreed

to

by

labour

to

prevent

future

job

losses

.

14

2.5

TRANSITION INTO THE NEW STRUCTURE

14

The

transition

to

the

new

structure

has

commenced

in

January

2021

and

will

be

completed

this

month,

with

March

2021

being

a

notice

period

for

employees

not

placed

.

The

acceptance

of

the

4

alternatives

is

key,

given

that

the

Board

approved

the

payroll

reduction

of

R

700

m

and

600

affected

employees

.

The

only

outstanding

matter

for

Organised

Labour

to

make

a

concession

on

is

the

following

4

key

alternatives

:

(

i

)

the

annual

increase

freeze

;

(

ii

)

the

reduction

of

annual

leave

days

for

management

from

35

days

to

28

days

;

(

iii

)

the

reduction

of

sick

leave

from

30

days

per

year

to

36

days

in

three

-

year

cycle

;

and

)

iv

(

the

approval

of

Section

197

for

Call

Centre

and

TV

Licence

operations

.

15

2.6

TOTAL SEVERANCE AND TERMINATIONS CONT.

15

Many

employees

were

not

successful

in

seeking

alternative

placements

due

to

them

not

meeting

the

minimum

requirements

of

the

roles

and/or

were

found

not

to

be

suitable

for

positions

they

had

applied

for

.

Conversely,

a

significant

number

of

competent

employees

who

occupied

surplus

or

redundant

positions,

who

could

possibly

have

been

placed

in

new

roles,

took

advantage

of

the

severance

packages

and

their

marketability,

and

chose

to

exit

the

Corporation

.

The

entire

process

required

a

delicate

balance

between

transitioning

to

the

new

structure

while

retaining

efficient

operations

versus

achieving

reduced

total

cost

of

compensation

at

all

cost

and

compromise

operations

.

The

remaining

vacancies,

where

suitable

candidates

could

not

be

sourced,

will

enable

the

organisation

to

renew

itself

with

new

talent

at

the

right

remuneration

levels,

as

such

redressing

the

bloated

salary

bill

further

over

the

coming

years

.

The

severance

pay

will

be

funded

from

the

operational

cash

that

has

been

set

aside

each

month

since

the

process

was

initiated

.

17

2.8

CONCLUSION

17

The

SABC

acknowledges

that

the

retrenchment

process

was

difficult

for

all

stakeholders

and

emotionally

charged

at

times

.

The

extended

process

also

created

prolonged

uncertainty

.

However,

it

was

a

necessary

part

of

the

SABC’s

turnaround

plan

to

reposition

the

public

broadcaster,

ensure

its

stability

and

financially

sustainability

and

allow

the

Corporation

to

execute

its

public

mandate

to

serve

all

the

people

of

South

Africa

in

all

our

languages

and

across

all

platforms

.

The

importance

of

transforming

the

SABC

into

a

learning

organisation

in

which

talent

capability

are

constantly

transformed

to

align

to

business

demands

are

critical

.

This

will

be

enabled

through

the

implementation

of

the

recently

approved

Talent

and

Performance

Management

frameworks

.

This

will

ensure

that

the

SABC

does

not

have

a

bloated

structure

with

28

%

of

its

workforce

not

possessing

the

minimum

qualifications

required

for

their

respective

jobs

.

In

addition,

this

will

prepare

the

Corporation

to

successfully

implement

its

turnaround

plan

to

fulfil

its

public

mandate,

effectively

and

efficiently

.

-

END

-