## Slide 1
SUGARCANE
VALUE CHAIN MASTER PLAN TO 2030
1

## Slide 2
“The Master Plan seeks to create a diversified and globally competitive, sustainable and transformed sugarcane-based value chain that actively contributes to South Africa’s economic and social development, creating prosperity for stakeholders in the sugarcane value chain, the wider bio-economy, society and the environment.”
(Government Gazette, 23 June 2020)
SUGARCANE VALUE CHAIN MASTER PLAN TO 2030
2

## Slide 3: THE JOURNEY
Nov 2017
Trade and Industry PPC initiates transformation journey for sugar industry
June 2019
President Ramaphosa announces Sector Master Plan Approach
Aug 2019
Sunrise Plan for the Sugar Industry
Aug 2018
Dollar Based Reference Price increased from $566 to $680
April 2018
Sugar Industry March for Tariff
Dec 2018
Trade and Industry PPC: Sugar Industry commits R1b over 5 years for transformation
3
November 2019
SASA Requests Designation of the Sugar Industry
October 2020
Sugar Industry Competition Exemption received
January 2021
Task Teams Initiated
Nov 2020
Master Plan Signed by Stakeholders
June 2020
High level Master Plan Gazetted, Sugar industry designated
Sept 2019
Master Plan engagement Process initiated

## Slide 4: COMPETITION COMMISSION EXEMPTION
ACTION COMMITMENTS
Restore local market offtake
Producer Price Restraint
Strategic Trade Protection
Job Retention and Mitigation
Small-Scale Grower Retention and Support*
Transformation
Managed Industry Restructuring Plan*
* Exempted
TASK TEAMS
SACU Harmonisation*
Job Retention and Mitigation strategy
Small-scale grower masterplan*
Transformation
Crop diversification
Sugarcane-based value chain diversification strategy
Product Tax Policy
Managed Industry Restructuring*
Local offtake commitments
Sugar Converters
4

## Slide 5: TASK TEAMS CONVENED AND CHAIRED BY SASA
TT3 : Small-scale grower masterplan –
chaired by SASA vice chairperson Joanmariae Fubbs.
TT4 : Transformation –
chaired by SASA chairperson Sindi Mabaso-Koyana
TT8 : Managed industry restructuring –
chaired by SASA chairperson Sindi Mabaso-Koyana
SASA management serves on all Task Teams excluding TT2 (job retention) and TT 5 (crop diversification)
5

## Slide 6: PROGRESS ON TASK TEAM 3: SMALL SCALE GROWERS MASTERPLAN
Short Term Plan | Current status | Challenges | Target date
Development of a preferential pricing model (premium payment) structure to support SSG’s while longer term support structures are developed. | Stakeholder discussions regarding what constitutes the Universe of Small Scale Growers. Once agreed, will proceed to determine the premium price. | Members currently hold divergent views in terms of the quantum of the premium payment. Failing consensus, the matter will be escalated to the Executive Oversight Committee. | By 31 March 2021, deadline not met, new deadline of 31 May 2021
6

## Slide 7
PROGRESS ON TASK TEAM 3: SMALL SCALE GROWERS MASTERPLAN
Medium Term Plan | Current status | Challenges | Target date
Determination of a Problem Statement for SSG’s, using existing studies as well as data collected and analysed from growers and millers. The medium-term work runs in parallel with the Competition Exemption expiry on 30 June 2021. | Need to carefully scope this work to yield the best value. Commenced with determination of metadata and identification of data sources. This work must be undertaken during the exemption period (by 30 June 2021) due to its confidential nature. | Overlap between data required for TT3, and information needed for work in TT4 (Transformation). It is anticipated that work, including the appointment of a service provider, may not be completed within the current exemption period. | TBD – mid 2021
Long Term Plan | Not yet started |  | 
7

## Slide 8
PROGRESS ON TASK TEAM 4: TRANSFORMATION
Short Term Plan | Current status | Challenges | Target date
Stakeholder engagements with the leadership of all industry associations, milling companies, other industry bodies and government in order to obtain insights on trends, achievements, gaps and challenges with regard to transformation | Eight of eleven transformation bilateral engagements already held. Next engagement planned for 14 May. | Availability of key stakeholders/ postponement of engagements | End May 2021
8

## Slide 9
PROGRESS ON TASK TEAM 4: TRANSFORMATION
Medium Term Plan | Current status | Challenges | Target dates
Perform grower baseline study | Grower baseline study terms of reference approved. Appoint Service Providers to calculate baseline and determine challenges preventing/ delaying achievement of 51% target for delivery of cane by black growers. | None anticipated. Need to align closely with TT4 data collection process. | By August 2021
Review the existing sugar industry transformation strategy | Industry 5-year plan and transformation commitments previously presented to PPC, will be used as a baseline to formulate strategic framework that underpins the Masterplan terms of reference and action commitments. | None anticipated. | By December 2021
9

## Slide 10
PROGRESS ON TASK TEAM 8: MANAGED INDUSTRY RESTRUCTURING
Output | Current status | Challenges | Target dates
Appoint industry restructuring expert service provider | Tender published: 19 April 2021 Submission of bids: 5 May | None anticipated. | Evaluation process: 7 – 21 May Anticipated SASA Council approval: By 28 May Appointment of service provider: 1 June 2021
Verification phase: collection and collation of data | Metadata sets and sources identified. Service provider has not yet started |  | To be determined
Causation phase: Analysis of data | Not yet started |  | To be determined
Remedy: Proposed restructuring | Not yet started |  | To be determined

## Slide 11: KEY HIGHLIGHTS AND ACHIEVEMENTS
Local market: Exceeded our Year 1 goal of 150,000 t being restored to the local market
Demand for locally-produced sugar increased by 14% or 178,174 t
22% increase in “direct market” (including retailer & wholesaler) procurement of local sugar
7% increase in soft drink manufacturer procurement of local sugar
10

## Slide 12: KEY HIGHLIGHTS AND ACHIEVEMENTS
Chart: Tons
| 2016/2017 | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021
Local Market sales | 1643000 | 1178299 | 1227709 | 1247282 | 1435515
Eswatini | 379083 | 402000 | 391494 | 475477 | 385099
Deep sea imports | 283582 | 519231 | 196782 | 40000 | 21435
SADC protocol access | 9114 | 5922 | 23500 | 34528 | 29741
Zim bilaterals | 0 | 0 | 0 | 13000 | 15000
Exports | 4998 | 795434 | 1042831 | 967579 | 545213
11
Positive reduction in deep sea imports
Positive increase in local sales since 2017/18
Positive reduction in exports
Introduction of HPL

## Slide 13: KEY HIGHLIGHTS AND ACHIEVEMENTS
Producer price restraint: SASA has delivered on the notional price restraint & certainty commitment
Notional Price increases implemented by SASA:
  3% in September 2020
  1.8% in March 2021
The previous notional price increase was in November 2019
12

## Slide 14: KEY HIGHLIGHTS AND ACHIEVEMENTS
Small scale grower support and transformation:
Supplementary payments (SPF) to SSGs grew by 10% to R 68,591,410 in 2020/21
2020/21 is year 2 of the five-year, R 1 billion transformation plan being implemented by SASA, i.e. R200m annually of which 2019/20 and 2020/2021 amounts have already been disbursed.
13

## Slide 15: SASA TRANSFORMATION INTERVENTIONS
Intervention |  | Intervention Description | Budget 2019/20 (R’m) | Budget 2020/21 (R’m)
Interventions aimed at Remedying Inequalities | 1 | Grant funding for black sugar cane farmers delivering under 1 800 tons per season | R60m | R87m
 | 2 | Grant funding for black sugar cane farmers delivering above 1 800 tons per season | R35m | R51m
 | 3 | Subsidy for Transport Cost for black small scale sugar cane farmers | R20m | R20m
 | 4 | Access to seed cane of appropriate cane variety for black small scale sugar cane farmers | R20m | R0m
 | 5 | SASA levy subsidy for black small scale sugar cane farmers | R 7m | R7m
 | Total commitment per annum |  | R142m | R165m
In 2019/20, R142 million per annum has been committed to the remedying of inequalities experienced by black sugar cane farmers particularly small-scale farmers and in the 2020/2021 season, R165m was disbursed.

## Slide 16: SASA TRANSFORMATION INTERVENTIONS
Intervention |  | Intervention Description | Budget 2019/20 (R’m) | Budget 2020/21 (R’m)
Interventions aimed at Remedying Inequalities | 6 | Grant funding for institutional capacity building of new emerging black SASA member associations | R10m | R10m
 | 7 | Funding to develop, educate and train black sugar cane farmers & new emerging black sugar cane farmer associations | R10m | R5m
 | 8 | Establishment of sugar industry job creation accelerator programme for black youth and women | R10m | R10m
 | 9 | Additional Support to the Sugar Industry Trust Fund for Education | R0m | R5m
 | 10 | Establishment of the Growers Baseline Study | R0m | R5m
 |  | Other interventions to be agreed by SASA Council | R28m | R14.220m
 | Total commitment per annum |  | R58m | R49.220m
R58m and R49,22m was disbursed in 2019/20 and 2020/21 respectively

## Slide 17
SACU harmonization matters
  With Eswatini as a sugar producer
  With Botswana, Lesotho and Namibia (BLN) as non-sugar producers
  Demands from BLN countries for tariff-free imports
Future of the Health Promotion Levy (HPL) and broader food policy
Strategic trade protection
KEY AREAS TO BE ADDRESSED
14

## Slide 18
The Social Compact formed by the signing of the Sugar Master Plan ensured that all parties, including government, labour, consumers and the sugar industry as a whole committed to a process of transformation and growth.
The process has begun, and some key achievements can be registered.
The momentum must now be maintained to see all the action commitments to fruition.
KEY MESSAGE
15

## Slide 19: THANK YOU
16