## Slide 1
PORFOLIO COMMITTEE BRIEFING
AGRARIAN REVOLUTION
28 June 2021
CWP: Mr Litha Twaku / Mr Keotsetse Matlhola

## Slide 2: OUTLINE OF THE PRESENTATION
Background
Summary of Agrarian Revolution Projects
Details per each project
Conclusion

## Slide 3: 1. BACKGORUND
The Agrarian Revolution programme was implemented from 2018/19 as part of CWP useful work and a budget of R100 million was allocated to implement during the pilot phase . In 2019/20 another allocation of R100 million was made available in order to complete the projects started in 2018/19 and to start new projects.
In 2020/21 financial an amount of R124 million was allocated and approved in order to complete the projects that were funded and started in 2019/20 and new projects to be started in 2020/21.
The department decided not to start new projects with the current NPOs for the reason that the term of their contracts is ending on the 31 March 2021. Therefore, it was not desirable to give NPOs new projects instead, they were given funds to complete the projects that were started in 2019/20 financial year in order to complete them.
An amount of R51 million was advanced to the NPOs to complete the projects referred to above.
There are currently thirty five (36) projects funded by the department in seven (7) provinces (WC, EC, KZN, FS, NW, Limpopo and Mpumalanga)

## Slide 4: 2. SUMMARY OF THE PROJECTS PER PROVINCE, DISTRICT AND LOCAL
Province | District | Municipality / Traditional Councils | No. of projects | Focus of the projects | Benefitting Traditional Authorities / Communities
Eastern Cape (SAYM) (Thembalethu Development ) | Joe Gqabi | Senqu Elundini | 5 1 | 2x Sheep Production 3x Vegetable Production 1x Vegetable Production | Hlubi, Batlokoa, Amavundle, Amaqwathi and Mnyemane Traditional Authorities; Ngxasa-Hlubi Traditional Authority
 | Chris Hani | Intsika Yethu | 2 | Vegetable Production Sheep Production | Mtshenyane & Muncuncuzo Traditional Authorities
 | OR Tambo | King Sabatha Dalindyebo | 1 | Grain Production | Hegebe Traditional Authority
 | Alfred Nzo | Umzimvubu | 1 | Mixed Vegetables ( Hydroponic project) and irrigation systems for Grain production | Makhaula & Fikeni Traditional Authorities
Western Cape (Insika Foundation) | Cape Winelands | Drakenstein | 1 | Mixed Vegetables ( Hydroponic project) | Wellington Community

## Slide 5: 2. SUMMARY OF THE PROJECTS PER PROVINCE, DISTRICT AND LOCAL…continue
Province | District | Municipality / Traditional Councils | No. of projects | Focus of the projects | Traditional Authorities / Communities
North West (Seboka Training & Support Network) | Bojanala | Rustenburg | 1 | Piggery project | Bakwena Ba Mogopa Traditional Authority
Free State (Seboka Training & Support Network) | Thabo Mafutsanyana | Maluti-A-Phofung | 1 | Livestock Farming (Beef and Lamb feedlots | Makholokoe Traditional Authority
Mpumalanga (Joubert Park Youth Outreach Project) | Gert Sibande | Mkhondo | 1 | Vegetable Tunnel Project | Emaphepheni -Community Property Administration area
 | Ehlanzeni | Mbombela | 1 | Chickens and Vegetable Tunnel Project | Msholozi- Community Property A area
 | Nkangala | Chris Hani | 1 | Farm in the Box (Sheep Production and Vegetables) | Matshiding Village -Inkosi Mahlangu Mahlangu Traditional Authority

## Slide 6: 2. SUMMARY OF THE PROJECTS PER PROVINCE, DISTRICT AND LOCAL…Cont
Thembalethu Development | District | Municipality | No. of projects | Focus of the projects | Traditional Authorities / Communities
 | Waterberg | Mogalakwena | 01 | Vegetable Tunnels & Moringa Project | Bavaria Traditional Authority
 | Capricorn | Lepelle-Nkumpi | 01 | Gedroogte Goat Farming Agriculture Co-operative | Kekana Traditional Authority
 |  | Polokwane East | 01 | Baroi Goat Farming Co-operative | Kgosi Dikgale Traditional Authority
 |  | Polokwane West | 01 | Ramakgaphola Farming Primary Co-operative | Moloto Traditional Authority
 | Mopani | Greater Giyani | 01 | Angove Farming Co-operative | Mabunda Traditional Authority
Thembalethu Development | Sekhukune | Ephraim Mogale | 01 | Manotoloaneng Goat Farming Co-operative | Phokwane Traditional Authority
 | Vhembe | Collins Chabane | 01 | Mtititi Goat Farming Primary Co-operative | Mtititi Traditional Authority
 |  | Thulamela | 01 | Tshamunguyu Goats Primary Co-Operative | Makuya Traditional Authority

## Slide 7: 2. SUMMARY OF THE PROJECTS PER PROVINCE, DISTRICT AND LOCAL….Cont
Province | District | Municipality | No. of projects | Focus of the projects | Traditional Authorities/Communities
kwaZulu-Natal (Insika Foundation) | Ugu | Umuziwabantu | 02 | Mixed Vegetables | Jali Traditional Authority Machi Traditional Authority
Southern African Youth Movement | Ugu | Umzumbe | 02 | Mixed Vegetables and Piggery project | Shinga Traditional Authority
 | Ilembe | Ndwedwe | 01 | Goats Production | KwaNyuswa / Mlamuli Traditional Authority
 | Uthukela | Okhahlamba | 01 | Phase 2 Piggery Project | Amangwane Traditional Authority (Ngobe village)
 | Amajuba | Emadlangeni | 01 | Mixed Vegetables (Maize & Beans) | KwaMbatha Tribal Authority
 | Zululand | Abaqulusi | 01 | Citrus and Vegetables | Empangisweni Traditional Authority
 | Umkhanyakude | Big Five Hlabisa | 01 | Mixed Vegetables and Pineapple | Bushland/Hluhluwe (Induna Mkhize)
 | Harry Gwala | Dr Nkosazana Dlamini-Zuma | 03 | Vegetables & Orchards, Poultry Production & Goat production | Bhidla, Vezokuhle & Batlokoa Traditional Authorities

## Slide 8
Sustainability :
The project is not fully operational and more funding is needed to complete it so that it can fully operational.
Project Name: Sheep Production Project (Hlubi Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with sheep production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 3,500,000
Expenditure: R 3, 614,000
Beneficiaries: 24
Project Status 65% Complete
Outstanding:
Drilling of borehole, zinc dam, water supply pipes, installation of solar energy to power all operations, abluition facilities for workers, office, storage and Guard House
3. Details per project: Eastern Cape: Joe Gqabi District-Senqu- Southern African Youth Movement

## Slide 9
Sustainability :
Agricultural Farmers Association of South Africa (AFASA) has off take agreements with a number of entities both locally and internationally for emerging farmers to be able to sell their commodities if there is quality and consistency.
Project Name: Sheep Production Project (Hlubi Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with sheep production using intensive animal production method to enhance breeding and support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 3,500,000
Expenditure: R 3, 614,000
Number of Beneficiaries: 24
Status of the project: 65% Complete
Agrarian Projects : Eastern Cape: Joe Gqabi District-Senqu (Southern African Youth Movement )

## Slide 10
Sustainability :
The project is not yet complete and more funding to complete the project will be released during 2021/22 financial year.
Project Name: Sheep Production Project (Hlubi Traditional Council)
Objective:
To set up infrastructure to enable farming project within the traditional council to farm productively with sheep production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 3,500,000
Expenditure: R 3, 614,000
Number of Beneficiaries: 24
Status of the project: 65% Complete
Agrarian Projects : Eastern Cape: Joe Gqabi District-Senqu (Southern African Youth Movement )

## Slide 11
Sustainability :
Agricultural Farmers Association of South Africa (AFASA) has off take agreements with a number of entities both locally and internationally for emerging farmers to be able to sell their commodities if there is quality and consistency.
Project Name: Sheep Production (Batlokoa Traditional Council)
Objective:
To set up infrastructure to enable farming project within the traditional council to farm productively with sheep production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R4, 000, 000
Expenditure: R 3, 801, 000
Number of Beneficiaries: 22
Status of the project: 70% Complete
Agrarian Projects : Eastern Cape: Joe Gqabi District-Senqu (Southern African Youth Movement)

## Slide 12
Sustainability:
The project is still under construction and will be completed during 2021/22 financial year.
Project Name: Vegetable Production ( Amavundle Traditional Council
Objective:
To set up infrastructure to enable farming project within the traditional council to farm productively with vegetables both under tunnels and open fields.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 1,000,000
Expenditure: R 1,169, 500.60
Number of Beneficiaries: 20
Status of the project: 40% Complete
Agrarian Projects : Eastern Cape: Joe Gqabi District-Senqu ( Southern African Youth Movement)

## Slide 13
Sustainability :
Agricultural Farmers Association of South Africa (AFASA) has off take agreements with a number of entities both locally and internationally for emerging farmers to be able to sell their commodities if there is quality and consistency.
Project Name: Vegetable Production (Amaqwathi Traditional Council)
Objective:
To set up infrastructure to enable farming project within the traditional council to farm productively with vegetables both under tunnels and open fields.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R1,000,000
Expenditure: R 1, 234, 000
Number of Beneficiaries: 24
Project Status: 40 % Complete
Agrarian Projects : Eastern Cape: Joe Gqabi District-Senqu ( Southern African Youth Movement)

## Slide 14
Sustainability:
The project will have off take agreements with the local markets to supply them with fresh produce.
Project Name: Vegetable Production (Mnyemane Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with vegetables both under tunnels and open fields.
To support Agricultural project and establish commercial enterprise that would also manage production.
Project Budget: R 1, 000,000
Expenditure: R 1, 249, 000
Number of Beneficiaries: 25
Project Status: 40 % Complete
The project still needs the pack house, Drilling of boreholes, zinc dam, water supply pipes, installation of solar energy to power all operations, abluition facilities for workers, office and storage etc.
Agrarian Projects : Eastern Cape: Joe Gqabi District-Senqu ( Southern African Youth Movement)

## Slide 15
Sustainability:
Project Name: Vegetable Production (Ngxasa-HlubiTraditional Council)
Objective:
To set up infrastructure to enable farming project within the traditional council to farm productively with vegetables both under tunnels and open fields.
Project Budget: R 1, 000,000
Expenditure: R 950, 000
Number of Beneficiaries: 25
Project Status: 40% Complete
Outstanding:
Geophysics investigation to establish water sources, Installation of back-up generator (to be used during extensive rains and dark winters), Construction of Pack house for vegetables, Drilling of boreholes, water supply pumps and zinc dam, 2000 litres of diesel for tractors and generator, Guard house, Office, Storage and abluition facilities.
Agrarian Projects : Eastern Cape: Joe Gqabi District-Elundini ( Southern African Youth Movement)

## Slide 16
Sustainability:
Project Name: Sheep Production (Mtshenyane Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with sheep production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 3, 500, 000
Expenditure: R 3, 633, 982.
Number of Beneficiaries: 17
Project Status: 65% Complete
Geophysics investigation to establish water sources, Installation of back-up generator (to be used during extensive rains and dark winters), Drilling of boreholes, water supply pumps and zinc dam, 2000 litres of diesel for tractors and generator, Guard house, Office, Storage and Ablution facilities.
Agrarian Projects : Eastern Cape: Chris Hani District-Intsika Yethu (Southern African Youth Movement)

## Slide 17
Sustainability :
Project Name: Vegetable Production (Mncuncuzo Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with vegetables both under tunnels and open fields.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 1,000, 000
Expenditure: R 1,040,000
Number of Beneficiaries: 25
Project Status: 40 % Complete
Geophysics investigation to establish water sources, Installation of back-up generator, Construction of Pack house for vegetables, Drilling of boreholes, water supply pumps and zinc dam, 2000 litres of diesel for tractors and generator, Guard house, Office, Storage and abluition facilities.
Agrarian Projects : Eastern Cape: Chris Hani District-Intsika Yethu (Southern African Youth Movement)

## Slide 18
Sustainability:
Establish production that will supply RED HUB with maize in Mqanduli
Project Name: Grain Production (Hegebe Traditional Council)
Objectives:
To set up infrastructure to enable the grain production farming project within the traditional authority areas to farm with maize production.
To Support Agricultural inputs and set up commercial enterprises that would manage production.
Project Budget: R 29, 518,000
Expenditure: R 24, 358, 473
Number of Beneficiaries: 162
Project Status: 80% Complete
Agrarian Projects : Eastern Cape: OR Tambo District-King Sabata Dalindyebo (Southern African Youth Movement)

## Slide 19
Sustainability:
Project Name: Sheep Production (Mtshenyane Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with sheep production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 3, 500, 000
Expenditure: R 3, 633, 982.
Number of Beneficiaries: 17
Project Status: 40 % Complete
Agrarian Projects : Eastern Cape: Chris Hani District-Intsika Yethu (Southern African Youth Movement)

## Slide 20
Sustainability:
Agricultural Farmers Association of South Africa (AFASA) has off take agreements with a number of entities both locally and internationally for emerging farmers to be able to sell their commodities if there is quality and consistency.
Project Name: Goat Production (Batlokoa Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with sheep production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 4, 800, 000
Expenditure: R 5, 105, 225
Number of Beneficiaries: 22
Project Status: 70 % Complete
Agrarian Projects : KwaZulu-Natal-Harry Gwala District-Dr Nkosazana Dlamini-Zuma (Southern African Youth Movement)

## Slide 21
Sustainability:
Project Name: Orhards and Vegetable Production (Bidla Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with Fruits and Vegetables.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 4, 900, 000
Expenditure: R 5, 620, 184
Number of Beneficiaries: 40
Project Status: 60% Complete
Outstanding:
Construction of the pack house for vegetables and fruits, guard room, admin office, storage and ablution facilities, installation of Solar energy to power all operations including tunnel drippers and orchard irrigation
Agrarian Projects : KwaZulu-Natal-Harry Gwala District-Dr Nkosazana Dlamini-Zuma (Southern African Youth Movement)

## Slide 22
Sustainability:
Project Name: Poultry Production (Vezokuhle Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with chickens.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 4, 300, 000
Expenditure: R 3, 513, 266
Number of Beneficiaries: 27
Project Status: 60% Complete
Outstanding:
Installation of 3 Ha perimeter wall, Procurement of 5000 point of lay punnets/hens, Procurement of grading machines, permanent plastic trays, cardboard trays, Trolleys and boxes, Construct guard room and ablution facilities, installation of Solar energy to power all operations including water supply, lighting and heaters for chickens.
Agrarian Projects : KwaZulu-Natal-Harry Gwala District-Dr Nkosazana Dlamini-Zuma (Southern African Youth Movement)

## Slide 23
Sustainability:
Project Name: Citrus and Vegetables (Emapngisweni Traditional Council)
Objectives:
To develop self-sustainable Small Medium and Manufacturing Enterprise and supply local retailers with fresh produce and create employment opportunities.
Project Budget: R 9, 806, 695
Expenditure: R 9, 806, 695
Number of Beneficiaries: 25
Project Status: 100% Complete
Agrarian Projects : KwaZulu-Natal-Zululand District-Abaqulusi (Insika Foundation)

## Slide 24
Sustainability:
Project Name: Maize and Beans Production (KwaMbatha Traditional Council)
Objective:
To develop self-sustainable Small Medium and Manufacturing Enterprise and supply local retailers with fresh produce and create employment opportunities
Project Budget: R 7,321,771
Expenditure: R 7, 321, 771
Number of Beneficiaries: 25
Project Status: 100% Complete
Agrarian Projects : KwaZulu-Natal- Amajuba District-Emadlangeni (Insika Foundation)

## Slide 25
Sustainability :
The project has been selling the fresh produce like cabbages to the local market.
Project Name: Mixed Vegetable Production and Piggery (KwaShinga Tribal Authority)
Objectives:
To establish a small scale farm to supply local retailers with fresh produce and ;
To supply local abattoirs and create employment opportunities
Project Budget: R 9, 166,989
Expenditure: R 9, 166, 989
Number of Beneficiaries: 50
Project Status: 100% Complete
Agrarian Projects : KwaZulu-Natal-Ugu District-Uzumbe (Insika Foundation)

## Slide 26
Sustainability:
Project Name: Mixed Vegetables (Jali Tribal Authority)
Objective:
To develop self-sustainable Small Medium and Manufacturing Enterprise and supply local retailers with fresh produce and create employment opportunities.
Project Budget: R 5, 510, 512
Expenditure: R 5, 510, 512
Number of Beneficiaries: 25
Project Status: 100% Complete
Agrarian Projects : KwaZulu-Natal- Ugu District-Umuziwabantu (Insika Foundation)

## Slide 27
Sustainability:
Project Name: Mixed Vegetables (Machi Tribal Authority)
Objective:
To develop self-sustainable Small Medium and Manufacturing Enterprise and supply local retailers with fresh produce and create employment opportunities
Project Budget: R 7, 164, 623
Expenditure: R 7, 164, 623
Number of Beneficiaries: 25
Project Status: 100% Complete
Agrarian Projects : KwaZulu-Natal- Ugu District-Umuziwabantu (Insika Foundation)

## Slide 28
Sustainability:
Project Name: Goats Production (Mlamuli Tribal Authority)
Objective:
To establish a small scale farm to supply local markets and surrounding communities and create job opportunities
Project Budget: R 7, 232, 086
Expenditure: R 7, 232, 086
Number of Beneficiaries: 20
Project Status: 100% Complete
Agrarian Projects : KwaZulu-Natal-Ilembe District-Ndwedwe (Insika Foundation)

## Slide 29
Sustainability:
The project had an off take agreement with the local abattoir to supply it with pigs. and 456 of the 480 procured were sold to this abattoir.
The project is in the process of procuring pregnant pigs for breeding purposes and continue to supply the local abattoirs
Project Name: Phase 2 Piggery Production (Amangwane Tribal Authority)
Objective:
To establish small scale farm and a Cooperative to supply local abattoirs and creation of job opportunities
Project Budget: R 11, 900,000
Expenditure: R 11, 836, 742
Number of Beneficiaries: 29
Project Status: 95% Complete
Agrarian Projects : KwaZulu-Natal-Uthukela District-Okhahlamba (Insika Foundation)

## Slide 30
Sustainability :
The project is running and selling the pineapple to the market and no permanent jobs created as yet as it is still supported by CWP participants.
Project Name: Pineapple and Mixed Vegetables (Hluhluwe- Induna Mkhize)
Objective:
To develop self-sustainable Small Medium and Manufacturing Enterprise and supply local retailers / markets with fresh produce and pineapple and to create employment opportunities
Project Budget: R 9, 166, 989
Expenditure: R 9, 166, 989
Number of Beneficiaries: 25
Project Status: 100% Complete
Agrarian Projects : KwaZulu-Natal-Umkhanyakude District-Big Five Hlabisa (Insika Foundation)

## Slide 31
Sustainability:
The project is currently not doing well due to the fact that the plants are destroyed by the baboons and monkeys as a result there are plans to relocate it to another area within the same community.
Project Name: Mixed Vegetables-Hydroponic project ( Wellington Community)
Objective:
To create viable agricultural business to be run as a cooperative and supply local retailers and markets
Project Budget: R 4, 000, 000
Expenditure: R 4, 000, 000
Number of Beneficiaries: 11
Project Status: 100% Complete
Agrarian Projects : Western Cape- Winelands District- Drakenstein (Insika Foundation)

## Slide 32: FEEDLOT AND CROP FARMING PROJECT – FREE STATE PROVINCE
Project Name: Feedlot and crop farming (Makholokoe Traditional Council)
Objectives:
To create a viable and sustainable vegetable and live stock business through formation of co-operatives.
Project Budget: R 13, 500, 000
Expenditure: R 13 470, 035
Number of Beneficiaries: 19
Project Status: 95% - borehole to be drilled by mid July 2021
Sustainability:
After 90-120 days – Sell cattle to the abattoir to generate income and buy weaners/calves from local farmers, feeds and medication.
Sell crops to the local community members to ensure steady flow of funds to maintain the facility and create more job opportunities

## Slide 33: PIGGERY PROJECT – NORTH WEST PROVINCE
Project Name: Piggery (Bakwena ba Mogopa Traditional Council)
Objectives:
Reduce poverty and unemployment in the community through the introduction of sustainable income generating piggery activities.
Project Budget: R 17,186,517.00
Expenditure: R 9, 922, 656
Number of Beneficiaries: 12
Project Status: 89 %
Finisher house to be completed by the end of July 2021
Sustainability:
Off-take agreement in place, Solar power and SA Pork & Quality Assurance & Traceability Standards (Pork 360)

## Slide 34: Vegetable tunnels and Moringa project Limpopo province
Project Name: Chicken and vegetable farming (Mathebula CPA)
Objectives:
To provide viable broiler production infrastructure and agricultural business for CWP participants.
Project Budget: R8, 450, 000
Expenditure: R7, 538, 369
Number of Beneficiaries: 20
Project Status: 95% - Ablution facilities to be constructed by end of July 2021
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 35: CHICKEN AND VEGETABLE FARMING –EHLANZENI – MBOMBELA- MPUMALANGA
Project Name: Chicken and vegetable farming (Mathebula CPA)
Objectives:
To provide viable broiler production infrastructure and agricultural business for CWP participants.
Project Budget: R7, 050, 000
Expenditure: R6 988 639
Number of Beneficiaries: 20
Project Status: 95% - Ablution facilities to be constructed by end of July 2021
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 36: VEGETABLE FARMING PROJECT GERT SIBANDE- MKHONDO -MPUMALANGA PROVINCE
Project Name: Vegetable farming ( Emaphepheni CPA)
Objectives:
Develop self-sustainable SMMEs , supply local retailers with fresh produce, & create employment opportunities
Project Budget: R6 550 000.00
Expenditure: R4 999 973.00
Number of Beneficiaries: 15
Project Status: 70% -Completed however the project was vandalised and lot of equipment stolen
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 37: SHEEP PRODUCTION – NKANGALA – DR JS MOROKA MPUMALANGA
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.
Project Name: Sheep farming and Vegetables (Mahlangu Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with sheep production using intensive technology for animal production.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R9 995 648.00
Expenditure: R9 724 046.00
Number of Beneficiaries: 01
Project Status: 100% Completed and managed by the local traditional leader

## Slide 38: Agrarian Projects : HYDROPONIC TUNNELS AND IRRIGATION SYSTEMS ALFRED NZO - EC
Project Name: Hydroponic tunnels and irrigation systems (Makaula & Fikeni Traditional Councils)
Objectives:
To provide income generation opportunity for farmer and also to become commercial grain and vegetables farmers
Project Budget: R
Expenditure: R 16,000,000.00
Number of Beneficiaries: 407
Project Status: 85% Complete
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 39: Agrarian Projects : GOAT FARMING – CAPRICON – LEPELLE – NKUMPI - LIMPOPO
Project Name: Goat farming (Kekana Traditional Council)
To set up infrastructure to enable farming project within the traditional council to farm productively with goat production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 1, 300, 000
Expenditure: R 1, 360, 767
Number of Beneficiaries: 08
Project Status: 85% Complete
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 40: Agrarian Projects : GOAT FARMING – CAPRICON – POLOKWANE West - LIMPOPO
Project Name: Goat farming (Moloto Traditional Council)
To set up infrastructure to enable farming project within the traditional council to farm productively with goat production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 2, 360, 802
Expenditure: R 1, 568, 803
Number of Beneficiaries: 06
Project Status: 85% Complete
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 41: Agrarian Projects : GOAT FARMING – CAPRICON – POLOKWANE East - LIMPOPO
Project Name: Goat farming (Dikgale Traditional Council)
To set up infrastructure to enable farming project within the traditional council to farm productively with goat production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 2, 200, 000
Expenditure: R 2, 137, 897
Number of Beneficiaries: 07
Project Status: 85% Complete
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 42: Agrarian Projects : GOAT FARMING – MOPANI – GREATER GIYANI - LIMPOPO
Project Name: Goat farming (Ngove Traditional Council)
To set up infrastructure to enable farming project within the traditional council to farm productively with goat production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 2, 100, 000
Expenditure: R 875, 167
Number of Beneficiaries: 06
Project Status: 80% Complete
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 43: Agrarian Projects : GOAT FARMING – SEKHUKHUNE – EPHARAIM MOGALE - LIMPOPO
Project Name: Goat farming (Bakone Ba Phokwane Traditional Council)
To set up infrastructure to enable farming project within the traditional council to farm productively with goat production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 2, 360, 802
Expenditure: R 1, 312, 876
Number of Beneficiaries: 05
Project Status: 85% Complete
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 44: Agrarian Projects : GOAT FARMING – VHEMBE – COLLINS CHABANE - LIMPOPO
Project Name: Goat farming (Mtititi Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with goat production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 2, 360, 802
Expenditure: R 679, 839
Number of Beneficiaries: 07
Project Status: 85% Complete
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 45: Agrarian Projects : GOAT FARMING – VHEMBE – THULAMELA - LIMPOPO
Project Name: Goat farming (Makuya Traditional Council)
Objectives:
To set up infrastructure to enable farming project within the traditional council to farm productively with goat production using intensive animal production method to enhance breeding.
To support Agricultural project and set up commercial enterprises that would also manage production.
Project Budget: R 2, 360, 802
Expenditure: R 1, 573, 629
Number of Beneficiaries: 06
Project Status: 85% Complete
Sustainability:
To create viable agricultural business to be run by CWP participants as a cooperative and supply local retailers and markets.

## Slide 46: 4. Conclusion
The department is in the process of verifying all the items procured for the projects starting and look at what is still needed to complete those that are not completed.
It will also be verifying the agrarian revolution programme assets for the all projects including those that are 100% complete.
There will be disbursed funds to the Non Profit Organisation in order to complete all the projects that still need to be completed.
The department will also be verifying the list of beneficiaries submitted by the Non Profit Organisation in order to confirm whether they are the project owners and their names are appearing in the registration documents of the cooperatives established for the projects.