## Slide 1: PRESENTATION TO THE PORTFOLIO COMMITTEE AUGUST 2021

## Slide 2: PRESENTATION OVERVIEW
Implementation of the TKLA (April – August)
Training and awareness of traditional leaders on the Act
Municipal awareness of the amendment to S81 of the Structures Act, Act 117 of 1998;
Amendment of Standing Rules and Orders to accommodate the amendment to S81 of the Structures Act

## Slide 3: IMPLEMENTATION OF THE TKLA
AREA | LEGISLATIVE REQUIREMENTS AND COMMENTS | TIMEFRAME | PROGRESS | RESPONSIBLE PARTY
Provincial and local houses | Provincial House: Gauteng does not have a provincial house and it will consider the establishment of a provincial house once the recognition process for Khoisan Leaders have been finalised. The TKLA states that a provincial house may be established. | 2023/24 Financial Year when provincial legislation comes into effect. | Not applicable to Gauteng. | CoGTA (Gauteng)
 | Local House (LHTL): Gauteng meets the requirements to establish a LHTL, where more than one traditional council is recognised in a municipality. | 2022/23 Financial Year | A LHTL must have at least 5 recognised traditional leaders, in the City of Tshwane, namely 2 Senior Traditional Leaders and 4 headmen/women. The project will run concurrently with the reconstitution of the National House and will conclude in March 2022 to align to the term of office of the NHTL. Headmen/women in Hammanskraal are appointed on a 5 year term which concludes on 31 March 2022. The Process of re-appointing the 4 headmen and headwomen commenced in Hammanskraal | CoGTA (Gauteng)

## Slide 4: IMPLEMENTATION OF THE TKLA
AREA | LEGISLATIVE REQUIREMENTS AND COMMENTS | TIMEFRAME | PROGRESS | RESPONSIBLE PARTY
Headmen and headwomen | Gauteng has four recognised headmenship/womenship positions in the Amandebele ba Lebelo traditional community. The Amandebele Ndzundza Sokhulumi traditional council does not have any headmenship/womenship positions. The province would be ready to conduct an audit of both traditional communities to assess whether they meet the current recognition criteria set out in clauses 3, 7 and 8. | Audit of headmenship/ womenship positions to commence in September 2021 | Concept note for the audit of headmen/womenship positions in Sokhulumi has been prepared and aligned to the legislative requirements. | CoGTA (Gauteng)

## Slide 5: IMPLEMENTATION OF THE TKLA
AREA | LEGISLATIVE REQUIREMENTS AND COMMENTS | TIMEFRAME | PROGRESS | RESPONSIBLE PARTY
Partnerships and agreements | The Audit will commence in October 2021 and agreements will be handed over to the Minister in terms of Section 24(6)(b) by December 2021. | August - November 2021 | The two (2) traditional councils have been tasked to prepare a list of the current partnerships and agreements they have in place. | Senior Traditional Leaders, Traditional Councils and CoGTA Gauteng.
Commission on Khoi San Matters | Establish a Commission on Khoi San Matters in terms of Section 51 | October 2021 – March 2022. | Concept note to host roadshows in the 5 regions of Gauteng on the TKLA was developed. The anticipated date of implementation was August, however, the Commission has not been established yet by Minister of CoGTA. The scope of the roadshows will include the responsibilities of the Commission on Khoi San Matters; legislative requirements for recognition and the application process for Khoi and San leaders. | CoGTA Gauteng and DTA.

## Slide 6: IMPLEMENTATION OF THE TKLA
AREA | LEGISLATIVE REQUIREMENTS AND COMMENTS | TIMEFRAME | PROGRESS | RESPONSIBLE PARTY
Constitution/ reconstitution of traditional councils | Communicate the Minister’s proclamation of the formula. | August | Pending | DTA
 | Appointment of project manager and project team (required management capacity) for the reconstitution of TCs. | March 2022 | A concept document has been developed to appoint a project manager for the reconstitution of the TC’s, which will include the election process. | CoGTA
 | Develop a list of recognised Senior Traditional Leaders in the province and a list of recognised headmen and headwomen under each Senior Traditional Leader per metropolitan, district and local municipality. | July 2021 | Completed and copies of provincial government notices signed/issued for: each recognised traditional community each recognised senior traditional leader each headman or headwoman copies of identity documents of each senior traditional leader and headman or headwoman. | CoGTA

## Slide 7: IMPLEMENTATION OF THE TKLA
AREA | LEGISLATIVE REQUIREMENTS AND COMMENTS | TIMEFRAME | PROGRESS | RESPONSIBLE PARTY
Constitution/ reconstitution of traditional councils | Convene meetings with Royal Families and traditional communities to among others decide on which of the three election choices for the 40% will apply (section 21 of the TKLA): Electoral Commission, provided that the Commission and the Premier of the province enters into an agreement; or By way of a community meeting, of which can be done according to the customs of the community; or By a body consisting of one or more persons appointed by the Premier. | June – July 2021 | Meetings held with the Royal Families selected Option “C”. | CoGTA
 | Traditional community area/map/ boundaries | July – August 2021 | Completed, maps prepared for both traditional councils. (DALR) | CoGTA

## Slide 8: IMPLEMENTATION OF THE TKLA
AREA | LEGISLATIVE REQUIREMENTS AND COMMENTS | TIMEFRAME | PROGRESS | RESPONSIBLE PARTY
Legislative Review to align the current provincial legislation with the TKLA | Identify the gaps and write proposed amendments and legislative requirements in terms of the TKLA: Section 15 on Resources and Resources for traditional and Khoi San leaders; Section 23 on strengthening the capacity of traditional and Khoi San Councils; Section 24 on Partnerships and agreements; Section 25 on the allocation of roles for traditional and Khoi San leaders; Section 49 on the establishment of Provincial Houses of Traditional Leaders; Section 59 on the management of disputes; Section 63 (5) on the disestablishment of community authorities. | August 2021 - March 2023 | Implementation plan for the review of legislation developed. Draft policy document for the amendment of provincial legislation developed and will be consulted with key stakeholders. | CoGTA

## Slide 9: IMPLEMENTATION OF THE
AREA | COMMENTS | PROGRESS | RESPONSIBLE PARTY
Organisational Review | Gauteng CoGTA commenced its Organisational Review in April 2021 and will conclude on the 31st March 2022. In Gauteng, the function is currently operated at a sub-directorate level. | The proposed structure recommends that the function be elevated to a Directorate reporting directly to the Head of Department. Sub-directorates will be limited to the following: Traditional and Khoi San support; Provincial and Local House support; Customary Initiation; and Traditional and Khoi San Leadership Claims and Disputes. | CoGTA

## Slide 10: TRAINING/AWARENESS OF TRADITIONAL LEADERS
An induction programmes on the TKLA:
  One held in May for Senior Traditional Leaders and their Traditional Councils.
  A request for additional training was made and will be held in September 2021.
Meetings with Khoi and San Leaders on the TKLA:
  A meeting was facilitated between the DTA and Khoi and San Leaders in Gauteng to address key concerns from Khoi and San leaders. The meeting assisted to clarify all matters related to the implementation of TKLA;
  Khoi and San leaders met with the MEC to raise their concerns about the Act, it was agreed that Gauteng CoGTA would host roadshows in Khoi and San communities in Gauteng. The roadshows will commence once the Commission on Khoi and San Matters is established by the Minister of CoGTA.

## Slide 11: AMENDMENT TO S81
Awareness of municipalities of the amendment to S81 of the Structures Act, Act 117 of 1998:
National DTA will host awareness programmes across all the provinces, however the province plans to host awareness programmes in each of the 5 Districts of Gauteng.
These awareness programmes will be linked to the TKLA awareness programmes in partnership with DTA.
Amendment of Standing Rules and Orders:
At present, the Department has no records of the amendment of the Standing Rules and Orders by municipalities.
The Department will finalise an audit of all the municipal processes of amending the Standing Rules and Orders by 30th September 2021.

## Slide 12: THANK YOU