## Slide 1: LDOE Conditional Grants Expenditure Report
Presented to Parliament
18 – 19 August 2021

## Slide 2: Status report of LSPID Conditional Grant

## Slide 3: CONTENTS
Status report of LSPID Conditional Grant
Status report of HIV/AIDS Life Skills Conditional Grant

## Slide 4: PURPOSE OF LPSID GRANT
Purpose: LSPID grant is established to provide the necessary support, resources and equipment to identified care centres and schools for the provision of education to children with severe to profound intellectual disabilities (SPID)
Outcomes: Improved access to quality basic education for children with severe to profound intellectual disabilities in conditions that ensure dignity, promote self-reliance and facilitate active participation in the community.

## Slide 5: 2020/2021 LPSID Q1 Expenditure Breakdown
First Quarter : April to June 2020 |  |  |  | 
 | Budget | Projection | Expenditure | Variance
 | R'000 |  |  | 
Compensation of employees | 21 081 | 4 965 | 4 363 | 602
Goods and services | 8 451 | 1 740 | 78 | 1 662
Current transfers and subsidies | - | - | - | -
Payments for capital assets | 2 900 | 450 | - | 450
Total | 32 432 | 7155 | 4 441 | 2 714

## Slide 6: 2020/2021 Q2 Expenditure Breakdown
Second Quarter: July to September 2020 |  |  |  | 
 | Budget | Projection | Expenditure | Variance
 | R'000 |  |  | 
Compensation of employees | 21 081 | 4 966 | 5 591 | (625)
Goods and services | 8 451 | 1 150 | 44 | 1 106
Current transfers and subsidies | - | - | - | -
Payments for capital assets | 2 900 | - | 27 | (27)
Total | 32 432 | 6 116 | 5 662 | 454

## Slide 7: 2020/2021 Q3 Expenditure Breakdown
Third Quarter: October to December 2020 |  |  |  | 
 | Budget | Projection | Expenditure | Variance
 | R'000 |  |  | 
Compensation of employees | 21 081 | 5 272 | 5 643 | (371)
Goods and services | 8 451 | 4 516 | 516 | 4 000
Current transfers and subsidies | - | - | - | -
Payments for capital assets | 2 900 | 2 450 | 285 | 2 165
Total | 32 432 | 12 238 | 6 444 | 5 794

## Slide 8: 2020/2021 Q4 Expenditure Breakdown
Fourth Quarter: January to March 2021 |  |  |  |  |  | 
 | Budget | Projection |  | Expenditure |  | Variance
 | R'000 |  |  |  |  | 
Compensation of employees | 21 081 |  | 5 878 |  | 5 608 | 270
Goods and services | 8 451 |  | 1 045 |  | 1 747 | (702)
Current transfers and subsidies | - |  | - |  | - | -

## Slide 9: 2021/2022 LSPID Expenditure
R32 666 000 is allocated to LSPID. 65% is for CoE. The project manager and 35 specialists have been appointed.
Q1 target was 25% for LSPID. 18,12% was spent (implying a variance of 6.88%, an accrual of 3 months)
Reasons for under-spending:
  Changes in conditions of service from contract of five months to contract of six months which reduced employee allowance benefits (housing and medical)
To mitigate, the savings (6.88%) will be used to cover the 1.5% increase in salaries and allowances
Procurement for goods and services (worth R12 million) is at an advantaged stage

## Slide 10: Status report of HIV/AIDS

## Slide 11: PURPOSE OF HIV & AIDS LIFE SKILLS GRANT
To support South Africa’s HIV prevention strategy by:
Providing comprehensive sexuality education and access to sexual and reproductive health services to learners.
Supporting the provision of employee health and wellness programme for educators.
To mitigate the impact of HIV, TB and Covid-19 by providing a caring, supportive and enabling environment for learners and educators.
Reducing the vulnerability of children to HIV, TB, STI’s and Covid-19 with particular focus on orphaned children and girls

## Slide 12: 2020/21 HIV & AIDS LIFE SKILLS GRANT PERFORMANCE
Initial allocation: R 28 137 000.00
Budget cut in 2nd Quarter: 24.16%
New allocation: R 21 339 000.00
Rollover amount(Q3): R1 376 000.00
Total : R 22 715 000.00

## Slide 13: QUARTERLY TRANCHES RECEIVED
1ST QUARTER | 2ND QUARTER | 3RD QUARTER | 4TH QUARTER
10% (Apr 2%, May 4%, Jun 4%) | 30% (Jul 14%, Aug 8%, Sep 8%) | 40% (Oct 22%, Nov10%, Dec 8%) | 20% ( Jan 7%, Feb 12%, Mar 1%)
2 133 900 | 6 401 700 | 8 535 600 | 4 267 800

## Slide 14: Q1 Expenditure Breakdown
ALLOCATION | APRIL-JUNE EXPENDITURE | COMMITMENT | AVAILABLE BUDGET
28 137 000,00 | 617 000,00 | 0 | 27 520 000,00
100% | 2% | 0 | 98%
Note: (a) The R24.16% budget cut was effected after quarter 1 (b) Closing and re-opening of schools during the 2020/2021 affected activities that targets learners, School Management Team, School Based Support Team and teachers

## Slide 15: Q2 Expenditure Breakdown
ALLOCATION | JULY – SEPTEMBER EXPENDITURE | COMMITMENT | AVAILABLE BUDGET
21 339 000,00 | 1 715 001,37 | 595 890,26 | 19 028 108,37
100% | 8% | 3% | 89%
Note: (a) Due to the budget cut of 24.16% from total allocation of 28 137 000, new allocation was 21 339 000 (b) Closing and re-opening of schools during the 2020/2021 affected activities that targets learners, School Management Team, School Based Support Team and teachers

## Slide 16: Q3 Expenditure Breakdown
ALLOCATION | OCTOBER-DECEMBER EXPENDITURE | COMMITMENT | AVAILABLE BUDGET
22 715 000,00 | 5 832 923,49 | 4 010 443,12 | 12 871 633,39
100% | 25% | 18% | 57%
Note: (a) Total allocation R21 339 000 +2019/20 Roll-over R1 376 000 = R22 715 000,00 (b) The amended business plan was approved in October 2020 to make up for the activities that could not be implemented during the lockdown alert levels 5, 4 and 3 in quarters 1 and 2 (c) Closing and re-opening of schools during the 2020/2021 affected activities that targets learners, School Management Team, School Based Support Team and teachers

## Slide 17: Q4 Expenditure Breakdown
ALLOCATION | JANUARY-MARCH EXPENDITURE | COMMITMENT | AVAILABLE BUDGET
22 715 000 Inclusive of roll-over | 14 136 819.55 As per BAS report 31 March 2021 | 2 657 604,22 | 5 920 576,23
100% | 62.2% (inclusive of roll-over) | 11.7% | 26.1%
Note: (a) The wrong debiting of two officials salaries (at DCES level) was corrected in the fourth quarter (b) All five posts could not be filled due to late approval and delayed recruitment process that was finalised at the end of the financial year (c) Closing and re-opening of schools during the 2020/2021 affected activities that targets learners, School Management Team, School Based Support Team and teachers

## Slide 18: Reasons for under expenditure in 2020/21
Underspending was caused by the delay of activities due to National Lockdown and COVID 19 Regulations & Protocol for support and management at schools, hence trainings and advocacies were affected.
Procurement processes were slow, leading to delay in issuing of purchase orders while most activities were overtaken by scheduled activity dates.
Salaries of 2 District based HIV & AIDS Life Skills officials (2 X DCES) were debited from the Voted funds instead of the Conditional Grant, but the matter was corrected during the fourth quarter.
Non completion of filling of 4 new posts(1 CES & 3 DCES’s) budgeted from September 2020 but the recruitment process could on only be finalized in March 2021 and 3 DCESs employees assumed duty from beginning of May 2021.
Delayed interviews processes for 10 District based and 20 school based Learner Support Agents (LSAs) posts budgeted from August and October 2021, respectively, due to Covid-19 led to some funds not to be spent.

## Slide 19: 2021/2022 HIV/AIDS Expenditure
Total allocation for HIV AIDS is R26 552 000. The first tranche of R2 655 200 was transferred by DBE to Limpopo.
R5 395 172,56 (203% of the first tranche received) has been spent in Q1. R1 010 761 has been committed.
Over expenditure was due to the accrual of R2 363 000. The rollover was approved. Expenditure from April to July 2021 is 24,26%.
The planned trainings during July school vacation could not be realized due to Ciovid-19 level 4 restrictions.
Mitigation strategies to be used in quarters 2- 4 are: weekend training sessions for teachers, SBSTs, Learner support agents, Learners and SMTs; SGBs will be trained during office hours, materials for learners to protect themselves from HIV/AIDS and TB infections, SABC talk-shows.
Deviation for April 2021 salaries for five employees (one CES, three DCESs and one admin clerk) will be requested and use it for goods and services.

## Slide 20: INTERVENTIONS IMPLEMENTED IN 2021/22
The Department has approved the use of one service provider to give services for items such as: rental and hiring of training venues and transport, sound system, stage, chairs, catering, etc.
Provincial Treasury appointed travel agents, wherein the Department was allocated one.
The appointment of 3 DCESs in the three districts shall improved coordination and trainings planned.
The Project managers of conditional grants are having monthly meetings with the CFO to report on performance and develop mitigation strategies.

## Slide 21: The End!
Thank you!