## Slide 1: FOURTH QUARTER PERFORMANCE OF THE DEPARTMENT OF BASIC EDUCATION IN MEETING ITS PRE-DETERMINED OBJECTIVES FOR 2020/21
Portfolio Committee on Basic Education
24 August 2021

## Slide 2: PRESENTATION OUTLINE
PART A
Performance Indicators and Targets
PART B:
Financial Report: Fourth Quarter Expenditure

## Slide 3: PURPOSE
To report on the Fourth Quarter outputs of the Department against the planned targets of the pre-determined objectives in the Annual Performance Plan (APP) for the 2020/21 Financial Year.
To report on the Department’s expenditure for the Fourth Quarter of the 2020/21 Financial Year.

## Slide 4: PART A
PERFORMANCE INDICATORS AND TARGETS

## Slide 5: MAJOR HIGHLIGHTS…
The Combined 2020 November Examination Results: Despite the challenges posed by the COVID-19 pandemic and against all odds, the Class of 2020 persevered and ensured that more than 75% of candidates attained the National Senior Certificate (NSC).
On 22 February 2021, the Minister Mrs Angie Motshekga, MP released the NSC results with overall pass rate at 76.2%, which is a 5.1% decline from the 81.3% achieved in 2019.
The overall number of candidates who achieved Bachelor passes in 2020 is 210 820, an improvement of 13.3% from 2019. This represents 36.4% of the total number of candidates, who wrote the 2020 NSC exams.
74 165 more learners wrote the 2020 NSC examination compared to 2019
440 702 candidates attained a NSC, an increase of 30 796 from 2019
24 762 more candidates attained admission to Bachelor Studies compared to 2019
Notes: Still needs to be edited

## Slide 6: MAJOR HIGHLIGHTS…
The Combined 2020 November Examination Results: 65.0% of the distinctions were attained by girl learners, including distinctions in critical subjects such as Accounting, Business Studies, Economics, Mathematics, and Physical Science.
Director-General visited and monitored 175 Marking Centres for the 2020 NSC Exams
Director-General visited and monitored 164 construction sites for the SAFE Programme in addition to weekly meetings with CEOs of Implementing Agents
A total number of 13 085 Funza Lushaka bursaries were awarded for Initial Teacher Education by 31 March 2021.
Deputy Minister Dr MR Mhaule, MP visited three (3) provinces, namely: Gauteng, Mpumalanga and Limpopo to monitor compliance of risk adjusted level 1 protocols for the phased in return to schools by School Management Teams (SMTs), teachers and learners. Schools and provinces complied with the CEM directives and schools re-opened with less incidents.
Notes: Still needs to be edited

## Slide 7: PROGRAMMES OF THE DEPARTMENT OF BASIC EDUCATION (DBE)
The Annual Performance Plan (APP) summarises the priorities of the DBE as aligned to the Medium Term Strategic Framework (MTSF) 2019-2024 and the Action Plan to 2024: Towards the Realisation of Schooling 2030.
The activities of the DBE have been structured into five (5) programmes as elaborated in the APP:
PROGRAMME 1: ADMINISTRATION
PROGRAMME 2: CURRICULUM POLICY, SUPPORT AND MONITORING
PROGRAMME 3: TEACHERS, EDUCATION HUMAN RESOURCES AND INSTITUTIONAL DEVELOPMENT
PROGRAMME 4: PLANNING, INFORMATION AND ASSESSMENT
PROGRAMME 5: EDUCATIONAL ENRICHMENT SERVICES

## Slide 8: 2020/21 Q4 STATUS BAR FOR INDICATORS
All Annual Targets are WHITE unless fully achieved.
Where 50% of the target has not been achieved, the status is reflected as RED.
Where 50% or more of the target has been realised, the status is reflected as AMBER.
Where the target has been fully achieved, the status is reflected as GREEN.
Programme | No. of indicators per programme | Annual Targets | Quarterly Targets | Bi-annual Targets | Q4 status 2019/20 |  | 
 |  |  |  |  | Not achieved | Partially achieved | Achieved
One | 2 | 1 | 1 |  |  |  | 1
Two | 14 | 9 | 4 | 1 | 1 | 1 | 3
Three | 10 | 4 | 6 |  | 1 |  | 5
Four | 12 | 8 | 3 | 1* (bi-ennial) | 3 |  | 
Five | 5 | 2 | 3 |  |  | 1 | 2
Total distribution | 43 | 24 | 17 | 2 | 5/18 | 2/18 | 11/18
Percentage distribution | 100% | 56% | 40% | 5% | 28% | 11% | 61%
Programme | No. of indicators per programme | Annual Targets | Quarterly Targets | Bi-annual Targets | Q4 status 2020/21 |  | 
 |  |  |  |  | Not achieved | Partially achieved | Achieved
One | 5 | 2 | 3 |  |  |  | 3
Two | 30 | 28 | 1 | 1 |  |  | 2
Three | 12 | 10 | 2 |  |  |  | 2
Four | 18 | 18 |  |  |  |  | 
Five | 4 | 1 | 3 |  |  | 1 | 2
Total distribution | 69 | 59 | 9 | 1 | 0/10 | 1/10 | 9/10
Percentage distribution | 100% | 86% | 13% | 1% | 0% | 10% | 90%

## Slide 9: PIE CHART STATUS
Chart: Q4 status 2019/20
| Not achieved | Partially achieved | Achieved
 | 0.27778 | 0.11111 | 0.61111
Chart: Q4 status 2020/21
| Not achieved | Partially achieved | Achieved
 | 0 | 0.1 | 0.9

## Slide 10: PROGRAMME 1: ADMINISTRATION
The purpose of Programme 1 is to manage the Department and provide strategic and administrative support services.

## Slide 11: PROGRAMME 1 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
1.1.1 Percentage of valid invoices paid within 30 days upon receipt by the Department | Quarterly | 100% | Q1: 96.30% 1 561/1 621 Q2: 98.93% 2 408/ 2 434 Q3: 99.76% 4 712/4 723 Q4: 99.47% 5 448/5 477 Total: 99.12% 14129/14255 | -0.88% | Deviation was due to delay by project managers | Currently invoices are approved manually, this poses limitation since we are currently operating with limited resources due to Lockdown restrictions. Financial Service Directorate will continue to engage project managers to ensure they comply to submitting invoices within 30 Days as required by Treasury regulations.
 | Q4 | 100% | 99.47% 5 448/5 477 | -0.53 | The delay was due to officials working from home due to illness/commodity as per COVID-19 pandemic. This made it difficult for invoices to be submitted on time for processing within 30 days. | Financial Service Directorate will continue to engage project managers to ensure they comply to submitting invoices within 30 Days as required by Treasury regulations.

## Slide 12: PROGRAMME 1 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
1.1.2 Number of reports on misconduct cases resolved within 90 days | Quarterly | 4 | 4 | No deviation | Not applicable | Not applicable
 | Q4 | 1 | 1 | No deviation | Not applicable | Not applicable
1.1.3 Number of capacity building programmes offered to the DBE officials | Annually | 10 | Q1: 0 Q2: 2 Q3: 13 Q4: 4 Total: 19 | +9 | The additional training programmes were addressing training needs identified by officials through the PMDS as articulated in the Personal Development Plans. | Not applicable
 | Q4 | 10 | 4 Courses were attended | Annual target | Not applicable | Not applicable

## Slide 13: PROGRAMME 1 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
1.2.1 Annual Performance Plan approved by 31 March each financial year | Annually | 2020122 APP approved by March 2021 | 2021/22 APP approved by March 2021 | No deviation | Not applicable | Not applicable
 | Q4 | 2021/22 APP approved by March 2021 | The 2021/22 APP was approved by Minister on 05 March and tabled in Parliament on 12 March 2021 | Annual target | Not applicable | Not applicable
1.2.2 Quarterly Reports submitted to National Treasury (NT) and the Department of Planning, Monitoring and Evaluation 30 days after the end of each quarter | Quarterly | Four Quarterly Reports submitted to NT and DPME 30 days after the end of each quarter | Four Quarterly Reports submitted to NT and DPME 30 days after the end of each quarter | No deviation | Not applicable | Not applicable
 | Q4 | Quarterly Report submitted to NT and DPME 30 days after the end of the quarter | Third Quarterly Report 2020/21 submitted to NT and DPME on 29 January 2021 | No deviation | Not applicable | Not applicable

## Slide 14: PROGRAMME 1
  Staffing Services and Human Resource (HR) Support to Provinces
33 posts were advertised and 16 officials were appointed.
The recruitment process for the Government to Government (G2G) Project has been finalised.
Training and Social Responsibility
Four (4) training courses were held and 46 DBE officials attended.
Five (5) interns were hired.
Labour Relations
The Departmental Bargaining Chamber virtual meeting was held on 18 February 2021 and Task Team meeting was held on 12 March 2021.
One (1) progressive discipline (Final Written Warning) was issued.
One (1) complaint in relation to performance assessment was received and resolved amicably between the parties.

## Slide 15: PROGRAMME 1 …
Financial Services
The 2021/22 Estimate National Expenditure (ENE) database and Chapter, were compiled and submitted to National Treasury on the prescribed dates.
The 2020/21 Adjusted Estimate of National Expenditure (AENE) and ENE and budgets were captured on Basic Accounting System (BAS).
Monthly Conditional Grants Expenditure reports from Provincial Education Departments (PEDs) were received and submitted to the National Treasury as prescribed by the DoRA.
Public Entities Quarterly and Annual Reports were received and analysed on time.
Supply Chain Management
Five (5) tenders were advertised. One (1) was finalised, one (1) is being evaluated and three (3) are awaiting evaluation.
Eight (8) Bid Specification Committee meetings were held.

## Slide 16: PROGRAMME 1 …
Security and Assets Management
Daily health screening of officials and visitors at the Conference area and the process fully comply with COVID-19 protocol measures.
All the unitary fees were paid to the Private Party.
The additional generator was installed on March 2021. A successful changeover was completed and the generator is operational.
1 594 inventory Information Technology (IT) equipment were issued to 21 Schools in various provinces and proof of delivery notes has been provided for the reporting and audit purposes.
Legal Services
26 new contracts were received and 19 were finalised. All the other contracts were vetted, however, there are still outstanding issues.
Ten (10) requests for Legal Opinions were received and eight (8) were completed.
The admission Policy has been published to call for comments. A Task Team has been established to peruse the comments and consolidate the Admission Policy.

## Slide 17: PROGRAMME 1 …
Quality Learning and Teaching Campaign (QLTC)
Advocacy and Mobilisation of society- The unit coordinated provincial visits as part of the mobilisation strategy and lead the introduction of Coding and Robotics as part of the strategy to demonstrate stakeholders to support the implementation of this curriculum.
Initiated and participated workshop in the Psycho-Social Services (PSS) workshop with National Education Collaboration Trust (NECT) in support of Sekhukhune East districts.
Stakeholder meetings were held with South African Council for Educators (SACE) to develop a strategy and mechanism for working together.
Government Information Technology Office
Governance of Information and Communications Technology (ICT): Two (2) DBE Service Level Agreement (SLA) meetings were held on 27 January and 30 March 2021.
ICT Steering Committee meeting was held on 19 March 2021.
United Nations Educational, Scientific and Cultural Organisation (UNESCO)
The President of the South African National Commission for UNESCO, and Minister of Basic Education, Mrs AM Motshekga , MP, has appointed new ex-0fficio members to serve on the 7th National Commission for a term of four (4) years, 2021-2024.

## Slide 18: PROGRAMME 1 …
Strategic Planning and Reporting
The 2021/22 APP was submitted to the Department of Planning, Monitoring and Evaluation (DPME) and National Treasury (NT) on 29 January 2021.
The DBE 2021/22 APP was tabled in Parliament on 12 March 2021.
The Departmental third quarter performance report for 2020/21 was submitted to the DPME and NT on 29 January 2021, and successfully uploaded to the electronic Quarterly Performance Reporting System (eQPRS) on the same date.
The SACE and Umalusi 2021/22 APP were tabled in Parliament on 11 March 2021. The SACE and Umalusi 2020/21 third Quarterly Performance Reports were analysed and feedback was provided to the entities on 12 February 2021.
Branch Review meetings were successfully held from 08-24 March 2021 to support planning and improve reporting.
The Heads of Education Departments Committee (HEDCOM) Subcommittee on Planning, Monitoring and Evaluation was held on 18 February 2021 to discuss planning and reporting as well as the Medium-Term Strategic Framework (MTSF) alignment.
The MTSF revisions were incorporated in the 2021/22 APP.

## Slide 19: PROGRAMME 1 …
Research Co-ordination, Monitoring and Evaluation (RCME)
Second Early Grade Reading Study (EGRS II): The data from the fifth wave of data collection was analysed and a research note was developed to calculate the impact of the COVID-19 pandemic on learning losses in the Foundation Phase.
Early Grade Reading Improvement Programme (EGRP): Coach training took place between 18-21 January 2021 and Teacher training took place on 17-25 February 2021 for Grades 1 to 3 respectively.
The Reading Support Project (RSP) : A telephonic survey aimed at investigating how COVID-19 affected schooling, curriculum delivery, teaching performance and learner performance, the extent of alternative learning provisions and the psycho-social wellbeing of teachers and principals was conducted.
HEDCOM Subcommittee on Planning, Monitoring and Evaluation meeting was held on 18 February 2021.
Analysis of State of the Nation Addresses (SONA): A presentation was prepared and delivered for Parliament’s Portfolio Committee on Basic Education in February 2021.
General Household Survey Report: The data for the 2019 General Household Survey was received in March 2020 and a draft Focus on Schooling report was compiled.

## Slide 20: PROGRAMME 1 …
COORDINATING MECHANISM | SCHEDULED MEETINGS | MEETINGS HELD | UNSCHEDULED MEETINGS HELD | MEETINGS NOT HELD
BM | 3 | 0 | 1 | 3
CEM | 1 | 0 | 3 | 1
HEDCOM | 1 | 0 | 5 | 1
SM | 4 | 0 | 2 | 4
SPCHD Cluster | 2 | 1 | 0 | 1
SPCHD Cluster TWG | 3 | 1 | 0 | 2
TOTAL | 14 | 2 | 11 | 12
14 virtual meetings were scheduled, two (2) of which were convened during the period under review. Furthermore, 11 special virtual meetings were convened. 12 scheduled meetings could not be convened and these comprised of three (3) Broad Management Meeting (BMM), one (1) Council of Education Ministers (CEM), one (1) HEDCOM, four (04) Senior Management Meeting (SMM), one (1) Social Protection, Community and Human Development (SPCHD) Cluster, and two (2) SPCHD Cluster Technical Working Group (TWG). The DBE has successfully managed the logistical arrangements, agenda - setting and record drafting for all the 13 convened virtual meetings.
Coordination and Secretariat Support

## Slide 21: PROGRAMME 1 …
International Relations and Multilateral Affairs
The DBE hosted webinars with several African countries to share experiences on protocols put in place to respond to the COVID-19 pandemic in the schooling sector, as well as COVID-19 responsive plans for the 2021 academic year. The DBE held exchanges with the following countries:
  The Republic of Namibia on 27 January 2021;
  The Republic of Rwanda on 09 February 2021; and
  The Republic of Kenya on 16 February 2021.
Partnerships
2020 National Senior Certificate (NSC) Exam Results Announcement, the following partners and sponsors of the DBE contributed by sponsoring the learners with bursaries, cash prizes, ICT gargets and sponsored the hosting of event: MTN, Kagiso Trust, AVBOB, and Fundi
  Estimated number of schools: 33 schools and 33 learners benefited.
  Estimated number of Estimated monetary value: R 1 505 067.13

## Slide 22: PROGRAMME 2: CURRICULUM POLICY, SUPPORT AND MONITORING
The purpose of Programme 2 is to develop curriculum and assessment policies and monitor and support their implementation.

## Slide 23: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.1.1 Number of Technical schools monitored for implementation of Curriculum and Assessment Policy Statements (CAPS) | Quarterly | 18 | Q1: 6 Q2: 6 Q4: 6 Total: 18 | No deviation | Not applicable | Not applicable
 | Q4 | 6 | 6 | No deviation | Not applicable | Not applicable

## Slide 24: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.1.2 Number of learners obtaining subject passes towards a National Senior Certificate (NSC) or extended Senior Certificate, including upgraded NSC per year | Bi-annually | 60000 | 60 063 | +63 | The programme supported learners through four platforms: face-to-face centres, broadcast, online and provision of study materials. The Department increased the number of the face-to-face classes from 90 to 133 centres throughout the country. Working in partnership with different entities, the Department introduced the Woza Matric intervention that broadcast dedicated educational programmes to support Matric learners. The Woza Matric programmes were on SABC 1, DSTV Catch-Up and DBETV Channel 122 on Openview broadcasted matric catch-up lessons in 11 high enrolment subjects to help learner revise. The Department also increased the distribution of its online study materials through the partnerships. Furthermore, the Department also provided hard copy study materials to more learners. | Not applicable
 | Q4 | 30000 | 60 063 | +63 |  | Not applicable

## Slide 25: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.1.3 Number of Children/ Learners with Profound Intellectual Disability (C/LPID) using the Learning Programme for C/LPID | Annually | 3 527 | 3423 | -104 | COVID-19 restrictions resulted in closing of special care centres and some learners remained at home even when special care centres were eventually allowed to operate by the DSD. In addition, some residential high care special care centres did not allow teams to have direct contact with the learners fearing that the learners may get infected with COVID-19 Therefore, outreach team members could not reach all the learners to provide the necessary services that enables these learners to use the Learning Programme for LPID | 1. Some learners remain at home and some learners in residential high care centres cannot to be reached because centres management is protecting learners from getting infected with COVID-19 1.1 Remote support will be provided where and when necessary 1.2 DBE to ensure that PEDs provide appropriate PPEs to team members so that they continue providing services 1.3 DBE is working with DSD to assist Special Care Centres (SCCs) to comply with COVID-19 regulations so that SCCs are able to open and operate safely 2. The closure of special care centres resulted in teams not conducting cognitive assessments whose results enables learners to be on-boarded onto the Learning Programme for LPID 2.1 The DBE will use the online tracking tool to monitor and support PEDs and ensure the necessary support, that enables learners to participate in learning and development, is provided
 | Q4 | 3 527 | 3 315 | Annual target | Not applicable | Not applicable

## Slide 26: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.1.4 A National Report is produced on monitoring of the implementation of the Policy on Screening, Identification, Assessment and Support (SIAS) as a mechanism for early identification and intervention | Annually | Approved National Report on monitoring of the implementation of the Policy on Screening, Identification, Assessment and Support (SIAS) as a mechanism for early identification and intervention | Approved National Report on monitoring of the implementation of the Policy on Screening, Identification, Assessment and Support (SIAS) as a mechanism for early identification and intervention | No deviation | Not applicable | Not applicable
 | Q4 | Approved National Report on monitoring of the implementation of the Policy on Screening, Identification, Assessment and Support (SIAS) as a mechanism for early identification and intervention | Number of Teachers trained on the Policy on SIAS: 22 460 Number of Grade R practitioners trained on the SIAS policy: 1 939 Number of officials trained on the SIAS policy: 1 962 Number of schools whose teachers participated in the training of SIAS policy: 2 919 Number of learners identified and assessed in terms of the policy: 21 412 Number of Individual Support Plans (ISP) developed for the above learners: 15 571 Number of cases successfully resolved by schools: 10 086 Number of cases referred to DBSTs: 12 344 Number of cases successfully resolved by DBSTs: 8 785 Number of schools that have a functional SBST: 3 958 Number of schools monitored for the functionality of SBSTs by DBSTs: 2 033 Number of schools monitored for the implementation of the Policy on SIAS: 3 118 | Annual target | Not applicable | Not applicable

## Slide 27: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.1.5 Amend legislation to regulate the new Early Childhood Development (ECD) landscape | Annually | A joint submission for determination on the ECD function shift is submitted to the Minister of Public Service and Administration | Diagnostic report has been approved Draft Determinations not provided- dependent on the promulgation of the proclamations. | Proclamation not finalised by end of 2020/21. | The delay in signing the proclamations, which would enable the labour relations process to start, where DBE and DSD would negotiate the number of posts and staff to be transferred, delayed the finalisation of the submission for determination as it needed to include the resources in terms of posts, budget and assets that will be transferred | The President signed the proclamation on 30 June 2021, allowing for the finalisation of the submission for determination. The joint submission was submitted to the DPSA on 21 July 2021.
 | Q4 | Determination submitted to DPSA | Updated proclamations are back from the office of OCSLA and are being processed to the DPSA | Annual target | Not applicable | Not applicable
2.1.6 Develop new funding models for ECD delivery | Annually | Report on investigation into ECD funding models | Report on investigation into ECD funding models | No deviation | Not applicable | Not applicable
 | Q4 | Approved report with recommendations | Financial diagnostic report on the current funding model for ECD has been approved. | Annual target | Not applicable | Not applicable

## Slide 28: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output * | Deviation | Reason for deviation | Comment/ Corrective Action
2.1.7 Conduct an Early Childhood Development census to inform the integration of ECD into the EMIS | Annually | Preparations for ECD census is concluded | Signed MoU DBE RSA and Lego Foundation provided. South Africa ECD Census 2021 Request for Tender provided. | Preparations for ECD census were not concluded | Due to delays in appointing a service provider, the ECD Census pilot was only conducted in June 2021. | The pilot was successfully conducted in June 2021 and a pilot report was submitted to the DBE on 5 July 2021.
 | Q4 | Preparations for ECD census is concluded | Appointed service provider | Annual target | Not applicable | Not applicable
2.1.8 Develop and operationalise an Early Childhood Development (ECD) Human Resource Development (HRD) Plan | Annually | Report on ECD service delivery model and its workforce implications | Report on ECD service delivery model and its workforce implications. | No deviation | Not applicable | Not applicable
 | Q4 | Approved HRD plan | Financial diagnostic report on the current human resources connected to the ECD functions has been approved. | Annual target | Not applicable | Not applicable

## Slide 29: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.1.9 Number of districts monitored on implementation of the National Curriculum Statement (NCS) for Grades 10 - 12 | Annually | 8 | 8 | No deviation | Not applicable | Not applicable
 | Q4 | 8 | Eight (8) Districts monitored and annual report developed | Annual target | Not applicable | Not applicable
2.1.10 Number of provinces monitored on extra-support classes to increase the number of learners achieving Bachelor level passes | Annually | 3 | 3 | No deviation | Not applicable | Not applicable
 | Q4 | 3 | Three (3) provinces monitored and annual report developed | Annual target | Not applicable | Not applicable

## Slide 30: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.1.11 Number of schools monitored for implementing compulsory entrepreneurship education | Annually | 90 (10 per province) | 86 | -4 | The negative deviation of 4 is as a result of: The closure of schools due to COVID-19 The delay in starting the monitoring of schools The data collection process commenced on 24 September 2020 – 10 March 2021. Instead of May 2020. The consequence being that in some provinces, the target of 10 was not achieved, and in some it surpassed the target of 10 as noted below: Eastern Cape: 11 Gauteng: 9 Free State: 10 KwaZulu-Natal: 9 Limpopo: 11 Mpumalanga: 10 Northern Cape: 10 North West: 9 Western Cape: 7 Total schools monitored: 86 | Conduct a workshop with the Monitoring and Evaluation team to plan for 2021/2022 to mediate the challenge of COVID-19 and plan accordingly Ensure collection of data starts in June 2021 Improve engagements with provinces and districts Provide extensive training to capacitate field workers in collecting data Set quarterly targets to achieve the annual target.
 | Q4 | 90 (10 per province) | 85 schools monitored | Annual target | Not applicable | Not applicable

## Slide 31: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output * | Deviation | Reason for deviation | Comment/ Corrective Action
2.1.12 An Annual Sector Report is produced on the implementation of the General Education Certificate (GEC) | Annually | Approved Annual Sector Report on the implementation of the General Education Certificate (GEC) | Approved Annual Sector on the implementation of the General Education Certificate (GEC). | Nine (9) PED reports substantiating the Annual Sector Report are not provided. | The first cycle of the GEC roll-out is scheduled for November 2023. The milestone reached in 2020/21 is the provisional approval of Umalusi of the draft policy framework. | The GEC pilot study has been scheduled for the 3rd and 4th school terms of 2021. The pilot study report will be consolidated from 9 PED reports.
 | Q4 | Approved Annual Sector Report on the implementation of the General Education Certificate (GEC) | Umalusi provisionally approved the draft policy framework which must go out for public comment. | Annual target | Not applicable | Not applicable
2.1.13 An Annual Sector Report is produced on schools that are prepared to respectively implement and pilot the Technical Occupational Stream | Annually | An Approved Annual Sector Report on Schools of Skill that pilot the Technical Occupational Stream in 2020/21 | An Approved Annual Sector Report on Schools of Skill that pilot the Technical Occupational Stream in 2020/21 | Nine (9) PED Reports not provided to substantiate achievement by 31 May 2021 | The deviation was caused by delays in the submission of reports by PEDs. | PEDs were chased and all reports were submitted to AGSA on 9 July 2021
 | Q4 | An Approved Annual Sector Report on Schools of Skill that pilot the Technical Occupational Stream in 2020/21 | LTSM (Learner Books and Teacher Guides) for Fundamental Subjects were developed in the February 2021 workshop; the Fundamental Subjects were submitted to Umalusi for appraisal and feedback to DBE; LTSM for term 1 for the Fundamental Subjects were uploaded on the DBE website for access by PEDs and schools. | Annual target | Not applicable | Not applicable

## Slide 32: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.2.1 Number of schools monitored on the implementation of the reading norms | Annually | 10 | 10 | No deviation | Not applicable | Not applicable
 | Q4 | 10 | 10 schools were monitored | Annual target | Not applicable | Not applicable
2.2.2 Number of schools monitored on the implementation of the Incremental Introduction to African Languages (IIAL) | Annually | 10 | 10 | No deviation | Not applicable | Not applicable
 | Q4 | 10 | 10 schools were monitored | Annual target | Not applicable | Not applicable
2.2.3 Number of underperforming schools monitored on the implementation of the Early Grade Reading Assessment (EGRA) | Annually | 10 | 10 | No deviation | Not applicable | Not applicable
 | Q4 | 10 | 10 schools were monitored | Annual target | Not applicable | Not applicable

## Slide 33: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.2.4 Number of schools with Multi-grade classes monitored for implementing the Multi-grade toolkit | Annually | 10 | 10 | No deviation | Not applicable | Not applicable
 | Q4 | 10 | 10 schools were monitored | Annual target | Not applicable | Not applicable
2.2.5 An Annual Sector Report is produced on the implementation of the National Reading Plan | Annually | Approved Annual Sector Report on the implementation of the National Reading Plan | Approved Annual Sector Report on the implementation of the National Reading Plan | No deviation | Not applicable | Not applicable
 | Q4 | Approved Annual Sector Report on the implementation of the National Reading Plan | Provinces submitted reports on reading activities | Annual target | Not applicable | Not applicable

## Slide 34: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output * | Deviation | Reason for deviation | Comment/ Corrective Action
2.2.6 An Annual Sector Report is produced on the number of public schools monitored on the availability of readers | Annually | Approved Annual Sector Report on the number of public schools monitored on the availability of readers | Approved Annual Sector Report on the number of public schools monitored on the availability of readers | No deviation | Not applicable | Not applicable
 | Q4 | Approved Annual Sector Report on the number of public schools monitored on the availability of readers | Signed-off Provincial reports have been received from six (6) provinces thus far. A letter has been sent with reminders for outstanding PEDs to send the reports. | Annual target | Not applicable | Not applicable
2.3.1 Number of schools per province monitored for utilisation of Information and Communications Technology (ICT) resources | Annually | 27 (3 per province) | 27 (3 per province) | No deviation | Not applicable | Not applicable
 | Q4 | 27 (3 per province) | Twelve (12) schools were monitored as follows: Limpopo (3 schools) Eastern Cape (3 schools) Northern Cape (3 schools) Free State (3 schools) | Annual target | Not applicable | Not applicable

## Slide 35: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.3.2 Percentage of public schools provided with Home Language workbooks for learners in Grades 1 to 6 per year after having placed an order | Annually | 100% Annually | 100% 17077/17077 | No deviation | Not applicable | Not applicable
 | Q4 | 100% | Delivery of Home Languages workbooks progressed to 100%. A total of 17 077 of 17 077 schools that placed Grades 1 to 6 Home Language workbook received their consignment | Annual target | Not applicable | Not applicable
2.3.3 Percentage of public schools provided with Mathematics workbooks for learners in Grades 1 to 9 per year, after having placed an order | Annually | 100% Annually | 100% 22955/22955 | No deviation | Not applicable | Not applicable
 | Q4 | 100% | Delivery of Mathematics workbooks progressed to 100%. A total number of 22 955 of 22 955 schools that placed Grades 1 to 9 Mathematics workbooks orders received their consignment. | Annual target | Not applicable | Not applicable

## Slide 36: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.3.4 Percentage of public schools provided with workbooks for learners in Grades R per year, after having placed an order | Annually | 100% Annually | 100% 16125/16125 | No deviation | Not applicable | Not applicable
 | Q4 | 100% | Delivery of Grade R workbooks progressed to 100%. A total of 16125 of 16 125 schools that placed Grade R workbook orders received their consignment | Annual target | Not applicable | Not applicable
2.3.5 An Annual Sector Report is produced on the learners provided with Mathematics and English First Additional Language (EFAL) textbooks in Grades 3, 6 and 9 | Annually | Approved Annual Sector Report | Approved Annual Sector Report on the learners provided with Mathematics and English First Additional Language (EFAL) textbooks in Grades 3, 6 and 9 | Two (2) PED reports substantiating the Annual Sector Report not provided. | Late submission by the PEDs | The two provinces submitted their reports in June and the Annual Sector Report was updated.
 | Q4 | Approved Annual Sector Report | DBE has written to provinces for provinces to submit their Annual Reports, furthermore the Department held a teams meeting 04-12 February 2021 with Provinces to discuss LTSM matters including the PPM (agenda items) | Annual target | Not applicable | Not applicable

## Slide 37: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.3.6 The number of schools monitored for home languages in which Literacy Grades 1-3 Lesson Plans have been developed for terms 1-4 | Annually | 10 | 10 | No deviation | Not applicable | Not applicable
 | Q4 | 10 | 10 schools have been monitored | Annual target | Not applicable | Not applicable
2.3.7 Number of special schools with access to electronic devices | Annually | 140 | 145 | +5 | The rollout of electronic devices and connectivity to Public Special Schools is funded by the Mobile Network Operators (MNO) not the DBE. Therefore, the rollout of the equipment is based on the availability of funding from the MNOs. It is in this regard that the number of Schools provided with ICT resources exceeded the DBE target of 140 schools for 2020/21. | Not applicable
 | Q4 | 140 | Liquid Telkom (19) and CELL C (1) provided 20 special schools with ICT Electronic Devices | Annual target | Not applicable | Not applicable

## Slide 38: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output * | Deviation | Reason for deviation | Comment/ Corrective Action
2.4.1 An Annual Sector Report is produced on the number of teachers trained on inclusion | Annually | Approved Annual Sector Report on the number of teachers trained on inclusion | Approved Annual Sector Report on the number of teachers trained on inclusion | 3 PED Reports not provided to substantiate achievement | There were delays in the submission of provincial reports. | The DBE has written to PEDs, requesting them to submit reports on specific dates for 2021/22.
 | Q4 | Approved Annual Sector Report on the number of teachers trained on inclusion | A total of 1 197 teachers from EC, LP and NW were trained on various inclusive education topics including technical occupational subjects. Facilitated the process of preparing provinces for the submission of data for the annual report. Guidance provided on what and how to submit. Dry runs were conducted where provinces made presentations on the implementation of the indicator during the Inter-provincial Meeting on Inclusive Education held on 19 March 2021. | Annual target | Not applicable | Not applicable
2.4.2 An Annual Sector Report is produced on the number of learners in public special schools | Annually | Approved Annual Sector report on the number of learners in public special schools | Approved Annual Sector report on the number of learners in public special schools | PED Reports not provided to substantiate achievement | There were delays in the submission of provincial reports. | The DBE has written to PEDs, requesting them to submit reports on specific dates for 2021/22. The PED reports were later submitted.
 | Q4 | Approved Annual Sector report on the number of learners in public special schools | Collaborated with EMIS to provide the number of leaners in public special schools. To date there are 133 055 learners in public special schools. | Annual target | Not applicable | Not applicable

## Slide 39: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output* | Deviation | Reason for deviation | Comment/ Corrective Action
2.4.3 An Annual Sector Report is produced on the percentage of public special schools serving as resource centres | Annually | Approved Annual Sector Report on the percentage of public special schools serving as resource centres | Approved Annual Sector Report on the percentage of public special schools serving as resource centres | 4 PED Reports not provided to substantiate achievement | There were delays in the submission of provincial reports. | The DBE has written to PEDs, requesting them to submit reports on specific dates for 2021/22. The 4 PED reports were submitted
 | Q4 | Approved Annual Sector Report on the percentage of public special schools serving as resource centres | 139 of the 447 special schools have been designated as resource centres. That is 31.1% of special schools that serve as resource centres. 62 of these 139 resource centres have received ICT, assistive devices and connectivity as part of the USAO project initiated by Vodacom, cell-C, MTN and Liquid telecoms. Facilitated the process of preparing provinces for the submission of data for the annual report. Guidance provided on what and how to submit. Dry run sessions were conducted, where provinces made presentations on the implementation of the indicator during the Inter-provincial Meeting Inclusive Education held on 19 March 2021. | Annual target | Not applicable | Not applicable

## Slide 40: PROGRAMME 2 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
2.4.4 An Annual Sector Report is produced on the establishment of Focus Schools per Provincial Education Department | Annually | Approved Annual Sector Report on the establishment of Focus Schools per Provincial Education Department | Approved Annual Sector Report on the establishment of Focus Schools per Provincial Education Department | No deviation | Not applicable | Not applicable
 | Q4 | Approved Annual Sector Report on the establishment of Focus Schools per Provincial Education Department | DG letters requesting PEDs to submit their Annual reports by 30 April 2021 have been sent to PEDs | Annual target | Not applicable | Not applicable

## Slide 41: PROGRAMME 2…
Curriculum, Implementation and Quality Improvement (FET)
Developed and implemented the 2020 Curriculum Trimming and Reorganisation Framework, including Annual teaching Plans for 2020 and 2021. 45 Grades 10-12 Literature Study Guides and 12 Creative Writing Study guides developed for all Home Languages.
Monitoring of Curriculum Coverage and Implementation in eight (8) Districts and Monitoring Extra Support Classes offered to provide extra tuition to Grade 12 learners.
Developed policy to guide the implementation of the revised and trimmed curriculum as well as promulgated the Abridged Section 4 of Curriculum and Assessment Policy Statement (CAPS) for Grade 12.
Developed the Midyear and Final Evidence Based Report (EBR) and presented to Umalusi as part of the 2020 NSC standardisation.
Supported the 2020 NSC Standardisation by evaluating question papers, conducting item and error analysis and prepared and presented subject standardisation reports.

## Slide 42: PROGRAMME 2 …
Curriculum, Implementation and Quality Improvement (GET)
Recovery Multi-grade Annual teaching for all subjects in Grades 4 – 9 were developed.
Project Based Learning activities for Life Skills, Life Orientation, Creative Arts (Performing Arts {Music} and Visual Arts) were developed.
Teacher and Learners Guides were developed for the Occupational subjects for schools of skills namely, Life Skills, Creative Arts, Home and English First Additional Languages.
Inclusive Education
Finalised the 2021/22 Severe to Profound Intellectual Disability (LSPID) Grant Framework and Allocations.
Monitored procurement of Learning and Teaching Support Material (LTSM), Assistive Devices, Personal Protective Equipment (PPE), COVID-19 consumables and technology to be used to support teaching and learning in special care centres in five (5) provinces namely, Free State, Gauteng, Limpopo, Northern Cape and North West.
Facilitated a meeting with Limpopo PED to intervene on the challenges in the implementation of LSPID Conditional Grant. Provided guidance on how to address challenges that were impacting on the performance of the Conditional Grant in the province .

## Slide 43: PROGRAMME 2
Mathematics, Science and Technology (MST) and Information and Communication Technology (ICT)
DBE Cloud: Created e-Learning Platform for the training of the e-Cadres. The following courses are available online: Basic ICT Training; Coding and Robotics; and South African School Administration and Management System (SASAMS). Uploaded 3 000 videos on the DBE Cloud platform.
ICT Professional Teacher Development in collaboration with VVOB: A total number of 91 teachers are uploaded, with username and passwords created on the DBE Cloud Platform. These teachers are busy with the Professional Learning Community (PLC) courses on the DBE Cloud Platform.
Connectivity: A total number of 191 Special Schools have been provided with connectivity as part of the Universal Service Access Obligations (USAO). Department of Communications and Digital Technologies (DCDT) submitted a list of 599 schools that were connected as part of the SA Connect Initiative.
Content Development and Distribution: Facilitated a virtual workshop for discussion between authors and subject specialist regarding the framework that informs the development and digitisation of Grades 10-12 Business Studies State-owned Textbooks.

## Slide 44: PROGRAMME 2
Mathematics, Science and Technology (MST) and Information Communication Technology (ICT)
The Basic Education Sector appointed youth and provided training so that they can support teachers and learners.
The appointed e-Cadres were trained in the following ICT related programmes identified:
  SASAMS Training (10 951 e-Cadres trained);
  Special schools training (1 147 e-Cadres trained);
  Microsoft ICT skills training (1 430 e-Cadres trained);
  Skills for Innovation training (727 e-Cadres trained); and
  e-Readiness ICT maturity Assessment (22 Officials and 2 849 e-Cadres trained).
Focus Schools: Consultations between the DBE and PEDs have resulted in the development of Focus Schools Guidelines, inter alia, for the definition/classification, establishment and management of Focus Schools.

## Slide 45: PROGRAMME 2
Mathematics, Science and Technology (MST) and Information Communication Technology (ICT)
Coding and Robotics: The draft CAPS documents for Grades R-3, Grades 4-6 and Grades 8-9 were developed and submitted to Umalusi for Quality Assurance, and Gazetted for public comments on 19 March 2021.
KwaZulu-Natal and Gauteng were visited to monitor the readiness for the implementation of the pilot:
  Project Management Teams have been established in the nine (9) PEDs;
  National Training Team (NTT) has been orientated on the Grades R-3 and Grade 7 CAPS;
  Facilitators and participants’ orientation manuals have been developed; and
  Learner and Teacher Resources have been uploaded on the DBE Moodle Platform.

## Slide 46: PROGRAMME 2 …
Enhancement of Programme and Evaluation of School Performance (LTSM) …
Workbooks: Delivered Volumes 1 and 2 Workbooks to public schools in order to achieve 100%. A total number of 61 027 095 Grades R-9 Volumes 1 and 2 were delivered to all 23 094 schools that placed workbook order for 2021 academic year.
Braille Workbooks: Provided Grades 1- 3 Life Skills Braille Volume 1 Workbooks in 11 African languages to 22 Special schools.
A review of Grade R workbooks was held in different provinces as follows: 08-10 March 2021 (KwaZulu-Natal), 13-15 March 2021 (Mpumalanga), 18-20 March 2021 (Western Cape) and 24-26 March 2021 (Eastern Cape). All 11 African languages have been checked and Artworks teams are implementing the recommendations.
The English master copies for Grades 4-6 Second Additional Language (SAL) toolkits for term 1 and 2 for Incremental Introduction of African Languages (IIAL) implementation have been developed by National Education Collaboration Trust (NECT). Versioning of the master copy into 12 languages for term 1 has been completed.

## Slide 47: PROGRAMME 2 …
Enhancement of Programme and Evaluation of School Performance (LTSM) …
State Owned Textbooks: A virtual workshop to present and unpack the Grades 10-12: Business Studies Framework to developers (TTRO) and partner Amalgamated Banks of South Africa (ABSA) was held on 12-15 March 2021. Reports were compiled and submitted to the developers including the framework for further development.
A virtual workshop for development of framework for Grades 4-9 Mathematics booklets was held on 12-15 March 2021. Framework for both workbooks and booklets were produced for use during the development process of the respective books.
Universal Coverage: Provinces reported that all schools received necessary ordered LTSM for Section 20 and 21 schools for 2021 academic year. The sector is working towards ensuring that 100% Universal coverage is met.
The LTSM Electronic System is at 80% development stage to ensure procurement, monitoring and retention and retrieval of resources in provinces, districts and schools.

## Slide 48: PROGRAMME 2: GRADES R-9 WORKBOOKS (VOLUME 1)
Workbooks: 2021 Delivery Status: Volume 1 Grade R,1-9
Provinces | Total Schools Allocated | Total Books Allocated | Schools Dispatched | Books Dispatched | Schools Delivered | Books Delivered | % Schools Delivered | % Books Delivered
EC | 5,147 | 4,660,025 | 5,147 | 4,660,025 | 5,147 | 4,660,025 | 100% | 100%
FS | 1,033 | 1,830,500 | 1,033 | 1,830,500 | 1,033 | 1,830,500 | 100% | 100%
GP | 2,114 | 5,449,175 | 2,114 | 5,449,175 | 2,114 | 5,449,175 | 100% | 100%
KZN | 5,923 | 7,175,210 | 5,923 | 7,175,210 | 5,923 | 7,175,210 | 100% | 100%
LP | 3,704 | 4,766,070 | 3,704 | 4,766,070 | 3,704 | 4,766,070 | 100% | 100%
MP | 1,676 | 2,951,480 | 1,676 | 2,951,480 | 1,676 | 2,951,480 | 100% | 100%
NC | 541 | 773,200 | 541 | 773,200 | 541 | 773,200 | 100% | 100%
NW | 1,438 | 2,002,225 | 1,438 | 2,002,225 | 1,438 | 2,002,225 | 100% | 100%
WC | 1,518 | 2,844,610 | 1,518 | 2,844,610 | 1,518 | 2,844,610 | 100% | 100%
Grand Total | 23,094 | 32,452,495 | 23,094 | 32,452,495 | 23,094 | 32,452,495 | 100% | 100%
Data Set: 31 March 2021

## Slide 49: PROGRAMME 2: GRADES R-9 WORKBOOKS (VOLUME 2)
Workbooks 2021 Delivery Status Volume 2 Grade 1-9
Provinces | Total Schools Allocated | Total Books Allocated | Schools Dispatched | Books Dispatched | Schools Delivered | Books Delivered | % Schools Delivered | % Books Delivered
EC | 5,139 | 4,082,925 | 5,139 | 4,082,925 | 5,139 | 4,082,925 | 100% | 100%
FS | 1,032 | 1,646,525 | 1,032 | 1,646,525 | 1,032 | 1,646,525 | 100% | 100%
GP | 2,098 | 4,850,245 | 2,098 | 4,850,245 | 2,098 | 4,850,245 | 100% | 100%
KZN | 5,878 | 6,236,090 | 5,878 | 6,236,090 | 5,878 | 6,236,090 | 100% | 100%
LP | 3,700 | 4,212,485 | 3,700 | 4,212,485 | 3,700 | 4,212,485 | 100% | 100%
MP | 1,625 | 2,578,935 | 1,625 | 2,578,935 | 1,625 | 2,578,935 | 100% | 100%
NC | 541 | 678,200 | 541 | 678,200 | 541 | 678,200 | 100% | 100%
NW | 1,422 | 1,778,315 | 1,422 | 1,778,315 | 1,422 | 1,778,315 | 100% | 100%
WC | 1,505 | 2,510,880 | 1,505 | 2,510,880 | 1,505 | 2,510,880 | 100% | 100%
Grand Total | 22,940 | 28,574,600 | 22,940 | 28,574,600 | 22,940 | 28,574,600 | 100% | 100%
Data Set: 31 March 2021

## Slide 50: PROGRAMME 2 …
Early Childhood Development (ECD)
A draft booklet on the Understanding of Qualifications in ECD has been developed for the ECD practitioners and circulated for comments;
ECD Function Shift: Final Proclamations certified by the Office of the Chief State Law Advisor (OCSLA) has been implemented;
Proclamations translated into ten (10) of the 11 languages;
A Memorandum of Understanding (MoU) between the DBE and Department of Social Development (DSD) drafted to regulate the transition period in 2021;
A joint briefing was held with the Portfolio Committees responsible for DBE and DSD on 16 March 2021.

## Slide 51: PROGRAMME 2…
Reading
Primary School Reading Improvement Programme (PSRIP) : DBE in collaboration with NECT wrapped up the implementation of the Phase 3 of PSRIP where mop–up training was provided to 146 teachers.
The implementation of Phase 4 of PSRIP has ensued with the training of a new cohort of 141 Foundation Phase Subject Advisors and 29 School Management Teams (SMTs) Master Trainers. The training was undertaken using online platforms, MS Teams and Zoom.
Reading Champions Programme: 23 286 Reading Champions were placed in schools across the provinces as part of the Basic Education Employment Initiative (BEEI):
Province | Number placed | Province | Number placed
North West | 1 501 | Northern Cape- | 3 069
Eastern Cape | 5 389 | Gauteng | 2 521
Western Cape | 665 | Limpopo | 3 360
Free State | 435 | Mpumalanga | 1 103
KwaZulu-Natal | 5 243 |  | 

## Slide 52: PROGRAMME 2…
Rural Education
Rural Education Assistants Project (REAP): The Project Management Team undertook monitoring visits to five (5) REAP schools in three (3) provinces. Edulution Programme: The project was launched in KwaZulu-Natal on March 2021.
Second Chance Matric Programme (SCMP)
Inter-Provincial meeting was held to discuss the preparation for the plans of the 2021 academic year on 05 January 2021.
The Development of Study Guides: 37 Content Access Points (CAPs) that have been uploaded with the digital content. The CAPs will be distributed to the centre that are not connected to the Internet.
The SCMP website has been zero-rated by Vodacom. The website will be accessible to teachers and learners without any data. Engaged with MTN to secure the same zero rate on the website.
Funded and facilitated the development of Mind the Gap Study Guides as follows:
  Hosted and facilitated the development of 14 Occupational subjects; and
  Finalised the 57 South African Sign Language (SASL) LTSM.

## Slide 53: PROGRAMME 3: TEACHERS, EDUCATION HUMAN RESOURCES AND INSTITUTIONAL DEVELOPMENT
The purpose of Programme 3 is to promote quality teaching and institutional performance through the effective supply, development and utilisation of human resources.

## Slide 54: PROGRAMME 3 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
3.1.1 Percentage of School Governing Bodies (SGBs) that meet the minimum criteria in terms of effectiveness | Annually | 90% of 1 000 sampled schools | 96% 960/1 000 | +6% | The deviation is attributed to the experience of governors after 3 years in office. | Not applicable
 | Q4 | 90% of 1 000 sampled schools | 96% 960/1 000 | Annual target | Not applicable | Not applicable
3.1.2 Percentage of schools producing the minimum set of management documents at a required standard | Annually | 100% of 1 000 sampled schools | 100% 1000/1000 | No deviation | Not applicable | Not applicable
 | Q4 | 100% of 1 000 sampled schools | 100% 1000/1000 | Annual target | Not applicable | Not applicable

## Slide 55: PROGRAMME 3 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
3.1.3 Number of Funza Lushaka bursaries awarded to students enrolled for Initial Teacher Education | Annually | 12 500 | 13 085 | +585 | The deviation is attributed to tuition fees being less than what was projected resulting in more bursaries being awarded | Not applicable
 | Q4 | 12 500 | 13 085 | Annual target | Not applicable | Not applicable
3.1.4 Number of quarterly monitoring reports tracking the percentage of Funza Lushaka graduates placed within six months upon confirmation that the bursar has completed studies | Quarterly | 4 | Q1: 1 Q2: 1 Q3: 1 Q4: 1 Total: 4 | No deviation | Not applicable | Not applicable
 | Q4 | 1 | 1 | No deviation | Not applicable | Not applicable

## Slide 56: PROGRAMME 3 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
3.1.5 Number of quarterly monitoring reports indicating the number and percentage of schools where allocated teaching posts are all filled | Quarterly | 4 | Q1: 1 Q2: 1 Q3: 1 Q4: 1 Total: 4 | No deviation | Not applicable | Not applicable
 | Q4 | 1 | 1 | No deviation | Not applicable | Not applicable
3.1.6 An Annual Sector Report is produced on the number of qualified teachers aged 30 and below entering the public service as teachers | Annually | Approved Annual Sector Report on the number of qualified teachers aged 30 and below entering the public service as teachers | Approved Annual Sector Report on the number of qualified teachers aged 30 and below entering the public service as teachers | No deviation | Not applicable | Not applicable
 | Q4 | Approved Annual Sector Report on the number of qualified teachers aged 30 and below entering the public service as teachers | Preliminary report on the number of educators aged 30 and below entering the public service as teachers produced. | Annual target | Not applicable | Not applicable

## Slide 57: PROGRAMME 3 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
3.2.1 A National Report is produced on monitoring the functionality of Provincial Teacher Development Institutes and District Teacher Development Centres | Annually | Approved National Report on monitoring the functionality of Provincial Teacher Development Institutes and District Teacher Development Centres | Approved National Report on monitoring the functionality of Provincial Teacher Development Institutes and District Teacher Development Centres | No deviation | Not applicable | Not applicable
 | Q4 | Approved National Report on monitoring the functionality of Provincial Teacher Development Institutes and District Teacher Development Centres | 6 Provincial Teacher Development Institutes (PTDIs) and 31 District Teacher Development Centres (DTDCs) monitored. 9 PEDs’ narrative quarterly reports received. | Annual target | Not applicable | Not applicable

## Slide 58: PROGRAMME 3 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
3.2.2 A National Report is produced on monitoring the implementation of Teacher Development Programmes by PEDs with special focus on EFAL, Mathematics, Physical Science and Accounting | Annually | Approved National Report on monitoring the implementation of Teacher Development Programmes by PEDs with special focus on EFAL, Mathematics, Physical Science and Accounting | Approved National Report on monitoring the implementation of Teacher Development Programmes by PEDs with special focus on EFAL, Mathematics, Physical Science and Accounting | No deviation | Not applicable | Not applicable
 | Q4 | Approved National Report on monitoring the implementation of Teacher Development Programmes by PEDs with special focus on EFAL, Mathematics, Physical Science and Accounting | Preliminary report on monitoring the implementation of Teacher Development Programmes by PEDs with special focus on EFAL, Mathematics, Physical Science and Accounting produced. | Annual target | Not applicable | Not applicable

## Slide 59: PROGRAMME 3 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
3.2.3 Number of PEDs that had their post provisioning processes assessed for compliance with the post provisioning norms and standards | Annually | 9 | 9 | No deviation | Not applicable | Not applicable
 | Q4 | 9 | 9 provincial monitoring meetings completed and the Report compiled | Annual target | Not applicable | Not applicable
3.2.4 An Annual Sector Report is produced on the number of Grade R practitioners with at least an National Qualifications Framework (NQF) level 6 and above qualification | Annually | Approved Annual Sector Report on the number of Grade R practitioners with at least an NQF level 6 and above qualification | Approved Annual Sector Report on the number of Grade R practitioners with at least an NQF level 6 and above qualification | No deviation | Not applicable | Not applicable
 | Q4 | Approved Annual Sector Report on the number of Grade R practitioners with at least an NQF level 6 and above qualification | The approved annual sector report declares that there are 7 900 Grade R Practitioners (36%) who are appropriately qualified to teach in the Grade R class with at least NQF level 6 and above qualifications. | Annual target | Not applicable | Not applicable

## Slide 60: PROGRAMME 3 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
3.3.1 Number of PEDs monitored on the Integrated Quality Management System (IQMS) | Annually | 9 | 9 | No deviation | Not applicable | Not applicable
 | Q4 | 9 | Annual Monitoring Status on the IQMS developed | Annual target | Not applicable | Not applicable
3.3.2 Number of PEDs monitored on the implementation of the Education Management Service: Performance Management and Development System (EMS: PMDS) | Annually | 9 | 9 | No deviation | Not applicable | Not applicable
 | Q4 | 9 | Annual monitoring status report on EMS: PMDS developed | Annual target | Not applicable | Not applicable

## Slide 61: PROGRAMME 3 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
3.3.2 Number of PEDs monitored on the implementation of the Education Management Service: Performance Management and Development System (EMS: PMDS) | Annually | 9 | 9 | No deviation | Not applicable | Not applicable
 | Q4 | 9 | Annual monitoring status report on EMS: PMDS developed | Annual target | Not applicable | Not applicable

## Slide 62: PROGRAMME 3 …
Education Labour Relations and Conditions of Service
The Protocol document between SACE and the employers on Managing Educators Conduct: The purpose of this document is to facilitate an understanding of distinctiveness, interdependence and interrelatedness of the DBE and the SACE regarding the disciplinary Code and Procedure and the Code of Professional Ethics applicable to educators.
  The document is completed and has been signed by all the nine (9) Provincial Heads of Education Departments (HODs), SACE and The Education Labour Relations Council (ELRC)
  It is being circulated to the School Governing Body Associations, the DSD and the Department of Justice and Constitutional Development for their endorsement.
DBE Circular 1 of 2021: The Return Of Educators and Support Staff to Schools for the 2021 Academic Year amidst COVID-19 Pandemic: This Circular was issued to provide guidance during Alert Level 3 on procedures to be followed when educators and learners returned to schools and alleviate anxieties amongst educators/education workers and learners, when the country experienced the rising COVID-19 infections.

## Slide 63: PROGRAMME 3 …
Education Labour Relations and Conditions of Service.
Addendum to Circular 1 of 2021: An Addendum to DBE Circular 1 of 2021 was drafted to clarify any ambiguities and uncertainties with regard to the return of educators and support staff to schools during Alert Level 3.
When the country was moved to Alert Level 1 of lockdown, the DBE drafted Circular 2 of 2021 to provide guidance to schools in order to facilitate the return of all educators to schools but also alleviate fears amongst educators and support staff with comorbidities.

## Slide 64: PROGRAMME 3 …
Education Human Resource Planning, Provisioning and Monitoring
Nine (9) provincial virtual monitoring meetings were held and a consolidated Report was compiled.
Compiled a preliminary Annual Report on appointment of educators age 30 and below. In 2020/21, a total number of 9 338 young and qualified educators were appointed in schools.
An Annual Report on the placement of Funza Lusaka graduates in schools covering the 2020 placement cycle and the first quarter of the 2021 placement cycle was compiled. 82% (3 613 of 4 413) were in 2020 and 967 of 4 329 were placed for the 2021 cycle.

## Slide 65: PROGRAMME 3 …
Placement of Funza Lushaka Graduates in 2020
Source: PERSAL and PED reports: March 2021
PED | Placed | Unplaced | Allocation | Placement%
Eastern Cape | 541 | 113 | 654 | 83%
Free State | 300 | 22 | 322 | 93%
Gauteng | 896 | 126 | 1 022 | 88%
KwaZulu-Natal | 356 | 235 | 591 | 60%
Limpopo | 412 | 18 | 431 | 96%
Mpumalanga | 313 | 68 | 381 | 82%
North West | 255 | 14 | 269 | 95%
Northern Cape | 93 | 3 | 96 | 97%
Western Cape | 447 | 201 | 648 | 69%
Grand Total | 3 613 | 800 | 4 413 | 82%

## Slide 66: PROGRAMME 3 …
Number and percentage of schools where allocated posts were filled per province
Source: PERSAL, March 2021
Province | Not All Filled | All Filled | Total | Percentage All Filled-Q4 | Percentage All Filled-Q3 | Percentage All Filled-Q2 | Percentage All Filled-Q1
Eastern Cape | 2 095 | 3 058 | 5 153 | 59% | 66% | 62% | 63%
Free State | 357 | 700 | 1 057 | 66% | 80% | 75% | 72%
Gauteng | 789 | 1 451 | 2 240 | 65% | 85% | 75% | 74%
KwaZulu-Natal | 1 993 | 3 894 | 5 887 | 66% | 46% | 38% | 36%
Limpopo | 2 127 | 1 597 | 3 724 | 43% | 38% | 31% | 32%
Mpumalanga | 494 | 1 180 | 1 674 | 70% | 49% | 41% | 40%
North West | 632 | 836 | 1 468 | 57% | 76% | 71% | 71%
Northern Cape | 150 | 405 | 555 | 73% | 94% | 88% | 86%
Western Cape | 343 | 1 172 | 1 515 | 77% | 94% | 86% | 78%
Total | 8 980 | 14 293 | 23 273 | 61% | 60% | 54% | 53%

## Slide 67: PROGRAMME 3 …
Continuing Professional Teacher Development (CPTD)
The Annual Report on the Grade R practitioners with above level 6 is completed.
Key observations are the difference in payments by provinces for the same qualifications. The verification of qualifications are costly and some provinces did not have a budget for it. This led to the appointment of practitioners with fraudulent qualifications.
Professional Learning Communities (PLC) refresher was done with six (6) provinces with a specific focus on real examples based on training programs per province as submitted to Teacher Development Curriculum Management (TDCM).
The Course on English Language Teacher (COELT) course was completed by 93 Subject Advisers and was rolled out to all provinces.
Educator Performance Management and Development and Whole School Evaluation
Annual monitoring status reports were prepared on IQMS and Education Management System.
Principals were trained on the Quality Management System (QMS) by their respective Provincial Training Teams (PTTs) in GP, LP, NW and WC.
Virtual monitoring of the School Self-Evaluation (SSE) and School Improvement Planning (SIP) was undertaken in KZN (12 schools) and LP (6 schools). Monitoring reports provided as feedback to the respective PEDs.

## Slide 68: PROGRAMME 3 …
Teacher Development Implementation (TDI)
The DBE in collaboration with the NECT and Zenex Foundation, completed a General Education and Training (GET) Subject Advisor profiling study, focusing on Mathematics and English.
Trained 459 FET Accounting teachers and 402 Economics teachers from identified districts in all provinces using the MS Teams platform. A competent team of subject coordinators conducted the training.
Conducted orientation for Coding and Robotics to 205 National Training Team (NTT) members from all provinces, on a five-day programme. Training was conducted on the Moodle platform
Received Teacher Development reports from nine (9) PEDs.
Curriculum Research
Six (6) Provincial Teacher Development Institutes (PTDIs) and 31 District Teacher Development Centres (DTDCs) monitored and nine (9) PED narrative quarterly reports received.

## Slide 69: PROGRAMME 3
Initial Teacher Education
13,085 Funza Lushaka bursaries were awarded for initial teacher education by 31 March 2021.
Education Management and Governance Development
1 000 survey tools were captured and 95.9% of the schools met the minimum criteria in terms of effectiveness; and
1 000 survey tools were captured and 100% of the schools were found to have produced the minimum set of management documents at a required standard.

## Slide 70: PROGRAMME 4: PLANNING, INFORMATION AND ASSESSMENT
The purpose of Programme 4 is to promote quality and effective service delivery in the basic education system through planning, implementation and assessment.

## Slide 71: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
4.1.1 Number of new schools built and completed through Accelerated Schools Infrastructure Delivery Initiative (ASIDI) | Annually | 24 | 32 | +8 | COVID-19 proved to have had a positive impact on the ASIDI programme. After the closure of construction sites for the hard lockdown, contractors came back and put additional resources to catch up on the construction progress so that they can make up for the lost revenue. The introduction of MS Teams also introduced a platform where frequent meetings were organised. The Director-General instituted weekly meetings with the Heads of Implementing Agents so as to track on progress of projects under construction. For the last quarter of the financial year, the DBE Infrastructure Unit increased their site monitoring visits of projects under construction and this put pressure on the contractors and the implementing agents to finalise their construction. The 5 Built Environment Experts appointed in the DBE Infrastructure Unit in 2019 also proved to be a valuable factor in the over-achievement of the APP target. | Not applicable
 | Q4 | 24 | Q1: 2 Q2: 6 Q3: 10 Q4: 14 Total: 32 | Annual target | Not applicable | Not applicable

## Slide 72: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
4.1.2 Number of schools provided with sanitation facilities through ASIDI | Annually | 600 | 298 | -302 | The national lockdown due to COVID-19 prohibited any construction work. Poor management of contractors by the Implementing Agents resulted in low output. Inadequate monitoring at all levels failed to identify blockages and delays. | All sanitation projects have been allocated to Implementing Agents Increased focus on Alternative Building Technology to speed up delivery Simplified designs and specifications Limited the number of schools allocated per Contractor Intensified the monitoring of Implementing Agent performance on all levels: Weekly visits to construction sites by the Programme Support Unit Regular visits to construction sites by the DG Weekly meetings with operational staff of Implementing Agents Weekly meetings with Executive Management of Implementing Agents Weekly progress reporting to the Office of the Minister
 | Q4 | 600 | Q1: 4 Q2: 19 Q3: 97 Q4: 143 Total: 263 | Annual target | *The deviation and corrective action is summarised under the actual annual target and output summary for the indicator | *The deviation and corrective action is summarised under the actual annual target and output summary for the indicator

## Slide 73: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output* | Deviation | Reason for deviation | Comment/ Corrective Action
4.1.3 Number of schools provided with water facilities through ASIDI | Annually | 100 | 101 | +1 | The deviation of 1 (one) is due to pressure exerted on the IA’s to ensure that the targets are achieved and they complete as many of the projects as possible. | Not applicable
 | Q4 | 100 | Q1: 3 Q2: 15 Q3: 11 Q4: 71 Total: 100 | Annual target | *The deviation and corrective action is summarised under the actual annual target and output summary for the indicator | *The deviation and corrective action is summarised under the actual annual target and output summary for the indicator
4.1.4 Number of schools served with emergency water supply | Annually | 3000 | 3 216 | +216 | The deviation of 216 (3216 – 3000) is due to the additional need that was posed by provinces to Rand Water as a result of Covid-19 requirements. | Not applicable
 | Q4 | 3000 | Schools were served with emergency water supply in the first quarter | Annual target | Not applicable | Not applicable

## Slide 74: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output* | Deviation | Reason for deviation | Comment/ Corrective Action
4.1.5 Number of schools served with emergency sanitation | Annually | 1300 | 1303 | +3 | The deviation of 3 is due to the additional need that was posed by provinces as a result of Covid-19 requirements during the implementation of the programme. | Not applicable
 | Q4 | 1300 | Schools were served with emergency sanitation supply in the first quarter | Annual target | Not applicable | Not applicable

## Slide 75: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
4.2.1 Number of General Education and Training (GET) test items developed in Language and Mathematics for Grades 3, 6 and 9 | Annually | 500 | 500 | No deviation | Not applicable | Not applicable
 | Q4 | 500 | Grades 3, 6 and 9 Language and Mathematics items were quality assured and finalised | Annual target | Not applicable | Not applicable
4.2.2 Number of NSC reports produced | Annually | 4 | 4 | No deviation | Not applicable | Not applicable
 | Q4 | 4 | NSC Examination 2020: Examination Report School Performance Report School Subject Report Diagnostic Report Part 1, 2 and 3 were produced. | Annual target | Not applicable | Not applicable

## Slide 76: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
4.2.3 Number of question papers set for June and November examinations | Annually | 292 | 145 | -147 | The June 2020 SC/NSC examination was merged with the November 2020 NSC examinations and the 145 question papers for the June 2020 examination were used for the merge examination in November 2020. Given the merged, the targeted 147 question papers for November 2020 were not set. | Not applicable
 | Q4 | 292 | 144 of the 145 question papers for SC/NSC June 2021 approved by Umalusi. The remaining IT P1 back-up question paper is in final stages of moderation and proofreading. 127 of the 162 NSC November 2021 question papers are in various stages of setting. | Annual target | Not applicable | Not applicable

## Slide 77: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
4.2.4 Percentage of public schools using the standardised school administration system (SA-SAMS) for reporting | Annually | 98% | 98.6% 21480/21795 | +0.6% | Advocacy and Provincial circulars supporting collection of data via SA-SAMS | Not applicable
 | Q4 | 98% | 98.6% (21,152 Ordinary + 340 SNE) 21,492 Total (Numerator) / 21,796 (Denominator) | Annual target | Not applicable | Not applicable

## Slide 78: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
4.2.5 A National Report is produced on the number of provinces monitored for implementation of Learner Unit Record Information Tracking System (LURITS) | Annually | Approved National Report on the number of provinces monitored for implementation of LURITS | Approved National Report on the number of provinces monitored for implementation of LURITS | No deviation | Not applicable | Not applicable
 | Q4 | Approved National Report on the number of provinces monitored for implementation of LURITS | Preliminary results and report prepared and presented to the 3 PED HODs. 9 provincial reports finalised. One annual monitoring report covering nine (9) PEDs that were monitored, was consulted with PEDs and finalised. Monitoring results presented to HEDCOM Sub Committee of e-Education (ICTS) | Annual target | Not applicable | Not applicable
4.2.6 A National Report is produced on learning outcomes linked to the National Assessment Framework | Annually | Approved National Report on learning outcomes linked to the National Assessment Framework | Approved National Report on learning outcomes linked to the National Assessment Framework | No deviation | Not applicable | Not applicable
 | Q4 | Approved National Report on learning outcomes linked to the National Assessment Framework | The TALIS Volume 2 country note was released in October 2020 and the TIMSS 2019 Highlights Report was released in December 2020. | Annual target | Not applicable | Not applicable

## Slide 79: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
4.2.7 A National Report is produced on developing and operationalising a school readiness assessment system | Annually | Approved National Report on developing and operationalising a school readiness assessment system | Approved National Report on developing and operationalising a school readiness assessment system | No deviation | Not applicable | Not applicable
 | Q4 | A National Report is produced on developing and operationalising a school readiness assessment system | The preparations for the Early Learning National Assessment (ELNA) administration in sampled schools were finalised in March 2021 | Annual target | Not applicable | Not applicable

## Slide 80: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
4.3.1 Number of officials from districts that achieved below the national benchmark in the NSC participating in a mentoring programme | Annually | 33 | 33 | No deviation | Not applicable | Not applicable
 | Q4 | 33 | Due to the COVID-19 Alert Level 3 restrictions only a couple of virtual sessions were held with mentees in this quarter. A cumulative number of 33 targeted district officials (district directors and circuit managers) were mentored in the 2020/21 financial year. | Annual target | Not applicable | Not applicable

## Slide 81: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
4.3.1 Number of officials from districts that achieved below the national benchmark in the NSC participating in a mentoring programme | Annually | 33 | 33 | No deviation | Not applicable | Not applicable
 | Q4 | 33 | Due to the COVID-19 Alert Level 3 restrictions only a couple of virtual sessions were held with mentees in this quarter. A cumulative number of 33 targeted district officials (district directors and circuit managers) were mentored in the 2020/21 financial year. | Annual target | Not applicable | Not applicable

## Slide 82: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
4.3.2 Percentage of school principals rating the support services of districts as being satisfactory | Biennially | 75% | 57.2% 618/1080 | -17.8% | Duplication of survey instrument; All survey questions not completed; Data collected with 3 different google links, electronic survey instruments and hard copy survey instruments | Not all principals were familiar with completing google forms, forms were not saved properly or certain pages were missing. Google forms were sent numerous times to address the low response rate To address this challenge, SISCOs and officials completed forms during the School Readiness visits February 2021. Not all schools were in the same geographical area as the identified school readiness schools. To further address the low response rate, the google form, link and sample were sent to Circuit Managers. Circuit Managers did not send the link to the sample schools only, but to all their schools which led to a response rate of 2848 of which the majority of schools were not part of the sample. The extension of the submission date had a very negative impact on the completion of the final report.
 | Q4 | 75% | 502 (47%) responses received to date. Data capturing and analysis is currently underway. | Annual target | Not applicable | Not applicable

## Slide 83: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output* | Deviation | Reason for deviation | Comment/ Corrective Action
4.3.3 Percentage of District Directors that have undergone competency assessment prior to their appointment | Annually | 95% | 100% 2/2 | +5% | Administration of competency assessment for District Directors (SMS members) is now mandatory. | Not applicable
 | Q4 | 95% | Conducted analysis of PED responses | Annual target | Not applicable | Not applicable

## Slide 84: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output * | Deviation | Reason for deviation | Comment/ Corrective Action
4.3.4 Percentage of underperforming schools visited at least twice a year by district officials for monitoring and support purposes. | Annually | 75% | 13.8% 371/2325 | -61.2% | Schools were visited, however some were visited during the first term of 2020 which falls outside the 2020/21 Financial Year. Due to school closure as a result of COVID-19, Primary schools were not visited. Provinces that were hit hard by the pandemic, e.g. EC, issued Instruction Notes that prohibited visits to schools so as to contain the virus. | The TID to be revised to specify that visits will be done as per Academic year and not Financial Year. Monitoring Plans will be discussed with district officials
 | Q4 | 75% | The Department received Monitoring tools for schools that were visited from only four provinces. GP: 12 out of 15 schools (80%) MP: 58 of the 294 schools (19.22%) FS: 6 out of 6 schools (100%) KZN: 117 out of 450 (26%) | Annual target | Not applicable | Not applicable
4.3.5 Number of District Director forums held | Annually | 3 | Q1: 1 Q2: 2 Q3: 0 Q4: 0 Total: 3 | No deviation | Not applicable | Not applicable
 | Q4 | 3 | A full complement of targeted number of meetings held. | Annual target | Not applicable | Not applicable

## Slide 85: PROGRAMME 4 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output* | Deviation | Reason for deviation | Comment/ Corrective Action
4.3.6 Number of districts in which teacher development has been conducted as per district improvement plan | Annually | 55 | 61 | +6 | District Improvement plans were not signed by the District Directors and 14 did not indicate teacher development. | Most districts value teacher development support
 | Q4 | 55 | 75 districts had submitted to DBE District Improvement Plans (DIPs), District Development Plans (DDPs), or Academic Improvement Plans (AIPs). Analysis of all the plans received show that there are 61 DIPs where teacher development took place | Annual target | Not applicable | Not applicable

## Slide 86: PROGRAMME 4 ...
Examination and Assessment Systems Administration (SA-SAMS)
Maintenance: SA-SAMS version 21.0.0 was released on 3 February 2021 relaxing validation rules for Curriculum 2021 to allow schools to continue with their administration in order to report for 10-day SNAP survey, Annual School Survey and Grade 12 NSC registration. Test version for 21.1.0 was released on 26 March 2021 for PED User Acceptance Testing, containing Curriculum and Assessment updates.
SA-SAMS Modernisation: The agreement between UNESCO and the National Education Collaboration Trust (NECT) has been approved for professional and advisory services, training and support for the development and implementation of the OpenEMIS solution.
LURITS Data uploads: Term 4 LURITS uploads for the academic year were closed on 18 March 2021 and data was uploaded for 25,223 schools to LURITS, with 13,307,479 learners and 435,797 educators.
Masterlist of Schools: The Quarter 4 Masterlist is approved for publishing on the DBE website.

## Slide 87: PROGRAMME 4 …
District Level Planning and Implementation Support
School Principals’ Satisfaction Survey: A total number of 502 (47%) completed survey forms from the sampled schools were received on 28 February 2021.
National Education Excellence Awards: The remaining four (4) Team building sessions for schools that got position one (1) in the 2020 National Education Excellence Awards categories were conducted from 04 February to 18 March 2021.
Support for underperforming districts: Due to the COVID-19 Alert Level 3 restrictions only a few of virtual sessions were held with mentees. A cumulative number of 33 targeted District Directors and Circuit Managers were mentored in the 2020/21 financial year.
Developed a database of Data Driven District (DDM) coordinators for the basic education sector. A virtual session was convened by the Department of Cooperative Governance and Traditional Affairs (COGTA) with national sector departments on 25 March 2021 to strengthen the DDM plans and implementation in the Free State.

## Slide 88: PROGRAMME 4 …
Provincial and District Planning and Implementation Support
Publication of Amended 2021 School Calendar: The Latest Amended 2021 School Calendar was published on 16 February 2021 on Government Gazette 44162.
Proposed Draft 2022 and 2023 School Calendar has been submitted to HEDCOM for approval and recommendation to Council of Education Ministers (CEM) for public comment.
The DBE coordinated the School Readiness Monitoring with the PEDs officials.
  A total number of 653 schools in 24 Districts were monitored in all provinces between 15-26 February 2021.
  Schools were generally found to be ready for the 2021 academic year.

## Slide 89: PROGRAMME 4…
School level Planning and Implementation Support
A total number of 1 363 underperforming secondary schools were visited at least twice in 2020 for purposes of support.
Strengthening the utilisation of performance data for improved performance: Limpopo and Northern Cape Teams were augmented to strengthen support of circuits that are struggling with respect to learner performance.
A total number of 458 schools in 18 districts were visited to assess school readiness.
Chart: 
| Eastern Cape | Free State | Gauteng | Kwa-Zulu Natal | Mpumalanga | Limpopo | Northern Cape | North West
Number of Schools Monitored | 56 | 48 | 50 | 89 | 61 | 90 | 22 | 42

## Slide 90: PROGRAMME 4 …
  National Education Evaluation and Development Unit (NEEDU)
  DBE COVID-19 Provincial oversight reports : NEEDU prepared two (2) reports on measures that schools were taking to mitigate and contain the spread of COVID-19 while providing basic education in Grades R to 12 amidst the COVID-19 pandemic.
  A report based on the survey about the effect of COVID-19 on the functionality of schooling amidst the COVID-19 pandemic
  Qualitative and quantitative data was analysed to prepare the report; and
  The analysis of data culminated into a report Evaluation of the functionality of schooling in the COVID-19 Environment.
  Improvement of the quality of the DBE home language workbooks with a view to improving literacy skills in the Foundation Phase
  An in-depth analysis of activities in the DBE workbooks included the analysis of errors in four (4) home language DBE workbooks: Sepedi, isiZulu, isiXhosa and English.

## Slide 91: PROGRAMME 4 …
Donor Grant Management
Conditional Grants quarterly reports were approved and submitted to National Treasury:
  Education Infrastructure Grant (EIG);
  Human Immunodeficiency Virus (HIV) and Acquired Immune Deficiency Syndrome (AIDS);
  Learners with Severe to Profound Intellectual Disability (LSPID);
  Mathematics, Science and Technology (MST);
  National Schools Nutrition Programme (NSNP); and
  School Infrastructure Backlogs Grant (SIBG).
Project Management
Conducted telephonic survey to determine if schools have paid stipends of young people employed and how many School Governing Body (SGB) funded posts and posts at government subsidised independent schools were saved from presidential relief fund, 60 schools in Gauteng and 30 schools in Limpopo were contacted for survey.

## Slide 92: PROGRAMME 4 …
Financial Planning and Provincial Budget Monitoring
PEDs were provided with the National Norms and Standards for School Funding (NNSSF) implementation plan.
Published amendments to the NNSSF: National table of targets for the school allocation (2021-2023) and the updated national poverty distribution table.
Terms of reference (ToRs) were compiled in preparation for the Budget Standard Exercise (BSE) meetings.
The analysis of the draft 2021/22 Annual Performance Plan was compiled and sent to PEDs so that they could improve their final APPs.

## Slide 93: PROGRAMME 4 …
Public Examinations
Setting and moderation of June and November 2021 question papers
Umalusi approved a total number of 144 of the 145 question papers for SC/NSC June 2021 examination.
One (1) remaining question paper, Information Technology Paper 1 backup paper is undergoing the final stages of moderation and proofreading.
A total number of 162 question papers required for the NSC November 2021 examinations, 127 have been set and 107 internally moderated, 47 approved by Umalusi. 35 outstanding question papers are in various stages of setting.
17 Practical Assessment Tasks (PATs) for 2021 have been developed and external moderation by Umalusi were released to PEDs on 1 March 2021.
Examination Guidelines have been developed in all subjects and sent to the external moderation Umalusi and was released to PEDs on April 2021.

## Slide 94: PROGRAMME 4 …
Public Examinations
The Marking commenced on 3 January 2021 and ended on 22 January 2021 in 190 marking centres across all PEDs.
All marking centres implemented the Protocol on Marking procedure according to the COVID-19 requirements to ensure marker wellness and safety throughout the sessions.
The centralised marking of small enrolment subjects namely; Agricultural Technology (AT), Dance Studies and Music, Second Additional Languages (SALs) and South African Sign Language Home Language (SASL HL) was successfully administered on 3 - 22 January 2021 in Waterkloof High School.
The marking of scripts for blind and deaf candidates was centralised in GP and the WC.

## Slide 95: PROGRAMME 4 …
Public Examinations
Quality Assurance of Marking: On 6 to 20 January 2021, onsite moderators were deployed to marking centres across all nine (9) provinces to ensure quality of marking via onsite moderation.
Due to the COVID-19 pandemic, after Alert level 3 was announced, onsite moderation team was reduced and this resulted in none of the History moderators being deployed.
Irregularities: The National Examination Irregularities Committee (NEIC) virtual meeting was held on 30 January 2021.
NEIC was encouraged by the reduction in administrative errors, technical omissions, behavioral offences and acts of dishonesty in the NSC examinations.
The leakage of the Mathematics Paper 2 and Physical Sciences Paper 2 of the 2020 November examinations posed a threat to the credibility of the examinations.
However, the swift action of the DBE to deal with these irregularities ensured that the credibility of the examinations in these subjects and in the examinations as a whole was maintained.

## Slide 96: PROGRAMME 4 …
Public Examinations
The establishment of the National Investigation Task Team (NITT) was tasked to fully investigate the source and the extent of the leak, whether the examination in these papers were compromised and to make recommendations on how the examination system can be improved to avoid such leakages.
The recommendations by NITT were accepted by Umalusi and the investigations and hearings are continuing to ensure that the learners implicated are penalised appropriately.
Despite the identified isolated irregularities, including the group copying and the unprecedented leakages of the Mathematics Paper 2 and Physical Sciences Paper 2 question papers, the DBE was able to manage the conduct and administration of the November 2020 NSC examinations without any systemic irregularities that may have compromised the integrity and the credibility of the examination.
Umalusi approved the results of the 2020 NSC examinations as credible on Friday, 12 February 2021.

## Slide 97: PROGRAMME 4 …
Public Examinations
On 1 to 2 January 2021, a two-day pre-standardisation virtual meeting was hosted by the DBE involving provincial examination managers to prepare standardisation proposals that were presented to Umalusi on 3 January 2021.
Umalusi hosted the standardisation of the combined 2020 November results on 3 January 2021.
The Combined 2020 November Examination Results and Feedback: Despite the challenges posed by the COVID-19 pandemic and against all odds, the Class of 2020 persevered and ensured that more than 75% of candidates attained the NSC.
The combined 2020 November results were released to candidates on 22 February 2021.
In order to adequately consolidate all the data was presented to the PEDs, the stakeholders in education and the media, four (4) NSC reports and a pamphlet/booklet were produced and released during the release of results on 22 February 2021.
All four (4) NSC reports for the November 2020 examinations were uploaded on the DBE website.

## Slide 98: PROGRAMME 4 …
Systems Administration
Registration for the June 2021 Examination: The registration of the candidates is completed.
The online and manual registration of the June 2020 SC candidates has been completed.
Registration for the November 2021 Examination: The registration of the candidates is completed.
Data provisioning: All requests for data have been attended. System development and Enhancements: Development and enhancements is an ongoing process for all the different examination systems.
New Systems: Business Intelligence is integrated into the Examination system. The online Re-issue of Certificates is well in process at DBE and candidates are applying online.

## Slide 99: PROGRAMME 4 …
National Assessment
The development of test items for diagnostic testlets and manuals were completed.
The Trends in International Mathematics and Science Study (TIMSS) 2019 highlights report on Grades 9 and 5 Mathematics and Science was finalised and uploaded onto the DBE website.
Further dissemination of results to district officials and school principals was achieved through the Director-General roadshows.
Preparations for the 2021 Early Learning National Assessment (ELNA) was finalised for administration in May 2021.
Preparations for the administration of Progress in international Reading Literacy Study (PIRLS) 2021 study was finalised with the appointed service provider for administration in August 2021.
Systemic evaluation tools were externally audited. A conceptual framework and a technical standards document was finalised.

## Slide 100: PROGRAMME 5: EDUCATIONAL ENRICHMENT SERVICES
The purpose of Programme 5 is to develop policies and programmes to improve the quality of learning in schools.

## Slide 101: PROGRAMME 5 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
5.1.1 Number of schools monitored for the provision of nutritious meals | Quarterly | 115 | Q1: 26 Q2: 36 Q3: 18 Q4: 37 Total: 117 | +2 | The target has been exceeded by +2, because monitoring was intensified in 2020 following the Gauteng North High Court judgement against the Minister and eight MECs "to feed qualifying learners whether attending school or not" during the COVID-19 lockdown. | Not applicable
 | Q4 | 30 | Q1: 26 Q2: 36 Q3: 18 Q4: 37 Total: 117 | +7 | More schools were monitored to cover for the Q3 shortfall | Not applicable

## Slide 102: PROGRAMME 5 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
5.1.2 Number of PEDs with approved annual business plans for the HIV/AIDS Life Skills Education Programme | Annually | 9 | 9 | No deviation | Not applicable | Not applicable
 | Q4 | 9 | The HIV AIDS Life Skill provincial business plans (2021-2022) were submitted to Grants Management Directorate to route for approved by the DG. | Annual target | Not applicable | Not applicable
5.1.3 Number of districts monitored and supported in the implementation of National School Safety Framework (NSSF), social cohesion, sport and enrichment programmes per year | Quarterly | 43 | Q1: 0 Q2: 11 Q3: 16 Q4: 16 Total: 43 | No deviation | Not applicable | Not applicable
 | Q4 | 10 | Q1: 0 Q2: 11 Q3: 16 Q4: 16 Total: 43 | +6 | Six (6) more Districts were monitored to cover Q1 | Not applicable

## Slide 103: PROGRAMME 5 INDICATORS
Performance Indicator | Frequency | Target for 2020/21 | Output | Deviation | Reason for deviation | Comment/ Corrective Action
5.1.4 Number of learners, educators, parents, SGBs and other educations stakeholders reached through social cohesion programmes | Quarterly | 7 500 | Q1: 307 Q2: 693 Q3: 1 479 Q4: 1 266 Total: 3 745 | -3 755 | The matter of the deviation was as a result of TIDs not meeting the audit standards, which meant that the DBE discards some of the data. | The DBE has now strengthened the TIDs for 2021/22 in anticipation of this.
 | Q4 | 2 500 | Q1: 307 Q2: 693 Q3: 1 479 Q4: 1 266 Total: 3 023 | -1 235 | The DBE did not host the planned Jamboree for future choices due to lockdown restrictions. | The matter of the deviation was as a result of means of verification not meeting the audit standards, which meant that the DBE had to discard some of the data. The DBE has now strengthened the Technical Indicator Descriptor (TID) for 2021/22 in anticipation of this.

## Slide 104: PROGRAMME 5…
Sport and Enrichment in Education
Four (4) provinces were monitored on the implementation of Social Cohesion, School Safety and Sport and Enrichment programmes, including Northern Cape, Limpopo and Gauteng and North West.
Draft regulations for the return to play of school sport: Inputs were made on the draft regulations for the return of play for school sport in accordance with adjusted Alert Level 1.
Reading club’s competition (RCC): The draft document was approved by the Legal and Legislative directorate in the DBE for compliance with the legislation. The guidelines will be finalised once the Western Cape, KwaZulu-Natal and Mpumalanga provinces have commented.

## Slide 105: PROGRAMME 5…
Social Cohesion and Equity in Education
The COVID-19 pandemic forced the DBE to migrate all social cohesion programmes to online, virtual and digital platforms:
  District advocacy and awareness raising on the NSSF and Protocol on Reporting Management of Sexual Abuse in Schools was held on 3,4 and 10 March 2021 in Gauteng.
  Girl Boy Equity Movement (GBEM) online dialogues held in partnership with United Nations International Children Funds (UNICEF) on 02-04 March 2021 in Gauteng, 23-25 February 2021 in KwaZulu-Natal and 9-11 February 2021 in Mpumalanga.
Safety in Education
National School Safety Framework (NSSF): Monitored 16 districts across four (4) provinces Gauteng, Northern Cape, North West and Limpopo.

## Slide 106: PROGRAMME 5 …
Health Promotion
A total number of 12 school monitoring visits were conducted in the Eastern Cape and Gauteng.
The Government to Government (G2G) successfully completed the recruitment process of all staff members.
A total number of 17 819 girl learners were reached through the Adolescent Girls and Young Women (AGYW) programme, a 76% achievement against a target of 23 552.
On 03 March 2021, the Cluster approved for the draft DBE Learner Pregnancy Policy to be presented at Cabinet. The draft policy was presented on 13 April 2021.
A total number of 268 077 learners (233 525 learners screened and 34 552 learners immunised) were reached through health screening and immunisation programmes.
A total number of 80 368 learners were reached through the school deworming programme.

## Slide 107: PROGRAMME 5 …
Psycho-Social Support (PSS)
Interviews were conducted for the Common Elements Treatment Approach (CETA) programme, to appoint the Master Training Team which will receive the CETA training and then proceed to train the Learner Support Agents (LSAs) in schools.
School Nutrition
37 schools against the target of 30 schools were monitored.

## Slide 108: VOTE 16: BASIC EDUCATION
FINANCIAL EXPENDITURE

## Slide 109: QUARTER 4 PRESENTATION TO STANDING COMMITTEE ON APPROPARIATION FOR 2020/21 FINANCIAL YEAR

## Slide 110: EXPENDITURE PER PROGRAMMES FOR 2020/21
PROGRAMME | Budget R’000 | Expenditure R’000 | Variances R’000 | % Spent
Administration | 504 063 | 486 124 | 17 939 | 96.4%
Curriculum Policy, Support and Monitoring | 1 844 561 | 1 741 903 | 102 658 | 94.4%
Teachers, Education Human Resources and Institutional Development | 1 415 343 | 1 395 396 | 19 947 | 98.6%
Planning ,Information and Assessment | 11 708 938 | 11 375 084 | 333 854 | 97.1%
Educational Enrichment Services | 7 922 067 | 7 902 118 | 19 949 | 99.7%
Total | 23 394 972 | 22 900 625 | 494 347 | 97.9%

## Slide 111: REASONS FOR VARIANCES
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Administration: The reasons for underspending is due to unfilled vacant positions as well as payments for Auditors, Audit fees for preliminary audits were less as the number of auditors were reduced due to COVID 19. | Administration: The Department will ensure that the filling of posts is adhered to, by ensuring that vacant posts in this programme are filled even though not all posts will be filled due to budget cuts implemented within the government departments to reduce compensation budget. The posts will be filled based on priorities to ensure the recurring costs of filled posts will not have negative impact on the Department spending.

## Slide 112: REASONS FOR VARIANCES
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Curriculum Policy, Support and Monitoring: The underspending is due to the last transfer payment for Learners with Profound Disability Grant to KZN & WC not being made due to non-compliance on reporting. | The Department has requested a roll-over for Learners with Profound Disability grant from National Treasury for the under-transferred funds to KZN. The Province (KZN) has also been informed to tighten their reporting processes.
Teachers, Education Human Resources and Institutional Development: underspending results from UNESCO foreign transfer due to favourable exchange rate on the date of transaction as well as vacant positions. | The agreement is USD based and the final expenditure is governed by the Rand/Dollar exchange on the day of payment. Not much can be done as mitigation

## Slide 113: REASONS FOR VARIANCES
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Planning, Information and Assessment: Underspending is due to Schools Infrastructure Backlogs Grant as most construction sites started operational at level 2 of the covid19. COVID-19 hard lockdown stopped all construction projects. About 30% of the year was lost in terms of construction. After the hard lockdown, several contractors were in financial trouble as they could not pay sub-contractors during the lockdown. As factories were also closed, the industry experienced a shortage of roof sheeting and cement. | The DBE is now meeting weekly with Implementing Agents to track progress and to facilitate special measures to accelerate delivery on SAFE & ASIDI. Current projections are that the Schools Infrastructure Backlogs Grant allocation of R2.383 billion will be fully spent in 2021/22.

## Slide 114: REASONS FOR VARIANCES
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Educational Enrichment Services: Under expenditure is due to outside activities being scaled down to Virtual due to COVID | The Department is reviewing spending needs to shift funding to ICT as working Virtually has highlighted this need

## Slide 115: REASONS FOR VARIANCES
ECONOMIC CLASSIFICATION | BUDGET R’000 | EXPENDITURE R’000 | VARIANCES R’000 | % SPENT
COMPENSATION OF EMPLOYEES | 547 905 | 497 659 | 50 246 | 90.8%
GOODS AND SERVICES | 1 728 207 | 1 825 402 | (97 195) | 105.6%
INTEREST ON RENT AND LAND | 42 663 | 42 661 | 2 | 100.0%
TRANSFERS AND SUBSIDIES | 19 441 623 | 19 417 579 | 24 044 | 99.9%
PAYMENTS OF CAPITAL ASSETS | 1 633 499 | 1 116 500 | 516 999 | 68.4%
PAYMENTS OF FINANCIAL ASSETS | 1 075 | 824 | 251 | 76.7%
TOTAL | 23 394 972 | 22 900 625 | 494 347 | 97.9%

## Slide 116: REASONS FOR VARIANCES
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Compensation of Employees: the underspending is due non filling of posts due to hard COVID 19 lockdown. Goods and Services: The overspending is on School Infrastructure on operational budget due to rental and hiring of mobile toilets for schools as a result of COVID19. Transfers and Subsidies: The underspending was due to withheld transfer payments for Learners with Profound Disability Grant for KZN and WC due to non compliance on reporting. | Compensation of employees: The Department is gradually filling posts that couldn’t be filled due to the COVID lockdown Goods and Services: The overspending will not recur as arrangements will be made timeously for funds to be transferred from the capital to operational budget within the Grant. Transfers and Subsidies: The Department has requested for a roll-over of funds for Learners with Profound Disability Grant at National Treasury for KZN PED. The KZN Province has also been told to tighten their reporting processes.

## Slide 117: REASONS FOR VARIANCES
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Payments for Capital Assets: Underspending is due to Schools Infrastructure Backlogs Grant as most construction sites started operating at Lockdown Level 2 of Covid19. COVID-19 hard lockdown stopped all construction projects. About 30% of the year was lost in terms of construction. After the hard lockdown, several contractors were in financial trouble as they could not pay sub-contractors during the lockdown. As factories were also closed, the industry experienced a shortage of roof sheeting and cement. | The DBE is now meeting weekly with Implementing Agents to track progress and to facilitate special measures to accelerate delivery on SAFE & ASIDI. Current projections are that the Schools Infrastructure Backlogs Grant allocation of R2.383 billion will be fully spent in 2021/22.

## Slide 118: REASONS FOR VARIANCES
Economic Classification | Budget R’000 | Expenditure R’000 | Variances R’000 | % Spent
Learners with Profound Disability: Earmarked | 3 165 | 3 171 | (6) | 100.2%
Matric Second Chance | 34 175 | 34 708 | (533) | 101.6%
Workbooks | 1 109 945 | 1 046 056 | 63 889 | 94.2%
Oversight of MST | 6 538 | 3 721 | 2 817 | 56.9%
NSNP: Earmarked | 20 235 | 16 667 | 3 568 | 82.4%
Total | 1 174 058 | 1 104 323 | 69 735 | 94.1%

## Slide 119: REASONS FOR VARIANCES
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Workbooks: Underspending is due to non filling of posts due to the COVID 19 pandemic Other Earmarked: underspending due to reduction in physical monitoring of provinces for PED’s as well as providing support which was restricted by COVID19 lockdown implemented. | The Department is gradually filling posts that couldn’t be filled due to the COVID lockdown Other Earmarked: Monitoring of Provinces is done more and more virtually. Some of the funds will be diverted to ICT procurement in order to boost virtual processes

## Slide 120: DETAILS OF TRANSFERS AGAINST ACTUAL EXPENDITURE FOR THE 2020/21 FINANCIAL YEAR
SERVICE |  |  |  | Expenditure as % of Appropriation
 | APPROPRIATION | ACTUAL EXPENDITURE | VARIANCE | 
 | R’000 | R’000 | R’000 | 
Transfers to Public Entities | 149 735 | 149 735 | 0 | 100.0%
UMALUSI | 136 404 | 136 404 | 0 | 100.0%
ETDP SETA | 453 | 453 | 0 | 100.0%
SACE | 12 878 | 12 878 | 0 | 100.0%
Other Transfers | 1 448 213 | 1 441 272 | 6 941 | 99.5%
NSFAS: Fundza Lushaka Bursaries | 1 291 606 | 1 291 606 | 0 | 100.0%
UNESCO Membership Fees | 17 091 | 13 829 | 3 262 | 80.9%
ADEA | 155 | 151 | 4 | 97.4%
Household | 2 071 | 2 050 | 21 | 99.0%
Childline South Africa | 73 | 73 | 0 | 100.0%
Guidance Counseling & Youth Development Centre: Malawi | 193 | 0 | 193 | 0.0%
SACMEQ | 3 461 | 0 | 3 461 | 0.0%
NECT | 133 563 | 133 563 | 0 | 100.0%

## Slide 121: EXPENDITURE ON ASIDI MARCH 2021
Economic Classification | Budget R’000 | Expenditure R’000 | Variances R’000 | % Spent
Compensation of Employees | 6 730 | 8 242 | (1 512) | 122.5%
Goods and Services | 178 037 | 377 124 | (199 087) | 211.8%
Interest on Rent and Land | 245 | 244 | 1 | 99.6%
Building and Other Fixed Structures | 1 598 949 | 1 074 909 | 524 040 | 67.2%
Software and Intangible Assets | 2 994 | 2 994 | 0 | 100.0%
Total | 1 786 955 | 1 463 513 | 323 442 | 81.9%

## Slide 122: REASONS FOR VARIANCES
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Underspending on the ASIDI allocation Underspending is due to Schools Infrastructure Backlogs Grant as most construction sites started operating at Lockdown Level 2 of Covid19. COVID-19 hard lockdown stopped all construction projects. About 30% of the year was lost in terms of construction. After the hard lockdown, several contractors were in financial trouble as they could not pay sub-contractors during the lockdown. As factories were also closed, the industry experienced a shortage of roof sheeting and cement. | The DBE is now meeting weekly with Implementing Agents to track progress and to facilitate special measures to accelerate delivery on SAFE & ASIDI. Current projections are that the Schools Infrastructure Backlogs Grant allocation of R2.383 billion will be fully spent in 2021/22.

## Slide 123: EXPENDITURE ON CONDITIONAL GRANTS FOR MARCH 2021
Economic Classification | Budget R’000 | Expenditure R’000 | Variances R’000 | % Spent
Learners with Profound Disability Grant | 242 864 | 225 761 | 17 103 | 93.0%
Maths Science and Technology Grant | 332 862 | 332 862 | 0 | 100.0%
Education Infrastructure Grant | 9 414 967 | 9 414 967 | 0 | 100.0%
National School Nutrition Programme | 7 665 887 | 7 665 887 | 0 | 100.0%
HIV and Allocation Grants | 187 095 | 187 095 | 0 | 100.0%
Total | 17 843 675 | 17 826 572 | 17 103 | 99.9%

## Slide 124: REASONS FOR VARIANCES
CHALLENGES/DEVIATION | MITIGATORY MEASURES/PROGRESS
Learners With Profound Disability Grant: Underspending is due to withheld funds for KZN and WC PED due to non compliance on reporting. | Roll-over request was submitted to National Treasury for this Grant. The KZN Province has been told to tighten their reporting processes.