## Slide 1: PROGRESS REPORT OF THE PRESIDENTIAL TASK TEAM (PTT) ON MILITARY VETERANS 01 September 2021

## Slide 2: PRESENTATION LAYOUT
Purpose
Introduction
7 Work-Streams and their Purpose
Progress made to date on issues raised on the Consensus Document
Focus on the Finalization of the Amendment of the Bill

## Slide 3: PURPOSE
To provide an update on progress made in redressing the challenges faced by military veterans

## Slide 4: INTRODUCTION
The PTT on military veterans has committed to continuous engagements with military veterans in a bid to resolve issues raised during various interactions with military veterans since November 2020.
The PTT committed to work with all spheres of governments in accelerating the much needed service delivery to military veterans.
Subsequently, the PTT has started provincial visits in fulfilling the commitments.
Since the start of the engagements with different Military Veterans Associations, the PTT employed the Technical Task Team to establish Work-streams for the implementation of the issues contained in the consensus document.
A lot of work has been done and this report entails the progress thereof.

## Slide 5: 8 WORK-STREAMS AND THEIR PURPOSE
# | WORK STREAM | PURPOSE
1 | Legislative Review | To develop implementation plans aimed at addressing the policy and legislative issues raised by the Military Veterans.
 | ii. Organization Redesign | To align the DMV structure to its legislative mandate, strategy and business processes.
 | iii. Socio Economic Support | To facilitate meaningful interaction with the social cluster and facilitate the identification of short to medium and long term programmes of government to benefit MV’s.
 | iv. Database Verification, cleansing and Enhancement | To develop a project plan for an accelerated completion of the verification process
 | v. Heritage and memorialization | To facilitate collaborative research of best practices with relevant countries around matters of heritage and memorialization of liberation veterans
 | vi. Pension and Benefits | To review and update the pension actuarial enquiry undertaken by the DMV in 2014 in order to determine the appropriate Military Veterans quantum in line with inflation.
 | vii. Communications | To ensure that communication and engagement are harnessed effectively throughout the period of the Presidential Task Team.
 | viii. Land and Agriculture | To work with the Department of Agriculture, Forestry and Fisheries and the Department of Rural Development & Land Reform for the provision of Land and Agriculture interventions to the Military Veterans

## Slide 6: PROGRESS TO DATE
PROGRESS MADE TO DATE ON ISSUES RAISED IN THE CONSENSUS DOCUMENT

## Slide 7
# | ISSUE | PROGRESS MADE
2 | Conclusion of Memorandum of Understanding between the DMV, Provincial Government and other state entities. | The efforts of institutionalizing the relationship between the DMV and the three spheres of government including state-owned entities is on-going and is led at a work-stream and sub work-stream level. To date, Memorandum of Understanding have been concluded with the Provincial Governments of Gauteng, Eastern Cape as well as a number of State Owned entities. Discussions are underway with the Provincial Governments of Limpopo and Kwa-Zulu Natal to conclude the MoU’s. Additionally Provinces such as Gauteng and the Eastern Cape have already established Military Veterans Help Desks and have adopted Programmes of Action as well as policies that seeks to prioritise service provisioning for Military Veterans.

## Slide 8
# | ISSUES | PROGRESS TO DATE
3 | Education Support | A decision was taken to uplift the moratorium on new applications for education support Letters of Commitments have been issued to approved applicants. Payments of 2021 New application and continuing beneficiaries of education support is on going as we receive invoices from institutions. The involvement and the support of the Provincial Government has been identified a critical success factor. Some provincial department have already started to assist with bulk collection of invoices of learners supported by DMV. GP has lead the way as DMV support more learner from this province.
4 | Employment Opportunities | Military Veterans have been employed to assist on Covid-19 pandemic intervention in schools in GP The model above is being proposed for implementation across all provinces for Military Veterans

## Slide 9
# | ISSUES | PROGRESS TO DATE
5 | Database | Verification of 5 419 NSF Members work Started on the 06 May 2021, 385 are deceased. The process started with 1 980 cases in Gauteng. 377 of which are not traceable; The ones invited for interview are 411. Those invited but didn’t attend 182. The successful applicants 36. Proceeding to other Provinces, additional intelligent sound and video recording system is required to enable virtual interviews. The costed plan scenarios starting with KZN, Aloe Ridge is finalized. All Provinces will get the opportunity to be verified.
6 | Means Test | The abolishment of the means test and disbursement of the benefits is linked to the process of Amending the Military Veterans Act (Act no. 18 of 2011) as well as its Regulations. An advisory note from Legal Services indicated that the means test cannot be abolished as this would result in benefits being dispensed to every military veteran. Funds allocated for improving the lives of the vulnerable and indigent military veterans will be utilized to sustain those who can maintain themselves, should the means test be abolished. All government Departments who dispense benefits utilize means test to qualify and disqualify persons.

## Slide 10
# | ISSUES | PROGRESS TO DATE
7 | Restructuring of the DMV | The Service Delivery Model was refined and presented to the DPSA together with a proposed functional structure that had already been done for a technical analysis. The DPSA has sent back the analysis to DMV to re-work the proposed functional structure and within funded posts. The finalization of the structure is dependent on the finalization of the amendment of the Act as to ensure that DMV organizational structure is aligned to mandate of the amended Act The Department is seeking technical assistance from GTAC to cost the implementation of the proposed structure that will be aligned to the amended Act.
8 | Provision of Health to the dependents of Military Veterans | The provision of Healthcare to dependents is awaiting the review of the legislation and the related funding . This implementation is linked to the amendment of the Act and Regulations. Comparative study will be done with defence for the provision of similar benefit in the defence to ensure that provision of healthcare is aligned to what DoD offers to its members

## Slide 11
# | ISSUES | PROGRESS TO DATE
9 | Presidential pardon | One of the demands from the military veterans demands in the consensus document is the consideration for Presidential pardons and expungement of criminal records of LSWVs The Department of Justice and Constitutional Development has furnished the Office of the President with files of individuals (i.e. military veterans) who have applied for Presidential pardons dating back to the era of second President of the Republic. Furthermore, the LSWV to solicit their list of individuals who are eligible for a Presidential pardon and reasons why, as well as to provide a list of individuals who should not be considered for Presidential pardon and why.

## Slide 12
# | ISSUES | PROGRESS TO DATE
10 | Housing | Delivery of MVs housing and rescue of distressed mortgages is on-going under the current legislative and regulatory provisions. To date, the Department (working with stakeholders) has delivered in excess of 1 700 houses nationally, and settled more than 200 distressed mortgage bonds. The modalities of the 80sqm was a proposal that will form part of the gazetting, although a risk has been highlighted that houses of Military Veterans should not be different from the houses being offered to ordinary citizens as evidence shows that it is one of the source of conflicts in the communities DPWI houses Government is assessing the inventory and status of the houses to confirm which houses might be available and their conditions.

## Slide 13
# | ISSUES | PROGRESS TO DATE
11 | Pension | The content of the Pension policy has been finalised by the work stream. The policy was also consulted with the Deputy Minister of Defence and Military Veterans in July 2021. Some issues are being referred to the legal services and legislative review work stream for concurrence and clarify on some of the definitions. The DMV database section has since provided the data file of the Military Veterans to GPAA to enable the determination of the number of possible Military Veterans that will benefit. High level budget implications was done based on the information received from GPAA The work stream is currently working on the finer details on the financial modelling and budget implications of the benefit. (Preliminary work will be completed in August to allow for further engagement by the principals, namely, PTT, Minister of Defence and Military Veterans and the Minister of Finance).

## Slide 14
# | ISSUES | PROGRESS TO DATE
12 | Social Relief of Distress (SRD) | Unemployment Top up for Military Veterans’ A decision was taken by Council on Defence to augment the unemployment grant of R350 (given to citizens) by R850 for Military Veterans (Total receivable by Military Veterans is R1 200). A total number of 982 MVs are in payment. To date, about R5,6 Million has been spent on top up. 527 (54%) are from Non-Statutory Forces while 455(46%) is from Statutory members. Military Veterans who do not qualify for the R350 Covid grant The PTT directed that these Military Veterans must be considered for an amount of R1 200 by the DMV within budget. Subsequently the DMV received 1 200 applications, 614 of which have been verified by the UIF, GPAA, and SASSA. SARS has been engaged to do the final confirmations before the payment can be made. There are 221 potential beneficiaries whilst waiting for SARS verification.

## Slide 15
# | ISSUES | PROGRESS TO DATE
13 | Amending the Military Veterans Act | 
14 | Heritage | On-going engagements are being held with the Departments of Arts and Culture and its agencies such as SAHRA, NHC, and Freedom Park. A draft MOU is in place and is expected to be signed off by the respective Accounting Officers as well as the attendant Implementation Agreements with the DSAC agencies.
Legislative Process | Timelines
Internal and External consultation process | Done
Draft Bill sent to DPME for signing-off of the Initial SEIAS (certificate issued) | Done
Incorporating public inputs and finalise Bill for approval | September 2021
Presentation of the draft Bill to the Executive Authority | September 2021
Bill tabled at Cluster meetings | September 2021
Approval of the Bill to be gazette for public participation. | End of October 2021
Finalise Bill and supporting documents to be submitted to Cabinet Office | December 2021

## Slide 16
# | ISSUES | PROGRESS TO DATE
15 | Capacitation of the DMV | The vacancies of Director General has been filled. All vacant posts will be filled by end of November 2021.
16 | Empowerment and skilling of Military Veterans | The model of empowerment is linked to the Government Programme of Action which is Infrastructure, Agriculture, Safety and Security, Poverty Alleviation, Business Entrepreneurship and Cooperatives Government department and provinces are beginning to report on interventions for Military Veterans. Provinces are continuously committing interventions set aside for Military Veterans and their dependents on training for sewing, training in security and protection services, training fashion design program, Artisan programs (Mechanical, Electrical etc.), Plumbing training, Welding Program and Solar Installation training. Our provincial offices continuously advise MVs on programmes that have exit strategies The provincial offices are being strengthen and 8 Administrators have been appointed to the various office in August 2021 as it is envisaged that some of the benefits such as health, housing and empowerment will be decentralized

## Slide 17: AMENDMENT OF THE BILL
FOCUS ON THE FINALISATION OF THE AMENDMENT OF THE BILL

## Slide 18
PROCESS TO BE FOLLOWED- BILL
SER No | PROCESS | PROPOSED TIMEFRAME | FOSAD ENGAGEMENT
1 | All inputs received and tabulated – shall be incorporated into the Bill | August 2021 | 
2 | Re-draft Bill and send to Chief State Law Advisor for pre-certification | Sept 2021 | 
3 | Finalise Final SEIAS assessment and send to DPME for sign-off | Sept 2021 | 
4 | Presentation to the Eecutive Authority | Sept 2021 | 
5 | Presentation to PTT | Sept 2021 | 
6 | Submit draft Bill to Cluster meetings for inputs and approval | Sept 2021/Oct 2021 | 13 Oct 2021 – SPCHD CLUSTER 21 Oct 2021 – JCPS CLUSTER
7 | Gazette for Public Participation | 90 days | End of October
8 | Prepare pack for Cabinet Office and final certification from Chief State Law Advisory |  | 
9 | Table in Parliament |  | 

## Slide 19: PROPOSED WAY FORWARD
  Engage the Executive Authority
  Gazette Draft Bill
  Engage Study group
  Submit to JCPS for discussion
  Table Draft Bill at the Cabinet Technical Committee
  Table Bill before Cabinet
  Engage the PCD&MV on the proposed Bill

## Slide 20: Thank You