## Slide 1
08 September 2021
Progress Report on the Refurbishment of the Rail Infrastructure
Select Committee on Transport, Public Service and Public Works & Infrastructure

## Slide 2: Table of Contents
  1. Presidential Projects
  a. Mabopane Rehabilitation Programme
  b. Central Line Rehabilitation Programme
  2. Other Priority Projects
  3. Depot Modernisation Project
  4. Service Resumption Plan

## Slide 3: Mabopane Rehabilitation Programme
Project | Description | 
Substation Rehabilitation | Made up of 14 Substations​ Broken into two (2) WP’s ​ | 70% reduction in Cu content
Rehabilitation of OHTE System | Made up of 160km of OHTE​ Broken into Five (5) WP​ | Reduce copper content
Re-signalling | Made up of nine (9) Signaling Stations​ Part of the Siemens Re-signaling Programme | Reduction of copper content Reinforcement of critical content
Train Stations Rehabilitation | Made up of 23 Train stations​ Broken into six (6) WPs​ | 
Walling and Security Programme | Smart Walling solution: Broken into 16 WPs​ Security intervention: Deployment of targeted security interventions for the corridor​ | 
Street to Street Bridges Projects | Made up of 8 bridges​ Divided into 8 WPs​ | 

## Slide 4: Programme Overview

## Slide 5: High Level Remedy Plan
PROJECT NAME​ | REMEDY ACTION​ |  | EST. FINISH DATE​ | ​
OHTE Rehabilitation project​ | Acceleration plan (Compress 8 months construction plan into 3 months through shift working) ​ |  | 03 Nov 21​ | Construction​
Substation Rehabilitation project​ | None​ |  | 26 Oct 21​ | Construction​
Station Rehabilitation​ | Start service with 22% station availability​ Increase availability to 52% (deviation from normal tender process, Turnkey approach)​ Increase availability to 100% (Turnkey approach)​ |  | 03 Nov 21​ 26 Nov 21​ March 22​ | In place​ ​ Advertisement​ ​ Specification​
Security Intervention Project​ | Targeted security unit for the Now and Post construction before walling Solution​ |  | Oct 21​ | Advertised​
ELECTRICAL TRAIN SERVICE WITH 92% OF AUTOMATED TRAIN AUTHORISATION CAN START​ 04 NOV 2021​ |  |  |  | 
Walling Programme​ | Unbundle Work Packages (16 WPs) for an accelerated construction phase.​ WP1-3: Walling around 31 strategic buildings​ WP4-14: Corridor Walling (Inc. Dewildt)​ WP15: Security Technology​ WP 16: Upgrade of Civil Works​ WP17: Wolmerton Walling​ | ​ ​ Staggered (Nov 21 – Jan 21)​ ​ Staggered (Nov 22 – Jul 22)​ ​​ Jan 22 ​ | ​ ​ Staggered (Nov 21 – Jan 21)​ ​ Staggered (Nov 22 – Jul 22)​ ​​ Jan 22 ​ | ​ ​ Evaluation​ ​ Designs Done​ ​ Designs Done​
Re-signalling Project​ | On track​ | Dec 21​ | Dec 21​ | Construction​
ELECTRICAL TRAIN SERVICE WITH FULL AUTOMATED TRAIN AUTHORISATION CAN START​ END DEC 2021​ |  |  |  | 
Street to street bridges​ | On track​ | May 21​ |  | CFST Approved​

## Slide 6: Programme Performance
258 local labourers have been appointed.
12 interns in the build environment have been appointed under KBCE​
Local SMME's participation:
  Security (1),
  Stenciling (5),
  Ablution facilities (5),
  Site establishment (3),
  Clearing and transportation and small building works (12). 26 in total​
30% of all contract value was sub-contracted which was a pre-requisite from PRASA in line with regulation 9 of the Preferential Procurement Regulations of PPPFA 2017

## Slide 7: Central Line Rehabilitation Programme
Project | Description
Substation Rehabilitation | 3 x substation work packages out on tender (closing end Sept 2021)​ Smaller regional project at Nyanga substation underway for Phase 1 to Nyanga and Bellville​
Rehabilitation of OHTE System | 5 x contractors appointed for 33kV and 3kV works​ Works expected to start in September 2021 (6 month duration)​ 3 x 11 kV work packages out on tender (closing end Sept 2021)​
Re-signalling | Final discussions taking place with Thales Maziya to obtain agreement with them on how to proceed with Central Line Re-signalling​
Train Stations Rehabilitation | Consultant tender closing on 31 August 2021 so that repair tenders can be professionally scoped and administered​ Station repair works estimated to start in November 2021
Walling Project | Designs completed except for control room locations​ 12 work packages proposed​ 5 x walling work packages at CFST
Removal of illegal settlements | Prioritised Langa settlement removal​ Obtained eviction order for Langa settlement only on 28 July 2021​ Latest estimate to remove all illegal settlements using accelerated approach is beginning of October 2021. Matter escalated to the Executive Mayor to fast-track removal of illegal settlements on the PRASA reserves.

## Slide 8: Central Line Rehabilitation Programme

## Slide 9: Priority Corridors Recovery
Goals
Improve Reliability Availability of the
railway network ​
Improve safety ​
Improve asset life span
Objectives
Routine Preventative Maintenance (Inspect& Correct) – Time Based ( Short Term)​
Capital Intervention (Correct-Major Breakdown ) – Short, Medium & Long-Term Projects

## Slide 10: Infra Maintenance Projects Overview

## Slide 11: Programme Performance

## Slide 12: Project Implementation - Dashboard (2021/22)
​ Corridor ​ | Implementation Status (RAG)​ ​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ ​ ​ ​ ​ ​ ​ ​ ​ Pienaarspoort –PTA​ | Electrical (Substations / OHTE)​ | Refurbishment of Rissik, Koedoespoort and Eerste Fabrieke subs and Ties​ Refurbishment of OHTE Pienaarspoort to Pretoria ​ | Substations :22 March2022 ​ OHTE : 24March2022​ ​ | Subs & OHTE BEC Stage : To be finalized by 23 Sept 2021​ | Subs : R64m​ OHTE: R44m​
 | Perway ​ | Perway Performance Improvement Works (Perway Available):​ (On Track Machines ): Screening, Regulation, Tamping and Rail Grinding ​ | ​ 31 March 2022​ ​ | Project at Award stage: 30 August2021​ | R10.2mil​
 |  | ​ Perway Performance Improvement Works - Supply & Delivery of Rails(Perway Available) : 48kg/m Rail Replacement on the main line​ | 30 August2022​ | Project Contracting Stage:30 August2021​ | R32.4mil​
 | Signalling​ | Refurbishment of the Signalling System : Points, Train Detection System and Signals ​ | 31 March 2023​ | Awaiting CFST appointment:15 Sep2021​ | R91.5mil​
 | Telecoms ​ | Rehabilitation of Aerial Optic fibre network​ Rehabilitation of underground fibre network & Optical Transport network​ Rehabilitation of Public Address Systems, Electronic Display Boards, RailCom and Help points​ Rehabilitation of integrated access control systems​ | 31 March 2023​ | Project Design Stage: 15 Sep2021​ | R20 mil​ R34 mil​ R34.5 mil​ ​ R19.9 mil​
​ | Stations​ ​ | Phase 1 of the programme is to achieve functionality of 7 stations ​ Phase 2 of the programme is to achieve functionality of 5 stations​ 01 ABT is planned to be completed ​ | 28 February 2022​ 29 May 2022​ 28 December 2021​ ​ | Consultants have been advertised and closing 08 Sep 2021​ The ABT advert closed 24-Aug-21 and in BEC​ | R30.4mil​ R37mil​ R6.6mil​

## Slide 13: Project Implementation – Dashboard (2021/22)
Corridor​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ ​ ​ ​ ​ Naledi-JHB ​ | Electrical (Substations / OHTE)​ | Refurbishment of Naledi, Inhlazane, Dube, New Canada; Braamfontein, Langlaagte , New Canada & Dube , Langlaagte, Braamfontein Substations​ Refurbishment of OHTE Naledi - Johannesburg​ | ​ Substations March 2022​ OHTE March 2022​ | Subs & OHTE BEC Stage : To be finalized by 23 Sept 2021​ | Subs: R133m​ OHTE: R45m​
 | Perway / Infrastructure​ | Perway Performance Improvement Works (Perway Available):​ (On Track Machines ): Screening, Regulation, Tamping and Rail Grinding ​ | ​ 31 March 2022​ | Project at Award stage: 30 August2021​ | R10.2mil​
 |  | ​ Perway Performance Improvement Works - Supply & Delivery of Rails(Perway Available) : 48kg/m Rail Replacement on the main line​ | 30 August2022​ | Project Contracting Stage:30 August2021​ | R48.6mil​
 | Signalling​ | Refurbishment of the Signalling System(Points, Train Detection & Signals) at : Naledi to New Canada​ Refurbishment of the Signalling System (Points, Train Detection & Signals at : New Canada to Johannesburg​ | 31 March 2023​ ​ 31 March 2023​ | Awaiting CFST appointment​ | R51.2mil​ R69.1mil​
 | Telecoms ​ | Rehabilitation of Aerial Optic fibre network​ Rehabilitation of underground fibre network & Optical Transport network​ Rehabilitation of Public Address Systems, Electronic Display Boards, RailCom and Help points​ Rehabilitation of integrated access control systems​ | 31 March 2023​ | Service requests at PRASA TECH CEO office for approval​ | R20 mil​ R22 mil​ R18.6 mil​ ​ R24 mil​
​ | Stations​ ​ | 14 stations are planned to be delivered ​ The scope of work includes station and platform lighting, access control, platform resurfacing, functional ticket office, waiting facilities, yellow lines, etc.​ | 01 September 2022​ | Consultant have been advertised and closing 16 Aug 2021 ​ | R56.6mil​

## Slide 14: Project Implementation (2021/22)
Corridor​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ ​ ​ Leralla- Elandsfontein -JHB ​ | Electrical (Substations / OHTE)​ | Refurbishment of Leralla; Thembisa, Kaalfontein; Birchleigh; Kempton Park; Elandsfontein; Knights; Germiston; George Goch Ties and Substations​ Refurbishment of OHTE Leralla - Johannesburg​ | Substations :22 March2022 ​ OHTE : 24 March2022​ | Subs & OHTE BEC Stage : To be finalized by 23 Sept 2021​​ | Sub:R238m​ OHTE: R76m​
 | Perway​ | Perway Performance Improvement Works (Perway Available):​ (On Track Machines ): Screening, Regulation, Tamping and Rail Grinding ​ | ​ 31 March 2022​ | Project at Award stage: 30 August2021​ | R10.2mil​
 |  | ​ Perway Performance Improvement Works - Supply & Delivery of Rails(Perway Available) : 48kg/m Rail Replacement on the main line​ | 30 August2022​ | Project Contracting Stage:30 August2021​ | R32,6mil​
 | Signalling​ | Rehabilitation of the signalling system(Signals, Points & Train Detection System) at : Leralla to Knights​ Rehabilitation of the Signalling System(Signals, Points & Train Detection System )at : Knight to Johannesburg​ | 31 March 2023​ | Awaiting CFST appointment​ | R77,2mil​ R77,2mil​
 | Telecoms ​ | Rehabilitation of Aerial Optic fibre network​ Rehabilitation of underground fibre network & Optical Transport network​ Rehabilitation of Public Address Systems, Electronic Display Boards, RailCom and Help points​ Rehabilitation of integrated access control systems​ | 31 March 2023​ | Service requests at PRASA TECH CEO office for approval​ | R25 mil​ R31.5 mil​ 62.2 mil​ ​ R33.1 mil​
​ | Stations​ ​ | Phase 1 of the programme is to achieve functionality of 7 stations ​ Phase 2 of the programme is to achieve functionality of 9 stations​ ​ ​ | 28 February 2022​ | Consultants have been advertised and closing 16 Aug 2021 ​ | R21.3mil​ R40.2mil​

## Slide 15: Project Implementation (2021/22)
Corridor​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ ​ Saulsville- PTA ​ | Electrical (Substations / OHTE)​ | Refurbishment of Saulsville, Cor Delfos; Mitchell Street, Pretoria Ties and substations​ Refurbishment of OHTE on the second line​ | Substations :22 March 2022 ​ OHTE : 24 March 2022​ | Subs & OHTE BEC Stage : To be finalized by 23 Sept 2021​ | Subs: R29m​ OHTE: R12m​
 | Perway​ | Perway Performance Improvement Works (Perway Available):​ (On Track Machines ): Screening, Regulation, Tamping and Rail Grinding ​ | ​ 31 March 2022​ | Project at Award stage: 30 August2021​ | R10.2mil​
 | ​ | ​Perway Performance Improvement Works - Supply & Delivery of Rails(Perway Available) : 48kg/m Rail Replacement on the main line​ | 30 August 2022​ | Project Contracting Stage: 30 August2021​ | R18mil​
 | Signalling​ | Rehabilitation of the Signalling System (Signals, Points, Train Detection) at : Saulsville to Pretoria ​ | 31 March 2023​ | Awaiting CFST appointment​ | R42.8mil​
 | Telecoms ​ | Rehabilitation of Aerial Optic fibre network​ Rehabilitation of underground fibre network & Optical Transport network​ Rehabilitation of Public Address Systems, Electronic Display Boards, RailCom and Help points​ Rehabilitation of integrated access control systems​ | 31 March 2023​ | Service requests at PRASA TECH CEO office for approval​ | R10 mil​ R17 mil​ R13 mil​ ​ 6.8 mil​
​ | Stations​ | 3 Stations are planned to be delivered on NSIP ​ 2 station are planned to be delivered on CIP​ ​ ​ | 29 January 2022​ 31 March 2022​ | Consultants have been advertised and closing 08 Sep 2021​ CIP tender specification in progress​ | R6mil​ R6.5mil​

## Slide 16: Project Implementation (2021/22)
Corridor​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ PTA- Kaalfontein ​ | Electrical (Substations / OHTE)​ | Refurbishment of Verweoedburg; Pinedene and Oakmoor Subs​ Refurbishment of OHTE Pretoria - Kaalfontei​n | Substations : 22 March2022 ​ OHTE : 24March2022​ | Subs & OHTE BEC Stage : To be finalized by 23 Sept 2021​ | Subs: R53m​ OHTE :R55​
 | Perway​ | Perway Performance Improvement Works (Perway Available):​ (On Track Machines ): Screening, Regulation, Tamping and Rail Grinding ​ | ​ 31 March 2022​ | Project at Award stage: 30 August2021​ | R10.2mil​
 | Signalling​ | Rehabilitation of the Signalling System (Signals, Points & Train Detection System) at : Pretoria to Kaalfontein​ | 31March 2023​ | Awaiting CFST appointment ​ | R91,5mil​
 | Telecoms ​ | Rehabilitation of Aerial Optic fibre network​ Rehabilitation of underground fibre network & Optical Transport network​ Rehabilitation of Public Address Systems, Electronic Display Boards, RailCom and Help points​ Rehabilitation of integrated access control systems​ | ​ ​ 31March 2023​ ​ | Service requests at PRASA TECH CEO office for approval​ | R20 mil​ R38 mil​ R15.5 mil​ ​ R9,9 mil​
 | Stations​ | Phase 1 of the programme is to achieve functionality of 3 stations ​ Phase 2 of the programme is to achieve functionality of 3 stations​ ​ | 28 February 2022​ 07 June 2022​ | Consultants have been advertised and closing 20 Sep 21​ ​ | R13mil​ R13.4mil​

## Slide 17: Project Implementation (2021/22)
Corridor ​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ ​ ​ ​ ​ ​ Daveyton –Germiston​ | Electrical (Substations / OHTE)​ | Refurbishment of the Substations: Alliance, Dunswart, Boksburg East, Angelo, Van Ryn​ Refurbishment of the OHTE : Daveyton-Germiston ​ ​ (Work to be executed subject to Perway Availability)​ | Substations :30 August 2022 ​ OHTE : :30 August 2022 ​ | Subs & OHTE BEC Stage : To be finalized by 23 Sept 2021​ ​ | Subs: R88.7mil​ ​ OHTE: R 50mil​
 | ​ ​ ​ Perway​ | Perway Recovery Works (22km of Rail Perway NOT Available):​ (On Track Machines ): Screening, Regulation, Tamping and Rail Grinding ​ | ​ 30 August 2022​ ​ ​ | Project at Award stage: 30 August2021​ | R10.2mil​
 |  | ​ Perway Performance Improvement Works - Supply & Delivery of Rails(Perway Available) : 48kg/m Rail Replacement on the main line​ | 30 August2022​ | Project Contracting Stage:30 August2021​ | R61.2mil​
 | Signalling​ | Refurbishment of the Signalling System at Daveyton to Germiston ​ | 31 March 2023​ | Awaiting CFST appointment​ | R79.5 mil​
 | Telecoms ​ | Rehabilitation of Aerial Optic fibre network​ Rehabilitation of underground fibre network & Optical Transport network​ Rehabilitation of Public Address Systems, Electronic Display Boards, RailCom and Help points​ Rehabilitation of integrated access control systems​ | 31 March 2023​ | Service requests at PRASA TECH CEO office for approval​ | R25 mil​ R33 mil​ R31.5 mil​ ​ R13.4 mil​
 | Stations​ | 7 Stations are planned to be delivered on NSIP ​ 2 station are planned to be delivered on ABT​ ​ | 31 July 2022​ 08 January 2022​ | Consultants advertised closing 20 Sep 2021​ ABT advert closes 31 Aug 21​ | R24.5mil​ R8mil​

## Slide 18: Project Implementation (2021/22)
Corridor​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ ​ Umlazi-Durban​ | Electrical (Substations / OHTE)​ | Repair vandalised substations: Umbilo and Umlazi​ Repair vandalised switching station at Duffsroad.​ | 30 June 2022​ 30 March 2022​ | CFST:17 Sept 2021​ Re-Advertised:03 Sep2021​ | R23mil​ R1mil​
 | Perway​ | Bridges:rehabilitation:Umlaascanal bridge, Lindokuhle, Umlazi and Zwelethu ​ | 30 March 2023​ ​ | CFST:08 Sept 2021​ ​ | R82mil​
 | ​ | Reunion - Zwelethu rehabilitation of formation​ | 30 March 2022​ ​ | Execution:50% progress​ ​ | R1mil​ ​
 | ​ | Perway Performance Improvement Works (Perway Available):​ (On Track Machines ): Screening, Regulation, Tamping and Rail Grinding ​ | ​ 31 March 2022​ ​ | Project at Award stage: 30 August2021​ | R17.3mil​
 | ​ | ​Perway Performance Improvement Works - Supply & Delivery of Rails(Perway Available) : 48kg/m Rail Replacement on the main line​ | 30 August2022​ | Project Contracting Stage:30 August2021​ | R27mil​
 | Signalling​ | Replace stolen Signal cables between Durban and Congella​ | 30 Sept 2022​ | CFST: 03 Sep2021​ | R16mil​
 | Telecoms ​ | Installation of underground fiber between Durban and Umlazi​ | 30 June 2022​ | Specification: 31 August 2021​ | R5mil​
​ | Stations​ | 7 Stations are planned to be delivered on NSIP as part of Priority 1​ 7 Stations are planned to be delivered on NSIP as part Priority 2​ 3 station are planned to be delivered on ABT​ ​ | 30 March 2022​ 26 July 2022​ 07 January 2022​ | Consultants have been advertised and closing on 08-Sep-21​ ABT advertised and closing on 10-Sep-21​ | R88mil​ R51mil ​ R8mil​

## Slide 19: Project Implementation 2021/22
Corridor​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ ​ ​ ​ ​ Kwamashu-Durban​ | Electrical (Substations / OHTE)​ | Replace stolen overhead wires on the Greenwood Park line and Duffsroad - KwaMashu​ | 30 Sept 2022​ | Project at CFST:10 Sep 2021​ | R28mil​
 | Perway​ | Rehabilitation of Umgeni footbridge​ Rehabilitation of drainage and formatio: Thembalihle to KwaMashu and Avoca to Duffs Road.​ | 30 Sept 2022​ 30 Jun 2022​ ​ | Project at CFST:08 Sep 2021​ Project at CFST:25 Aug 2021​ | R3mil​ R6mil​ ​
 |  | Perway Performance Improvement Works (Perway Available):​ (On Track Machines ): Screening, Regulation, Tamping and Rail Grinding ​ | ​ 31 March 2021​ ​ | Project at Award stage: 30 August2021​ | R17.3mil​
 | ​ | ​Perway Performance Improvement Works - Supply & Delivery of Rails(Perway Available) : 48kg/m Rail Replacement on the main line​ | 30 August2022​ | Project Contracting Stage:30 August2021​ | R16.2 mil​
 | Signalling​ | Replace stolen signal equipment at Greenwood Park, Umgeni, Thembalihle and bridge City​ | 30 Nov 2022​ | Project Specification:​ Greenwood Park: 30 Sept 2021​ Umgeni, Thembalihle and Bridge city 03 Sept 2021​ | R35mil​
 | Telecoms ​ | Installation of underground fiber between Durban and KwaMashu​ | 30 June 2022​ | Project: Specification: 31 August 2021​ | R3mil​
 | Stations​ | 4 Stations are planned to be delivered on NSIP as part of Priority 1​ 2 Stations are planned to be delivered on NSIP as part Priority 2​ 2 station are planned to be delivered on ABT​ ​ | 30 March 2022​ 01 August 2022​ 25 February 2022​ | Advert for consultant closing 08 September 2021​ ABT advert closing 02 September 2021​ | R30 .8mil​ R18.4mil​ R18.7mil​

## Slide 20: Project Implementation (2021/22)
Corridor​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/ Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ ​ Cape Town- Simonstown(Wynburg)​ ​ | Electrical Distribution Lines​ | Reinstatement of 11 kV at Steenberg and 33 kV Distribution lines (Thornton to Good Wood)​ | 30 Jan2022​ | Project Advertised:10Sep2021​ | R1m​
 | Electrical Substations​ | Installation of high speed circuit breakers – Diep River sub​ | 30 March 2023​ | Project at BAC:30Aug2021​ | R6m​
 |  | Supply and installation of Substation Safety doors ​ | 30 March2022​ | Project Awarded: Orders placed : 30 October2022​ | R2mil ​
 |  | Supply and Installation of 5MVA Transformer, Rectifier and Wave Filter at False Bay ​ | 30 March 2023​ ​ | Project Awarded: Orders placed : 30 March2022​ | R4.5mil​
 | Perway​ | Supply and delivery of Track Ballast in the Western Cape Region ​ ​ | 30 March2022​ ​ | Awaiting tender briefing:03Sep2021 | R1mil​ ​
 |  | Procurement of Ultrasonic Measuring Services : UMC ​ | 30 Dec2024​ | Project at Award Stage: 15Sep2021​ | R8mil ​
 |  | Refurbishment of Perway assets to address RSR Directives​ ​ | 12 months :30March2022​ ​ | Execution:70% progress ​ ​ | R 0.7mil​ ​
 |  | Perway Maintenance Services to Augment MO Capacity (WC Region) on Adhoc basis ​ | 25April2022​ ​ | Awarded: 40% progress​ | R 3.6mil​

## Slide 21: Project Implementation (2021/22)
Corridor​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ Cape Town- Simonstown(Wynburg) (Cont)​ | Perway​ | Perway Performance Improvement Works (Perway Available):​ (On Track Machines ): Screening, Regulation, Tamping and Rail Grinding ​ | ​ 31 March 2021​ | Project at Award stage: 30 August2021​ | R15.2mil​
 |  | ​ Perway Performance Improvement Works - Supply & Delivery of Rails(Perway Available) : 48kg/m Rail Replacement on the main line​ | 30 August2022​ | Project Contracting Stage:30 August2021​ | R18mil​
 |  | Manual Screening of Level crossing at various locations within Cape Metrorail Western Cape Region (Cape Town – Woodstock)​ | 17 April2022​ ​ | Execution:20% progress​ ​ | R 2.1mil​
 |  | Replacement of full Double Slip and Single Slip Turnout sets, and Supply of associated Material in Cape Town Metrorail Region (Cape Town – Woodstock)​ | 31 Dec 2023​ | At BEC Stage : 30Sep2021​ ​ | R 7.4mil​ ​
 |  | Rehabilitation of Bridges in the Metrorail Western Cape Region (Salt River, Kenilworth - Wynberg, Plumstead – Steurhof)​ | 30 September 2023​ | At BEC Stage : 30Sep2021​ ​ | R 12.9mil​

## Slide 22: Project Implementation (2021/22)
Corridor​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ ​ ​ Cape Town- Simonstown (Wynburg) cont​ | Signalling​ | Vandalproofing Trackside elements (Signals,Point Machines, Axle Counters)​ | 30 March 2022​ ​ | Project at Passed BEC & still be advertised: 03 Sep2021​ ​ | R3mil​ ​
 |  | Signalling Spares (Point Machine & LED spares, Signalling Cables)​ ​ | 30 March 2022​ | Project at CFST :07 Sep2021​ ​ | R5mil​ ​
 |  | Procurement of Signalling Mission Critical Components​ ​ | 30 March 2022​ | Project Confinement Motivation at Legal for vetting :30August2021​ ​ | R49mil​ ​
 |  | Upgrade Level Crossings​ ​ | 30 March 2022​ | Execution: Material Ordered: 08October2021​ | R3.5mil​ ​
 | Telecoms ​ | Supply, Deliver, and Install PA Adapters for the WC Region​ | 30 March 2022​ | Project at CFST: 03 Sep2021​ | R 4,8mil​
 | Telecoms ​ | Supply, Delivery, Install and Commission of VoIP telephone system​ | 30 March 2022​ | Project at CFST:03Sep2021​ | R 2mil​
 | Stations​ | 35 stations to be delivered on the NSIP​ | 03 February 2023​ | Consultants have been advertised and closing 31 August 2021​ | R214 mill​

## Slide 23: Project Implementation (2021/22)
Corridor​ | Implementation Status (RAG)​ |  |  |  | 
 | Scope​ | Project Scope Details​ | Schedule/Time ​ | STATUS​ | Budget​
​ ​ ​ ​ ​ ​ ​ ​ ​ Cape Town- Simonstown (Athlone )​ ​ | OHTE/ Substations​ | Supply and Installation of 5MVA Transformer, Rectifier and Wave Filter at Crawford​ | 30 March 2023​ | Project Awarded: Orders placed : 30 March2022​ | R4.5mil​
 | Perway / Infrastructure​ | Perway Performance Improvement Works (Perway Available):​ (On Track Machines ): Screening, Regulation, Tamping and Rail Grinding ​ | ​31 March 2021​ | Project at Award stage: 30 August2021​ | R15.2mil​
 |  | ​Perway Performance Improvement Works - Supply & Delivery of Rails(Perway Available) : 48kg/m Rail Replacement on the main line​ | 30 August2022​ | Project Contracting Stage:30 August2021​ | R18mil​
 | ​ | Supply and Installation of Concrete Universal Sleepers at Various within MetroRail ( Maitland, Ndabeni and Hazendal​ | 03 April2022​ | Project in Execution:10% ​ | R6mil​
 | ​ | Procurement of Ultrasonic Measuring Services : UMC ​ | 30 Dec 2024​ | Project at Award Stage: 30 August2021​ | R8mil ​
 | Signalling​ | Vandalproofing Trackside elements (Signals,Point Machines, Axle Counters)​ | 30 March2022​ | Project at Passed BEC & still be advertised: 03 Sep2021​ | R3mil​
 |  | Rehabilitation of Maitland Indoor and Outdoor Signalling Equipment​ | 30 March2022​ | Project at Passed BEC & still be advertised: 03 Sep2021​ | R5mil​
 |  | Signalling Spares (Point Machine & LED spares, Signalling Cables)​ | 30 March 2022​ | Project at CFST :07 Sep2021​ | R8mil​ ​
 |  | Procurement of Signalling Mission Critical Components​ | 30 March 2022​ | Project Confinement Motivation at Legal for vetting :30August2021​ | R49mil​
 | Telecoms ​ ​ | Supply, Deliver, and Install PA Adapters for the WC Region​ | 30 March 2022​ | Project at CFST: 03 Sep2021​ | R 5mil​
 |  | Supply, Delivery, Install and Commission of VoIP telephone system​ | 30 March 2022​ | Project at CFST:03Sep2021​ | R 1.9mil​
 | Stations​ | 9 Stations are planned to be delivered on NSIP as part of Priority 1​ 12 Stations are planned to be delivered on NSIP as part Priority 2​ ​ | 08 Dec 2021​ 03 Mar 2023​ | Advert for consultants closes 31-Aug-21 and the contractor pre-qualification advert placing on 30 Aug 2021​ | R94.1 mil​ R200 mil​

## Slide 24: Depot Modernisation Projects - Progress
  Focus: Sep21–Mar22​
Projects at Initiation stage​
Culemborg/Bloemfontein to advertise and tenders to close in March 2022.​
PE and East London depots, finalise land transfers and advertise tenders.​
Motherwell, Complete approvals for the MOA.​
Projects at CFST Stage​
Braamfontein/Benrose & Wolmerton depots: ​
Advertise tenders in Sept21 – Nov21​
BECs – (Dec21-Jan22), ​
Award Braamfontein in Feb.22, Wolmerton Feb22 and Benrose Jan22. ​
Projects at BEC Stage​
Paadern Eiland depot, to appoint in Jan22 for work to start in Feb22.​
Depot fencing to appoint contractors end of Oct21.​
Projects awarded (Salt River/Durban Yard/Springfield)​ (This project has been put on hold due to a court case)
Detailed designs and tender documentation to be completed in Dec21,​
CFST and Approach to market approvals in Jan22. ​
Tender advertisements Jan-Mar22.​
​

## Slide 25: National Service Resumption Plan
​

## Slide 26: Corridor Rollout Plan