## Slide 1: SOUTH AFRICAN HUMAN RIGHTS COMMISSION
Annual Report 2020-21
and
Quarter 2 Performance 2021-22
-
Portfolio Committee on Justice and Correctional Services
10 November 2021

## Slide 2: Contents
Chairperson’s overview
An overview of performance as at 31 March 2021:
  Programme 1: Administration
  Programme 2: Promotion of Human Rights
  Programme 3: Protection of Human Rights
  Programme 4: Monitoring of Human Rights
Overview: 2020-21 Annual Financial Statement and Budget 2021 - 2022
Performance overview 2021-22 as at 30 September 2021

## Slide 3: Chairperson’s overview
Human rights implications of the Covid-19 pandemic
Corporate implications of the Covid-19
Civil unrest July 2021
Civil society and stakeholder participation
Resources capacity: Budget reductions; cost of employees; new Commissioners; vacancies

## Slide 4
An overview of performance
Financial year ended on 31 March 2021

## Slide 5: Overview of Performance 2020-21 Achievement of targets over the last 5 years
Chart: 
| 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21
% Achieved | 0.84 | 0.75 | 0.73 | 0.88 | 0.64

## Slide 6: Overview of Performance 2020-21 Achievement of targets by Programme
Strategic Objective and Programme | Total Targets | Annual Targets Fully Achieved
Programme 1: Administration | 12 | 7
Programme 2: Promotion of Human Rights | 9 | 6
Programme 3: Protection of Human Rights | 4 | 3
Programme 4: Monitoring of Human Rights | 11 | 7
Total | 36 | 23

## Slide 7
Programme 1 achievements: Administration
A stable institution with capacity to effectively deliver on planned priorities

## Slide 8: Programme 1 achievements: Administration
Administration programme key achievements
Governance, audit, risk and compliance: stable operations and oversight, unqualified audit, risk strategy review and largely compliant
Innovative use of ICT: ensured ongoing corporate communications and remote work
Human capital management: strategy, recruitment, remuneration structure
Planning and execution: reviews and Covid-19 Protocol

## Slide 9: Programme 1: Administration Areas of under - performance (1)
No. | Performance Indicators | Annual Target | Annual Achievement | Reasons for Variances and Corrective Actions
1 | Percentage expenditure against total budget | 95% - 105% expenditure | 90% | There were open purchase orders or commitments which, on actual spend would increase expenditure to 95%.
2 | Percentage implementation of Risk Management Plan | 80% - 100% Implementation | 72% | Delays due to attention on the Covid-19 demands. Low levels of responsiveness to Risk treatment planning. Reviewed risk management environment and revised policy. Improvements expected.
3 | Submission of SAHRC Conditions of Service and Remuneration | Develop SAHRC Conditions of Service and Remuneration | Recommendations reports completed but conditions of service not developed. | Delays were due to unavailability of Committee members. Guideline and Recommendations will be tabled with Commissioners for implementation in the new financial year.

## Slide 10: Programme 1: Administration Areas of under - performance (2)
No. | Performance Indicators | Annual Target | Annual Achievement | Reasons for Variances and Corrective Actions
4 | Percentage resolution of audit findings | 80% - 100% resolution | 49% | Capacity constraints. Temporary capacity sourced.
5 | Percentage compliance with Institutional Governance Framework | 80% - 100% compliance with identified aspects of Comprehensive Institutional Governance Framework | Governance Report completed. Board Charter not developed. | Realisation to acquire a more comprehensive and digitised institutional governance framework, as opposed to the limited scope of a Board Charter alone. Cost implications meant that the item had to be included in the procurement plan of the next financial year.

## Slide 11
Programme 2: Promotion of Human Rights
Influenced pro-human rights policies, legislation, service delivery and awareness

## Slide 12: Programme 2 Promotion of human rights
7 thematic pillars informed the institutional response:
Promoting good governance, anti-corruption and human rights
Human settlements, water and sanitation
Promoting the right to health and of persons living with disability
Promoting respect and observance of the right to equality
Commemorating 25 years of existence and human rights month
Empowering human rights champions in communities
Promoting human rights through advancements in Information and Communications Technology

## Slide 13: Programme 2 Promotion of human rights (2)
Risk Adjusted Strategies and Rationale
Performance in the context of the national state of disaster and Regulations
With a view to sustaining contact with communities and stakeholders, the Commission intervened at international, regional, policy and local efforts using community radio, webinars, and engagements with stakeholders to promote awareness and advocate for human rights.
Participated in the development of international model emergency housing legislation in the context of Covid-19 and provided submissions to SALGA in respect of service standards for local government service delivery, influence on DHA policy relating to identity documents.
Supporting tools developed to provide resources in response to identified areas of high need in the form of an Equality Toolkit.
The Commission is investing in ensuring its website and communications are more accessible.

## Slide 14: Programme 2 achievements Promotion of human rights (3)
Methodologies
To sustain community based interaction, interventions directed at empowering locally based human rights champions multiplied the presence of human rights advocates at community level. Approximately 200 groups were reached through these interventions.
Webinars and conferences conducted virtually included a conference on racism; and one on the 4th Industrial Revolution which explored the impact of 4IR on human rights together with the Human Sciences Research Council. A book taking this forward would be produced.
Together with virtual commemorative events celebrating 25 years of the Commission, remote communities on provincial borders were engaged through Inter-border Roadshows.

## Slide 15: Programme 2 achievements: Promotion of human rights (4)
Strategic Stakeholders
A range of stakeholders have had contact with the Commission comprising statutory bodies, policy makers, traditional authorities, civil society organisations, experts and other human rights defenders.
Notable engagement in the course of wider work on access to health: Engagements with the South African Depression and Anxiety Group to promote the rights of persons living with psycho-social and intellectual disabilities.
Key stakeholders such as the Water Research Commission were also engaged in respect of systemic violations to the rights to access water and sanitation.
At the local level the Commission responded to specific trends in provinces including the use of non-violent means and human rights based approaches by law enforcement to handle protests, interventions in respect of racism including at schools, in respect of GBV; and child rights.

## Slide 16: Programme 2 achievements: Promotion of human rights (5)
Media Coverage of the Commission 2020/2021: Volume, Audience, Value and Sentiment |  |  |  |  |  | 
Media Type | Number of Items | Audience Reached | Average Value Equivalent | Positive Sentiment | Neutral Sentiment | Negative Sentiment
Print | 1643 | 485 304 765 | R 65 528 113.85 | 0.06% | 98.7% | 0.07%
Broadcast | 1417 | 1 418 160 728 | R 51 148 261.10 | 1.06% | 98% | 0.14%
Online | 4545 | 6 785 702 803 | R 177 177 727.26 | 0.06% | 99% | 0.04%
Totals | 7 605 | 8 689 168 296 | R293 854 102,21 | - | - | -

## Slide 17: Programme 2: Promotion of Human Rights Areas of under – performance (6)
No. | Performance Indicators | Annual Target | Annual Achievement | Reasons for Variances and Corrective Actions
1 | Number of agreements of cooperation implemented | Implement 5 Agreements of cooperation | 1 Agreement of Cooperation implemented | High dependence on external stakeholders. Continuous engagements held to promote the realisation of the commitments.
2 | Completion of Quarterly Media Monitoring Reports | Complete 4 Quarterly Media Monitoring Reports | 3 Quarterly Media Monitoring Reports Completed | Incomplete reporting due to contractual challenges with the media monitoring service provision. Procurement processes were underway for a different service provider, who would retrieve the previous information.
3 | Accessibility of the website to Persons with Disability | Make website accessible to people with disabilities | Engaged stakeholders and developed Terms of Reference. | Delays due to focus on Covid-19 demands, and suitable service provider not found on time. Secured budget to proceed in 2021-22.

## Slide 18
Programme 3: Protection of Human Rights
Appropriate redress secured where human rights have been violated

## Slide 19: Programme 3 achievements: Protection of human rights (1)
Complaints Summary
Protection efforts directed primarily to early resolution, however from time to time the Commission did resort to litigation on behalf of complainants or to support the courts.
Matters of significance during the national lockdowns involved service delivery, access to social support, the return of South African citizens, evictions, and police brutality.
Factors impacting on investigations and the provision of redress included access to courts, ability to conduct comprehensive on site inspections, and levels of responsiveness and resource constraints.
High impact litigation was initiated during the period. Notably the Commission has been admitted in the European Court of Human Rights as an intervenor in the matter of Caster Semenya/Switzerland. A landmark admission for an African NHRI.
Other litigation such as the matter involving whistle-blower, Mr Thabiso Zulu has influenced wider reform efforts being undertaken relating to law reform, and advocacy interventions.

## Slide 20: Programme 3 achievements: Protection of human rights (2)
Complaints Summary
In general equality related complaints continue to comprise the high number of complaint per category to the Commission, race being the most common ground of violation complained about.
The Commission has however, noted an increase in respect of complaints relating to socio economic rights.
Both Labour and administrative action rights are also brought to the attention of the Commission but are not an accurate reflection of the prevalence of violations as an equally high number of complaints in these categories are directed to the CCMA and the PPSA.

## Slide 21: Programme 3 achievements: Finalised cases by province
Province | Enquiries | Finalised complaints | Complaints Received | Complaints and Enquiries Received | Complaints and Enquiries finalised | %
EC | 164 | 274 | 396 | 560 | 438 | 78%
FS | 155 | 375 | 599 | 754 | 530 | 67%
GP | 1010 | 200 | 372 | 1382 | 1210 | 88%
KZN | 516 | 558 | 829 | 1345 | 1074 | 80%
LP | 264 | 390 | 707 | 971 | 654 | 67%
MP | 461 | 194 | 283 | 744 | 655 | 88%
NC | 239 | 130 | 248 | 487 | 369 | 76%
NW | 369 | 257 | 444 | 813 | 626 | 77%
WC | 1153 | 420 | 1560 | 2713 | 1573 | 58%
TOTALS | 4331 | 2798 | 5438 | 9769 | 7129 | 73%

## Slide 22: Programme 3 achievements: Top 5 complaints lodged
No. | Nature of Rights Violated | 2016-17 No. of cases | 2017-18 No. of cases | 2018-19 No. of cases | 2019-20 No. of cases | 2020-21 No. of cases
1. | Equality | 705 | 747 | 783 | 827 | 771
2. | Health Care, Food, Water and Social Security | 631 | 492 | 595 | 702 | 704
3. | Just Administrative Action | 407 | 457 | 452 | 641 | 501
4. | Labour Relations | 426 | 397 | 386 | 457 | 435
5. | Human Dignity | Not in Top 5 | 389 | 411 | 446 | 425
- | Arrested, Detained and Accused Persons | 443 | Not in Top 5 | Not in Top 5 | Not in Top 5 | Not in Top 5

## Slide 23: Programme 3: Protection of Human Rights Areas of under - performance
No. | Performance Indicators | Annual Target | Annual Achievement | Reasons for Variances and Corrective Actions
1 | Institute strategic impact litigation | Institute 20 High Court Matters | 13 matters instituted. | Delayed identification and approval processes on some of the matters proposed. Several other matters identified and many awaiting approval for litigation.

## Slide 24
Programme 4: Monitoring of Human Rights
Improved accountability for human rights in the country

## Slide 25: Programme 4 achievements: Monitoring of human rights (1)
Monitoring implementation of SAHRC recommendations
Recommendations based on health monitoring reports: mental health care; Esidimeni; emergency medical services in the EC; Inquiry on access to health care; and provision of health care for older persons.
Recommendations on water and sanitation from 2014 Report and 2018 Research Brief.
Recommendations on safety and security in farming communities: engagement with the Speaker of the KZN Provincial Legislature and other key stakeholders – focused on access to state facilities and safety and security in rural communities.
All engaged stakeholders welcomed the Commissions findings and recommendations, and committed to initiate mechanisms to address them and provide ongoing feedback.

## Slide 26: Programme 4 achievements: Monitoring of human rights (2)
Monitoring observance of the right to a basic education
Focus on schools monitoring: opening of schools; Covid-19 compliance; water, sanitation and infrastructure.
Several MECs for Education provided responses indicating efforts that would be undertaken by their respective provinces to address water, sanitation and learner safety challenges at schools.
Among others, there were serious challenges of non-compliance with the Covid-19 Safety Regulations, as well as water and sanitation, in the Pixley ka Seme District, Northern Cape, which the Commission is, to date, addressing with the provincial Education Department.

## Slide 27: Programme 4 achievements: Monitoring of human rights (3)
Monitoring the observance of children’s rights
Established Think Tank on Children’s Rights: to monitor and address inadequacies in laws, policies and instruments so as to ensure positive impact on the lives of children.
Think Tank noted challenges of inter-generational poverty, violence and stateless children – all exacerbated by the Covid-19 pandemic.
Agreed to convene a conference or study into the implications of the current economic austerity measures and the impact of Covid-19 on children, especially food security.
Children’s rights monitoring efforts would be enhanced by collaboration with the Center for Child Law to create a model mechanism for independent oversight to reinforce the rights of children in secure care in South Africa.

## Slide 28: Programme 4 achievements: Monitoring of human rights (4)
Monitoring the observance of the rights of persons with disability
Partnered with strategic stakeholders for the implementation of the Independent Monitoring Mechanism under the Convention on the Rights of Persons with Disabilities.
The collaboration is envisaged to contribute to the delivery of a Capacity Enhancement Programme to improve the government’s response towards barriers faced by persons with a disability in South Africa.
Economic vulnerability of persons with disabilities reduced through disability responsive budgeting;
Improved well-being of children with disabilities through regular, and systematic tracking; and
Increased capacity of persons with disability.
Key programme envisaged outcomes include:

## Slide 29: Programme 4 achievements: Monitoring of human rights (5)
National Preventive Mechanism – Optional Protocol to the Convention Against Torture
Report maps the progress on the implementation of the OPCAT in South Africa, and the institutional building processes; and documents findings and recommendations made on how persons in deprivation of liberty could be protected.
Several strategic stakeholder engagements were held to raise awareness and strengthen the NPM mandate, and conduct monitoring visits.
Marking the 1st anniversary of the establishment of the NPM, launched the 2019-20 NPM Annual Report in July 2020.
Findings and recommendations made relate to: overcrowding; inadequate safety and security; poor infrastructure and material conditions; inappropriate care for state patients; children deprived of liberty; and detention of migrants.

## Slide 30: Programme 4 achievements: Monitoring of human rights (6) Compliance with PAIA
Chart: 
| 2018-19 | 2019-20 | 2020-21
National | 26 | 20 | 25
Provincial | 59 | 40 | 53
Local | 31 | 25 | 37

## Slide 31: Programme 4: Monitoring of Human Rights Areas of under - performance
No. | Performance Indicators | Annual Target | Annual Achievement | Reasons for Variances and Corrective Actions
1 | Development of a Comprehensive Human Rights Monitoring and Evaluation System | Develop Children’s Rights Mapping Framework | Mapping exercise in progress. | Delays due to Covid-19 demands. Mapping exercise in progress for completion by Quarter 1 of 2021-22.
2 | Completion of State of Human Rights in South Africa Reports | Complete 3 SOHR Research Outputs (Brief or Paper or Bulletin) | 2 Research Briefs completed | Third Research Brief not completed due to resignation and vacancy in Civil and Political Rights Portfolio.
3 | Completion of Monitoring Report on Implementation of Social Media Charter | Develop and promote the Charter | Work in progress for development of the Charter. | Delays due to attention on Covid-19. Work in progress for completion in 2021-22.
4 | Completion of IMM-CRPD Monitoring Report | Complete IMM-CRPD Monitoring Report | On-going provincial monitoring conducted. Focus Area Report for Q3 not submitted. | Monitoring restricted due to Covid-19 challenges, and capacity constraints within the focus area. Plans to integrate the monitoring system.

## Slide 32
Overview
2020 – 2021 Annual Financial Statements
And
Budget 2021-22

## Slide 33: Overview of 2020-21 Financial Statements Financial Performance Review (1)
Review of financial performance for the year ending 31 March 2021
SAHRC received another unqualified audit for the year.
Internal controls need to be strengthened for strict adherence to policy and regulations.
Risk management processes have been strengthened after the completion of the review of the risk management policy and framework.
No audit comment was raised by the AG on the 30 day payment rule. Weekly mechanisms are in place to ensure payments are timeous.
Targeted policies and procedures have been reviewed and changed where required.

## Slide 34: Overview of 2020-21 Financial Statements Financial Performance Review (2)
Item |  | 2020-21 Actual | % of Total Expenditure | 2021-22 (Budget)
Personnel costs |  | R127.6m | 71% | R136.7m (66.4%)
Corporate support committed costs: |  | R33.4m | 18% | R43.5m (21.1%)
Office rentals and municipal charges (remaining budget covers motor vehicles, telephone, video-conferencing, inventories and other admin costs) Auditor-General Fees and other audit and finance fees Other costs included: ICT Infrastructure and contract related costs Human Resources: capacity development, employee wellness, recruitment, performance management |  | R23m R1.8m R5.1m R2.9m | - - - - | R13.8m R2.7m R5.5m R4.8m
Core operational costs | R18.3m |  | 10.2% | R25.8m (12.5%)

## Slide 35: Budget Overview Comparative analysis 2020-21 to 2021-22
Cost of employees and impact on organogram
Treasury Guidelines recommend that personnel costs should be at 60% of the institutional budget.
The Commission’s cost of employees has reduced from 71% in 2020-21 to 66% in 2021-22.
Ongoing mechanisms to reduce the cost of employees to recommended rate include a review of posts as and when they become vacant, as well as organisational structure redesigning.
The following implications of reduction in cost of employees need to be noted:
High risk of retrenchments, which is undesirable, to maintain lower personnel costs.
The personnel budget is aligned with the execution of the Commission’s mandate, as a largely service driven organisation. In effect therefore, reductions in personnel budget imply reduction in operations.
Elimination of critical posts including the Head of Commissioners Programme; management support to the Office of the COO.

## Slide 36: Budget Overview 2021 - 2022 Total Allocation
Item | Sub-Item | Budget Allocation
National Treasury Grant to the Commission for 2021-22 |  | R195 000 000
Other Income is budgeted as: |  | 
Interest income |  | R 1 000 000
Surplus Rollover from 2019-20 (earmarked for special projects including): - Human rights monitoring system - Head Office relocation - Supplementing the NPM budget allocation - Overseeing PAIA - Digitisation of records |  | R10 000 000
Total Budget |  | R 206 000 000
The Personnel budget is informed by the Compensation of Employees (COE) Guidelines as issued by National Treasury. |  | 

## Slide 37: Budget overview 2021-22 2021/22 budget vs spend per cost center as at Sept 2021

## Slide 38: Budget overview Forward Funding Needs
Mandate Area | Current (Rands) | 2022/23 (Rands)
National Preventive Mechanism | 4 100 000 | 4 100 000
Independent Monitoring Mechanism | 1 000 000 | 1 000 000
Information and Communications Technology | 5 500 000 | 7 000 000
Human rights monitoring | 2 400 000 | 4 800 000
Expanded Monitoring Framework: Local Government | 0 | 2 100 000
4 IR: Digitisation and Website: Accessibility | 3 000 000 | 3 000 000
Critical Reflection Publication – Handover | 0 | 500 000
TOTAL | 16 000 000 | 22 500 000

## Slide 39
Performance overview 2021-22
As at Quarter 2 (September 2021)

## Slide 40: Overview of Q2 Performance 2021-22 Achievement of Targets by Programme
Programme | Total no. of Programme Performance Indicators | No. of year-to-date targets fully achieved | No. of year-to-date targets behind schedule | % Achieved Q2 | % Achieved Q1
Administration | 13 | 7 | 6 | 54% | 46%
Promotion | 15 | 12 | 3 | 80% | 80%
Protection | 8 | 6 | 2 | 75% | 75%
Monitoring | 8 | 7 | 1 | 88% | 88%
Total | 44 | 32 | 12 | 73% | 70%

## Slide 41: Overview of Q2 Performance 2021-22 Promotion of human rights
Performance highlights as at 30 September 2021
Initiated National Campaign on Social Cohesion, Healing and Harmony.
Conducted workshops to promote awareness and the functionality of equality courts.
Hosted provincial rounds of the National Schools Moot Court Competition.
Secured undertaking to open sections of the Charlotte Maxeke Hospital in Gauteng.
Initiated mental health awareness project focusing externally and internally.
Hosted conference on impact of Covid-19 on children.
Implementing resolutions from the Anti-Corruption and Human Rights Conference.
Convened strategic engagements on the civil unrest of July 2021.
Media coverage attracted an Average Value Equivalent of approximately R186m.

## Slide 42: Overview of Q2 Performance 2021-22 Protection of human rights
Performance highlights as at 30 September 2021
Finalised more than 3 000 complaints and enquiries.
Dealt with violations pertaining to citizenship, identity and stateless persons, which often create problems of access to many other services.
Addressed service delivery complaints, especially relating to the provision of water and sanitation at local level, across the country.
Protected employees against mandatory vaccinations at the workplace.
Granted leave to intervene by the European Court of Human Rights in the Caster Semenya case.
Provided protection to evicted farm dwellers and other communities.

## Slide 43: Overview of Q2 Performance 2021-22 Monitoring of human rights
Performance highlights as at 30 September 2021
Monitoring the implementation of the national vaccine roll-out strategy.
Schools monitoring: opening of schools; Covid-19 compliance; water and sanitation provision and infrastructure; and learner teacher support material.
Child rights monitoring.
Monitoring under the National Preventive Mechanism.
Monitoring the implementation of the Commission’s recommendations: Mental health care; Vaal River inquiry; mining-affected communities.
Monitoring observance of the rights of persons with disability and older persons.
Completed annual report on compliance with the Promotion of Access to Information Act.

## Slide 44: END THANK YOU
www.sahrc.org.za
@sahrcommission