## Slide 1
implementation plans for systems downtimes and progress on abis
Portfolio COMMITTEE on home affairs Meeting
30 NOVEMBER 2021

## Slide 2
TABLE OF CONTENTS
Purpose
Progress on Plans to Resolve the Issue of Downtimes at DHA Offices
Maintenance Plan for Routers and Switches
Implementation of the Branch Appointment System
Automated Biometric Identification System (ABIS)
Recommendations

## Slide 3
PURPOSE
To present to the Portfolio Committee on Home Affairs a progress report on;
  The network related interventions by both DHA and SITA, including the maintenance of routers and switches.
  Implementation of the Branch Appointment System.
  Implementation Plan for Health Facilities to reduce queues in offices.
  The implementation of the Automated Biometric Identification System.

## Slide 4
IMPLEMENTATION OF THE PLANS TO RESOLVE THE ISSUE OF DOWNTIMES AT DHA OFFICES

## Slide 5
BACKGROUND
The DHA and SITA made a presentation to the Portfolio Committee on Home Affairs on 31 August 2021 on the plans to be implemented to resolve network downtimes
The following actions were going to be implemented with various timelines and some we beyond the current financial year:
  Increased usage of mobile connectivity supported by suitable connectivity media (antennae).
  Revision of architecture to deal with bloatware (software with excessive use of infrastructure facilities and components).
  Closer cooperation with other state and private entities on improving access to the internet.
  Queue management system.
  Maintain 196 generators in offices that have already been equipped to handle power outages.

## Slide 6: The Investment Plan high-level deliverables for Networks
PROGRESS ON THE NETWORK IMPLEMENTATION PLAN
Deliverable | Resp | Due Date | Status
Acceptance of the DHA Investment Plan | DHA/ SITA | 31/03/2022 | DHA’s highest technology priorities is the rollout and deployment of the uninterruptable network reference architecture. A reliable and high capacity network is essential to continued operations. This investment is guided by three strategic goals: a) Support, Maintain, and Secure Critical Infrastructure b) Improve Efficiency and Effectiveness of DHA Operations c) Increase Access and Transparency to Local Government & Citizens. DHA and SITA have made several investments in support of the implementation of the Investment Plan in a phased approach, more funding is required for further implementation of the Investment Plan.
Remote Environmental Management (REM) Solution | SITA | 31/03/2022 | Entails pro-active monitoring of the environmental systems on the SITA Switching Centres to prevent downtimes. The service provider has been contracted, equipment ordered and the implementation is to be completed by the end of June 2022.

## Slide 7: The Investment Plan high-level deliverables for Networks
PROGRESS ON THE IMPLEMENTATION PLAN
Deliverable | Resp | Due Date | Status
Software Defined Networking (SDN) |  |  | 
NGN Remedial Plan | SITA | 31/03/2022 | The SDN is modernizing the ageing core network infrastructure in order to prevent the impact of switching center outages on DHA front offices. Board has approved the appointment of the SDN Service Provider. The contract is to be finalized by end of November 2021. SITA to define regional implementation based on the approved design as per the award of the service provider as part of phase 1 The implementation of phase 1 of the project is expected to be completed by the end of March 2022.
SITA Core Network- layer 2 | SITA | 31/03/2022 | Process to appoint secondary service provider has been initiated for high availability of the SITA Core network.

## Slide 8: The Investment Plan high-level deliverables for Networks
PROGRESS ON THE IMPLEMENTATION PLAN
Deliverable | Resp | Due Date | Status
Software Defined Network (continued) |  |  | 
Internet failover | SITA | 31/03/2022 | Will assist in reducing outage impact on DHA services that are dependent on internet services, e.g. card payment services, online verification services, etc. Contract with the new service provider for Internet Services has been concluded and migration is completed. The backup links for both Centurion and Cape Town has been completed. The Internet failover between Cape Town and Centurion & vice versa to be concluded by March 2022.
VSAT Flat Panel Proof-of-Concept (POC) | SITA | 31/03/2022 | A Mobile Truck has been fitted with the VSAT flat panel and configured to work on LTE and VSAT for the deep rural site testing. VSAT Flat Panel POC in process.

## Slide 9: The Investment Plan high-level deliverables for Networks
PROGRESS ON THE IMPLEMENTATION PLAN
Deliverable | Resp | Due Date | Status
POC for Identified multiple access links (Gold) SLA Sites Identification of Sites POC will inform way forward in respect of desired SLA | SITA | 31/03/2022 | DHA submitted a list of sites currently connecting with multiple access links. DHA identified five (5) sites from the list for POC. After dependencies have been addressed, the POC to be conducted for a period of two months. Multiple Access Links at all sites must have the same bandwidth speed.
Consolidation of access links per province Revised approach for connectivity per region. Migration of access links from Copper based technology to other technologies | SITA | 30/09/2022 | Replacement of Diginet with LTE as a quick-win within two (2) months of 133 sites. Identified sites to be implemented incrementally and concluded by March 2022, SITA is appointing a single service provider per region. The North West will be used as a pilot, the bid is currently being evaluated. Technical specifications for other provinces will published before the end of December 2021. Expected appointment of service providers for all provinces by the end of September 2022.

## Slide 10: The Investment Plan high-level deliverables for Networks
PROGRESS ON THE IMPLEMENTATION PLAN
Deliverable | Resp | Due Date | Status
Environmental Management Power Supply continuity to DHA facilities | DHA | Done On-going as sites get Modernised | 176 Modernised Sites To provide power supply continuity during load shedding or power outages. 292 Non- Modernised Sites DHA must purchase and install back-up generators for non-modernized sites. DHA Front Office Managers to ensure that there is sufficient diesel for backup generators DHA Front Offices, in collaboration with Property Management, to ensure regular testing and maintenance of backup generators.
LAN and WAN Management Router Switches – Agency Procurement contract | DHA / SITA | 31/03/2022 | DHA to submit the Business Case to SITA for the replacement of routers & switches. DHA is considering various options including: Migrating from a Dedicated to Managed VPN. Leasing routers and switches from the market.

## Slide 11: The Investment Plan high-level deliverables for Networks
PROGRESS ON THE IMPLEMENTATION PLAN
Deliverable | Resp | Due Date | Status
Secure Enterprise Architecture Business Architecture Application Architecture Data Architecture Technology Architecture Implementation Plan | DHA / SITA | 31/03/2023 | To achieve greater alignment between Information Technology, Information Security & Business Strategies, and to guide the process of planning and designing the IT capabilities of DHA to meet desired organizational objectives and goals. SITA has offered to provide this service free of charge using their own personnel.
Application Management Full Redesign of Live Capture | DHA | 31/12/2021 | DHA has tasked SITA to publish a RFB for the Live Capture System. The project will take approximately 12 month after the service provider is appointed.
 |  | 31/03/2024 | Progressively move selected applications to secure on premise Tier III SITA Cloud hosted environment

## Slide 12: The Investment Plan high-level deliverables for Networks
PROGRESS ON THE IMPLEMENTATION PLAN
Deliverable | Resp | Due Date | Status
Information Systems Security (ISS) Security Operations Centre Capability (SOCC) Ensure that Information Systems are protected from cyber threats. | SITA | 31/03/22 | SITA is currently in the process of procuring and establishing a SOCC by end March 2022. The SOCC will assist with DHA’s overall Enterprise Operations Centre roadmap and provide the DHA with preventative measures and proactively detect the against cyber attacks. The onboarding of clients for the SOCC Services is projected to commence in Q1 of the FY 2022/23.

## Slide 13
IMPLEMENTATION PLAN FOR ROUTERS AND SWITCHES – KEY SITES
FY2022/23 | FY2023/24 | FY2024/25
Eastern Cape: East London Gqeberha, Mthatha | Gauteng: Harrison Street, Evaton, Akasia | Eastern Cape: Middledrift, Qonce/KWT, Aliwal North
Free State: Mangaung, Sasolburg, Phuthaditjaba | Limpopo: Polokwane, Modjadjiskloof, Malamulele | Free State: Botshabelo, Welkom, Kroonstad
Gauteng: Edenvale, Alberton, Randburg, Byron | Mpumalanga: Mbombela, Mashishing, Malelane | Gauteng: Centurion, Roodepoort, Springs
KwaZulu-Natal: Umngeni Road, Commercial Road, Ulundi | North-West: Mahikeng, Litchtenburg, Potchefstroom | KwaZulu-Natal: Newcastle, Ladysmith, Hluhluwe
Western Cape: Barrack Street, Khayelitsha, Malmesbury | Northern Cape: Kimberley, Calvinia, Galeshewe | Northern Cape: Kuruman, Prieska, Colesberg

## Slide 14
PROGRESS ON THE NETWORK IMPLEMENTATION PLAN
- ROUTERS AND SWITCHES
 | Routers | Switches
Financial Year | Replacement, Support & Maintenance | Replacement, Support & Maintenance
FY 2019/20 | 100 | 60
FY 2020/21 | 50 | 40
FY 2021/22 | 30 | 30
FY 2022/23 | 80 | 70
FY 2023/24 | 50 | 50
FY 2024/25 | 50 | 50
TOTAL | 360 | 300
Ongoing phased rollout since 2019/20 until 2020/25

## Slide 15: Monitoring & Support Hours
PROGRESS ON THE NETWORK IMPLEMENTATION PLAN
 | MONDAY-FRIDAY | WEEKENDS AND PUBLIC HOLIDAYS
Morning | 06:30, 08:00, 09:30, 11:30 | 06:30, 09:30, 11:30
Afternoon | 14:00, 15:30, 16:30, 17:30 | 14:00, 15:30, 17:30
For the period 18 October 2021 to 31 January 2022, all monitoring and support performed before 07:30 and after 16:00 on week days will be done remotely. The same is also true for weekends and public holidays, with the exception being the days where overtime for non-SMS members has been approved.
SITA monitors the DHA network 24/7/365 with the Network Monitoring System (NMS) tool.
Notes: Nevertheless, IS Senior Management has resolved to work out an after-hours rotation schedule for IS SMS members. However, a change management process will be required prior to implementation.
Part of the change management process will involve developing procedures for health checks. Such procedures should be intuitive to any IS senior manager regardless of the function/training that they may be currently capacitated for.

## Slide 16: Support Services
PROGRESS ON THE NETWORK IMPLEMENTATION PLAN
HALLMARK TEAM | CENTURION TEAM
DHA Data Centre Operations | DHA Data Centre Operations
DHA Information Systems Security | SITA Operational Security and Internet Services (OSIS)
DHA Networks | DHA Networks
DHA Applications Maintenance & Support | SITA Applications Maintenance & Support SITA officials from: SITA Networks (WAN and Internet Links) SITA Hosting (Power, Cooling, etc.) SITA Mainframe Application and SITA Infrastructure Support (NPR, MQ, MCS, BAS, PERSAL)
Notes: Nevertheless, IS Senior Management has resolved to work out an after-hours rotation schedule for IS SMS members. However, a change management process will be required prior to implementation.
Part of the change management process will involve developing procedures for health checks. Such procedures should be intuitive to any IS senior manager regardless of the function/training that they may be currently capacitated for.

## Slide 17: Governance
PROGRESS ON THE NETWORK IMPLEMENTATION PLAN
DHA/SITA Executive engagements are conducted on a quarterly basis
  Q3 engagement convened on 15 October 2021
  Q4 envisaged end-Dec 21 / early-Jan 2022
Project Management Methodology regular meeting conducted
  Regular SITA / DHA Coordination and Integration meetings
  Strategic Task Team meetings: Weekly
  Strategic Task Team Steering Committee: Monthly

## Slide 18
IMPLEMENTATION OF THE BRANCH APPOINTMENT BOOKING SYSTEM (BABS)

## Slide 19: Milestone Plan
PROGRESS ON THE IMPLEMENTATION PLAN FOR BRANCH APPOINTMENT BOOKING SYSTEM
Quality Assurance sign-off
User Acceptance Testing
Go live
System Security Test
Pilot
Milestone | Start date | End date
System Security Test | 25 Oct 2021 | 12 Nov 2021
Quality Assurance sign-off | 15 Nov 2021 | 19 Nov 2021
User Acceptance Testing (UAT) and Regression Testing | 22 Nov 2021 | 26 Nov 2021
Go-live (Release admin) | 29 Nov 2021 | 03 Dec 2021
Pilot (5 Offices) | 03 Dec 2021 | 31 March 2022
Status Summary – Green –The schedule is on track.

## Slide 20
IMPLEMENTATION PLAN FOR HEALTH FACILITIES TO REDUCE QUEUES IN OFFICES

## Slide 21
PROGRESS ON THE HEALTH FACILITIES IMPLEMENTATION PLAN
ROLL OUT STRATEGY | STRATEGY | CRITERIA | TYPE OF SERVICE | ROLLOUT STRATEGY TARGET | TIMELINE
FIRST PRIORITY | Permanent presence at health facilities where the birth rate was higher than 5 000 live births per year OR 400 births/month. | More than 5000 live births per year or more than 400 live births per month | Full time presence 7:30 – 15:30 | Optimisation of 41 Priority 1 health facilities | 31 MARCH 20
SECOND PRIORITY | Permanent presence at health facilities where the birth rate was between 5000 and 2000 actual live births per year or between 400 and 150 live births per month | Between 5000 and 2000 actual live births / year OR between 400 and 150 live births / month | Full time presence 7:30 – 15:30 | Optimisation of Priority 2 and priority 3 Health facilities (210) Priority 2 - 109 Health facilities | 31 MARCH 22
THIRD PRIORITY | Part time presence was proposed where the cutoff point was between2000 and 1000 / actual live births year OR between 150 and 75 births / month | Between 2000 and 1000 / actual live births year OR between 150 and 75 births / month | Part-time presence 08:00 – 13:00 | Priority 3 – 101 Health facilities | 31 MARCH 22
FOURTH PRIORITY | Roaming presence where actual live births are between 1000 and 500 / year OR between 75 and 50 births / month | Between 1000 and 500 / actual live births year OR between 75 and 50 births / month | Roaming service (4 to 5 health facilities per official) | Optimisation of Priority 4 and priority 5 Health facilities (127) Priority 4 - 48 Health facilities Priority 5 – 79 Health facilities | 31 MARCH 23
FIFTH PRIORITY | Roaming presence where actual live births are less than 500/ year OR between 1 and 50 births/ month | Less than 500 actual live births per year and less than 50 births per month. | Roaming service (4 to 5 health facilities per official) | Connect 1067 new Health facilities with uninterruptable network in order of priority Priority 4-47 Health facilities Priority 5 – 1020 health facilities | 31 MARCH 24
Implementation Strategy as per Classification of Health Facilities

## Slide 22: Birth Registration in Health Facilities
PROGRESS ON THE HEALTH FACILITIES IMPLEMENTATION PLAN
DHA has 160 Health Facilities(HF) with network connectivity, of these 121 can issue a birth certificate on the spot.
The 39 that cannot issue on the spot is due to inadequate IT equipment, including online verification scanners and human resources. We will be deploying additional IT equipment to these health facilities.
A bid specifications for network connectivity for additional HF has been finalised with SITA and they will be advertising before the 15th December 2021.
The revised bid specifications for mobile structures in health facilities that do not have space for DHA will be presented to BAC on the 1st December 2021.

## Slide 23
IMPLEMENTATION OF THE AUTOMATED BIOMETRIC IDENTIFICATION SYSTEM (ABIS)

## Slide 24
BACKGROUND
On 27 October 2020 the DHA made a presentation to the Portfolio Committee on the steps taken to rescue the ABIS project.
On 25 May 2021 the Department returned to the Portfolio Committee indicating that the DHA received all the necessary National Treasury approvals for the assignment/ceding of the ABIS contract to IDEMIA and the assignment/ ceding was concluded in March 2021.
IDEMIA undertook to deliver Phase 1 of the ABIS Project between – 01 May 2021 to December 2021.
The next slides provide an update on the above-mentioned commitment made to the Portfolio Committee.

## Slide 25
DHA/IDEMIA ABIS PROJECT EXECUTION
The DHA entered into an Amended and Restated Master Turnkey Solutions Agreement with IDEMIA in line with all the necessary conditions and scope of the project as per the initial tender requirements on 31 March 2021;
Hand over process between EOH and IDEMIA took place during the month of April 2021. During this period EOH handed over all ABIS documents produced during EOH tenure and update IDEMIA on the technical work performed;
The following tasks also commenced during the month of April 2021:
Project scoping & planning, establishment of Project structures/Work Streams, Governance and on-boarding of technical resources;
The project execution under IDEMIA commenced in May 2021 for completion of Phase 1 in December 2021.

## Slide 26
ABIS ARCHITECTURE

## Slide 27
ABIS PHASE 1 ROADMAP
Change Agent Network
Kick-Off
May 2021
Strategic Stakeholder Mobilisation
Operational Mobilisation
As-Is Analysis
UAT
Business Readiness Action Plans / Parallel RUN
Establish DHA ABIS PMO
Customised System
AS -IS
June 2021
Post Go-Live Support Model
Training Roll-out
To-Be Business Process
Change Impact
Nominate / Appoint / Induct
Business Preparation
URS
Vision and Case for Change
Stakeholder Matrix/ Mobilisation
Ongoing Change Management
Data Centres Ready
Ongoing Testing, Integration
Validation & Migration
Acceptance
Acceptance Tests
4 Wks Training prior to Go-Live
PHASE 2
Go-Live NOV 2021
Communication
SIT
BOIP / BOSS / IMS
We are Here
Data Migration
Impact
Business Requirements Validation
TO-BE
Delta2 Migration
Mobilise for Go-Live
BOIP / BOSS / IMS
Business Engagements
Training Approach/ Plan
Leadership Alignment
Business Readiness Action Plans
Impact Assessment
People
Process
Technology
Training Material Development
Training Report

## Slide 28
ABIS PROGRESS REPORT
DELAYS & CHALLENGES
  As indicated in the previous report to PCHA, whilst good progress has been made with the “Build Phase” following cessation to IDEMIA in April 2021, the programme still encountered serious constraints within two of its primary work streams which contributed to delays and not achieving the envisaged completion of Phase 1 by end October 2021. The Workstreams are:
  (i) Data Migration and;
  (ii) Application and Interfaces.
  Both have now been mitigated and by 19th November 2021 Stage 2 testing was assessed to be sufficiently complete to migrate to the next phase which is Stage 3 Testing – or also known as “Parallel Run”. This is the final process step towards pre-production sign-off and completion of ABIS Phase 1 to proceed to an implementation – or go-live status. This is of course, subject to audit of its compliance with the terms of the MSA and the Bid Specification Requirements.

## Slide 29
ABIS PROGRESS REPORT
Stage 3 Testing and Run
  Stage 3/ Parallel Run is required by terms of the MSA to be conducted for a period 20 business days and the system must conform to stipulated performance metrics and criteria for synchronization to existing HANIS reporting. The commencement of this run is underway and the targeted dated for completion is 23 December 2021.
  The performance of ABIS should (must) be an improvement of the existing performance derived from HANIS and it must support integration of various interface applications for Live Capture, NPR, IJS (Integrated Justice System), NIIS (National Immigration Identification System), ONLV (DHA On-line Verification) and CONLV (Commercial On-Line Verification) – the latter supporting the Banks.
  The successful conclusion of Phase 1 will only be established at the end of this period and it is likely that given the technical complexity of the ABIS build that this could over-run into early 2022, with Phase 2 and Phase 3 of the programme to commence immediately thereafter.

## Slide 30
To recommend that the Portfolio Committee on Home Affairs notes the progress on ABIS Phase 1 completion and progress made to resolve network connectivity and long queues at DHA Offices.
RECOMMENDATIONS

## Slide 31
Ndo livhuwa
Dankie
Ke a leboga
Ndiyabulela
Ngiyabonga
Thank you
Inkomu