## Slide 1
The National Red Meat Development Programme (NRMDP)’s Custom Feedlots programme
– response to challenges raised by Custom Feedlot beneficiaries and Livestock farmers.
Presentation to the Portfolio Committee on Agriculture, Land Reform and Rural Development
30 November 2021

## Slide 2
The NRMDP Background
Background : Virtual meeting of the Portfolio Committee on Agriculture, Land Reform and Rural Development was held on 26 May 2021, between DALRRD, ARC, NAMC, OBP and the Custom Feed Association representatives on the National Red Meat Development Programme (NRMDP).
Challenge: No existing legal institutional agreement to implement the project and challenges raised by the Custom Feedlot Association Representatives
Purpose: Update and report back to the Portfolio Committee on Agriculture, Land Reform and Rural Development by the Implementing Stakeholders on the challenges raised by the beneficiaries and the implementation of the NRMDP.
2

## Slide 3
The NRMDP Background Cont…
Implementing Stakeholders: DALRRD, NAMC, ARC, and OBP
Roles, Responsibility and Resources (Human capital, finances, etc.)
DALRRD: Funder, Project Mandate Owner
NAMC: Implementing Partner for completing the outstanding work of the transitional work over the 7 months period
ARC : Implementing Partner beyond the 7 months to 3 Years in partnership with NAMC & OBP
3

## Slide 4
Feedback and Status
The estimated budget projection for the next 3-year period is R308 323 126,30 and broken-down as follows:
FY 1 - R100 485 485,09, FY 2- R100 894 379,92 & FY 3 - R106 943 261,29
Start Date: The NAMC completion phase of the NRMDP Programme is scheduled to start on 1st December 2021
4

## Slide 5
Delays in signing of the SLA:
August 2020: the Supply Chain Unit consulted National Treasury to obtain clarity on deviation conditions in appointing NAMC as an implementing agent.
25 May 2021: National Treasury supported the deviation on the following conditions: that …
  the work is not already done by NAMC; and
  NAMC will not outsource the work.
In response to the above, the NAMC requested clarity on the condition that NAMC will not outsource the work, such that by the 3rd August 2021: National Treasury granted the deviation as long as no core work will be outsourced.
NAMC then revised the Transitional plan to align it with the National Treasury conditions; paving the way for SLA finalization by DALRRD.
5

## Slide 6
Feedback and Status Cont…
Current Status:
DALRRD and NAMC have since signed the SLA on the 10th November 2021 for the implementation of the NRMDP in Eastern Cape (EC), KwaZulu-Natal (KZN) and North West Provinces as part of NAMC finishing phase in response to the challenges raised by the Livestock farmers.
Funds allocation:
The transitional plan has a budget of R26 226 472,72 and the funds are already with the NAMC since they are surplus from the previous implementation phase.
The National Treasury has approved the rollover of funds.
191 Employees will be recruited for the implementation of the transitional plan.
6

## Slide 7
Project Governance and Reporting
Project Governance:
The Project Governance and Reporting is provided for in the Service Level Agreement.
There is strict governance to manage the Project where the Stakeholders will hold regular management and technical meetings to monitor the implementation.
The two committees namely: Project Steering Committee and Provincial Technical Committee are in place as spelt out in the SLA but will only be completed once the NAMC has reinstated its personnel for the Project, which process has already started.
7

## Slide 8
Project Governance and Reporting cont…
The first committee, the Provincial Technical Committee (PTC) – will meet monthly or as required to provide the Status and Milestone Reports of the NRMDP
The second committee, the Project Steering Committee (PSC) – will meeting Quarterly or as required to obtain Feedback status and / or Milestone Reports.
The Stakeholders will brief the Portfolio Committee as and when required.
8

## Slide 9
THANK YOU
9