## Slide 1: Standing Committee on Finance Audit Outcomes of the PIC

## Slide 2: Background
The purpose of the presentation is to appraise the Standing Committee on Finance on the corrective actions taken by the PIC to address the internal control deficiencies identified during the audit by the AGSA for the financial year 2020/21. The PIC received an unqualified audit opinion with findings for the financial year ended 31 March 2021. The AGSA identified significant control deficiencies which were highlighted in the audit report for the year ended 31 March 2021. The PIC is responding to the controls identified to ensure that all the deficiencies are mitigated and do not reoccur when the audit commences for the year ending 31 March 2022.

## Slide 3
Financial Systems and Internal Controls
Finding | Action Plan | Progress to Date | Timelines
Management did not implement effective financial systems of internal controls to ensure accurate disclosure notes to the financial statements. The preparation and review of the disclosure notes were not adequately reviewed. | Annual Financial Statements were previously presented once a year and disclosure notes were prepared and reviewed at the end of the financial year. Management has implemented controls to prepare and review disclosure notes more frequently. | In progress, the disclosure schedules were prepared and reviewed for December and will also be prepared and reviewed in February and March 2022. | In progress, the completion date is the end of March 2022.
 | Annual refresher training on changes relating to International Financial Reporting Framework (IFRS) has been completed. This will ensure staff is up to date with all changes and that those changes are implemented in the AFS for 2022. | IFRS training took place in September 2021. | Completed
 | A detailed assessment of the impact the new accounting standard will have on the PIC AFS has been performed and implemented for the 2022 AFS. | PIC is currently utilizing the latest IFRS checklist to ensure the AFS comply with IFRS. | Completed

## Slide 4: Due Diligence and PEPs
Finding | Action Plan | Progress to Date | Timelines
Management did not ensure that enhanced due diligence (EDD) is performed on the identified Politically Exposed Persons (PEPs) as required by the applicable PEP policy. This is due to misalignment between the PEP policy and FICA Risk Management and Compliance Programme (guideline). The PEP policy requires EDD to be performed for all PEPs identified, whereas the guideline requires EDD to be performed when PEPs are identified as high risk. | The finding was based on the 2019 PEP Policy, an updated policy that addresses the shortfalls will be approved by the Board before the end of the financial year. | In progress, a new policy addressing the risk identified by AGSA has been updated and is due for approval by the Board in March 2022. | In progress, the completion date is March 2022.

## Slide 5: Irregular Expenditure
Finding | Action Plan | Progress to Date | Timelines
Effective and appropriate steps were not taken to prevent irregular expenditure disclosed in note 38 to the annual financial statements, as required by section 51(1)(b)(ii) of the PFMA. | Preventative controls are in place to prevent irregular expenditure from occurring. | The controls in place were found to be working effectively by the AGSA, and additional training would need to be provided to staff. Training on the PFMA and Procurement Policy is scheduled for February 2022. | In progress, the completion date is end of February 2022