## Slide 1
presentation to PORTFOLIO COMMITTEE on home affairs
Performance & EXPENDITURE report for q1, q2 and q3 of 2021/22
15 FEBRUARY 2022

## Slide 2
PRESENTATION OUTLINE
Purpose
2. Vision, Mission and Value Statement
3. DHA Mandate
4. DHA Outcomes
5. DHA Performance for Quarter 1, 2 & 3 of 2021
6. Financial Information
7. Challenges
8. Way Forward

## Slide 3
PURPOSE OF THE PRESENTATION
To present the 2021/2022 1st, 2nd and 3rd quarterly performance reports and budget versus expenditure reports of the Department of Home Affairs to the Portfolio Committee on Home Affairs

## Slide 4
Vision
A South Africa where identity, status and citizenship are key enablers of citizen empowerment and inclusivity, economic development and national security
Mission
The DHA carries out its mission in line with its commitment to citizen empowerment and inclusivity, economic development and national security, by:
Being an efficient and secure custodian of citizenship and civil registration
Securely and strategically managing international migration
Efficiently managing asylum seekers and refugees
Efficiently determining and safeguarding the official identity and status of persons
Value Statement
The Department of Home Affairs is committed to being:
People-centered and caring
Patriotic
Professional and showing leadership
Effective, efficient and innovative
Ethical and having integrity
Security conscious
Development oriented

## Slide 5
DHA ‘s services are divided into two broad categories: Civic Services and Immigration Services
dHA MANDATE
Mandate 1
Management of citizenship and civil registration
Mandate 2
Management of international migration
Mandate 3
Management of refugee protection

## Slide 6
The Department of Home Affairs has identified the following outcomes for the 2020 to 2025 period:
Secure management of international migration resulting in South Africa’s interests being served and fulfilling international commitments
Secure and efficient management of citizenship and civil registration to fulfil constitutional and international obligations
Efficient asylum seeker and refugee system in compliance with domestic and international obligations
Secure population register to empower citizens, enable inclusivity, economic development and national security
DHA positioned to contribute positively to a capable and developmental state
dHA Outcomes

## Slide 7
DHA OVERALL APP PERFORMANCE FOR QUARTER 1
The Department of Home Affairs (DHA) had 27 targets planned for the 1st quarter of 2021/22 financial year of which 19 (70%) were achieved and 8 (30%) targets were not achieved.
Chart: DHA quarter 1 performance Period April to June
| Achieved | Not achieved
 | 0.69 | 0.31

## Slide 8
PERFORMANCE PER PROGRAMME FOR Q1
Programme | Planned targets | Achieved | % | Not achieved | %
1. Administration | 14 | 11 | 79% | 3 | 21%
2. Citizen Affairs | 4 | 4 | 100% | 0 | 0%
3. Immigration Affairs | 3 | 1 | 33% | 2 | 67%
4 Institutional support and Transfers (BMA) | 6 | 3 | 50% | 3 | 50%
TOTAL | 27 | 19 | 70% | 8 | 30%

## Slide 9
APP PERFORMANCE COMPARISON FOR QUARTER1 OF 2021-22 AND QUARTER1 OF 2020-21
Chart: 
| Q1 - 2021-22 | Q1 - 2020-21
Achieved | 0.7 | 0.29
Not achieved | 0.3 | 0.71
The department achieved an increase of 41% in comparison to the same period in 2020-21 financial year

## Slide 10
DHA OVERALL APP PERFORMANCE FOR QUARTER 2
The DHA had 30 targets planned for the 2nd quarter of the 2021/22 financial year of which 24 (80%) were achieved and 6 (20%) targets were not achieved.
Chart: DHA quarter 2 performance Period July to September
| Achieved | Not achieved
 | 0.8 | 0.2

## Slide 11
PERFORMANCE PER PROGRAMME FOR Q2
Programme | Planned targets | Achieved | % | Not achieved | %
1. Administration | 17 | 15 | 88% | 2 | 12%
2. Citizen Affairs | 5 | 5 | 100% | 0 | 0%
3. Immigration Affairs | 3 | 2 | 67% | 1 | 33%
4 Institutional Support and Transfers (BMA) | 5 | 2 | 40% | 3 | 60%
TOTAL | 30 | 24 | 80% | 6 | 20%

## Slide 12
APP PERFORMANCE COMPARISON FOR QUARTER 2 OF 2021-22 AND QUARTER 2 OF 2020-21
In the 2021/22 financial year the department improved its performance by 21% when compared with the same period in the 2020-21 financial year.
Chart: 
| Q2-2021-22 | Q2-2020-21
Achieved | 0.8 | 0.59
Not achieved | 0.2 | 0.41

## Slide 13
PERFORMANCE COMPARISON FOR QUARTER 1 AND QUARTER 2 OF 2021-22
BRANCH | Quarter 1 |  |  |  |  | Quarter 2 |  |  |  | 
 | PLANNED TARGETS | ACHIEVED | % | NOT ACHIEVED | % | PLANNED TARGETS | ACHIEVED | % | NOT ACHIEVED | %
CS | 4 | 4 | 100% | 0 | 0% | 5 | 5 | 100% | 0 | 0%
IMS | 3 | 1 | 33% | 2 | 67% | 3 | 2 | 67% | 1 | 33%
BMA | 6 | 3 | 50% | 3 | 50% | 5 | 2 | 40% | 3 | 60%
IS | 1 | 1 | 100% | 0 | 0% | 3 | 2 | 67% | 1 | 33%
IPS | 4 | 2 | 50% | 2 | 50% | 5 | 5 | 100% | 0 | 20%
HRM&D | 1 | 1 | 100% | 0 | 0% | 1 | 1 | 100% | 0 | 0%
CC&SS | 4 | 4 | 100% | 0 | 0% | 4 | 4 | 100% | 0 | 0%
DG’s O | 4 | 3 | 75% | 1 | 25% | 4 | 3 | 75% | 1 | 25%
TOTAL | 27 | 19 | 70% | 8 | 30% | 30 | 24 | 80% | 6 | 20%
The department improved its performance by 10% in Q2 when compared with the Q1 performance of the 2021-22 financial year.
Improved
Unchanged
Regressed

## Slide 14
DHA OVERALL PERFORMANCE FOR QUARTER 3
Chart: DHA quarter 1 performance Period April to June
There were 28 targets planned for the 3rd quarter of the 2021/22 FY.
Of these 28 targets, 20 were achieved equating to a 71% achievement rate and 8 (29%) targets were not achieved. This is depicted in the graph below
Chart: DHA quarter 3 performance Period July to September
Chart: DHA quarter 3 performance Period Oct to Dec
| Achieved | Not achieved
 | 0.71 | 0.29

## Slide 15
PERFORMANCE PER PROGRAMME
Programme | Planned targets | Achieved | % | Not achieved | %
1. Administration | 16 | 12 | 75% | 4 | 25%
2. Citizen Affairs | 4 | 3 | 75% | 1 | 25%
3. Immigration Affairs | 3 | 3 | 100% | 0 | 0%
4. Institutional Support and Transfers | 5 | 2 | 40% | 3 | 60%
TOTAL | 28 | 20 | 71% | 8 | 29%

## Slide 16
APP PERFORMANCE COMPARISON FOR QUARTER 3 OF 2021-22 AND QUARTER 3 OF 2020-21
Chart: 
| 2020-21 | 2021-22
Achieved | 0.59 | 0.71
Not achieved | 0.41 | 0.29

## Slide 17
PERFOFORMANCE COMPARISON FOR QUARTER 2 AND QUARTER 3 OF 2021-22
Chart: 
The department performance have dropped by 9% in Q3 when compared to Q2 of the 2021-22 financial year.
BRANCH | Quarter 2 |  |  |  |  | Quarter 3 |  |  |  | 
 | PLANNED TARGETS | ACHIEVED | % | NOT ACHIEVED | % | PLANNED TARGETS | ACHIEVED | % | NOT ACHIEVED | %
CS | 5 | 5 | 100% | 0 | 0% | 4 | 3 | 75% | 1 | 25%
IMS | 3 | 2 | 67% | 1 | 33% | 3 | 3 | 100% | 0 | 0%
BMA | 5 | 2 | 40% | 3 | 60% | 5 | 2 | 40% | 3 | 60%
IS | 3 | 2 | 67% | 1 | 33% | 3 | 1 | 33% | 2 | 67%
IPS | 5 | 5 | 100% | 0 | 0% | 4 | 3 | 75% | 1 | 25%
HRM&D | 1 | 1 | 100% | 0 | 0% | 1 | 1 | 100% | 0 | 0%
CC&SS | 4 | 4 | 100% | 0 | 0% | 4 | 4 | 100% | 0 | 0%
DG’s O | 4 | 3 | 75% | 1 | 25% | 4 | 3 | 75% | 1 | 25%
TOTAL | 30 | 24 | 80% | 6 | 20% | 28 | 20 | 71% | 8 | 29%
Improved
Unchanged
Regressed

## Slide 18
PERFORMANCE OVER THE THREE QUARTERS OF 2021-22
Chart: 
| Quarter 1 | Quarter 2 | Quarter 3
Achieved | 0.7 | 0.8 | 0.71
Not achieved | 0.3 | 0.2 | 0.29

## Slide 19
Performance by programme (Q1 – Q3)

## Slide 20
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET: 23 selected ports of entry with biometric movement control system (BMCS) implemented as per approved specifications |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
Service provider contracted | Procurement of IT equipment finalised | 13 selected ports of entry with biometric movement control system (BMCS) implemented as per approved specifications
Achieved The Service provider was contracted. | Not achieved Quotations were sourced from service provider; however, the procurement was not finalized. Reasons for under achievement Procurement process through Work Orders took longer than anticipated due to the introduction of reasonableness testing for such procurements by National Treasury. Way forward/Remedial action Procurement challenges escalated to EXCO as there was less chance of the target being met. | Not achieved Quotations were sourced from service provider; however, the procurement was not finalized. Reasons for under achievement The delay to procure IT equipment affected the roll out of BMCS at the ports. Way forward/Remedial action BMCS will be implemented to selected land ports (production testing) in the first quarter of the new financial year depending on the receipt of IT equipment. Once Port Control is satisfied with the system at the land ports, full rollout will proceed to all earmarked ports during the 2022/23 financial year.

## Slide 21
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET: e-Visa phase 2 module developed onto live capture and deployed in quality assurance (QA) environment: Temporary Residence Visas Critical skills visa and Business visa Permanent Residence Permits General work, section 26(a); Critical skills, section 27(b); Business, section 27(c) |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
N/A | Business requirement specifications for e-Visa phase 2 approved by DDG: IMS | Technical specifications for e-Visa phase 2 approved by DDG: IS
N/A | Achieved Business requirements specifications were approved by DDG: IMS. | Achieved The following types of permit technical specifications were approved as part of TRP (tourist):- Temporary Residence Visas Critical skills visa and Business visa General work, section 26(a); Critical skills, section 27(b); Business, section 27(c Technical specification for Permanent Residence Permits (PRP)

## Slide 22
PROGRAMME 1: ADMINISTRATION |  | 
Annual Target: Asylum Seeker and Refugee system development onto live capture - Prototype |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
N/A | User requirements approved by DDG: IMS | Technical specifications approved by DDG: IS
N/A | Achieved User requirements were approved by DDG: IMS | Not Achieved Awaiting the appointment of a Service Provider after the initial tender cancellation. Reasons for under achievement The technical specifications were not developed because the service provider was not appointed as the tender was cancelled. Way forward/Remedial action Re-advertisement of the Tender through SITA - The process of appointing the service provider through SITA is in progress. SITA indicated that the appointment of a service provider will be done before the end of the current financial year 2021/22.

## Slide 23
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET : DHA Bill submitted to Cabinet for approval |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
Final draft of DHA Bill submitted to Cabinet to request approval for public consultation | DHA Bill gazetted for public consultation | Consultation with Clusters on revised Bill (JCPS and GSCID)
Not Achieved The draft Legal Opinion was received from Office of the Chief State Law Advisor (OCSLA); however, the department needed to provide further information to the OCSLA prior to the finalisation of the Legal Opinion. The Bill was revised in line with the draft Legal Opinion. Reasons for under achievement Delays in the revision of the Bill necessitated by the need for further engagement with the OCSLA on the draft Legal Opinion. Way forward/Remedial action A revised Bill, incorporating the legal opinion, will be submitted to the Minister for approval during the second quarter. | Not Achieved A revised Bill, incorporating the legal opinion received from Office of the Chief State Law Advisor, was presented to EXCO on 28 September 2021. Reasons for under achievement Delay in the finalisation of the legal opinion. Way forward/Remedial action The Bill will be submitted to the Minister for approval and submission to Cabinet. | Not Achieved Bill was submitted to Minister on 22 October 2021 to consider and approve the Bill, as well as the and Cabinet Memo. Minister directed that the Bill be presented during Ministerial Management Meeting (MMM) of 15 December 2021. The Bill was removed from the Agenda of MMM (on 15 December 2021) due to time constraints. Reasons for under achievement Delay in the finalisation of the legal opinion. Way forward/Remedial action The Bill will be re-submitted to the next MMM for presentation and approval.

## Slide 24
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET : DHA Communication Strategy and Plan implemented through: 20 Media engagements 6 Outreach engagements 3 Campaigns |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
5 Media engagements 1 Campaign 2 Outreach Engagements | 5 Media engagements 1 Campaign 2 Outreach Engagements | 5 Media engagements 1 Outreach Engagement 1 Campaign
Achieved 15 Media engagements conducted. 4 Outreach engagements conducted. 1 Campaign conducted on Green Paper on Marriages in SA | Achieved 11 Media engagements /Advisories were conducted. 5 Outreach engagements were conducted. 2 Campaigns were conducted on ID Collection and Community TV infomercial. | Achieved 13 Media engagements conducted. 7 Outreach engagements conducted on Green Paper on Marriages in South Africa in provinces. 3 Campaigns conducted on second phase ID Collection, Community TV infomercials and DHA Operational Plan during festive season.

## Slide 25
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET: Official Identity Management Policy (OIDM) submitted to Cabinet for approval |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
Final SEIAS Report submitted to DPME for approval | Official Identity Management Policy submitted to the GSCID and ESEID Clusters for recommendation to Cabinet. | Official Identity Management Policy submitted to the JCPS Cluster for recommendation to Cabinet
Achieved The final SEIAS for the Official Identity Management Policy was submitted to the DMPE. | Achieved The Official Identity Management Policy was tabled at the GSCID, ESEID and SPCHD Clusters and recommended to Cabinet for approval. | Achieved The Official Identity Management Policy was submitted to the JCPS Cluster for approval and submission to Cabinet. While the Policy was submitted to the JCPS Cluster in December 2021 as per the target, the meeting was postponed to January / February 2022.

## Slide 26
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET : Green Paper on the management of Citizenship, International Migration and Refugee Protection submitted to Cabinet to request approval for public consultation |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
Draft Green Paper on the Management of Citizenship, International Migration and Refugee Protection submitted to Minister for approval | SEIAS Report submitted to DPME for approval Interdepartmental Workshop with JCPS and GSCID departments convened to consider the Draft Green Paper on the management of Citizenship, International Migration and Refugee Protection | Second Draft of the Green Paper on the Management of Citizenship, International Migration and Refugee Protection submitted to the JCPS and GSCID clusters for recommendation to Cabinet
Achieved The Green Paper on the Management of Citizenship, International Migration & Refugee Protection was submitted to Minister for approval. | Achieved The SEIAS Report for the Green Paper on the Management of Citizenship, International Migration & Refugee Protection was submitted to DPME for approval. The Interdepartmental Workshop with government departments (including JCPS and GSCID departments) was convened on the 02nd September 2021. | Achieved The Green Paper on Citizenship, International Migration & Refugee Protection was tabled at the GSCID Cluster Meeting. The meeting recommended that it be tabled at Cabinet. While the Green Paper was submitted to the JCPS Cluster in December 2021 as per the target, the meeting was postponed to January / February 2022.

## Slide 27
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL Target: Revised Service Delivery Model approved by Minister |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
Service provider for development of Service Delivery Model appointed | 4 Dimensions of Service Delivery Model (SDM) reviewed and approved by DDG: IPS | 5 Dimensions of Service Delivery Model reviewed and approved by DDG: IPS
Not achieved The Bid Adjudication Committee (BAC) approved the terms of reference (TOR) for the appointment of the service provider. The TOR were subsequently published, inviting service providers to submit bids. Reasons for under achievement Non-availability of the Bid Evaluation Committee (BEC) members due to competing SCM priorities. Way forward/Remedial action Evaluation of bids and appointment of the service provider. | Achieved Analysis and background research on the 4 dimensions of the SDM were conducted and 4 dimensions of the SDM reviewed and approved by the DDG: IPS. | Not achieved Service provider appointed in September 2021 and the draft SLA was finalized on the 15th November 2021 which was shared with the service provider. The meeting was held with service provider in November 2021 in which the pricing schedule was discussed and the service provider to make inputs on the SLA for finalization and signing of the SLA. The service provider cannot commence with the work until the SLA has been signed by both parties. Reasons for under achievement Delays in evaluation of the tender which led to the delay in the appointment of the service provider. Delays in finalization of the SLA which resulted in the delay in commencement of the project by the service provider. Way forward/Remedial action Finalization and signing of the SLA by both parties.

## Slide 28
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET: DHA Access Model implemented through revised Footprint Optimisation Plan / User Asset Management Plan (U-AMP) submitted to DPW&I for submission to National Treasury |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
DHA Footprint Development Strategy (Infrastructure Plan) approved by the DG in line with the approved Access Model | User Asset Management Plan (U-AMP) revised in line with the Footprint Development Strategy (submitted to DDG: IPS for consideration) | User Asset Management Plan (U-AMP), developed in line with DHA Footprint Development Strategy, costed and approved by DDG: IPS
Not achieved DHA Footprint Strategy in line with the approved DHA Hybrid Access Model was drafted but not submitted to the DG for approval as consultations with relevant stakeholders were not finalized. Reasons for under achievement Delays in the finalisation of consultations due to inadequate human capacity and non-availability of some stakeholders. Way forward/Remedial action Conduct consultative workshops with all relevant stakeholders and submit the footprint strategy to the DG for approval. | Achieved The revised User Asset Management Plan (U-AMP) was revised and submitted to DDG: IPS. | Achieved The target was achieved during Q2 in which DDG:IP&S considered and approved the U-AMP. The approved U-AMP will be updated once consultative workshops with provinces are completed for submission to DPW&I and National Treasury during Q4.

## Slide 29
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET: 13 Awareness sessions on gender-based violence and femicide, gender and disability mainstreaming conducted |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
3 awareness sessions on gender-based violence and femicide, gender and disability mainstreaming conducted. | 3 awareness sessions on gender-based violence and femicide, gender and disability mainstreaming conducted. | 4 awareness sessions on gender-based violence and femicide, gender and disability mainstreaming conducted.
Achieved The Department held 4 awareness sessions focusing on the following: 7 April 2021 - to socialise key functionaries from different units within the Department, on the content of the National Strategic Plan on Gender Based Violence and Femicide (NSP on GBVF), its ramifications on DHA Mandate as well as to discuss reporting requirements. 20 May 2021 - to sensitise the Gauteng Province officials on the rights of LGBTIQIA+ persons in the delivery of DHA services. 28 May 2021 - to sensitise Northern Cape Officials on DHA Sexual Harassment Policy and the content of the NSP on GBVF. 7 June 2021 - with Western Cape Officials to discuss the rights of LGBTIQA+ persons and how such rights interface with DHA services. | Achieved The Department held 3 awareness sessions focusing on the following: 11 August 2021 - focusing on the following topic: Positioning yourself for the next big opportunity 19 August 2021 - focusing on Gender Based Violence and Femicide challenges faced by the LGBTIQA+ Community. 31 August 2021 - focusing on the following topic: “#Womandla: DHA Women Forging ahead”. | Achieved The Department held the following awareness sessions: DHA Disability Forum held on 4 – 5 October 2021. North West Men’s Forum held on 29 October 2021 focusing on the role of men as partners in the fight against GBV. KZN Men’s Forum held on 12 November 2021 focusing on the role of men as partners in the fight against GBV. Free State Men’s Forum held on 18 November 2021 focusing on the role of men as partners in the fight against GBV.

## Slide 30
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET: 1 (One consolidated report on process evaluation to focus on the 6 identified areas) |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3TARGET
Information gathering conducted on BMA in identified ports of entry (ORTIA, King Shaka, Lebombo, Maseru, Cape Town International Airport and Beitbridge - Report on part 1 of process evaluation signed off by DDG: CCSS). | Report signed off by DDG: CCSS on process evaluation conducted on BMA at ORTIA and King Shaka (Part 2 of process evaluation). | Report signed off by DDG: CCSS on process evaluation conducted at POEs for BMA at King Shaka International Airport and Maseru Border Post during Q3 (Part 3 of process evaluation)
Achieved Information gathering was conducted on BMA process in identified ports of entry (ORTIA, King Shaka, Lebombo, Maseru, Cape Town International Airport and Beitbridge). Report on part 1 of process evaluation signed off by DDG: CCSS). | Achieved Additional information was gathered through engagements with SSA and SAPS and report on part 2 of process evaluation was signed off by DDG: CCSS. | Achieved Process review conducted at two ports of entry (Maseru Border Post and King Shaka International Airport) and report signed of by DDG: CC & SS

## Slide 31
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET: 50% of reported cases on fraud and corruption finalised within 90 working days |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
50% of reported cases on fraud and corruption finalised within 90 working days | 50% of reported cases on fraud and corruption finalised within 90 working days | 50% of reported cases on fraud and corruption finalised within 90 working days
Achieved Achieved 60% Received 45 Finalised 27 | Achieved Achieved 69% Received 55 Finalised 38 | Achieved Achieved 66% Received 89 Finalised 59

## Slide 32
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET: 40 Threat and Risk Assessments (TRAs) conducted in accordance with the requirements of Minimum Information Security Standards (MISS) and / or Minimum Physical Security Standards (MPSS |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
10 Threat and Risk Assessments (TRAs) conducted in accordance with the requirements of Minimum Information Security Standards (MISS) and / or Minimum Physical Security Standards (MPSS). | 10 Threat and Risk Assessments (TRAs) conducted in accordance with the requirements of Minimum Information Security Standards (MISS) and / or Minimum Physical Security Standards (MPSS). | 10 Threat and Risk Assessments (TRAs) conducted in accordance with the requirements of Minimum Information Security Standards (MISS) and / or Minimum Physical Security Standards (MPSS).
Achieved 10 Threat and Risk Assessments (TRAs) were conducted in accordance with the requirements of Minimum Information Security Standards (MISS) and / or Minimum Physical Security Standards (MPSS). | Achieved 14 Threat and Risk Assessments (TRAs) were conducted in accordance with the requirements of Minimum Information Security Standards (MISS) and/ or Minimum Physical Security Standards( MPSS). | Achieved 16 Threat and Risk Assessments (TRAs) conducted in accordance with the requirements of Minimum Information Security Standards (MISS) and/ or Minimum Physical Security Standards( MPSS).

## Slide 33
PROGRAMME 1:ADMINISTRATION |  | 
ANNUAL TARGET: 300 vetting files referred to State Security Agency (SSA) for evaluation |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
75 vetting files referred to State Security Agency (SSA) for evaluation). | 75 vetting files referred to State Security Agency (SSA) for evaluation). | 75 vetting files referred to State Security Agency (SSA) for evaluation).
Achieved 99 vetting files were referred to State Security Agency (SSA) for evaluation. | Achieved 86 vetting files were referred to State Security Agency (SSA) for evaluation. | Achieved 94 vetting files referred to State Security Agency (SSA) for evaluation.

## Slide 34
programme 2: civic affairs

## Slide 35
PROGRAMME 2: CITIZEN AFFAIRS |  | 
ANNUAL TARGET: 700 000 births registered within 30 calendar days |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
100% fully functional front offices – 177 980 75% functional front offices – 133 485 50% fully functional front offices – 88 990 33.3 % functional front offices – 59 267 Level 5 No service to be rendered Revised Quarter 1 Target 166 680: 100% capacity from 1 April to 15 June. Reduced capacity to 50% from 16 to 30 June 2021 due to implementation of lockdown levels 3 & 4. | 100% fully functional front offices – 178 596 75% functional front offices – 133 947 50% fully functional front offices – 89 298 33.3 % functional front offices – 59 473 Level 5 No service to be rendered Revised Quarter 2 Target 95 676: 50% capacity from 1 July to 16 September. Increased capacity to 75% from 17 September 2021. | 100% fully functional front offices – 168 424 75% functional front offices – 126 318 50% fully functional front offices – 84 212 33.3 % functional front offices – 56 085 Level 5 No service to be rendered Revised Quarter 3 Target 165 751: 75% capacity from 01 – 06 October 2021. (Target = 8 020) 100% capacity from 07 October to 31 December 2021. (Target = 157 731)
Achieved 207 935 Births were registered within 30 days. | Achieved 199 708 Births were registered within 30 days. | Achieved 188 306 Births registered within 30 days.

## Slide 36
PROGRAMME 2: CITIZEN AFFAIRS |  | 
Annual Target: 1 600 000 smart ID cards issued to citizens (including naturalised and holders of permanent residence permits) 16 years of age and above Scenario Planning – 1 566 985 smart ID cards issued to citizens (including naturalised and holders of permanent residence permits) 16 years of age and above |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
Revised Quarter 1 Target 381 920: 100% capacity from 1 April to 15 June. Capacity reduced to 50% from 16 to 30 June 2021 due to implementation of lockdown level 3 & 4. | Revised Quarter 2 Target 214 063: 50% capacity from 1 July to 16 September. Increased capacity to 75% from 17 September 2021. | Revised Quarter 3 Target 362 159: 75% capacity from 01 – 06 October 2021; 100% capacity from 07 October to 31 December 2021)
Achieved The target for Quarter 1 was 381 920. The Department issued a total of 518 312 Smart ID cards which was an overachievement of 136 392 (35,71%). | Achieved The target for Quarter 2 was 214 063. The Department issued a total of 400 284 Smart ID cards which was an overachievement of 186 221 (86,99%). | Achieved The target for Quarter 3 was 362 159. The branch issued a total of 548 562 Smart ID cards which was an overachievement of 186 403 (51,5%). (75% capacity from 01 – 06 October 2021; 100% capacity from 07 October to 31 December 2021)

## Slide 37
PROGRAMME 2: CITIZEN AFFAIRS |  | 
ANNUAL TARGET | QUARTER 1 TARGET | Progress for Quarter 1
90% of machine readable adult passports (new live capture system) issued within 13 working days for applications collected and processed within the RSA (from date of receipt of application until passport is scanned at office of application). | Level 4 & 5 No service During level 3 the passport target will be 90% of adult passports issued within 42 working days. During level 2 the passport target will be 90% of adult passports issued within 32 working days. During level 1 the passport target will be 90% of adult passports issued within 13 working days. | Level 4: No Target 2 540 passports issued. (These passports were received at the offices and clients were allowed to collect documents though no new applications were allowed during Lockdown Level 4). Level 3: Achieved 99,52% of machine readable adult passports were issued within 42 working days. Level 2: Achieved 97,99% of machine readable adult passports were issued within 32 working days. Level 1: Achieved 91,95% of machine readable adult passports were issued within 13 working days.

## Slide 38
PROGRAMME 2: CITIZEN AFFAIRS |  | 
ANNUAL TARGET | QUARTER 2 TARGET | Progress for Quarter 2
90% of machine readable adult passports (new live capture system) issued within 13 working days for applications collected and processed within the RSA (from date of receipt of application until passport is scanned at office of application). | During level 3 the passport target will be 90% of adult passports issued within 42 working Days. During level 2 the passport target will be 90% of adult passports issued within 32 working days. During level 1 the passport target will be 90% of adult passports issued within 13 working days. | Achieved Level 3: 99,52% of machine readable adult passports passports were issued. Level 2: 99,26% of machine readable adult passports were issued within 42 working days. Level 1: 99,28% of machine readable adult passports were issued within 32 working days.

## Slide 39
PROGRAMME 2: CITIZEN AFFAIRS |  | 
ANNUAL TARGET: 90% of machine readable adult passports (new live capture system) issued within 13 working days for applications collected and processed within the RSA (from date of receipt of application until passport is scanned at office of application). |  | 
QUARTER 3 TARGET | Reasons for under achievement Lockdown Level 1 (07 Oct – 31 Dec 2021) | Way forward
From 01-06 October 2021; Level 2 the passport target was; 90% of adult passports issued within 32 working Days Achieved Level 2: 99,28% issued within 32 working days (5649 issued within 32 working days and 41 above. The total issued was 5690). | During quarter 2, the Branch observed and reported an increased number of cases where hand over messages were not received by GPW. This resulted in lost batches wherein application data had to be re-submitted. The impact manifested in quarter three wherein batch errors occurred affecting the turnaround time resulting in applications processed outside the specified turnaround time. Passport applications stuck on ACP for more than 3 days resulting in passports being issued outside the specified turn-around time. Inability of GPW to handover passports on the system to Passport Dispatch Centre for quality assurance and dispatch as a result of duplicated print requests that were sent. Covid-19 infections at GPW resulting in closure. Water outages at GPW resulting in office closure. Non-availability of bins at SKYNET resulting in delayed dispatching. | Use of DHA drivers to deliver passports to local offices around Johannesburg and Tshwane metros to reduce the turn-around time. Engagement of stakeholders to deal with stuck passport applications. Daily monitoring of performance at Image enhancement. Issuance of exception reports to indicate volumes stuck on ACP as well as Image Enhancement
From 07 October – 31 December 2021; Level 1 the passport target was; 90% of adult passports issued within 13 working Days Not Achieved Level 1: 77,41% issued within 13 working days (98 218 issued within 13 working days and 28 665 issued above. The total issued was 126 883) |  | 

## Slide 40
PROGRAMME 2: CITIZEN AFFAIRS |  | 
ANNUAL TARGET: Marriage Policy submitted to Cabinet for approval |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
Marriage Policy Colloquium convened with key representative of all sectors (Religious, Cultural and Gender interest groups) | Draft Marriage Policy, incorporating public comments, submitted to Minister for approval Marriage Policy Colloquium convened and final SEIAS report submitted to DPME for approval | Draft Marriage Policy submitted to JCPS and Social Clusters for recommendation to Cabinet
Achieved The Minister hosted a National Colloquium on the 28th of June with various stakeholders. Leading up to that the Department held various consultative engagements with traditional and religious leaders, government departments, civil society groups, chapter 9 institutions and various lobby groups. | Achieved The draft Marriage Policy (White Paper) was submitted to DDG: CS for approval and subsequently to Minister for consideration and approval. Achieved The Minister hosted a National Colloquium on 28 June 2021. The SEIAS report was issued during September 2021 and was submitted to DPME. | Achieved The Draft Marriage Policy and presentation was submitted to JCPS and Social Cluster for recommendation to Cabinet.

## Slide 41
programme 3: IMMIGRATION affairs

## Slide 42
PROGRAMME 3: IMMIGRATION AFFAIRS |  | 
ANNUAL TARGET: 220 law enforcement operations/ inspections conducted to ensure compliance with immigration legislation |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
55 law enforcement operations/ inspections conducted to ensure compliance with immigration legislation. | 55 law enforcement operations/ inspections conducted to ensure compliance with immigration legislation. | 55 law enforcement operations/ inspections conducted to ensure compliance with immigration legislation
Achieved 75 law enforcement operations/ inspections conducted. | Achieved 81 law enforcement operations/ inspections were conducted. | Achieved 74 law enforcement operations/ inspections conducted to ensure compliance with immigration and departmental legislation

## Slide 43
PROGRAMME 3: IMMIGRATION AFFAIRS |  | 
ANNUAL TARGET:85% of critical skills visas adjudicated within 4 weeks for applications processed within the RSA (from date of receipt of application until outcome is in scan at VFS Centre -office of application) |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
85% of critical skills visas adjudicated within 4 weeks for applications processed within the RSA (from date of receipt of application until outcome is in scan at VFS Centre - office of application) | 85% of critical skills visas adjudicated within 4 weeks for applications processed within the RSA (from date of receipt of application until outcome is in scan at VFS Centre - office of application) | 85% of critical skills visas adjudicated within 4 weeks for applications processed within the RSA (from date of receipt of application until outcome is in scan at VFS Centre - office of application
Not achieved 68.5% (855 out of 1 248) of critical skills visas were adjudicated within 4 weeks for applications processed within the RSA. Reasons for under achievement Target not achieved due to the delays with verification of visas issued abroad especially where some of those missions were under lockdown Way forward/Remedial action Requested DG to authorise the revised “verification process” which will assist in reducing the delays experienced when verifying visas issued abroad. If approved by DG the process will significantly reduce the delays caused by verification of visas issued abroad. | Not achieved 35.4% (377 out of 1 066) of critical skills visas were adjudicated within 4 weeks for applications processed within the RSA. Reasons for under achievement Staff were working on rotation thereby making the 4 week turnaround time too short to work within the rotation schedule Way forward/Remedial action The return of all officials to work. | Achieved 85.3% (1 160 out of 1 360) of critical skills visas adjudicated within 4 weeks for applications processed within the RSA (from date of receipt of application until outcome is in scan at VFS Centre – office of application)

## Slide 44
PROGRAMME 3: IMMIGRATION AFFAIRS |  | 
ANNUAL TARGET: 90% of business and general work visas adjudicated within 8 weeks for applications processed within the RSA (from date of receipt of application until outcome is in scan at VFS Centre - office of application) |  | 
ANNUAL TARGET | QUARTER 1 TARGET | QUARTER 2 TARGET
90% of business and general work visas adjudicated within 8 weeks for applications processed within the RSA | 90% of business and general work visas adjudicated within 8 weeks for applications processed within the RSA | 90% of business and general work visas adjudicated within 8 weeks for applications processed within the RSA
Not Achieved 86.2% (237 out of 275) of business and general work visas were adjudicated within 8 weeks for applications processed within the RSA. Reasons for under achievement Target not achieved due to the delays with verification of visas issued abroad especially where some of those missions were under lockdown and could not respond on time Way forward/Remedial action Requested DG to authorise the revised “verification process” which will assist in reducing the delays experienced when verifying visas issued abroad. If approved by DG the process will significantly reduce the delays caused by verification of visas issued abroad. | Achieved 94.1% (158 out of 168) of business and general work visas were adjudicated within 8 weeks for applications processed within the RSA (from date of receipt of application until outcome is in scan at VFS Centre | Achieved 98% (243 out of 249) of business and general work visas adjudicated within 8 weeks for applications processed within the RSA (from date of receipt of application until outcome is in scan at VFS Centre)

## Slide 45
programme 4: institutional support and transfers (BMA)

## Slide 46
PROGRAMME 4: INSTITUTIONAL SUPPORT AND TRANSFER | 
ANNUAL TARGET: BMA incrementally established | 
QUARTER 1 TARGET | QUARTER 2 TARGET
Implementation Protocol with SARS concluded 10 Port Coordinators appointed to coordinate border operations in the BMA | Implementation Protocol with SAPS concluded Transfer of functions according to Section 97 of the Constitution (Department of Agriculture, Land Reform and Rural Development; Port Health and Border Facility Management)
1. Achieved The Implementation Protocol with SARS was concluded. 2. Not achieved The BMA Implementation Plan, containing proposals for the BMA’s transitional arrangements, was approved by MMM in July 2021 for implementation. A motivation for the appointment of 10 port coordinators was prepared. Reasons for under achievement Delays in the finalisation of the other posts that will be filled under the BMA’s transitional arrangements. Way forward/Remedial action The appointment of the 10 Port coordinators will be made as part of the posts to be filled under the BMA’s transitional arrangements. | Not achieved The Implementation Protocol with SAPS has not been concluded. The Transfer of Functions through a Section 97 Presidential Proclamation has not been finalized. Reasons for under achievement 1. Political intervention was required in respect of the finalization of the BMA-SAPS Implementation Protocol. To this end, a letter addressed to the Minister of Police was prepared for Minister’s consideration wherein the latter is requested to designate senior officials with whom the BMA PMO can liaise regarding outstanding matters with SAPS including the Implementation Protocol and Section 97 Presidential Proclamation. 2. The Department is required to finalise the Section 97 Proclamation with SAPS and the Departments of Agriculture, Land Reform and Rural Development; Health; and Public Works and Infrastructure. Way forward/Remedial action The BMA-SAPS Implementation Protocol and Section 97 Presidential Proclamation will be finalised once feedback has been received from the affected stakeholders.

## Slide 47
PROGRAMME 4: INSTITUTIONAL SUPPORT AND TRANSFER | 
ANNUAL TARGET: BMA incrementally established | 
QUARTER 3 TARGET | Progress for Quarter 3
Implementation Protocol with Defence concluded | Not achieved The Implementation Protocol with Defence has not been concluded. Instead, discussions are underway on the Memorandum of Understanding (MoU) to pave way for the conclusion of the protocol. Reasons for under achievement Engagements are still ongoing with Defence to clarify matters pertaining to the Implementation Protocol, i.e. operational mandates in the border environment and this is done through the MoU concept. Way forward/Remedial action The SANDF has expressed its support for the establishment of the BMA and to this end, a Joint Task Team has been established to finalise and/or clarify areas of concern; where-after, a Memorandum of Understanding will be concluded as well as the Implementation Protocol.

## Slide 48
PROGRAMME 4: INSTITUTIONAL SUPPORT AND TRANSFER | 
ANNUAL TARGET: BMA incrementally rolled out at 11 ports of entry by incorporating frontline immigration, port health, border facility management and agriculture functions into the BMA | 
QUARTER 1 TARGET | QUARTER 2 TARGET
Draft plan for the incremental rollout of the BMA Border Guard to ports of entry, segments of the land border law enforcement area and community crossing point submitted to the Minister for consideration | Plan for the incremental rollout of the BMA Border Guard to ports of entry, segments of the land border law enforcement area and community crossing point approved by the Minister.
Not achieved The BMA Implementation Plan was approved by MMM on 1 July 2021. The Plan outlines key dates and activities for the roll-out of the BMA to Ports of Entry A draft Border Guard roll-out plan to the borderline is currently being finalised for submission to Minister. The draft will be presented to EXCO on 19 July 2021 for discussion and endorsement; and thereafter be submitted to MMM for consideration. Reasons for under achievement The successful roll-out of the BMA Border Guard to the borderline is dependent on support from the SANDF. Discussions are ongoing in this regard. Way forward/Remedial action The BMA Border Guard roll-out plan to the borderline will be submitted to Minister once finalised. | Not achieved A draft BMA Border Guard roll-out plan was presented to EXCO on 19 July 2021. The finalization of the plan is subject to the conclusion of engagements and Memorandum of Agreement with the SANDF. Reasons for under achievement The transitional arrangements for the establishment of the BMA entail the incubation of the BMA as a Branch within the Department of Home Affairs. Such incubation will enable the secondment of personnel from relevant organs of state to the BMA to perform border law enforcement functions. Processes are underway to seek approval for the creation of the BMA Branch. Way forward/Remedial action Incubation of the BMA as branch within DHA to enable the secondment of personnel from relevant organs of state to the BMA to perform border law enforcement functions. Memorandum of Agreement to be concluded with the SANDF for the secondment and deployment of personnel as BMA Border Guards.

## Slide 49
PROGRAMME 4: INSTITUTIONAL SUPPORT AND TRANSFER | 
ANNUAL TARGET: BMA incrementally rolled out at 11 ports of entry by incorporating frontline immigration, port health, border facility management and agriculture functions into the BMA | 
QUARTER 3 TARGET | PROGRESS FOR QUARTER 3
BMA incrementally rolled out at 11 ports of entry by incorporating frontline immigration, port health, border facility management and agriculture functions into the BMA | Not achieved The BMA has not been rolled-out to 11 ports of entry. . Reasons for under achievement The roll-out of the BMA is dependent on the incubation of the Authority as a Branch within the Department as it has not been listed as an autonomous entity. Such incubation will enable the secondment of border law enforcement officials from relevant departments to the BMA Branch to perform border law enforcement functions in the border environment. In addition, the Section 97 Proclamation pertaining to the transfer of functions from relevant organs of state to the Minister of Home Affairs has not been finalised however, engagements are ongoing with the relevant outstanding departments, i.e. SAPS, Health and DPWI. Way forward/Remedial action The BMA to be incubated as a branch within DHA following approval by Minister and the DPSA. Discussions on the Section 97 Proclamation to be concluded with the relevant departments. .

## Slide 50
PROGRAMME 4: INSTITUTIONAL SUPPORT AND TRANSFER |  | 
ANNUAL TARGET: BMA incrementally rolled out in phases along 5 segments of the land border law enforcement area (RSA/Zimbabwe; eManguzi; Skukuza; KZN/eSwatini; and Mpumalanga/eSwatini) |  | 
QUARTER 1&2 | QUARTER 3 TARGET | PROGRESS FOR QUARTER 3
N/A | BMA incrementally rolled out along 2 segments of the land border law enforcement area | Not achieved The BMA has not been rolled-out along the land border law enforcement area. Reasons for under achievement The roll-out of the BMA Border Guard along the land border law enforcement area requires support from the SANDF in the following areas: Assistance on human resource capacitation; Assistance on existing operational guidance notes; Assistance through the sharing of key infrastructure; and Assistance through conducting joint operations. In December 2021, the SANDF agreed to the establishment of a Joint Task Team to develop a Memorandum of Understanding addressing the above areas and other issues of concern. Way forward/Remedial action The Joint Task Team to finalise the draft Memorandum of Understanding in support of the BMA.

## Slide 51
PROGRAMME 4: INSTITUTIONAL SUPPORT AND TRANSFER |  | 
ANNUAL TARGET: NTC incrementally established commencing with the establishment of an interim NTC |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
1.Implementation protocols with relevant organs of state negotiated (SARS, SANDF and SAPS) 2,Proposed Interim NTC management structure submitted to EXCO for approval | Proposed Interim NTC operating model submitted to EXCO for approval | Proposed Interim NTC targeting priorities submitted to EXCO for approval
1. Not achieved NTC Implementation Protocols were not concluded with relevant organs of state. Nominations for the NTC Steering Committee have been received from DHA, Dept. of Environmental Affairs, SARS and Defence. Nominations are outstanding from Health, Dept. of Agriculture, SAPS and SSA. 2. Achieved. The NTC management structure was submitted to EXCO for approval. Reasons for under achievement The BMA PMO had envisaged that the NTC Steering Committee would drive the preparation and finalization of the NTC’s Implementation Protocols with relevant organs of state however, this could not be done as the Committee could not be established due to outstanding nominations for representatives. Way forward/Remedial action The BMA PMO will continue to follow-up on the outstanding nominations for the Steering Committee. | Achieved. The interim NTC Operating Model has been submitted to EXCO Secretariat for presentation in the latter part of October 2021. | Achieved. The interim NTC targeting priorities have been submitted to EXCO Secretariat for presentation.

## Slide 52
PROGRAMME 4: INSTITUTIONAL SUPPORT AND TRANSFER |  | 
ANNUAL TARGET: OSBP Policy submitted to Cabinet for approval |  | 
QUARTER 1 TARGET | QUARTER 2 TARGET | QUARTER 3 TARGET
Consultation with NEDLAC on the draft OSBP Policy undertaken | Draft OSBP Policy, incorporating public and NEDLAC comments, submitted to the Minister for approval Final SEIAS report submitted to the DPME for approval. | OSBP Policy submitted to JCPS, ICTS and ESEID Clusters for recommendation to Cabinet
Achieved The OSBP Policy was submitted to Nedlac for consultation. The DHA task team was appointed and the initial meeting was held. | Not Achieved The OSBP Policy was submitted to Nedlac for consultation; however, most meetings were cancelled due to the non-availability of other social partners. 2. Achieved The OSBP Policy SEAIS report was submitted to the DPME for approval. Reasons for under achievement Cancellation of NEDLAC meetings due to non-availability of other social partners. Way forward/Remedial action Conclusion of NEDLAC consultations and finalisation of the OSBP Policy. | Achieved The NEDLAC consultations on the OSBP Policy were finalized. The OSBP Policy was approved by the ESEID Cluster and ICTS Cluster for recommendation to Cabinet. The OSBP Policy was approved by JCPS DevCom and tabled at the December JCPS Meeting that is postponed till January 2022.

## Slide 53
ANALYSIS OF REASONS FOR NOT ACHIEVING TARGETS
The department had to observe the COVID-19 health and safety protocols whereby social distancing necessitated for officials to work on a rotation basis.
COVID- 19 continued to negatively impact on performance of the department for the period under review, i.e.
  Loss of productivity as a result of closure of offices owing to COVID-19 positive cases remains one of the biggest challenges.
  Temporary closure of missions abroad due to lockdown restrictions contributed to the non-achievement of some permitting targets.
Front and back offices did not function with 100% staff compliment and staff members could not be substituted due to capacity challenges.
Lack of cooperation from external stakeholders such as SANDF, SAPS in finalising required processes negatively impacted achievement of BMA targets.
Delays in the finalisation of the procurement processes by relevant business units.
Huge dependency on other organs of state to deliver services, i.e. SITA delayed the finalisation of the procurement processes.
Continued loss of staff and inability to fill vacancy due to insufficient compensation of employees (COE) budget.

## Slide 55
BUDGET VERSUS EXPENDITURE AS AT
30 JUNE 2021

## Slide 56
BUDGET VS EXPENDITURE AS AT 30 JUNE 2021

## Slide 57
EXPENDITURE AS AT 30/06/2021 – PER ECONOMIC CLASSIFICATION

## Slide 58
EXPENDITURE AS AT 30/06/2021 - PROVINCES
Note:
Spending for Provinces is within the linear projection of 25.0%.

## Slide 59: COVID -19 SPENDING AS AT 30 JUNE 2021

## Slide 60
REVENUE COLLECTED AS AT 30/06/2021
Note: The Department has collected R31 million for the month of June 2021 and R97 million to date. Given that expenditure for self financing is R177 million this results in under collection of revenue by R80 million.
This area needs to be closely monitored to ensure that we only expense against revenue generated.

## Slide 61
BUDGET VERSUS EXPENDITURE AS AT
30 SEPTEMBER 2021

## Slide 62
BUDGET VS EXPENDITURE AS AT 30 SEPTEMBER 2021

## Slide 63
EXPENDITURE AS AT 30/09/2021 – PER ECONOMIC CLASSIFICATION

## Slide 64
EXPENDITURE AS AT 30/09/2021 - PROVINCES
Note:
Spending for Provinces is within the linear projection of 50.0%.

## Slide 65: COVID -19 SPENDING AS AT 30 SEPTEMBER 2021

## Slide 66
REVENUE COLLECTED AS AT 30/09/2021

## Slide 67
BUDGET VERSUS EXPENDITURE AS AT
31 DECEMBER 2021

## Slide 68
BUDGET VS EXPENDITURE AS AT 31 DECEMBER 2021

## Slide 69
EXPENDITURE AS AT 31/12/2021 – PER ECONOMIC CLASSIFICATION

## Slide 70
EXPENDITURE AS AT 31/12/2021 - PROVINCES
Note:
Spending for Provinces is within the 2% variance of linear projection.

## Slide 71: COVID -19 SPENDING AS AT 31 DECEMBER 2021

## Slide 72
REVENUE COLLECTED AS AT 31/12/2021
Note: The Department has collected R38 million for the month of December 2021 and R322 million to date. Given that expenditure for self financing is R434 million this results in under collection of revenue by R112 million.
This area needs to be closely monitored to ensure that we only expense against revenue generated.

## Slide 73
CHALLENGES AND PRIORITIES MOVING FOWARD

## Slide 74
CHALLENGES
The following challenges continue to constrain the optimal performance of the DHA:
The department is experiencing unprecedented long queues in its offices. This is due to high client volumes caused by, inter alia, unpredictable walk-ins, discontinuation of Saturday working hours, high vacancy rate, unstable systems (networks and applications), accumulation of application for services which were not rendered under lockdown level 4 & 5 such as Smart ID card applications.
Non-integration of IT systems across the DHA and running of dual systems (digital and manual) in the same environment;
High vacancy rate (vacant unfunded posts) in frontline offices and in certain critical posts at a management level;
Huge dependency on other organs of state to deliver services (SITA, DPWI and SARS); and
The DHA service delivery model is labour intensive; thus, its services were affected by the COVID-19 pandemic.

## Slide 75
WAY FORWARD
The DHA key priorities include, amongst others, the following:
Proactively manage external dependencies to ensure achievement of set targets.
Development of recovery plans for targets that are at risk of not being achieved by end of financial year.
Enforcement of 100% return-to-work policy.
Encouragement of all employees to vaccinate – conduct awareness campaigns on the benefits of vaccination to ward off misinformation.
Strategies for dealing with back-office services, long queues and system downtime will be intensified and regarded as APEX priorities for the department.
Continuation of the modernisation programme.
Continue with implementation of “War on Queues” strategies to deal with long queues in offices.

## Slide 76
Ndiyabulela
Ngiyabonga
Thank you
Inkomu
Dankie
Ke a leboga
Ndo livhuwa
Ke a leboha