## Slide 1
DALRRD CONSOLIDATED Q1-Q3 PERFORMANCE REPORT
2021/22 FINANCIAL YEAR
PORTFOLIO COMMITTEE
15 FEBRUARY 2022

## Slide 2
OUTLINE
2021/22 Q1-Q3 Performance Scorecard
Acronyms
Introduction
Operational Environment
2021/22 Consolidated Q1-Q3 Performance Per Programme
Conclusion

## Slide 3
INTRODUCTION
This report gives a reflection of performance against targets planned to be achieved from Q1-Q3.
Catch up plans are already being implemented for targets which have not been achieved.
Improvements to some planning challenges are being introduced to have effect on APP planning g process for 2022/23.

## Slide 4
OPERATIONAL ENVIRONMENT

## Slide 5
VISION, MISSION AND STRATEGIC OUTCOMES
VISION: Equitable access to land, integrated rural development, sustainable
agriculture and food security for all
MISSION: To accelerate land reform, catalyse rural development and improve agricultural production to stimulate economic development and food security through:
transformed land ownership patterns;
agrarian reform;
implementation of an effective land administration system;
sustainable livelihoods;
innovative sustainable agriculture;
promotion of access to opportunities for youth, women and other vulnerable groups;
integrated rural development.

## Slide 6
VISION, MISSION AND STRATEGIC OUTCOMES
OUTCOME 1
Improved governance and service excellence
OUTCOME 3
Redress and equitable access to land and producer support
OUTCOME 5
Increased market access and maintenance of existing markets
OUTCOME 2
Spatial transformation and effective land administration
OUTCOME 4
Increased production in the agricultural sector
OUTCOME 6
Integrated and inclusive rural economy

## Slide 7
STRUCTURAL ARRANGEMENTS
DALRRD has six programmes
Programme 1 (Administration)
Ministry
Sub-programme: Department Management
Sub-programme: Internal Audit
Sub-programme: Financial Management Services
Sub-programme: Corporate Support Services
Sub-programme: Provincial Operations
Sub-programme: Office Administration
Programme 2 (Agricultural Production, Biosecurity, Natural Resources and Disaster Management)
Sub-programme: Plant Production and Health
Sub-programme: Animal Production and Health
Sub-programme: Inspection and Quarantine Services
Sub-programme: Natural Resources and Disaster Management
Sub-programme: Biosecurity
Agricultural Research Council (ARC)
Onderstepoort Biological Products (OBP)
Perishable Products Export Control Board (PPECB)
Programme 3 (Food Security, Land Reform and Restitution)
Sub-programme: Food Security and Agrarian Reform
Sub-programme: Land Redistribution and Tenure Reform
Sub-programme: National Extension Services and Sector Capacity Development
Sub-programme: Land Development and Post Settlement Support
Sub-programme: Restitution
Commission on Restitution of Land Rights
Agricultural Land Holdings Account
Ingonyama Trust Board
Office of the Valuer-General
Programme 4 (Rural Development)
Sub-programme: National Rural Youth Service Corps (NARYSEC)
Sub-programme: Rural Infrastructure Development
Sub-programme: Technology Research and Development

## Slide 8
STRUCTURAL ARRANGEMENTS Cont.
DALRRD has six programmes
Programme 5 (Economic Development, Trade and Marketing)
Sub-programme: International Relations and Trade
Sub-programme: Cooperatives and Development
Sub-programme: Agro-processing, Marketing and Industrial Development
National Agricultural Marketing Council (NAMC)
Programme 6 (Land Administration)
Sub-programme: National Geomatics Management Services
Sub-programme: Spatial Planning and Land Use Management
Sub-programme: Deeds Registration
South African Council for Planners
South African Geomatics Council
Integrated Land Administration

## Slide 9
Q1-Q3 PERFORMANCE SCORECARD

## Slide 11
Q1 PERFORMANCE SCORECARD
Programme | Q1 Targets 21/22 | Q1 Targets achieved | % Achievement
Administration | 1 | 0 | 0%
APB&NRM | 9 | 8 | 89%
Food Security Land Reform & Restitution | 8 | 3 | 38%
Rural Development | 4 | 4 | 100%
Economic Dev, Trade & Marketing | 6 | 4 | 67%
Land Administration | 4 | 4 | 100%
Total | 32 | 23 | 72%
Chart: 
| Not achieved | Partially achieved | Achieved
 | 0.47 | 0 | 0.53

## Slide 12
Q2 PERFORMANCE SCORECARD
Programme | Q2 Targets 21/22 | Q2 Targets achieved | % Achievement
Administration | 2 | 1 | 50%
APB&NRM | 11 | 10 | 91%
Food Security Land Reform & Restitution | 12 | 3 | 25%
Rural Development | 4 | 2 | 50%
Economic Dev, Trade & Marketing | 8 | 4 | 50%
Land Administration | 3 | 2 | 67%
Total | 40 | 22 | 55%
Chart: 
| Not achieved | Achieved
 | 0.47 | 0.53

## Slide 13
Programme | Q3 Targets 21/22 | Q3 Targets achieved | % Achievement
Administration | 1 | 0 | 0%
APB&NRM | 9 | 7 | 78%
Food Security Land Reform & Restitution | 11 | 1 | 9%
Rural Development | 5 | 1 | 20%
Economic Dev, Trade & Marketing | 8 | 3 | 38%
Land Administration | 4 | 1 | 25%
Total | 38 | 13 | 34%
Chart: 
| Not achieved | Partially achieved | Achieved
 | 0.68 | 0 | 0.32
Q3 PERFORMANCE SCORECARD

## Slide 14
Programme | Q1-Q3 Targets 21/22 | Q1-Q3 Targets achieved | % Achievement
Administration | 4 | 1 | 25%
APB&NRM | 29 | 25 | 90%
Food Security Land Reform & Restitution | 31 | 7 | 23%
Rural Development | 13 | 7 | 54%
Economic Dev, Trade & Marketing | 22 | 11 | 50%
Land Administration | 11 | 7 | 64%
Total | 110 | 58 | 53%
Chart: 
| Not achieved | Partially achieved | Achieved
 | 0.68 | 0 | 0.32
CONSOLIDATED Q1-Q3 PERFORMANCE SCORECARD

## Slide 15
2021/22 CONSOLIDATED Q1-Q3 PERFORMANCE PER PROGRAMME

## Slide 16
PROGRAMME 1: ADMINISTRATION
Purpose: Provide strategic leadership, management and support services to the department
Programme Structure:
Ministry
Department Management
Internal Audit
Financial Management Services
Corporate Support Services
Provincial Operations
Office Administration
Strategic Objectives:
Outcome 1: Improved governance and service excellence

## Slide 17
PROGRAMME 1: ADMINISTRATION
Performance indicator: 1.1.1 Unqualified audit opinion
Annual Target: Unqualified audit opinion
Target: Unqualified audit opinion on 2020/21 annual financial statements
Output: Unqualified audit opinion on 2020/21 annual financial statements was achieved.
Achieved
Reason for deviation
N/A
Planned intervention
N/A

## Slide 18
PROGRAMME 1: ADMINISTRATION
Performance indicator: 1.2.1 Percentage of valid invoices paid within 30 days upon receipt by the department
Annual Target: 100%
Target: 100%
Output: 97%
Not achieved
Reason for deviation
Service providers not registered on Basic Accounting System (BAS) causing delays in processing..
Planned intervention
Continuous consultation with service providers

## Slide 19
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND NATURAL RESOURCES MANAGEMENT
Purpose: Oversee livestock production, game farming, animal and plant health, natural resources and disaster management
Programme Structure:
Inspection and Quarantine Services
Plant Production and Health
Animal production and Health
Natural Resources and Disaster Management
Biosecurity
Agricultural Research Council
Onderstepoort Biological Products
Perishable Products Export Board
Strategic Objectives:
Outcome 4: Increased production in the agricultural sector
Outcome 7: Enhanced biosecurity and effective disaster risk reduction

## Slide 20
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 2.2.1 Number of animal improvement schemes for prioritised value chain commodities implemented
Annual Target: 2 animal improvement schemes for prioritised value chain commodities (KyD and poultry) implemented
Target: 2 animal improvement schemes for prioritised value chain commodities (KyD and poultry) implemented
Output: Poultry improvement scheme was implemented during Q3
Not achieved
Reason for deviation
TID requirements in particular on analysing data collected through physical mobilization of farmers for KYD has shown not to be more ideal than data that can be obtained from ARC, this has led to non fulfillment of TID and affecting performance though the actual participation by farmers do happen and ARC reports do confirm this.
Planned intervention
Review of the target to enable DALRRD to focus on strengthening oversight and reporting by ARC so as not to duplicate what need to be reported.

## Slide 21
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 2.3.1 Cannabis Master Plan implemented
Annual Target: Annual report on implementation of Cannabis Masterplan developed
Target: 3 Quarterly progress report
Output: 3 quarterly progress report were submitted
Achieved
Reason for deviation
N/A
Planned intervention
N/A

## Slide 22
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 2.4.1 Number of provinces with delineated protected agricultural areas
Annual Target: 3 provinces with delineated protected agricultural areas
Target: Spatial delineated report and Consultation with Limpopo, KZN and North West
Output: Spatial delineated report was submitted and cconsultations with North West, KZN and Limpopo PDA’s were held on the delineated protected agricultural areas
Achieved
Reason for deviation
N/A
Planned intervention
N/A

## Slide 23
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 3.1.1 Number of plant pest risk surveillances conducted
Annual Target: 3 plant pest risk surveillances conducted (Exotic fruit fly; Citrus greening survey; Banana bunchy top virus)
Target: : 3 quarterly reports on 3 plant pest surveillances conducted (Exotic fruit fly Surveillance; Citrus Greening Survey; Banana bunchy top virus )
Output: 3 plant pest surveillances conducted (Exotic fruit fly Surveillance; Citrus Greening Survey; Banana bunchy top virus ) and quarterly reports were compiled
Achieved
Reason for deviation
N/A
Planned intervention
N/A

## Slide 24
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 3.1.2 Number of animal disease risk surveillances conducted
Annual Target: 3 animal disease risk surveillances conducted (CBPP; PPR; FMD)
Target: 3 animal diseases risk surveillances conducted (CBPP, PPR, FMD)
Output: Quarterly reports on 3 animal disease risk surveillances conducted (CBPP; PPR; FMD) have been generated
Achieved
Reason for deviation
N/A
Planned intervention
N/A

## Slide 25
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 3.3.1 Number of agricultural inputs products evaluated
Annual Target: 4 500
Target: 3 375
Output: 3 632
Achieved
Reason for deviation
Working overtime to increase productivity on the processing of the registration applications
Planned intervention
N/A

## Slide 26
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 3.3.2 Number of agricultural provincial biosecurity coordinating structures established
Annual Target: 4 provincial agricultural biosecurity coordinating structures consulted
Target: 3 provincial agricultural biosecurity coordinating structures consulted
Output: 3 Provincial consultations took place with the Limpopo, Eastern Cape and Western Cape Provincial Department of Agriculture.
Achieved
Reason for deviation
N/A
Planned intervention
N/A

## Slide 27
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 3.3.3 Number of laboratories accredited
Annual Target: 1 laboratory accredited in Pretoria
Target: Accreditation of Pretoria laboratory
Output: The laboratory in Pretoria has been accredited
Achieved
Reason for deviation
N/A
Planned intervention
N/A

## Slide 28
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 3.3.4 Percentage of export protocols for phytosanitary requirements implemented
Annual Target: 100% export protocols for phytosanitary requirements implemented
Target: 100% export protocols for phytosanitary requirements implemented
Output: 100% export protocols for phytosanitary requirements were implemented
Achieved
Reason for deviation
N/A
Planned intervention
N/A

## Slide 29
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 3.4.1 Climate Change Adaptation and mitigation plan (CCAMP) Implemented
Annual Target: Report on evaluation of climate change variables on performance of sorghum grown under variable agronomic practices and agro-ecological zones in four provinces compiled
Target: Report on sorghum harvesting of 4 hectares planted in four provinces
Output: : Report on sorghum harvesting of 4 hectares planted in four provinces (FS, KZN, LP and MP) has been compiled.
Achieved
Reason for deviation
N/A
Planned intervention
N/A

## Slide 30
PROGRAMME 2: AGRICULTURAL PRODUCTION, BIOSECURITY AND
NATURAL RESOURCES MANAGEMENT
Performance indicator: 3.4.2 Number of smallholder producers capacitated on crop suitability to climate change programme
Annual Target: 140 Smallholder capacitated on crop suitability to climate
Target: 140
Output: 125 smallholder producers capacitated on crop suitability to climate change programme
Not achieved
Reason for deviation
There was a low turn out of farmers due to farmers unable to access the venue because of extreme weather conditions (heavy rain fall made it difficult for farmers to travel).
Planned intervention
A training session has been arranged for the 24th and 25th February 2022. A venue close to the farmers will be sourced to mitigate risk of inability to access venue due to heavy rains.

## Slide 31
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Purpose: Acquire and distribute land, and promote food security and agrarian reform programmes.
Programme Structure:
Food Security
Land Redistribution and Tenure Reform
National Extension Services and Sector Capacity Development
Farmer Support and Development
Restitution
Agricultural Land Holdings Account (ALHA)
Ingonyama Trust Board (ITB)
Office of the Valuer-General (OVG)
Strategic Objectives:
Outcome 3: Redress and equitable access to land and producer support.

## Slide 32
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 4.4.1 Number of CPA supported to be compliant with legislation
Annual Target: 577
Target: 450
Output: 420
Not achieved
Reason for deviation
Some of the training could not take place as planned due to conflicts in CPAs
Planned intervention
The Department is resolving these conflicts and training have resumed in some of these provinces.

## Slide 33
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.1.1 Employment of extension practitioners in the sector coordinated
Annual Target: Draft report on employment of extension practitioners compiled
Reason for deviation
N/A
Planned intervention
N/A
Target: Draft report on employment of extension practitioners compiled
Output: The draft report on the employment of Extension Practitioners has been compiled.
Achieved

## Slide 34
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.3.1 Number of hectares of strategically located land acquired
Annual Target: 33 720
Reason for deviation
There is a delay in transfer of properties due to prolonged administrative processes involving bond cancellation by banks, acceptance of guarantee as well as settling of the municipal rates and taxes by the sellers. These are some of the factors that affect the turnaround time for the acquisition of land.
Planned intervention
The Department is engaging banks and municipalities to find solution to deal with these bottlenecks
Target: 25 225 ha
Output:4 766 ha
Not Achieved

## Slide 35
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.3.2 Number of hectares acquired for farm dwellers and/or labour tenants
Annual Target: 6 150
Reason for deviation
Delays in the completion of the subdivisions. Issues with Municipality in the implementation of SPLUMA.
There is a delay in transfer of properties due to prolonged administrative processes involving bond cancellation by banks, acceptance of guarantee as well as settling of the municipal rates and taxes by the sellers. These are some of the factors that affect the turnaround time for the acquisition of land.
Planned intervention
The Department is engaging banks and municipalities to find solution to deal with these bottlenecks.
Target: 5 550 ha
Output:2 479,8 ha
Not Achieved

## Slide 36
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.4.1 Percentage of hectares allocated to women
Annual Target: 50%
Reason for deviation
Acquisition of land was low in the period under review
Planned intervention
Once the challenges of acquisitions are resolved, allocation will improve.
Target: 50%
Output:20%
Not Achieved

## Slide 37
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.4.2 Percentage of hectares of allocated to youth
Annual Target: 40%
Reason for deviation
Few applications are being received from youth
.Planned intervention
N/A
Target: 40%
Output: 29%
Achieved

## Slide 38
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.4.3 Percentage of hectares of allocated to people with disability
Annual Target: 10%
Reason for deviation
No application were received from People with disability
Planned intervention
Adverts for farm allocations will be tailor-made for disabled people so that they do not have to compete with other prioritized groups, and once the challenges of acquisitions are resolved, allocation will improve.
Target: 10%
Output: 0%
Not Achieved

## Slide 39
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.5.1 Number of TRANCRAA areas transferred
Annual Target: 11
Reason for deviation
Transfer of land to the affected communities is delayed due to conflicts and disputes amongst the members of the communities.
Planned intervention
The Department is resolving these conflicts and disputes to enable transfer of land and some of the areas are to be transferred in the current quarter.
Target: 10
Output: 0
Not Achieved

## Slide 40
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.6.1 Number of labour tenants’ applications finalised
Annual Target: 1000
Reason for deviation
Delays due to prolonged facilitation and negotiations have affected the finalization of applications..
Planned intervention
The department is looking at mechanisms to deal with the prolonged facilitation and negotiation
Target: 450
Output: 3 (KZN)
Not Achieved

## Slide 41
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.7.1 Number of land claims settled
Annual Target: 240
Target: 181
Output: 146
Not Achieved
Provinces | EC | FS | GP | KZN | LP | MP | NC | NW | WC | Total
Annual Target | 39 | 0 | 13 | 40 | 64 | 35 | 5 | 2 | 42 | 240
Q1-Q3 Target | 29 | 0 | 11 | 27 | 48 | 30 | 4 | 2 | 30 | 181
Q1-Q3 Achievement | 8 | 0 | 8 | 42 | 17 | 32 | 2 | 11 | 26 | 146
Reason for deviation
Delays in getting offers signed/accepted by the claimants and delays by Service Providers doing valuations.
Planned intervention
Priorities settlements in Quarter 4 as per recovery plan.

## Slide 42
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.7.2 Number of land claims finalised
Annual Target: 316
Target: 267
Output: 249
Not Achieved
Provinces | EC | FS | GP | KZN | LP | MP | NC | NW | WC | Total
Annual Target | 69 | 12 | 12 | 60 | 32 | 36 | 9 | 16 | 70 | 316
Q1-Q3 Target | 56 | 11 | 12 | 45 | 24 | 40 | 8 | 11 | 60 | 267
Q1-Q3 Achievement | 24 | 1 | 34 | 34 | 92 | 23 | 3 | 12 | 26 | 249
Reason for deviation
Lack of cooperation by family representatives once they have received their share of the award , Untraceable beneficiaries and outstanding Occupation Certificates
Planned intervention
Targeting family claims with small outstanding balances. Declarations to be drafted for untraceable beneficiaries and engage intensively regarding Occupation Certificates including escalation if need arise.

## Slide 43
PROGRAMME 3: FOOD SECURITY, LAND REFORM AND RESTITUTION
Performance indicator: 5.8.1 Number of farms supported through the Land Development Support Programme
Annual Target: 146
Reason for deviation
Delays in procurement processes affecting projects approval.
Planned intervention
Strategies are been formulated to fast track approval processes and to mainly focus on setting target for farms to be supported after granting of approvals.
Target: 128
Output: 35
Not achieved

## Slide 44
PROGRAMME 4: RURAL DEVELOPMENT
Programme Purpose: Initiate, facilitate, coordinate and act as a catalyst for the implementation of a comprehensive rural development programme leading to sustainable and vibrant rural communities.
Sub-programme:
National Rural Youth Service Corps (NARYSEC)
Rural Infrastructure Development
Technology Research and Development
Strategic Objectives:
Outcome 6: Integrated and inclusive rural economy.

## Slide 45
PROGRAMME 4: RURAL DEVELOPMENT
Performance indicator: 6.1.1 Number of NARYSEC youth trained
Annual Target: 1 409
Target: 752
Output: 1 089
Achieved
Provinces | EC | FS | GP | KZN | LP | MP | NC | NW | WC | Total
Annual Target | 185 | 113 | 100 | 120 | 200 | 275 | 127 | 179 | 110 | 1 409
Q1-Q3 Target | 165 | 72 | 50 | 60 | 0 | 275 | 0 | 82 | 48 | 752
Q1-Q3 Achievement | 0 | 43 | 54 | 128 | 349 | 389 | 0 | 110 | 16 | 1 089
Reason for deviation:
More certificates were received in Q1 and Q2 than anticipated resulting in overachievement in those quarters.
Planned intervention:
None

## Slide 46
PROGRAMME 4: RURAL DEVELOPMENT
Performance indicator: 6.1.2 Number of jobs created in rural development initiatives
Annual Target: 450
Target: 290
Output: 211
Not Achieved
Provinces | EC | FS | GP | KZN | LP | MP | NC | NW | WC | Total
Annual Target | 50 | 50 | 25 | 50 | 50 | 55 | 60 | 80 | 30 | 450
Q1-Q3 Target | 30 | 40 | 20 | 30 | 20 | 40 | 40 | 50 | 20 | 290
Q1-Q3 Achievement | 43 | 56 | 0 | 12 | 39 | 21 | 0 | 22 | 18 | 211
Reason for deviation
Delays on the appointments of contractors on the new projects.
Planned intervention
Tenders were advertised, Service Providers have been appointed and sites handed over for implementation and more jobs will be created.

## Slide 47
PROGRAMME 4: RURAL DEVELOPMENT
Performance indicator: 6.2.1 Number of infrastructure projects completed to support FPSUs
Annual Target: 25
Target: 14
Output: 12
Not Achieved
Provinces | EC | FS | GP | KZN | LP | MP | NC | NW | WC | Total
Annual Target | 3 | 1 | 3 | 4 | 3 | 4 | 2 | 4 | 1 | 25
Q1-Q3 Target | 0 | 1 | 2 | 3 | 0 | 3 | 1 | 4 | 0 | 14
Q1-Q3 Achievement | 0 | 3 | 0 | 14 | 1 | 0 | 0 | 2 | 0 | 12
Reason for deviation
MP: 2 FPSU projects planned to be achieved are in a process of termination due to Contractor breaching the contract (failing to perform and abandoning construction site) NW: Non-Response on quotation from Service Providers
Planned intervention
MP: Terminate the Contractor and appoint new Contractor after all SCM processes have been followed. NW: Re-Submit request for quotations to Service Providers.

## Slide 48
PROGRAMME 4: RURAL DEVELOPMENT
Performance indicator: 6.2.2 Number of infrastructure projects completed to support production (AVMP and RVCP)
Annual Target: 50
Target: 30
Output: 29
Not Achieved
Provinces | EC | FS | GP | KZN | LP | MP | NC | NW | WC | Total
Annual Target | 1 | 3 | 0 | 16 | 2 | 4 | 2 | 20 | 2 | 50
Q1-Q3 Target | 0 | 3 | 0 | 11 | 0 | 3 | 1 | 12 | 0 | 30
Q1-Q3 Achievement | 0 | 4 | 0 | 21 | 0 | 3 | 2 | 0 | 0 | 29
Reason for deviation
Procurement period taking longer than anticipated and affecting approval of projects
Planned intervention
New dates proposed to speed up the processes on all delays.

## Slide 49
PROGRAMME 4: RURAL DEVELOPMENT
Performance indicator: 6.2.3 Number of technology research projects completed
Annual Target: 5
Target: 2
Output: 0
Not Achieved
Reason for deviation
Project delayed due to an Animal Ethics Clearance. The service provider (CSIR) is not able to complete the projects due to various challenges experienced in the project, such as obtaining Animal Ethics Clearance. Damage caused by heavy rains in Thaba-Nchu college, Delays in approval of projects. Deviation memo not approved for Green Tea project.
Planned intervention
Legal intervention has been solicited (to have the project remedied by CSIR or to terminate the project).A request was advanced to SCM for the sourcing of the preferred supplier for the project. A response is still awaited. A catch-up plan has been developed.

## Slide 50
PROGRAMME 5: ECONOMIC DEVELOPMENT, TRADE AND MARKETING
Purpose: Promotes economic development, trade and market access for agriculture products and foster international relations for the sector
Sub-programmes
International Relations and Trade
Cooperatives and Development
Agro-processing, Marketing and Industrial Development
Development Finance
National Agricultural Marketing Council (NAMC)
Outcomes
Outcome 5: Increased market access and maintenance of existing markets.

## Slide 51
PROGRAMME 5: ECONOMIC DEVELOPMENT, TRADE AND MARKETING
Performance indicator: 7.1.1 Number of agricultural cooperatives trained
Annual Target: 90
Reason for deviation
The Farmer Production Support Unit (FPSU) in North West (NW) to which coops trained are affiliated has 6 coops in total. It was therefore logical to train all 6 instead of the initial targeted 5
Planned intervention
N/A
Target: 68
Output: 69
Achieved

## Slide 52
PROGRAMME 5: ECONOMIC DEVELOPMENT, TRADE AND MARKETING
Performance indicator: 7.3.1 Number of FPSUs supported towards functionality
Annual Target: 35
Reason for deviation
Delayed approvals and water and electricity challenges are the main contributors that negatively affected the achievement of set target.
Planned intervention
Constant follow ups with supply chain and appointed service provider to fastrack the delivery and engagement with relevant authorities to address water and electricity connectivity.
Target: 16
Output: 0
Not achieved
Provinces | EC | FS | GP | KZN | LP | MP | NC | NW | WC | Total
Annual Target | 16 | 2 | 0 | 10 | 0 | 3 | 2 | 0 | 2 | 35
Q1-Q3 Target | 8 | 2 | 0 | 0 | 0 | 3 | 2 | 0 | 1 | 16
Q1-Q3 Achievement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 53
PROGRAMME 5: ECONOMIC DEVELOPMENT, TRADE AND MARKETING
Performance indicator: 7.4.1 Number of new agricultural enterprises supported
Annual Target: 71
Reason for deviation
Delays in procurement processes and slower delivery of production inputs by appointed service. Have major impact of non achievement of this target.
Planned intervention
Constant follow-up and intensify monitoring of the work by appointed Service providers.
Target: 64
Output: 13
Not achieved
Provinces | EC | FS | GP | KZN | LP | MP | NC | NW | WC | Total
Annual Target | 2 | 16 | 7 | 8 | 1 | 0 | 8 | 25 | 4 | 71
Q1-Q3 Target | 0 | 16 | 6 | 7 | 0 | 0 | 8 | 25 | 2 | 64
Q1-Q3 Achievement | 0 | 0 | 4 | 9 | 0 | 0 | 0 | 0 | 0 | 13

## Slide 54
PROGRAMME 5: ECONOMIC DEVELOPMENT, TRADE AND MARKETING
Performance indicator: 7.4.2 Number of new non-agricultural enterprises supported
Annual Target: 15
Reason for deviation
Delayed in supply chain processes that affected pace of service delivery.
Planned intervention
Constant follow ups with supply chain and appointed service provider to fastrack the delivery.
Target: 6
Output: 2
Not achieved
Provinces | EC | FS | GP | KZN | LP | MP | NC | NW | WC | Total
Annual Target | 3 | 0 | 3 | 8 | 0 | 0 | 0 | 0 | 1 | 15
Q1-Q3 Target | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 6
Q1-Q3 Achievement | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2

## Slide 55
PROGRAMME 5: ECONOMIC DEVELOPMENT, TRADE AND MARKETING
Performance indicator: 7.5.1 Number of smallholder producers accessing MAFISA loan
Annual Target: 150
Reason for deviation
This target is demand driven.
Planned intervention
Continue to evaluate ways in which target setting can be set taking into account demand driven for this service
Target: 75
Output: 53
Not achieved

## Slide 56
PROGRAMME 5: ECONOMIC DEVELOPMENT, TRADE AND MARKETING
Performance indicator: 7.6.1 Marketing of Agricultural Products Act reviewed
Annual Target: Public consultation on Marketing of Agricultural Products Amendment Bill
Reason for deviation
Public consultations on the Marketing of Agricultural Products (MAP) Bill was not done due to comments from the OCSLA that took longer than anticipated to be obtained.
Planned intervention
OCSLA’s comments are been incorporated onto the revised MAP Bill and public consultation will commence soon.
Target: Published Government Gazette of the Marketing of Agricultural Products Amendment Bill.
Output: Preliminary Legal Opinion from the Office of the Chief State Law Advisor (OCSLA) received on the 20th of December 2021.
Not Achieved

## Slide 57
PROGRAMME 5: ECONOMIC DEVELOPMENT, TRADE AND MARKETING
Performance indicator: 7.8.2 Bilateral agreements implemented
Annual Target: Status report on bilateral engagements (South-South and North-South)
Reason for deviation
N/A
Planned intervention
N/A
Target: Quarterly progress report on bilateral engagements (South-South and North-South)
Output: 3 quarterly progress report on bilateral engagements (South-South and North-South) were compiled
Achieved

## Slide 58
PROGRAMME 5: ECONOMIC DEVELOPMENT, TRADE AND MARKETING
Performance indicator: 7.8.2 Bilateral agreements implemented
Annual Target: Status report on bilateral engagements (Africa continent)
Reason for deviation
N/A
Planned intervention
N/A
Target:Quarterly progress report on bilateral engagements (Africa continent)
Output: 3 quarterly progress report on bilateral engagements (Africa continent) were compiled
Achieved

## Slide 59
PROGRAMME 6: LAND ADMINISTRATION
Programme Purpose: Provide geospatial information, cadastral surveys, deeds registration and spatial planning, as well as technical services in support of sustainable land development.
Sub-programmes
National Geomatics Management Services
Spatial Planning and Land Use
Deeds Registration
South African Council of Planners
South African Geomatics Council
Integrated Land Administration
Outcomes
Outcome 2: Spatial transformation and effective and efficient land administration.

## Slide 60
PROGRAMME 6: LAND ADMINISTRATION
Performance indicator: 8.1.1 e-DRS phases completed
Annual Target: e-DRS phase 1 – 75% completed
Target: eDRS phase 1- 45% completed, Web-based software product for e-DRS portal with UAM functionality and Acceptance certificate for e-DRS and UAM modules
Output: 0%
Completion of eDRDS was not realised, web-based software product for e-DRS portal with UAM functionality was not done and Acceptance certificate for e-DRS and UAM modules was not received
Not Achieved
Reason for deviation
Delayed Procurement due to SITA interest in Developing EDRS.
Planned intervention
Speed up the development process by ensuring that other modules are developed in parallel as soon as the solution partner is on board.

## Slide 61
PROGRAMME 6: LAND ADMINISTRATION
Performance indicator: 8.2.1 Deeds Registries Amendment Bill and Cabinet Memorandum to be submitted to the minister for submission to Cabinet for promulgation purposes
Annual Target: Submission of Bill and Cabinet Memorandum to the minister for submission to Cabinet for promulgation purposes
Target: Submission of Bill to the Office of Chief State Law Advisor for final certification
Output: Bill and Object Memorandum submitted to OCSLA on 26 October 2021.
Bill presented at 1st NEDLAC meeting on 18 Nov 2021.
Not Achieved
Reason for deviation
OCSLA advised that final certification of Bill is premature and can only be issued after adoption of the Bill by NEDLAC.
Planned intervention
Attending further NEDLAC meetings for purpose of adoption of Bill. Next meeting scheduled for 26 January 2022.

## Slide 62
PROGRAMME 6: LAND ADMINISTRATION
Performance indicator: 8.4.1 Average number of working days taken to process cadastral documents, from date of lodgment to date of dispatch
Annual Target: 15 Days
Target: 15 days
Output: 15 days
Achieved
Reason for deviation
N/A
Planned intervention
N/A

## Slide 63
PROGRAMME 6: LAND ADMINISTRATION
Performance indicator: 8.3.1 Monitoring Framework for National Spatial Development Framework (NSDF) spatial action areas implementation plans developed
Annual Target: Monitoring Framework for NSDF Spatial Action Areas Implementation Plan developed
Target: Develop NSDF Partnership Implementation Protocol
Output: Final NSDF Implementation Protocol Avalable
Not Achieved
Reason for deviation
The NSDF is currently a DRAFT. The Department is in the process of processing the Draft NSDF through Cabinet Clusters, there has been delays in some Clusters. Approval received from DG Governance and Administrative Cluster, awaiting presentation to Governance and Administration Cluster. Approval granted by Social Protection and Community Development and International, International Cooperation, Trade and Security clusters. Follow up presentation to Economic Sectors and Employment Clusters is outstanding. The Department has also developed an Implementation Charter and Draft Monitoring Framework. Draft Implementation Protocols have been developed.
Planned intervention
The NSDF is anticipated to be approved by March 2022. Protocols will be signed after the Approval of the NSDF by Cabinet.

## Slide 64
CONCLUSION
Quality of APP planned targets has been identified as an area that require urgent improvement going into 2022/23 planning.
Department is subjecting all planned targets for 2022/23 to assessment tool been developed to ascertain their suitability.
The tool intend to minimise risky targets causing uncertainties during reporting.
Amongst others it is hoped that the tool will assist with reasonable targets setting, formulation of TID to reflect only what is key to prof the execution of intended interventions, strengthening of controls and improve quality of reporting and quality assurance processes.

## Slide 65
APB&NRM : Agricultural Production, Biosecurity and Natural Resources
Management
AVMP : Animal and Veld Management Programme
CED : Cooperative and Rural Enterprise Development
COVID : Coronavirus disease
CPA : Communal Property Association
CBPP : Contagious Bovine Pleuropneumonia
CSIR : Council for Scientific and Industrial Research
DALRRD : Department of Agriculture, Land Reform and Rural
Development
DBSC : District Beneficiary Selection Committee
EC : Eastern Cape
e-DRS : Electronic Deeds Registration System
FMD : Foot-and-Mouth Disease
FPSU : Farmer Production Support Unit
FS : Free State
GP : Gauteng Province
ACRONYMS

## Slide 66
KZN : KwaZulu-Natal
KYD : Kaonafatso ya Dikgomo
LP : Limpopo
MP : Mpumalanga
N/A : Non-applicable
NLAACC : National Land Acquisition and Allocation Control Committee
NARYSEC : National Rural Youth Service Corps
NEDLAC : National Economic Development and Labour Council
NC : Northern Cape
NDSF : National Spatial Development Framework
Nov : November
NW : North West
OCSLA : Office of the Chief State Law Advisor
PBAC : Programme, Budget and Administration Committee
PoE : Portfolio of Evidence
PPR : Peste des Petits Ruminants
PTC : Provincial Technical Committee
Q1 : Quarter 1
Q2 : Quarter 2
ACRONYMS

## Slide 67
Q3 : Quarter 3
RID : Rural Infrastructure Development
RVCP : River Valley Catalytic Programme
SCM : Supply Chain Management
SITA : State Information Technology Agency
SP : Service Provider
TRANCRAA : Transformation of Certain Rural Area Act
WC : Western Cape
WCDARD : Western Cape Department of Agriculture and Rural Development
ACRONYMS