## Slide 1
Presentation to the Portfolio Committee on Women, Youth and Persons with Disabilities
1 March 2022
REPORT ON THE IMPLEMENTATION OF THE ANNUAL PERFORMANCE PLAN FOR QUARTER THREE 2021/2022

## Slide 2: PRESENTATION STRUCTURE
INTRODUCTION
STRATEGIC FOCUS
OUTCOMES
APP PROGRAMME SUPPORTING SONA, NDP, MTSF & INTERNATIONAL INSTRUMENTS
SUMMARY OF ACHIEVEMENTS
QUARTERLY COMPARISON
APP TARGETS

## Slide 3: INTRODUCTION
The Commission for Gender Equality (CGE) is one of the institutions established in terms of Chapter 9 of the Constitution of the Republic of South Africa, 108 of 1996. In terms of section 187 of the Constitution, the mandate of the CGE is to contribute to strengthening and deepening constitutional democracy in South Africa through the promotion, protection, development and attainment of gender equality.
The powers and functions of the CGE are further outlined in the CGE Act 39 of 1996 as amended (“CGE Act”), which include monitoring and evaluating the policies and practices of government, the private sector and other organisations to ensure that they promote and protect gender equality; public education and information; reviewing existing and upcoming legislation from a gender perspective; investigating inequality; commissioning research and making recommendations to Parliament or other authorities; investigating complaints on any gender-related issue and monitoring and reporting on South Africa’s compliance with international conventions.
The CGE is therefore an independent institution that is subject to the Constitution and the law and must be impartial in the exercise of its powers and perform its functions without fear, favour or prejudice.

## Slide 4: STRATEGIC FOCUS
Vision
A society free from all forms of gender oppression and inequality
Mission
To promote, protect, monitor and evaluate gender equality through research, public education, policy development, legislative initiatives, effective monitoring and litigation
Values
Are anchored in the supremacy of the Constitution and the rule of law, and we perform all our functions with an ethos grounded in the following values:
  Independence – we impartially perform our duties without fear or favour, mindful of the independence of our office.
  Professionalism – we timeously execute our responsibilities with the utmost care and diligent
  Accountability – we always give an account of our actions and decisions
  Ethical behaviour – we strive to maintain high standards of:
Trustworthiness and honesty
Respect and empathy
  Integrity
Teamwork – we support and work in collaboration with our colleagues, state organs and civil society to maximise the attainment of our objectives.

## Slide 5: OUTCOMES
  3.1. An enabling legislative environment for gender equality
  Purpose: To evaluate legislation, policies, practices and mechanisms within public and private institutions
  and make recommendations to bring about continuous improvements to advance gender
  equality.
3.2. Gender equality promoted and protected through information, education, investigations and
litigations.
Purpose: To conduct advocacy initiatives, public education, investigations and litigations in promotion of
gender equality and a society free from gender discrimination.
3.3. Monitoring and research investigations on issues that undermine the attainment of gender equality
and women’s empowerment.
Purpose: To identify and monitor key issues that impact on gender equality, to evaluate the contribution
being made by role-players, to make recommendations and undertake interventions to promote
and attain gender equality.
3.4. An efficient, effective and sustainable organisation that promotes good corporate governance.
Purpose: To build and maintain efficient and effective organisational systems, processes and
mechanisms to promote and protect gender equality.

## Slide 6: APP PROGRAMMES SUPPORTING THE SONA, NDP, MTSF & INTERNATIONAL INSTRUMENTS
# | SONA | NDP | MTSF | CGE Programmes
4.1 | A capable, ethical and developmental state | Ch12: Building a capable and developmental state | Priority 1: Building a capable, ethical and developmental state | Compliance with international and regional agreements relating to gender equality (e.g., CEDAW, Maputo Protocol, SDGs)
4.2 | Economic transformation and job creation | Ch 3: Economy and Employment | Priority 2: Economic Transformation & Job Creation | Gender Transformation hearings on TVET institutions, private and public institutions; Status report: enabling & sustaining women empowerment (GRBF and WEP); Gender Mainstreaming programme
4.3 | Education, skills and health | Ch 9: Improving Education, Innovation & Training Ch 10: Promoting Health | Priority 3: Education, Skills & Health | Outreach, advocacy and legal clinics; Systemic investigation, Community Radio programme Social media campaigns
4.4 | Consolidating social wage through reliable & quality basic services | Ch 11: Social Protection | Priority 4: Consolidating social wage through reliable & quality basic services | Tracking and follow up on the implementation of findings and recommendations
4.5 | Social Cohesion & Safe Communities | Ch 12: Building Safer Communities | Priority 6: Social Cohesion & Safe Communities | Legislative submissions; Complaints handling; Investigations, Status of the country’s response to GBV

## Slide 7: SUMMARY OF ACHIEVEMENTS
OUTCOME | Planned Quarterly Targets | Achieved Targets | Unachieved Targets | Percentage Achieved Targets
An enabling legislative environment t for gender equality. | 7 | 5 | 2, 1 partially achieved. | 71%
Gender equality promoted and protected through information, education, investigations and litigations. | 8 | 8 | 0 | 100%
Monitoring and research investigations on issues that undermine the attainment of gender equality and women’s empowerment. | 10 | 10 | 0 | 100%
An efficient, effective and sustainable organisation that promotes good corporate governance. | 13 | 13 | 0 | 100%
Total Targets Achieved: Q3 | 38 | 36 | 2 | 95%

## Slide 8: 6. QUARTERLY COMPARISON
QUARTER ONE |  |  | 
Planned Quarterly Targets | Achieved Targets | Unachieved Targets | Percentage Achieved Targets
38 | 30 | 8 | 79%
QUARTER TWO |  |  | 
38 | 32 | 6 | 84%
QUARTER THREE |  |  | 
38 | 36 | 2 | 95%

## Slide 9: 7. APP TARGETS OUTCOME 1: AN ENABLING LEGISLATIVE ENVIRONMENT T FOR GENDER EQUALITY
# | Output Indicators | Annual Targets | Q3 Targets | Actual Performance | Variance | Corrective Action
1 | Number of submissions on new and proposed legislation that substantively promotes and protects gender equality | 16 submissions on new and proposed legislation that substantively promotes and protects gender equality | 4 submissions on new and proposed legislation that substantively promotes and protects gender equality | 1 submission was made on maternity and parental benefits for self-employed workers in the informal economy. | In quarter 3 the cumulative variance is 6 submissions. | The CGE must identify 10 pieces of legislation for input by the end of the 4th quarter, to achieve the annual target.
2 | Number of consolidated reports to the president and the Speaker’s office on the submissions made and an analysis of the outcomes of the engagements with parliament and other key stakeholders on new and proposed legislation | A consolidated report on submissions and outcomes of engagements with parliament and other key stakeholders on new and proposed legislation | A report on submissions and outcomes of engagements with parliament and other key stakeholders on new and proposed legislation | A report was not compiled as no submissions were made. | 1 quarterly report. | 2 quarterly reports to be produced in Q4.

## Slide 10
OUTCOME 1: Cont…
# | Output Indicators | Annual Targets | Q3 | Actual Performance | Variance | Corrective Action
3 | Number of high-level meetings with identified key national stakeholders (i.e., national ministries, parliament and civil society organisations on the ratification and domestication of international and regional instruments). | 3 High-level meetings and a status report with outcomes of the meetings with identified key national stakeholders (i.e., national ministries, parliament and civil society organisations on the ratification and domestication of international and regional instrument). | 1 x High level meetings with identified key national stakeholders to inform the monitoring report (i.e., national ministries, parliament and civil society organisations on the ratification and domestication of international and regional instruments). | 1 High level meeting was conducted, where the CGE made a presentation to the PC: WYPD, on the assessment of SADC Protocol on Gender & Development and the potential impact on current legislation that deals with child marriages. | No Variance | No Corrective Action
4 | Number of monitoring and evaluation reports on policies and practices to promote gender transformation. | 3 Monitoring and evaluation reports on policies and practices to promote gender transformation | Analyses of Information from consultative meetings. | Transformation hearings were conducted with TVET colleges, public and private entities in November 2021, as part of consultative meetings to promote gender transformation. Analyses of information in this regard has been conducted and reports to be produced in Q4. | No Variance | No Corrective Action

## Slide 11
OUTCOME 1: Cont…
# | Output Indicators | Annual Targets | Q3 | Actual Performance | Variance | Corrective Action
5 | Number of High- level meetings with institutions and stakeholders on the findings and recommendations contained in the CGE gender transformation reports | 4 High level meetings with institutions and stakeholders on the findings and recommendations contained in the CGE gender transformation reports | 1 High level meetings with institutions and stakeholders on the findings and recommendations contained in the CGE gender transformation reports | A high-level meeting was conducted, where the CGE engaged the Portfolio Committee on Employment & Labour on the findings and recommendations of the following reports: Gender Transformation in Tertiary Institutions for 2018/2019. Follow-Up Hearings on Employment Equity and Gender Transformation in the Private Sector for 2019/2020. Progress Report: Transformation in the Public and Private Sectors. | No Variance | No Corrective Action
6 | Number of monitoring engagements with national government institutions on the implementation of rules & regulations for women’s empowerment | 2 monitoring engagements & a report on the outcomes of the engagements, with national government institutions on the implementation of rules & regulations for women’s empowerment | Monitoring engagements & a report on the outcomes of the engagements, with national government institutions on the implementation of procurement rules & regulations for women’s empowerment | Planned field work completed, including data collection with various public entities. However, accessing data on procurement figures remain a challenge. Research reports are currently being compiled. | No Variance | No Corrective Action
7 | Number of webinars and policy briefs conducted to follow up on commitments made in the 2020/2021 webinars. | 4 webinars and policy briefs conducted to follow up on commitments made in the 2020/2021 webinars. | 1 webinars and policy briefs conducted to follow up on commitments made in the 2020/2021 webinars. | 1 Webinar was conducted on the CGE LGBTQI+ Equality Project. | No Variance | No Corrective Action

## Slide 12
OUTCOME 2: GENDER EQUALITY PROMOTED AND PROTECTED THROUGH INFORMATION, EDUCATION,
INVESTIGATIONS AND LITIGATIONS
# | Output Indicators | Annual Targets | Q3 Targets | Actual Performance | Variance | Corrective Action
1. | Number of education and information programmes conducted based on a project plan | Consolidated Report on content development for education and information programmes | Implementation of project plan and report drafted on content development for education and information programmes | Content development for educational programmes was conducted including brochures on Widows/widowers Rights, SRHR and the printing of the Xhosa Gender Terminology Booklet. | No variance | No Corrective Action
2. | Number of training workshops on gender and development | 36 training workshops on gender and development | 9 training workshops on gender and development | 9 gender and development workshops were done focusing on the CGE mandate, Gender Equality and Equity. | No variance | No Corrective Action
3 | Number of consolidated reports on Media advocacy and outreach campaigns through community radio stations | A consolidated report on media, advocacy and outreach campaigns through community radio stations. | Implementation of project plan and report drafted the implementation of media, advocacy and outreach campaigns through community radio stations | 168 Radio Interviews were conducted, with a reach of 137 518 600 listenership. A report is included in the narrative below. 74 Television Interviews with a viewership of 118 690 078, across all channels. Print Articles: 168, with a reach of 5 687 260, across all publications. | No Variance. | No Corrective Action
4. | Number of High-level meetings with & a report with the outcomes of meeting with DBE, SACE & Teachers’ Unions on GBV & learner pregnancy. | 2 High level meetings & a report with outcomes of meeting with DBE, SACE & Teachers’ Unions on GBV & learner pregnancy. | 1 High level meetings & a report with outcomes of meeting with DBE, SACE & Teachers’ Unions on GBV & learner pregnancy. | Through the NC Office, in October 2022, the CGE engaged in a high-level consultation exercise, where a situation analysis was conducted with DoE, DSD and DOH amongst others, where prevailing issues of GBV were identified, including the high prevalence of teenage pregnancy and sexual harassment in schools. | No Variance. | No Corrective Action

## Slide 13
OUTCOME 2: Cont…
# | Output Indicators | Annual Targets | Q3 | Actual Performance | Variance | Corrective Action
5. | Number of social media and podcast campaigns focussing on GBV (men and boys, GBV with its interface with Disability, Covid 19, informal workers/traders, LGBTIQ+). | 4 social media and podcast campaigns focussing on GBV (men and boys, GBV with its interface with Disability, Covid 19, informal workers/traders., LGBTIQplus.) | 1 social media and podcast campaigns focussing on GBV (Men and boys, GBV with its interface with Disability, Covid 19, informal workers/traders, LGBTIQ+) | 1 social media and podcast campaign was conducted, consisting of: 03 Podcasts published on CGE Twitter page. 01 podcasts published on CGE YouTube channel. 449 posts published on CGE Twitter Page, promoting CGE Media Interviews, and CGE Messages on Gender Inequality, GBV, LGBTIQ and CGE Provincial Activities. 130 posts published on CGE Facebook on CGE media activities, GBV, men and boys and Gender Inequality. | No Variance. | No Corrective Action
6. | Number of assessment reports on gender mainstreaming interventions to lobby and influence decision makers within public and private institutions. | One assessment report on Gender Mainstreaming interventions to lobby and influence decision makers within public and private institutions. | A quarterly assessment report on Gender Mainstreaming interventions to lobby and influence decision makers within public and private institutions. | The CGE engaged in various gender mainstreaming exercises during the quarter, including a presentation to the DoE senior management. The narrative report is included below. | No variance | No Corrective Action

## Slide 14
OUTCOME 2: Cont…
# | Output Indicators | Annual Targets | Q3 | Actual Performance | Variance | Corrective Action
7. | Number of outreach, advocacy and access to justice interventions conducted guided by a project plan. | 108 outreach, advocacy and access to justice interventions conducted guided by a project plan. | 27 outreach, advocacy and access to justice interventions conducted guided by a project plan. | 27 Outreaches, Advocacy and Access to Justice interventions were conducted. | No variance | No Corrective Action
8. | Number of stakeholder engagements with likeminded organisations/institutions on topical issues relating to gender equality which will inform CGE planning and programmes | 36 stakeholder engagements with likeminded organisations/institutions on topical issues relating to gender equality which will inform CGE planning and programmes | 9 stakeholder engagements with like-minded organisations/institutions on topical issues relating to gender equality which will inform CGE planning and programmes | 9 stakeholder engagements were conducted with like-minded institutions focusing on gender related topical issues | No variance | No Corrective Action

## Slide 15
OUTCOME 3: MONITORING AND RESEARCH INVESTIGATIONS ON ISSUES THAT UNDERMINE THE
ATTAINMENT OF GENDER EQUALITY AND WOMEN’S EMPOWERMENT CONDUCTED
# | Output Indicators | Annual Targets | Q 3 Targets | Actual Performance | Variance | Corrective Action
1. | Number of Consolidated reports on complaints handled | Consolidated report on complaints handled | A quarterly report drafted on complaints handling | The quarterly report on complaints handling is included in the narrative section below. | No variance | No Corrective Action
2. | Number of courts monitored and a report of the outcomes. | 40 courts monitored and a report of the outcomes. | 10 courts monitored and a report of the outcomes. | 13 courts were monitored through a court monitoring tool. Data will be analysed, and a report produced in Q4. 2 physical court monitoring exercises were also conducted for the Amotoso case. | No variance | No Corrective Action
3. | Number of Monitoring reports on progress on compliance with the findings and recommendations of systemic investigations conducted. | Monitoring report on progress on compliance with the findings and recommendations of systemic investigations conducted. | Implement the project plan on monitoring of the implementation of the findings and recommendations of systemic investigations conducted | Responses were received from entities, many highlighting budgetary constraints for implementing the recommendations of the Commission. The Commission will compile a final report during Q4. Forced Sterilisation- The CGE awaits report from the new Minister in the Department of Health. | No variance | No Corrective Action
4. | Number of monitoring reports on government’s implementation of GBV Programmes (NSP, Multi-sectoral structure on GBV, concept note on GBV Index, develop GBV Index). | One monitoring report on government’s implementation of GBV Programmes (e.g., NSP, Multi-sectoral structure on GBV, concept note on GBV Index, develop GBV Index). | Draft report on the findings and recommendation | Field work continues in this project, is still underway, however, access to information on issues of GBV remains a challenge. The research report in this regard is currently being compiled. | No variance | No Corrective Action

## Slide 16
OUTCOME 3: CONT…
# | Output Indicators | Annual Targets | Q3 | Actual Performance | Variance | Corrective Action
5. | Number of status reports on the implementation of the CGE findings & recommendations of the ERAP Report. | 1 Status report on the implementation of the CGE findings & recommendations of the ERAP Report. | Draft report on the findings and recommendation | Follow up with the 22 implementing departments continued in this quarter, however, reluctance to provide information by participating stakeholders meant that reliance was put on official reports and publications to inform the report on progress and to gain greater insights into the responses of these institutions to the findings contained in the ERAP report. | No variance | No Corrective Action
6. | Number of monitoring reports on gender representation in the 2021 Municipal Elections | A monitoring report on gender representation in the 2021 Municipal Elections | Draft report on the findings and recommendations | The work of compiling the Local Government Elections Report is currently underway, scheduled to be completed in the fourth quarter. | No variance | No Corrective Action
7. | Number of police stations & Thuthuzela Care Centres in rendering GBV services. monitored. | 432 police stations & Thuthuzela Care Centres in rendering GBV services monitored & a report with outcomes of the monitoring. | 36 police stations & Thuthuzela Care Centres in rendering GBV services monitored & a report with outcomes of the monitoring. | 53 monitoring visits were conducted across the provinces, 42 on SAPS stations & 11 TCCs. | No variance | No Corrective Action
8. | Number of monitoring reports on the government's Gender Responsive Planning, Budgeting, Monitoring, Evaluation, Auditing Framework (GRPBMEAF) | A monitoring report on the government's Gender Responsive Planning, Budgeting, Monitoring, Evaluation, Auditing Framework (GRPBMEAF) | Draft report on the findings and recommendations | Fieldwork was completed and a draft report has been compiled for finalisation in quarter 4. | No variance | No Corrective Action

## Slide 17
OUTCOME 3: CONT…
# | Output Indicators | Annual Targets | Q3 | Actual Performance | Variance | Corrective Action
9. | Number of high- level meetings and a report on the outcomes, with institutions, stakeholders and policy makers on the findings and recommendations contained in the CGE monitoring and research reports | 4 high level meetings and a report on the outcomes of meetings with institutions, stakeholders and policy makers on the findings and recommendations contained in the CGE monitoring and research reports | 1 High level meetings with institutions, stakeholders and policy makers on the findings and recommendations contained in the CGE monitoring and research reports | A high-level meeting was conducted, where the CGE presented the report on Follow-Up Hearings on Gender Transformation in Tertiary Institutions for 2019/20, to the Portfolio Committee on Higher Education, Science & Technology. | No variance | No Corrective Action
10. | Monitor procurement allocation for women’s empowerment | A report on procurement allocations for women’s empowerment | Quarterly report on procurement allocations for women’s empowerment | Planned field work completed, including data collection with various public entities. However, accessing data on procurement figures remain a challenge. Research reports are currently being compiled. | No variance | No Corrective Action

## Slide 18
OUTCOME 4: AN EFFICIENT, EFFECTIVE AND SUSTAINABLE ORGANISATION THAT PROMOTES GOOD
CORPORATE GOVERNANCE
# | Output Indicators | Annual Targets | Q3 Targets | Actual Performance | Variance | Corrective Action | 
1 | Number of reports on the assessment of plenary effectiveness | A report on the assessment of plenary effectiveness | No activity | - | - | - | 
2 | Number of reports on the assessment of Subcommittees’ effectiveness | A report on the assessment of Subcommittees’ effectiveness | No activity | - | - | - | 
3 | Status of audit outcome. | Unqualified Audit opinion on Financial and Non-financial report by AGSA | Implement Financial Management plan, supported by sound systems of internal controls, Risk Management and Management of Revenue, Expenses, Assets and Liabilities and report thereon in accordance with relevant prescripts | Unqualified audit opinion has been achieved, as the financial management plan continues to be implemented, supported by sound systems of internal controls. | No variance | No Corrective Action | 
4 | Number of business implementation plans and quarterly reports on HR Staffing adaptation in line with the business model | Report on the implementation of the business model & HR staffing adaptation in line with the business model. | Implement business model plan | The business model implementation plan has been developed outlining the process of unfolding the CGE business model. A session will take place in February 2022, to operationalise the implementation plan. | No variance | No Corrective Action | 

## Slide 19
OUTCOME 4: CONT…
# | Output Indicators | Annual Targets | Q3 | Actual Performance | Variance | Corrective Action
5. | Number of reports on the implementation of the IKM plan | Quarterly report on the implementation of IKM plan | Quarterly report on the implementation of IKM plan | A report was submitted indicating that the appointment of a service provider to operationalise the IKM plan is underway. | No variance | No Corrective Action.
6. | Number of reports on the implementation of the ICT Strategy and Plan | Quarterly reports on the implementation of ICT plan | Quarterly report on the implementation of ICT plan | A report was submitted indicating the implementation of the renewal of Microsoft Office 365 being was completed, renewal of email signatures, installation of TV monitors in most of the provinces, completion of Wi-Fi installation in all provincial offices and server software upgrade. | No variance | No Corrective Action.
7. | Number of reports on the implementation of the M&E Plan | Report on the implementation of M&E Plan | Implement M&E Plan | A quarterly report on the implementation of M&E Plan has been developed. | No variance | No Corrective Action.
8. | Number of reports on the implementation of the tracking tool. | Report on the implementation tracking tool | Implement tracking tool | The tracking tool has been updated with new project information. | No variance. | N/A

## Slide 20
OUTCOME 4: CONT…
# | Output Indicators | Annual Targets | Q3 | Actual Performance | Variance | Corrective Action
9. | Number of reports on the implementation of the performance information management policy informed by the business model and the M&E Plan | Report on the implementation of the performance information management policy informed by the business model and the M&E Plan | Implement performance information policy informed by business model and the M&E Plan | Implementation of the performance information policy commenced with the review of the policy to align it to the M&E Framework. | No variance. | N/A
10. | Number of strategic partnership agreements | 4 Strategic partnership agreements | 1 strategic partnership | A strategic partnership was entered into with the ETDP SETA. | No variance. | N/A
11. | Number of reports on the implementation of the Communications strategy and Plan Implemented | Report on the implementation of the Communications strategy and Plan implemented | Implement communications strategy and plan | The communications strategy and plan were implemented through the production of Three-monthly monitoring reports on radio interviews issued. | No variance. | N/A

## Slide 21
OUTCOME 4: CONT…
# | Output Indicators | Annual Targets | Q3 | Actual Performance | Variance | Corrective Action
12. | Number of Consolidated Media monitoring reports on coverage of gender issues through traditional and digital media | Consolidated Media monitoring reports on coverage of gender issues through traditional and digital media | Media monitoring report on coverage of gender issues through traditional and digital media | A media monitoring report was produced on TV interviews conducted by the CGE. | No variance. | N/A
13. | Number of reports on the implementation of the HR Plan | A report on the implementation of the HR Plan | Implement HR Plan | A tender was advertised, and Three (3) recruitment agencies were appointed to conduct the recruitment process. All vacant posts were advertised in November 2021. Interviews were conducted for the HR Manager and Finance Manager and currently at vetting stage. There was one resignation of the Legal Officer in Mpumalanga. The Employment Equity report has been submitted to the Labour Department as required by law. The newly appointed Wellness service provider was introduced to staff and all related information disseminated. | No variance. | N/A

## Slide 22
HAVE A GENDER RELATED COMPLAINT ????
REPORT IT TO
0800 007 709