## Slide 1
Presentation TO THE
HUMAN SETTLEMENTS PORTFOLIO COMMITTEE
On the
AUDIT ACTION PLAN ARISING FROM THE
2020/21 AUDIT OUTCOMES
16 February 2022
LAYING STRONG FOUNDATIONS FOR TOMORROW’S SUCCESS

## Slide 2: Table of Contents
Purpose
Key issues in the 2021 audit report
Supply chain management
Information Technology
Accounting
Key risks 2022 audit
Recommendation

## Slide 3: PURPOSE

## Slide 4: PURPOSE OF PRESENTATION
To update the Parliamentary Portfolio Committee on Human Settlements on action taken around the findings of the Auditor-General relating to the annual financial statements for 2020/21 of the National Housing Finance Corporation SOC Ltd

## Slide 5: KEY ISSUES IN THE 2021 AUDIT REPORT

## Slide 6: KEY ISSUES ADDRESSED BY THE AUDIT ACTION PLAN
Supply Chain Management - irregular expenditure
Supply Chain Management – Failure to pay invoices within 30 days of receipt
Information Technology – many challenges
Incorrect disclosure in annual financial statements submitted for audit
Lack of adequate reconciliations and reviews

## Slide 7: SUPPLY CHAIN MANAGEMENT

## Slide 8: SUPPLY CHAIN - MAJOR INTERVENTIONS
  Supply Chain Manager dismissed
  Loss Control Committee appointed
  LCC terms of reference include ensuring CFO implements recommendations to prevent irregular expenditure
  Internal recruitment of new Supply Chain Manager underway
  Supply Chain Department restructured
  Morale issues with supply chain employees being addressed
  Contract management system procured and operational

## Slide 9: SUPPLY CHAIN – OTHER INTERVENTIONS
  Supply Chain Policy updated
  Delegation of Authority amended to ensure appropriate positions are empowered to act around procurement
  Irregular, Fruitless and Wasteful Expenditure Policy updated to include reporting requirements and collection
  Contract management system procured and operational

## Slide 10: SUPPLY CHAIN – TIMELY PAYMENT OF INVOICES
  On Rental Repair Programme, we pay nearly all invoices within 14 days to 130 SMMEs
  Creditors age analysis currently reflects no invoices older than 30 days
  Not good enough yet as occasional invoices still being paid after 30 days
  Processes to resolve this are being implemented as part of remaining SCM solutions

## Slide 11: INFORMATION TECHNOLOGY

## Slide 12: INFORMATION TECHNOLOGY – GENERAL ACTIONS
  At merger IT systems were totally out of date
  IT Executive recruited – immediately started to implement improvement plan
  Her work enabled NHFC to work remotely from start of lockdown with only minor issues
  Conducted Enterprise Architecture Project to assess what processes were required
  Used this to issue tender in January – allowed longer than usual for submissions to ensure good quality received

## Slide 13: INFORMATION TECHNOLOGY – SECURITY
  Disaster recovery testing carried out twice during the current financial year
  Physical and environmental controls over server room improved, with most data now being stored in the cloud
  Continuous enhancement programme over IT security

## Slide 14: ACCOUNTING

## Slide 15: ACCOUNTING – GRAP COMPLIANCE
  Entire Finance team trained on GRAP
  Full review of annual financial statements prior to submission to AG on 31 May
  Earlier engagement with AG to ensure audit completed earlier (Audit plan approved January 2022 – prior year was April 2021)

## Slide 16: ACCOUNTING – RECONCILIATIONS AND FILING
  Reviews of reconciliations evidenced
  Electronic filing system in process of implementation

## Slide 17: KEY RISKS 2022 AUDIT

## Slide 18: 2022 AUDIT RISKS
  There is irregular expenditure – already identified and action being taken
  R57 million stolen from our ABSA money market account recovered – will lead to audit questions
  IT system enhancements still in progress

## Slide 19: RECOMMENDATION

## Slide 20: RECOMMENDATION
  It is recommended that the Portfolio Committee note the progress on clearing the audit findings for the 2020/21 audit of the NHFC’s financial statements.

## Slide 21: THANK YOU