## Slide 1
PRESENTATION TO THE PORTFOLIO COMMITTEE ON COOPERATIVE GOVERNANCE AND TRADITIONAL AFFAIRS
DCOG 3RD QUARTER PERFORMANCE REPORT 2021/22 FY
22 March 2022
Presented by Ms. Avril Williamson- Director-General

## Slide 2: PRESENTATION OUTLINE
Purpose
Overview- Summary of performance
Part A: DCOG Annual Performance Report for 2020/21 FY
Part B: DCOG Annual Financial Performance for 2020/21 FY
Response to issues raised in the BRRR for 2020/21 and 2022/21
Recommendations

## Slide 3: PURPOSE
To present to the Portfolio Committee on Cooperative Governance and Traditional Affairs, Quarter 3 Performance for the Department of Cooperative Governance

## Slide 4: Summary Dashboard Performance for quarter 3
Chart: 2021/22 Q3
| Achieved | Not Achieved
 | 21 | 7
Q3 |  |  |  | 
Branch | Total | Achieved | Not Achieved | %
Admin | 5 | 4 | 1 | 80%
LGSIM | 9 | 6 | 3 | 67%
ID | 8 | 6 | 2 | 75%
NDMC | 4 | 4 | 0 | 100%
CWP | 2 | 1 | 1 | 50%
TOTAL | 28 | 21 | 7 | 75%
The performance of the set targets has improved to 75% in Q3 compared to 60% in Q2.
Quarterly Comparison |  | 
Q1 | Q2 | Q3
62% | 60% | 75%

## Slide 5
PART A
ANNUAL PERFORMANCE INFORMATION REPORT FOR 2020/21 FY

## Slide 6: List of ACHIEVED targets per programme
ADMINISTRATION
Q2 CSIP Progress report was presented to EXCO on 25 October 2021.
34% implementation of CSIP as contained in progress report by 31 December 2021.
Q2 FMIP progress report was submitted to EXCO on 26 October 2021.
30% implementation of FMIP as contained in progress report has been achieved.
LOCAL GOVERNMENT SUPPORT AND INTERVENTIONS MANAGEMENT
39 One Plans have been finalised (6 metros and 33 districts).
Draft report on the alignment of One Plans and IDPs finalized.
A draft report on the Integration of Economic Recovery/ Development Plans into the DDM has been developed
R7 billion (44%) of the 2021/22 MIG allocations was reported by municipalities as spent.
Draft One-Plan targets and indicators for three smart cities submitted to Minister by 15 December 2021
1 Section 139 Report on the implementation of Intervention Improvement Plans compiled and submitted.

## Slide 7: List of ACHIEVED targets per programme continued
Institutional Development
For the quarter under review consultations were conducted with the National Treasury and the South African Local Government Association (SALGA) to review and provide inputs on the Draft Municipal Financial Viability Assessment and Improvement Tool. The inputs from the consulted key stakeholders were considered and incorporated in the Draft Municipal Financial Viability Assessment and Improvement Tool.
Quarterly report on support provided on preparations for the 2021 LGE was developed by 15 December 2021
Draft Integrated Local Government Capacity Building Strategy developed.
Stakeholder engagements undertaken and reports developed for Vhembe district ,Waterberg district, Sarah Baartman district, Thaba Chweu LM, EC IGR forum, WC Communicators Forum, EC Technical MuniMEC, Registering Property working group, Moqhaka LM, Mafube LM, Fezile Dabi district and Buffalo City metropolitan municipality.
Three MPAC functionality reports were developed by 31 December 2021.
Report on the implementation of actions to address issues raised by the AGSA in line section 134 of the MFMA developed and submitted to form part of section 48 report and/ state of local government report.

## Slide 8: List of ACHIEVED targets per programme continued
NATIONAL DISASTER MANAGEMENT CENTRE
Two (2) district municipalities (Umkhanyakude and Ehlanzeni) in priority disaster areas were supported to prevent, prepare and mitigate disaster risks through applicable disaster management plans by 31 December 2021.
A comprehensive presentation on the disaster funding arrangements was prepared and presented by the NDMC in the meeting of 17 November 2021 with DHS. A report was prepared and approved by the NDMC-HOC.
The performance and financial reports have been prepared and submitted to National Treasury as per the Division of Revenue Act. A comprehensive report on the disaster grant performance and expenditure for the Municipal and Provincial Disaster Relief Grants for quarter 3 has been prepared and approved by the Head of Centre.
An introductory letter was written to the Department of Health and a meeting was held through MS Teams with the Department of Health on 26 November 2021.
COMMUNITY WORK PROGRAMME
251 221 people participating in the CWP programme by the 31December 2021. SITA is still busy processing the December 2021 Wage Bill Extract; The December 2021 Wage Bill Report is not yet available. The report will be available after all procedures have been completed.

## Slide 9: Administration- targets not achieved
Annual Target | Achievement | Reasons for Deviation
1.6) Percentage implementation of the Internal Audit Plan | Not Achieved, 54% implementation of the Internal Audit plan has been achieved (14 out of the 26 yearly targets). | The project started late in November 2021 The panel of service provider have been appointed and started with audit work in December 2021. It is anticipated that two of the outstanding audits(cyber security & CWP Site visits) will be finalized in Quarter 4.

## Slide 10: Local Government Support and Interventions- targets not achieved
Annual Target | Achievement | Reasons for Deviation
2.3) Integrated Monitoring Framework for DDM reporting developed by 31 March 2022 | Not achieved, An initial Draft Framework developed with the assistance of a service provider appointed by the DBSA was not ready for consultation with key stakeholders.. | Agreement was reached with the DBSA that the services of an M&E specialist, with the necessary experience and expertise would be obtained. Such an M&E specialist was subsequently appointed by the DBSA to have a revised draft framework ready by the end of January 2022 for consultation with key role players in February 2022.
2.4) First release of the DDM IMS priority modules developed | Not achieved, The solution development for the DDM IMS was put on hold from 28 June 2021 since the service provider failed to deliver the milestones that were agreed upon in the contract which included the 1st and 2nd quarter APP targets. A new service provider has subsequently been appointed for the implementation of the IMS solution and a kick off meeting was held on the 2nd December 2021. The contractual documents are currently being finalised to enable the teams to commence work in January 2022. An IMS Project Steering Committee framework has been drafted and reviewed by members who will be responsible for the approval of the IMS products. | A new service provider has subsequently appointed through DBSA contract for the implementation of the IMS solution and a kick off meeting was held on the 2nd December 2021. The contractual documents are currently being finalised to enable the teams to commence work in January 2022. An IMS Project Steering Committee framework has been drafted and reviewed by members who will be responsible for the approval of the IMS products. The requirements analysis and prioritization with the relevant stakeholders, and sign-off of the documentation for the priority module(s), will occur in January 2022.
2.9) Report on priority water infrastructure projects identified, funded and included in DDM One-Plans by 31 March 20222.9 | Not achieved, Draft report (Annexure A-C) available to be submitted to the Minister. A draft report is available with regard to MIG water projects per district. | Report to be submitted by end January 2022.

## Slide 11: Institutional development- TARGETS not achieved
Annual Target | Achievement | Reasons for Deviation
3.3) 52 municipalities with reduction of non-revenue electricity as a target in their SDBIPs. | Not achieved, 29 Municipalities have included a target to reduce non-revenue electricity losses on their SDBIPs. It is worth noting that even though in Q2 the target was met, This APP has been challenging from Q3 on non-revenue electricity has been met, it is going to be a challenge achieving Q4 target and annual target. This is mainly because the APP was crafted after the SDBIPs for 2021/22 were approved. | The plan is to use the upcoming budget review process to request information from municipalities that might relate to the target on reduction of NRE or any other plan to reduce the losses as this might be used as evidence that the municipalities have are considering the reduction of non-revenue losses. Furthermore, request the municipalities to include the target on reduction of NRE going forward.
3.4) 144 municipalities with reduction of non-revenue water as a target in their SDBIPs by June 2021. | Not achieved, 29 Municipalities have included a target to reduce non-revenue electricity losses on their SDBIPs. It is worth noting that even though in Q2 the target was met, This APP has been challenging from Q3 on non-revenue electricity to meet and it is going to be a challenge achieving Q4 target and annual target. This is mainly because the APP was crafted after the SDBIPs for 2021/22 FY were approved. | The plan is to use the upcoming budget review process to request information from municipalities that might relate to the target on reduction of NRW or any other plan to reduce the losses as this might be used as evidence that the municipalities have are considering the reduction of non-revenue losses. Furthermore, we will request the municipalities to include the target on reduction of Non-Revenue Water going forward.

## Slide 12: Community WORK PROGRAMME
Annual Target | Achievement | Reasons for Deviation
5.2) 25 000 CWP participants trained annually by 31 March 2022 | Not achieved, No participants were trained in Q3 using the CWP budget. The current Implementing Agents (IAs) took over the implementation of CWP on the 1st of October 2021 (Q3). They could not start immediately with training procurement as they were still being introduced to the key CWP stakeholders like the Provinces; CWP Municipal Champions; Local Reference Committees (LRCs) etc. They were also busy with the closeout reports and handover processes as well as the re-contracting of site staff and re-registration of participants. The Local Government Elections also delayed training as it was difficult to get LRCs to sit and endorse the reviewed Site Business before the elections. | A catch up plan will be drafted by mid January and more training will be done in Q4

## Slide 13
PART B
FINANCIAL PERFORMANCE

## Slide 14: Expenditure as at the end of 3rd quarter

## Slide 15: EXPENDITURE PER PROGRAMME EXCLUDING GRANTS AND ENTITIES AND THEIR GOODS AND SERVICES

## Slide 16: STATE OF EXPENDITURE ANALYSIS at the enD of 3rd QUARTER
COMPENSATION OF EMPLOYEES
The Department projected to spend R267.7 million on compensation of employees; however only R246.8 million (68.9%) was spent. This indicate that the Department has under spent by R20.9 million, which is 17.8 per cent less than the approved projected drawings.
The lower than anticipated spending is due to delays in:
The filling of vacant funded posts on staff turnover. (The vacancies are calculated for the remaining three months on the 2021/22 financial year),
The vacancies in the office of the Deputy Minister (DM) after his (Mr. Parks Tau) redeployment to Gauteng Provincial government which were only filled from October 2021 after the appointment of the new DM, Ms. Thembi Nkadimeng; and
The outstanding payments for performance bonuses and pay progressions for SMSs.
GOODS AND SERVICES
The Department has now spent R2.996 billion (83.1%) of the approved drawings/ planned expenditure of R3.610 billion (55.4%) on goods and services as at 31 December 2021. This indicates that the Department has spent R614 million (17.0%) less than planned expenditure/ approved drawings. The under spending is attributed to:
DBSA Invoicing is generally slow as the Implementing Agent for the Department on the DDM and IUDF and the delays in the implementation of the annual departmental Procurement Plan. The contracted of the NPO’s implementing CWP on behalf of the Department end in September 2021, which affected the procurement of materials because of the handover process that had to be completed to the new NPOs and clearing of the outstanding invoices.

## Slide 17: 2021/22 STATE OF EXPENDITURE PER ENTITY

## Slide 18
RECOMMENDATIONS
It is recommended that the Portfolio Committee note the quarter 3 performance report for the financial year 2021/22.

## Slide 19
Response to issues raised in the BRRR for 2020/21 and 2022/21
See Annexure A of the word document titled Response to issues raised in the BRRR for 2020/21 and 2022/21

## Slide 20
THANK YOU!