## Slide 1
DEPARTMENT OF TRADITIONAL AFFAIRS’ THIRD QUARTER PERFORMANCE INFORMATION AND FINANCIAL REPORT FOR THE 2021/22 FINANCIAL YEAR
22 MARCH 2022
PORTFOLIO COMMITTEE ON COOPERATIVE GOVERNANCE AND TRADITIONAL AFFAIRS
1
Notes: 1

## Slide 2: PRESENTATION OUTLINE
Part A:
  Summary of the Department of Traditional Affairs (DTA) Performance for the 3rd Quarter of 2021/22 FY
  Detailed 2021/22 DTA’s Quarter 3 Performance per Programme
  Summary of the National House of Traditional and Khoi-San Leaders (NHTKL) Performance for the 3rd Quarter of 2021/22 FY
  Detailed 2021/22 NHTKL Quarter 3 Performance
Part B:
  2021/22 Financial Performance
Part C: Progress report on the implementation of the Committees recommendations in the 2021
Budget Vote Report
Recommendation

## Slide 3
PART A
2021/2022 Third Quarter Performance per Programme

## Slide 4: SUMMARY OF OVERALL DTA PERFORMANCE FOR THE 3rd QUARTER OF 2021/2022 FY
Chart: 
The Department had 12 targets for the 3rd Quarter of 2021/2022, of which:
    11 (92%) of the targets were achieved
    1 (8%) of the targets was not achieved
Chart: 2021/22 3rd Quarter Performance
| Achieved | Not Achieved
 | 0.92 | 0.08

## Slide 5
Detailed 2021/2022 Quarter Three Performance per programme

## Slide 6: 3rd quarter performance for programme 1: Administration
7
Outputs | Output Indicators | Annual Target 2021-2022 | 3rd Quarter Targets | Actual performance against the quarterly targets | Reasons for Variance
Performance against Organisational performance Information (OPIM) Compliance Management Plan | % performance against organisational Performance information (OPIM) Compliance Management Plan | 80% performance against organisational performance information (OPIM) Compliance Management Plan | 80% of actions in the Organisational Performance Information Compliance Management Plan for the quarter implemented | Achieved 80% of actions in the Organisational Performance Information Compliance Management Plan for the quarter were implemented | N/A
 |  |  | 80% of actions in the CFM Compliance Management Plan for the quarter implemented | Achieved 80% of actions in the CFM Compliance Management Plan for the quarter were implemented | N/A

## Slide 7: 3rd quarter performance for programme 2:Research,Policy and Legislation (RPL)
8
Outputs | Output Indicators | Annual Target 2021-2022 | 3rd Quarter Targets | Actual performance against the quarterly targets | Reasons for Variance
2021/22 Report on implementation of the TKLA Five-Year Implementation Schedule | Number of 2021/22 projects/actions in the TKLA Five-Year Implementation Schedule implemented | 4 of 2021/22 projects/actions in the TKLA Five-Year Implementation Schedule implemented | TKLA five-year Implementation Schedule approved | Achieved TKLA five-year implementation schedule was approved | N/A
2021/22 Report on implementation of the CIA Five-Year Implementation Schedule | Number of 2021/22 projects/actions in the CIA Five-Year Implementation Schedule implemented | 3 of 2021/22 projects/actions in the CIA Five-Year Implementation Schedule implemented | CIA five-year Implementation Schedule approved | Achieved CIA five-year implementation schedule was approved | N/A

## Slide 8: 3rd quarter performance for programme 3: Institutional Support and Coordination(ISC)
10
Outputs | Output Indicators | Annual Target 2021-2022 | 3rd Quarter Targets | Actual performance against the quarterly targets | Reasons for Variance
Participation of Local Houses in government development programmes in terms of the District Development Model (DDM) monitored | Number of Provinces monitored on the participation of Local Houses of Traditional Leaders in government development programmes in terms of the DDM | 7 Provinces monitored on the participation of Local Houses in government development programmes in terms of the DDM | 7 Provinces monitored on the participation of Local Houses of Traditional Leaders in government development programmes in terms of the DDM | Achieved 7 Provinces were monitored on the participation of Local Houses of Traditional Leaders in government development programmes in terms of the DDM | N/A
Implementation of the remodelled Agrarian Revolution Programme in traditional communities monitored | Number of provinces monitored on the implementation of Agrarian Revolution programme in traditional communities | 8 provinces monitored on the implementation of Agrarian Revolution programme in traditional communities | 2 provinces monitored on the implementation of the Agrarian Revolution programme in traditional communities | Achieved The following 2 provinces were monitored on the implementation of the Agrarian Revolution programme in traditional communities: Mpumalanga and Northern Cape | N/A

## Slide 9: 3rd quarter performance for programme 3: ISC..Cont…
11
Outputs | Output Indicators | Annual Target 2021-2022 | 3rd Quarter Targets | Actual performance against the quarterly targets | Reasons for Variance
Provinces monitored on the functionality of the LHTLs | Number of provinces monitored on the functionality of the LHTLs | 8 Provinces monitored on the functionality of the LHTLs | 4 Provinces monitored on the functionality of the Local Houses of Traditional Leaders | Achieved Monitored the functionality of Local Houses in four (4) provinces as follows: 18 November 2021 – Limpopo 9 November 2021 – Free State 22 November 2021 – Northern Cape 9 December 2021 – North- West 18 January 2022 – Limpopo | N/A
Interventions in the integrated traditional and Khoi-San leadership support programme implemented | Number of interventions in the integrated traditional and Khoi-San leadership support programme implemented | 1 intervention in the integrated traditional and Khoi-San leadership support programme implemented: 8 houses trained on Gender Based Violence and Femicide (GBVF) | 3 houses trained on GBVF | Achieved The following 3 houses were trained on GBVF: Northwest Free State Limpopo | N/A

## Slide 10: 3rd quarter performance for programme 3: ISC..Cont…
12
Outputs | Output Indicators | Annual Target 2021-2022 | 3rd Quarter Targets | Actual performance against the quarterly targets | Reasons for Variance
Monitoring reports on the implementation of social cohesion programme by Provinces | Number of Provinces monitored on the implementation of social cohesion programme | 8 Provinces consulted on the Social Cohesion Programme Approved Social Cohesion Programme | 4 provinces consulted on the Social Cohesion Programme | Not Achieved Only 3 provinces were consulted | The non- achievement of the target is attributed to the last-minute cancellation by one of the provinces.
South African indigenous languages promotion plan developed | Number of South African indigenous languages promotion plan developed | 1 South African indigenous language promotion plan developed | Develop concept document for promotion of South African Indigenous Languages Consultation Report on Indigenous languages promotion plan | Achieved A concept document for promotion of South African Indigenous Languages was developed Achieved A consultation report on Indigenous languages promotion plan was developed | N/A N/A

## Slide 11: 3rd quarter performance for programme 3: ISC..Cont…
Outputs | Output Indicators | Annual Target 2021-2022 | 3rd Quarter Targets | Actual performance against the quarterly targets | Reasons for Variance
Structures of traditional leaders trained on CIA | Number of structures of traditional leaders trained on CIA | CIA training manual developed | Draft CIA training manual developed | Achieved A draft CIA training manual was developed | N/A

## Slide 12
Summary of the National House of Traditional & Khoi-San Leaders (NHTKL) performance for the Third Quarter of 2021/2022 FY

## Slide 13: SUMMARY OF OVERALL NHTKL PERFORMANCE FOR THE 3rd QUARTER 2021/2022 FY
Chart: 
The NHTKL had 7 targets for the 3rd Quarter of 2021/2022, of which:
    7 of 7 (100%) of the targets were achieved
Chart: 2021/22 NHTKL 3rd Quarter Performance
| Achieved
 | 1

## Slide 14
Detailed 2021/2022 NHTKL Quarter Three performance

## Slide 15: 3rd Quarter Performance for ISC sub-programme: National House of Traditional and Khoi-San Leaders (NHTKL)
17
Outputs | Output Indicators | Annual Target 2021-2022 | 3rd Quarter Targets | Actual performance against the quarterly targets | Reasons for Variance
Performance against organisation performance information and corporate and financial compliance management plan | % Performance against organisational performance information Compliance Management Plan | 80% performance against organisational performance information Compliance Management Plan | Organisational Performance Information and corporate and financial management compliance management plan developed | Achieved Organisational Performance Information Compliance Management Plan was developed | N/A N/A
 |  |  | 80% of actions in the organisation performance information and corporate and financial compliance management plan for the quarter implemented | Achieved 80% of actions in the organisation performance information and corporate and financial compliance management plan for the quarter were implemented | 

## Slide 16: 3rd Quarter Performance for ISC sub-programme: NHTKL..Cont…
18
Outputs | Output Indicators | Annual Target 2021-2022 | 3rd Quarter Targets | Actual performance against the quarterly targets | Reasons for Variance
2021 NHTKL projects in the CIA implemented | Number of 2021/22 NHTKL projects in the CIA implemented | 2 NHTKL projects in the CIA implemented: Cultural practices viewed/considered as being against human rights. | Develop draft minimum requirement for registration of Traditional Surgeons Develop Educational material for all role players regarding initiation | Achieved Draft Minimum Requirements for the registration of Traditional Surgeons were developed Achieved Draft educational Guidelines on the Roles for different role players in initiation were developed. | None none

## Slide 17: 3rd Quarter Performance for ISC sub-programme: NHTKL..Cont…
19
Outputs | Output Indicators | Annual Target 2021-2022 | 3rd Quarter Targets | Actual performance against the quarterly targets | Reasons for Variance
2021/22 NHTKL projects in the TKLA implemented | Number of 2021/22 NHTKL projects in the TKLA implemented | 2 NHTKL projects in the TKLA implemented Cultural practice viewed/considered as being against human rights Consultation of Kings/Queens and Principals TLS on Programmes of the NHTKL | Identification of cultural practice viewed/considered as being against human rights 1 Consultation of Kings/Queens and Principal TL’s on programmes of the NHTKL | Achieved Cultural practices viewed as against Human Rights were identified: Report on identified cultural practices viewed as harmful and against human rights was developed Achieved Consultation with the Eastern Cape Kings and Principal traditional leader on InvestRural took place on 09 November 2021 in Mthatha | N/A N/A

## Slide 18: 3rd Quarter Performance for ISC sub-programme: NHTKL..Cont…
Outputs | Output Indicators | Annual Target 2021-2022 | 3rd Quarter Targets | Actual performance against the quarterly targets | Reasons for Variance
Socio-economic development projects in traditional and Khoi-San communities implemented | Number of Socio-economic development projects promoted in traditional and Khoi-San communities | 2 Socio-economic development projects promoted in traditional and Khoi-San communities: Women empowerment (webinar on GBVF) Food Security | 1 Socio-economic development project promoted in traditional and Khoi-San communities: Webinar on women empowerment on GBVF | Achieved The Webinar on Women empowerment on GBVF was successfully held on 15 December 2021. | N/A

## Slide 19: PART B 2021/2022 Financial Performance

## Slide 20: Appropriation Statement per Programme and Economic Classification

## Slide 21: PART C Progress report on the implementation of the Committees recommendations in the 2021 Budget Vote Report

## Slide 22
Progress report on the implementation of the Committees recommendations in the 2021 Budget Vote Report:
2020/21 Preliminary BRR Recommendations | Progress
1.All the Departments and entities reporting to the Committee must ensure consistent submission of Quarterly Performance information, irrespective of whether or not there is a pandemic. This is a legislative requirement. | The Department of Traditional Affairs (DTA) has consistently submitted its quarterly performance reports to the Portfolio Committee. The following DTAs quarterly performance reports were submitted to the Committee: 13 July 2021- 2020/21 3rd and 4th quarter performance information reports. 10 August 2021-DTAs 2021/22 1st quarter performance information report
2.The Department of Traditional Affairs must consider arranging a session, within this quarter, to brief the Committee comprehensively on the key issues central to its mandate, so as to enable the Committee to engage the Department from a well-informed perspective. | The Department is ready to brief the Portfolio Committee on the key issues that are central to its mandate at the Committees earliest convenience.
3.The Department of Traditional Affairs must immediately furnish the Committee with the report on the finalisation and implementation of the Programme of Action (POA) on the Resolutions of the 2017 Traditional Leaders Indaba, as well as the Engagement Model between Government and the Institution of Traditional Leadership | The DTA submitted the following reports to the Committee: 12 May 2021-POA on the resolutions of the 2017 traditional leadership indaba. 10 August 2021-Engagement Model between Government and the Institution of Traditional Leadership
4.The Department of Traditional Affairs must immediately furnish the Committee with the report on the resolutions emanating from the dialogue for women in traditional leadership reportedly held in Mpumalanga and the Gender-based violence workshop reportedly held in Limpopo | 12 May 2021- Report: dialogue for women that took place in Mpumalanga. 13 July 2021-Report:Resolutions GBV workshop-Limpopo.

## Slide 23
Recommendation:
It is recommended that the Portfolio Committee notes:
The Department of Traditional Affairs and the National House of Traditional and Khoi-San Leaders (NHTKL) 2021/2022 third quarter performance reports on pre-determined objectives; and
The expenditure report for the period ended 31 December 2021.
Progress report on the implementation of the Committee recommendations in the 2021 Budget Vote Report
End